## P03-PMB
P03 - Dysart Road
| Project Start |  | 2011-10-17
| Display Week |  | 1
[8 empty] | 2011-10-17 | [6 empty] | 2011-10-24 | [6 empty] | 2011-10-31 | [6 empty] | 2011-11-07 | [6 empty] | 2011-11-14 | [6 empty] | 2011-11-21 | [6 empty] | 2011-11-28 | [6 empty] | 2011-12-05 | [6 empty] | 2011-12-12 | [6 empty] | 2011-12-19 | [6 empty] | 2011-12-26 | [6 empty] | 2012-01-02 | [6 empty] | 2012-01-09 | [6 empty] | 2012-01-16 | [6 empty] | 2012-01-23 | [6 empty] | 2012-01-30 | [6 empty] | 2012-02-06 | [6 empty] | 2012-02-13 | [6 empty] | 2012-02-20 | [6 empty] | 2012-02-27 | [6 empty] | 2012-03-05 | [6 empty] | 2012-03-12 | [6 empty] | 2012-03-19 | [6 empty] | 2012-03-26 | [6 empty] | 2012-04-02 | [6 empty] | 2012-04-09 | [6 empty] | 2012-04-16 | [6 empty] | 2012-04-23 | [6 empty] | 2012-04-30 | [6 empty] | 2012-05-07 | [6 empty] | 2012-05-14 | [6 empty] | 2012-05-21 | [6 empty] | 2012-05-28 | [6 empty] | 2012-06-04 | [6 empty] | 2012-06-11 | [6 empty] | 2012-06-18 | [6 empty] | 2012-06-25
 | time axis 2011-10-17 to 2012-07-01
| TASK | DURn | START | END |  |  | DAYS | time axis 2011-10-17 to 2012-07-01
WBS | Task Name |  | Baseline Start | Baseline Finish
2 | CONTRACT AWARD | 1 | 2011-10-17 | 2011-10-17 |  | 1 | bar: 2011-10-17
3 | PRACTICAL COMPLETION | 2 | 2012-03-15 | 2012-03-16 |  | 2 | bar: 2012-03-15 to 2012-03-16
5 | Schedule A - Roadworks Dysart Bypass Road Widening Preliminaries - Site establishment, Provision for Workplace Health & Safety, Site Cleanup and Dis-establishment |  | 2011-10-18 | 2011-10-19 |  | 0
9 | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | 3 | 2011-11-01 | 2011-11-03 | 0 | 3 | bar: 2011-11-01 to 2011-11-03
18 | Clearing & Grubbing and complete offsite disposal of Spoil inclusive of Dump Fees as required. | 6 | 2011-11-18 | 2011-11-23 |  | 6 | bar: 2011-11-18 to 2011-11-23
23 | Prepare Base Gravel Surface for Primerseal & for Council Inspection, incl provision of compaction test results - Bypass Road Widening Ch 18 to 2801 | 6 | 2012-02-17 | 2012-02-22 | 0 | 6 | bar: 2012-02-17 to 2012-02-22
27 | Primerseal complete in place (10mm stone ); spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED Bypass Road LHS Shoulder 1 metre wide Ch 510 to Ch 650 | 2 | 2012-02-27 | 2012-02-28 | 0 | 2 | bar: 2012-02-27 to 2012-02-28
28 | Primerseal complete in place (10mm stone ); spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED Bypass Road Widening plus 1 metre wide shoulder RHS Ch 510 to Ch 650 | 2 | 2012-02-28 | 2012-02-29 | 0 | 2 | bar: 2012-02-28 to 2012-02-29
29 | Bypass Road 7 metre section over where New RCBC culvert placement approx Ch 600 | 2 | 2012-02-29 | 2012-03-01 | 0 | 2 | bar: 2012-02-29 to 2012-03-01
30 | Bitumen Seal - First Coat complete in place (16mm primerseal ) ; spray rates nominally to be 1.6 l/sqm C170 - SHOULDER WIDENING, SEAL DESIGN TO BE CONFIRMED Bypass Road Widening Ch 18 to Ch 510 | 2 | 2012-03-01 | 2012-03-02 |  | 2 | bar: 2012-03-01 to 2012-03-02
31 | Bitumen Seal - First Coat complete in place (16mm primerseal ) ; spray rates nominally to be 1.6 l/sqm C170 - SHOULDER WIDENING, SEAL DESIGN TO BE CONFIRMED - Bypass Road Widening Ch 650 to Ch 2801 | 4 | 2012-03-02 | 2012-03-05 | 0 | 4 | bar: 2012-03-02 to 2012-03-05
32 | Bitumen Seal - Second Coat complete in place (10mm second coat); spray rates nominally to be 1.2 l/sqm C170 - 7 METRE WIDE SEAL, SEAL DESIGN TO BE CONFIRMED -Bypass Road Widening Ch 18 to Ch 510 | 2 | 2012-03-05 | 2012-03-06 | 0 | 2 | bar: 2012-03-05 to 2012-03-06
33 | Bitumen Seal - Second Coat complete in place (10mm second coat); spray rates nominally to be 1.2 l/sqm C170 - 7 METRE WIDE SEAL, SEAL DESIGN TO BE CONFIRMED - Bypass Road Widening Ch 650 to Ch 2801 | 3 | 2012-03-06 | 2012-03-08 | 0 | 3 | bar: 2012-03-06 to 2012-03-08
34 | DG10 Asphaltic Concrete Pavement 35mm minimum thickness - complete in place including sawcut edges and neat smooth joins - Bypass Road Floodway - Ch 510 to Ch 650 (x 9 metres wide) | 2 | 2012-03-08 | 2012-03-09 | 0 | 2 | bar: 2012-03-08 to 2012-03-09
38 | Soil Management Measures inclusive of: Prepare batters and drains for hydromulch placement | 13 | 2012-03-09 | 2012-03-21 | 0 | 13 | bar: 2012-03-09 to 2012-03-21
41 | Supply and Install New Guide Posts - allow new on widened side only and adjacent to end wall extensions | 1 | 2012-03-09 | 2012-03-09 |  | 1 | bar: 2012-03-09
42 | Supply and Install Floodway Depth markers (G9-22-1A) | 1 | 2012-03-09 | 2012-03-09 | 0 | 1 | bar: 2012-03-09
43 | Remove Signs for widening and reinstate | 1 | 2012-03-09 | 2012-03-09 | 0 | 1 | bar: 2012-03-09
45 | Schedule B - Drainage Dysart Bypass Rd: Ch 49.400 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 dia SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay and backfi | 2 | 2011-12-19 | 2011-12-20 | 0 | 2 | bar: 2011-12-19 to 2011-12-20
46 | 1 x 375 dia Endwall , Precast Type with wings Complete in place, incl. Excavate, sand, supply and install. | 1 | 2011-12-20 | 2011-12-20 | 0 | 1 | bar: 2011-12-20
47 | Ch 300 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 2 | 2011-12-20 | 2011-12-21 |  | 2 | bar: 2011-12-20 to 2011-12-21
48 | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 2 | 2011-12-21 | 2011-12-22 | 0 | 2 | bar: 2011-12-21 to 2011-12-22
49 | Ch 600 Extend 2/1800 x 600 RCBC and Add 3 New Cells 1800 x 600, Installation to Main Roads Std Dwg 1359 - Extend existing 2/1800 x 600 RCBC Complete in place, incl. removal of existing Endwalls with care, excavate, sand, supply, lay & backfill. | 6 | 2011-12-22 | 2011-12-27 | 0 | 6 | bar: 2011-12-22 to 2011-12-27
50 | Install NEW 3/1800 x 600 RCBC adjacent to existing lengthened Culvert Complete in place, incl. excavate, sand, supply, lay and backfill. | 3 | 2011-12-27 | 2011-12-29 |  | 3 | bar: 2011-12-27 to 2011-12-29
51 | NEW 5/1800 x 600 Cast Insitu Endwalls and Aprons to Main Roads Std Dwgs 1304 and 1371 Complete in place, incl. Excavate, supply and construct (existing to be removed) | 1 | 2011-12-29 | 2011-12-29 | 0 | 1 | bar: 2011-12-29
52 | Excavate inlet and outlet at 0.5% grade with 10m base width to connect to existing drains neatly and smoothly. | 2 | 2011-12-29 | 2011-12-30 | 0 | 2 | bar: 2011-12-29 to 2011-12-30
53 | Rip Rap Rock Protection in 250mm dia rock (layer 0.5m thick) to Outlet to extend 10m past culvert end and up batters a minimum of 1m - leave neat, tidy and even surface to rock. | 1 | 2011-12-30 | 2011-12-30 | 0 | 1 | bar: 2011-12-30
54 | Ch 800 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 2 | 2011-12-29 | 2011-12-30 |  | 2 | bar: 2011-12-29 to 2011-12-30
55 | 4 x 450 Cast Insitu Endwall ,Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 4 | 2011-12-30 | 2012-01-02 | 0 | 4 | bar: 2011-12-30 to 2012-01-02
56 | Ch 1300 Extend 4/450 dia SRC Pipe Class 2 SRC, Installation to Main Roads STD DWG 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay & backfill. | 2 | 2012-01-02 | 2012-01-03 | 0 | 2 | bar: 2012-01-02 to 2012-01-03
57 | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 1 | 2012-01-03 | 2012-01-03 | 0 | 1 | bar: 2012-01-03
58 | Ch 1500 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 2 | 2012-01-03 | 2012-01-04 | 0 | 2 | bar: 2012-01-03 to 2012-01-04
59 | 1 x 375 Endwall with wings , Precast Type Complete in place, incl. Excavate, sand, supply and install. | 2 | 2012-01-04 | 2012-01-05 |  | 2 | bar: 2012-01-04 to 2012-01-05
60 | Ch 1749.800 Extend 2/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 2 | 2012-01-05 | 2012-01-06 |  | 2 | bar: 2012-01-05 to 2012-01-06
61 | 2 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 4 | 2012-01-06 | 2012-01-09 | 0 | 4 | bar: 2012-01-06 to 2012-01-09
62 | Ch 1949.800 Extend 2/750 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 750 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 3 | 2012-01-09 | 2012-01-11 | 0 | 3 | bar: 2012-01-09 to 2012-01-11
63 | 2 x 750 Cast Insitu Endwall ,Main Roads Std Dwg 1304 Complete in place, incl. Excavate, supply and construct | 2 | 2012-01-11 | 2012-01-12 | 0 | 2 | bar: 2012-01-11 to 2012-01-12
64 | Ch 2200 Extend 1/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 2 | 2012-01-12 | 2012-01-13 | 0 | 2 | bar: 2012-01-12 to 2012-01-13
65 | 1 x 375 Endwall , Precast Type with wings, Complete in place, incl. Excavate, sand, supply and install. | 1 | 2012-01-13 | 2012-01-13 | 0 | 1 | bar: 2012-01-13
66 | Ch 2720 Extend 2/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2012-01-13 | 2012-01-13 |  | 1 | bar: 2012-01-13
67 | 1/600 x 300 Cast Insitu Endwall and Apron to Main Roads Std Dwgs 1304 and 1371 Complete in place, incl. Excavate, supply and construct | 5 | 2012-01-13 | 2012-01-17 | 0 | 5 | bar: 2012-01-13 to 2012-01-17
68 | Excavate inlet and outlet at 0.5% grade with 1.0m base width to connect to existing drains neatly and smoothly. | 2 | 2012-01-17 | 2012-01-18 | 0 | 2 | bar: 2012-01-17 to 2012-01-18
71 | Schedule C - Dysart Middlemount / Dysart Bypass Intersection - Provision for Traffic and Safety including an approved Traffic Management Plan required by Council prior to commencement of site works. | 1 | 2011-10-20 | 2011-10-20 | 0 | 1 | bar: 2011-10-20
74 | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | 1 | 2011-10-20 | 2011-10-20 | 0 | 1 | bar: 2011-10-20
81 | Clearing & Grubbing, removal of existing kerb and complete offsite disposal of Spoil inclusive of Dump Fees as required. | 1 | 2011-10-20 | 2011-10-20 | 0 | 1 | bar: 2011-10-20
82 | Earthworks - excavate and place as embankment as directed - Cut to Spoil - to achieve boxed out deep to 500mm - material will be spoiled at IRC Tip. | 1 | 2011-10-20 | 2011-10-20 |  | 1 | bar: 2011-10-20
83 | Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | 2 | 2011-10-20 | 2011-10-21 |  | 2 | bar: 2011-10-20 to 2011-10-21
84 | Prepare Dysart Bypass Rd - Middlemount Rd Intersection Subgrade Surface for Gravel Pavement & for Council / MRD Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 2 | 2011-10-27 | 2011-10-28 | 0 | 2 | bar: 2011-10-27 to 2011-10-28
85 | Prepare Dysart Bypass Rd - Middlemount Rd Intersection Subgrade Surface for Gravel Pavement & for Council / MRD Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 4 | 2011-10-28 | 2011-10-31 | 0 | 4 | bar: 2011-10-28 to 2011-10-31
86 | Prepare Base Gravel Surface for Primerseal & for Council / MRD Inspection, incl provision of compaction test results - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 4 | 2011-11-04 | 2011-11-07 | 0 | 4 | bar: 2011-11-04 to 2011-11-07
87 | Prepare Base Gravel Surface for Primerseal & for Council / MRD Inspection, incl provision of compaction test results - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 1 | 2011-11-07 | 2011-11-07 | 0 | 1 | bar: 2011-11-07
88 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS - Base QT Type 2.1 @ 150mm deep | 1 | 2011-11-04 | 2011-11-04 |  | 1 | bar: 2011-11-04
89 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS Upper Sub-Base QT Type 2.3 @ 200mm deep | 2 | 2011-11-01 | 2011-11-02 |  | 2 | bar: 2011-11-01 to 2011-11-02
90 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS - Lower Sub-Base QT Type 2.5 @ 150mm deep | 1 | 2011-11-01 | 2011-11-01 | 0 | 1 | bar: 2011-11-01
91 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS - Base QT Type 2.1 @ 150mm deep | 1 | 2011-11-04 | 2011-11-04 | 0 | 1 | bar: 2011-11-04
92 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS -Upper Sub-Base QT Type 2.3 @ 200mm deep | 1 | 2011-11-02 | 2011-11-02 | 0 | 1 | bar: 2011-11-02
93 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS -Lower Sub-Base QT Type 2.5 @ 150mm deep | 1 | 2011-11-01 | 2011-11-01 |  | 1 | bar: 2011-11-01
95 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 2 | 2011-11-07 | 2011-11-08 | 0 | 2 | bar: 2011-11-07 to 2011-11-08
96 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 2 | 2011-11-07 | 2011-11-08 |  | 2 | bar: 2011-11-07 to 2011-11-08
97 | Asphaltic Concrete Pavement MRD Type DG14 and 60 mm minimum thickness - complete in place. - Dysart Bypass Rd - Middlemount Rd Intersection Complete (overlaying existing seal area) | 2 | 2011-11-08 | 2011-11-09 | 0 | 2 | bar: 2011-11-08 to 2011-11-09
98 | Medians Kerb at Intersections - Type 5 Concrete Kerb in minimum 25 MPa concrete | 2 | 2011-11-02 | 2011-11-03 |  | 2 | bar: 2011-11-02 to 2011-11-03
99 | Street Lighting - Conduits and Bases - Electrical Mains Trenching and Conduiting including bends, draw-wire, sand, bed, backfill, warning tape: 1 x 100 dia LV (HD) + HARD COVER (Provisional Item) | 5 | 2011-10-21 | 2011-10-25 | 0 | 5 | bar: 2011-10-21 to 2011-10-25
100 | Electrical Under Road Bore complete including conduit bends and draw-wire: 1 x 100 dia LV (HD) (Provisional Item) | 2 | 2011-11-07 | 2011-11-08 | 0 | 2 | bar: 2011-11-07 to 2011-11-08
101 | Electrical Mains Cable Pit (Provisional Item) | 2 | 2011-11-08 | 2011-11-09 | 0 | 2 | bar: 2011-11-08 to 2011-11-09
102 | Street Light Bases Complete in Place, including supply of rag bolts and excluding Conduiting Major Pole Base (NB - ALL 10.5m POLES NEED THE LARGER BASES) | 5 | 2011-11-03 | 2011-11-07 |  | 5 | bar: 2011-11-03 to 2011-11-07
103 | Soil Management Measures inclusive of: Prepare batters and drains for hydromulch placement | 1 | 2011-11-09 | 2011-11-09 | 0 | 1 | bar: 2011-11-09
104 | Soil Management Measures inclusive of: Hydromulch to all disturbed areas as directed (batters and drains) | 2 | 2011-11-09 | 2011-11-10 | 0 | 2 | bar: 2011-11-09 to 2011-11-10
106 | Supply and Install New Guide Posts | 2 | 2011-11-09 | 2011-11-10 | 0 | 2 | bar: 2011-11-09 to 2011-11-10
107 | Supply and Install New Give Way Sign R1-2 | 1 | 2011-11-10 | 2011-11-10 | 0 | 1 | bar: 2011-11-10
108 | Linemarking Complete,Dysart Bypass Rd - Middlemount Rd Intersection - Reinstate existing and new lines as per drawing No 842 - R19 | 2 | 2011-11-10 | 2011-11-11 | 0 | 2 | bar: 2011-11-10 to 2011-11-11
109 | Drainage - Ch 140 Middlemount Road Culvert 1A - Extend existing 600 x 300 RCBC RHS, complete in place incl. excavate, sand, supply, lay and backfill | 2 | 2011-10-25 | 2011-10-26 | 0 | 2 | bar: 2011-10-25 to 2011-10-26
110 | Drainage - Ch 140 Middlemount Road - 1/600 x 300 Cast Insitu Endwall and Apron to Main Roads Std Dwgs complete in place | 2 | 2011-10-26 | 2011-10-27 | 0 | 2 | bar: 2011-10-26 to 2011-10-27
161 | Remove & replace unsuitable - ch0 | 2 | 2011-12-05 | 2011-12-06 | 0 | 2 | bar: 2011-12-05 to 2011-12-06
162 | Addiitonal drainage items | 3 | 2011-11-23 | 2011-11-25 | 0 | 3 | bar: 2011-11-23 to 2011-11-25
168 | Stabilisation of Edges - Bypass Road | 8 | 2012-02-10 | 2012-02-17 | 0 | 8 | bar: 2012-02-10 to 2012-02-17
| EDM Data - TED Baseline | 179 |  |  |  | 179 | 0 | 1 | 1 | 1 | 6 | 8 | 9 | 10 | 11 | 13 | 15 | 17 | 19 | 20 | 21 | 22 | 26 | 30 | 33 | 37 | 39 | 41 | 47 | 52 | 57 | 61 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 63 | 64 | 65 | 66 | 67 | 69 | 70 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 72 | 73 | 73 | 73 | 73 | 73 | 73 | 73 | 73 | 73 | 73 | 73 | 73 | 73 | 74 | 77 | 79 | 81 | 82 | 83 | 84 | 85 | 87 | 88 | 92 | 96 | 97 | 98 | 100 | 103 | 105 | 107 | 109 | 110 | 111 | 113 | 114 | 116 | 118 | 122 | 123 | 124 | 125 | 127 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 137 | 138 | 139 | 140 | 141 | 142 | 142 | 142 | 142 | 142 | 143 | 145 | 147 | 149 | 151 | 152 | 153 | 155 | 157 | 158 | 160 | 165 | 166 | 167 | 168 | 169 | 170 | 172 | 174 | 175 | 176 | 177 | 178 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## EDM
TED for each Task Using Linear completion rate or QM
t |  | EDM PLAN | TED | Actual | t | EDM-c | EDM-c+1 | EDM | SPIt | EACt
1 | 2011-10-30 | 21 | 22 | 12 | 1 | 21 | 71 | 1.02 | 1.02 | 8.8235
2 | 2011-11-30 | 71 | 84.254 | 111 | 2 | 71 | 96 | 2.5302 | 1.2651 | 7.1142
3 | 2011-12-30 | 96 | 126.7302 | 164 | 3 | 96 | 128 | 3.9603 | 1.3201 | 6.8176
4 | 2012-01-30 | 128 | 133 | 189 | 4 | 128 | 147 | 4.2632 | 1.0658 | 8.4444
5 | 2012-02-29 | 147 | 165 | 211 | 5 | 147 | 179 | 5.5625 | 1.1125 | 8.0899
6 | 2012-03-30 | 179 | 167 | 213 | 5 | 147 | 179 | 5.625 | 0.9375 | 9.6
7 | 2012-04-30 | 179 | 167 | 213 | 5 | 147 | 179 | 5.625 | 0.80357 | 11.2
8 | 2012-05-30 | 179 | 167 | 213 | 5 | 147 | 179 | 5.625 | 0.70312 | 12.8
9 | 2012-06-30 | 179 | 179 | 225 | 9 | 179 | 179 | 9 | 1 | 9
TED for each Task Using 50/50 progress estimation
t | 0 | EDM PLAN | TED | Actual | t | EDM-c | EDM-c+1 | EDM | SPIt | EACt
1 | 2011-10-30 | 21 | 22 | 12 | 1 | 21 | 71 | 1.02 | 1.02 | 8.8235
2 | 2011-11-30 | 71 | 84.5 | 111 | 2 | 71 | 96 | 2.54 | 1.27 | 7.0866
3 | 2011-12-30 | 96 | 126.5 | 164 | 3 | 96 | 128 | 3.9531 | 1.3177 | 6.83
4 | 2012-01-30 | 128 | 133 | 189 | 4 | 128 | 147 | 4.2632 | 1.0658 | 8.4444
5 | 2012-02-29 | 147 | 165 | 211 | 5 | 147 | 179 | 5.5625 | 1.1125 | 8.0899
6 | 2012-03-30 | 179 | 167 | 213 | 5 | 147 | 179 | 5.625 | 0.9375 | 9.6
7 | 2012-04-30 | 179 | 167 | 213 | 5 | 147 | 179 | 5.625 | 0.80357 | 11.2
8 | 2012-05-30 | 179 | 167 | 213 | 5 | 147 | 179 | 5.625 | 0.70312 | 12.8
9 | 2012-06-30 | 179 | 179 | 225 | 9 | 179 | 179 | 9 | 1 | 9
TED for each Task Using 0/100 progress estimation
t | 0 | EDM PLAN | TED | Actual | t | EDM-c | EDM-c+1 | EDM | SPIt | EACt
1 | 2011-10-30 | 21 | 22 | 12 | 1 | 21 | 71 | 1.02 | 1.02 | 8.8235
2 | 2011-11-30 | 71 | 84 | 111 | 2 | 71 | 96 | 2.52 | 1.26 | 7.1429
3 | 2011-12-30 | 96 | 126 | 164 | 3 | 96 | 128 | 3.9375 | 1.3125 | 6.8571
4 | 2012-01-30 | 128 | 133 | 189 | 4 | 128 | 147 | 4.2632 | 1.0658 | 8.4444
5 | 2012-02-29 | 147 | 165 | 211 | 5 | 147 | 179 | 5.5625 | 1.1125 | 8.0899
6 | 2012-03-30 | 179 | 167 | 213 | 5 | 147 | 179 | 5.625 | 0.9375 | 9.6
7 | 2012-04-30 | 179 | 167 | 213 | 5 | 147 | 179 | 5.625 | 0.80357 | 11.2
8 | 2012-05-30 | 179 | 167 | 213 | 5 | 147 | 179 | 5.625 | 0.70312 | 12.8
9 | 2012-06-30 | 179 | 179 | 225 | 9 | 179 | 179 | 9 | 1 | 9
TED for each Task Using LOE progress estimation
t | 0 | EDM PLAN | TED | Actual | t | EDM-c | EDM-c+1 | EDM | SPIt | EACt
1 | 2011-10-30 | 21 | 19 | 12 | 0 | 0 | 21 | 0.90476 | 0.90476 | 9.9474
2 | 2011-11-30 | 71 | 84 | 111 | 2 | 71 | 96 | 2.52 | 1.26 | 7.1429
3 | 2011-12-30 | 96 | 127 | 164 | 3 | 96 | 128 | 3.9688 | 1.3229 | 6.8031
4 | 2012-01-30 | 128 | 133 | 189 | 4 | 128 | 147 | 4.2632 | 1.0658 | 8.4444
5 | 2012-02-29 | 147 | 165 | 211 | 5 | 147 | 179 | 5.5625 | 1.1125 | 8.0899
6 | 2012-03-30 | 179 | 167 | 213 | 5 | 147 | 179 | 5.625 | 0.9375 | 9.6
7 | 2012-04-30 | 179 | 167 | 213 | 5 | 147 | 179 | 5.625 | 0.80357 | 11.2
8 | 2012-05-30 | 179 | 167 | 213 | 5 | 147 | 179 | 5.625 | 0.70312 | 12.8
6 | 2012-06-30 | 179 | 179 | 225 | 6 | 179 | 179 | 6 | 1 | 9
Note on DD343: Brett Thiele: Agreed 51 hrs @ $160 / hr.

## FINAL - EDM QM
P03 - Dysart Road
| Project Start |  |  | 2011-10-17
| Display Week |  |  | 1
[8 empty] | 2011-10-17 | [6 empty] | 2011-10-24 | [6 empty] | 2011-10-31 | [6 empty] | 2011-11-07 | [6 empty] | 2011-11-14 | [6 empty] | 2011-11-21 | [6 empty] | 2011-11-28 | [6 empty] | 2011-12-05 | [6 empty] | 2011-12-12 | [6 empty] | 2011-12-19 | [6 empty] | 2011-12-26 | [6 empty] | 2012-01-02 | [6 empty] | 2012-01-09 | [6 empty] | 2012-01-16 | [6 empty] | 2012-01-23 | [6 empty] | 2012-01-30 | [6 empty] | 2012-02-06 | [6 empty] | 2012-02-13 | [6 empty] | 2012-02-20 | [6 empty] | 2012-02-27 | [6 empty] | 2012-03-05 | [6 empty] | 2012-03-12 | [6 empty] | 2012-03-19 | [6 empty] | 2012-03-26 | [6 empty] | 2012-04-02 | [6 empty] | 2012-04-09 | [6 empty] | 2012-04-16 | [6 empty] | 2012-04-23 | [6 empty] | 2012-04-30 | [6 empty] | 2012-05-07 | [6 empty] | 2012-05-14 | [6 empty] | 2012-05-21 | [6 empty] | 2012-05-28 | [6 empty] | 2012-06-04 | [6 empty] | 2012-06-11
 | time axis 2011-10-17 to 2012-06-15
| TASK | DURn | Orig DURn | START | END |  | DAYS | time axis 2011-10-17 to 2012-06-15
WBS | Task Name |  |  | Start | Finish
2 | CONTRACT AWARD | 1 | 1 | 2011-10-17 | 2011-10-17 | 0 | 1 | bar: 2011-10-17
3 | PRACTICAL COMPLETION | 2 | 2 | 2012-03-15 | 2012-03-16 | 0 | 2 | bar: 2012-03-15 to 2012-03-16
5 | Schedule A - Roadworks Dysart Bypass Road Widening Preliminaries - Site establishment, Provision for Workplace Health & Safety, Site Cleanup and Dis-establishment | 245 |  | 2011-10-01 | 2012-06-01 | 0 | 0
9 | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | 2 | 3 | 2011-10-20 | 2011-10-21 | 0 | 3 | 2011-10-20: 1.5; 2011-10-21: 1.5
18 | Clearing & Grubbing and complete offsite disposal of Spoil inclusive of Dump Fees as required. | 12 | 6 | 2011-11-18 | 2011-11-29 | 0 | 6 | 2011-11-18: 0.5; 2011-11-19: 0.5; 2011-11-20: 0.5; 2011-11-21: 0.5; 2011-11-22: 0.5; 2011-11-23: 0.5; 2011-11-24: 0.5; 2011-11-25: 0.5; 2011-11-26: 0.5; 2011-11-27: 0.5; 2011-11-28: 0.5; 2011-11-29: 0.5
23 | Prepare Base Gravel Surface for Primerseal & for Council Inspection, incl provision of compaction test results - Bypass Road Widening Ch 18 to 2801 | 2 | 6 | 2011-12-06 | 2011-12-07 | 0 | 6 | 2011-12-06: 3; 2011-12-07: 3
27 | Primerseal complete in place (10mm stone ); spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED Bypass Road LHS Shoulder 1 metre wide Ch 510 to Ch 650 | 1 | 2 | 2011-12-08 | 2011-12-08 | 0 | 2 | 2011-12-08: 2
28 | Primerseal complete in place (10mm stone ); spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED Bypass Road Widening plus 1 metre wide shoulder RHS Ch 510 to Ch 650 | 1 | 2 | 2011-12-08 | 2011-12-08 | 0 | 2 | 2011-12-08: 2
29 | Bypass Road 7 metre section over where New RCBC culvert placement approx Ch 600 | 1 | 2 | 2011-12-08 | 2011-12-08 | 0 | 2 | 2011-12-08: 2
30 | Bitumen Seal - First Coat complete in place (16mm primerseal ) ; spray rates nominally to be 1.6 l/sqm C170 - SHOULDER WIDENING, SEAL DESIGN TO BE CONFIRMED Bypass Road Widening Ch 18 to Ch 510 | 1 | 2 | 2011-12-13 | 2011-12-13 | 0 | 2 | 2011-12-13: 2
31 | Bitumen Seal - First Coat complete in place (16mm primerseal ) ; spray rates nominally to be 1.6 l/sqm C170 - SHOULDER WIDENING, SEAL DESIGN TO BE CONFIRMED - Bypass Road Widening Ch 650 to Ch 2801 | 1 | 4 | 2011-12-13 | 2011-12-13 | 0 | 4 | 2011-12-13: 4
32 | Bitumen Seal - Second Coat complete in place (10mm second coat); spray rates nominally to be 1.2 l/sqm C170 - 7 METRE WIDE SEAL, SEAL DESIGN TO BE CONFIRMED -Bypass Road Widening Ch 18 to Ch 510 | 1 | 2 | 2011-12-13 | 2011-12-13 | 0 | 2 | 2011-12-13: 2
33 | Bitumen Seal - Second Coat complete in place (10mm second coat); spray rates nominally to be 1.2 l/sqm C170 - 7 METRE WIDE SEAL, SEAL DESIGN TO BE CONFIRMED - Bypass Road Widening Ch 650 to Ch 2801 | 1 | 3 | 2011-12-13 | 2011-12-13 | 0 | 3 | 2011-12-13: 3
34 | DG10 Asphaltic Concrete Pavement 35mm minimum thickness - complete in place including sawcut edges and neat smooth joins - Bypass Road Floodway - Ch 510 to Ch 650 (x 9 metres wide) | 3 | 2 | 2012-02-15 | 2012-02-17 | 0 | 2 | 2012-02-15: 0.66667; 2012-02-16: 0.66667; 2012-02-17: 0.66667
38 | Soil Management Measures inclusive of: Prepare batters and drains for hydromulch placement | 7 | 13 | 2012-02-15 | 2012-02-21 | 0 | 13 | 2012-02-15: 1.8571; 2012-02-16: 1.8571; 2012-02-17: 1.8571; 2012-02-18: 1.8571; 2012-02-19: 1.8571; 2012-02-20: 1.8571; 2012-02-21: 1.8571
41 | Supply and Install New Guide Posts - allow new on widened side only and adjacent to end wall extensions | 3 | 1 | 2012-01-18 | 2012-01-20 | 0 | 1 | 2012-01-18: 0.33333; 2012-01-19: 0.33333; 2012-01-20: 0.33333
42 | Supply and Install Floodway Depth markers (G9-22-1A) | 1 | 1 | 2012-01-18 | 2012-01-18 | 0 | 1 | bar: 2012-01-18
43 | Remove Signs for widening and reinstate | 1 | 1 | 2012-01-18 | 2012-01-18 | 0 | 1 | bar: 2012-01-18
45 | Schedule B - Drainage Dysart Bypass Rd: Ch 49.400 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 dia SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay and backfi | 1 | 2 | 2011-10-24 | 2011-10-24 | 0 | 2 | 2011-10-24: 2
46 | 1 x 375 dia Endwall , Precast Type with wings Complete in place, incl. Excavate, sand, supply and install. | 1 | 1 | 2011-11-01 | 2011-11-01 | 0 | 1 | bar: 2011-11-01
47 | Ch 300 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-18 | 2011-10-18 | 0 | 2 | 2011-10-18: 2
48 | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 2 | 2 | 2011-11-03 | 2011-11-04 | 0 | 2 | bar: 2011-11-03 to 2011-11-04
49 | Ch 600 Extend 2/1800 x 600 RCBC and Add 3 New Cells 1800 x 600, Installation to Main Roads Std Dwg 1359 - Extend existing 2/1800 x 600 RCBC Complete in place, incl. removal of existing Endwalls with care, excavate, sand, supply, lay & backfill. | 16 | 6 | 2011-11-01 | 2011-11-16 | 0 | 6 | 2011-11-01: 0.375; 2011-11-02: 0.375; 2011-11-03: 0.375; 2011-11-04: 0.375; 2011-11-05: 0.375; 2011-11-06: 0.375; 2011-11-07: 0.375; 2011-11-08: 0.375; 2011-11-09: 0.375; 2011-11-10: 0.375; 2011-11-11: 0.375; 2011-11-12: 0.375; 2011-11-13: 0.375; 2011-11-14: 0.375; 2011-11-15: 0.375; 2011-11-16: 0.375
50 | Install NEW 3/1800 x 600 RCBC adjacent to existing lengthened Culvert Complete in place, incl. excavate, sand, supply, lay and backfill. | 7 | 3 | 2011-11-17 | 2011-11-23 | 0 | 3 | 2011-11-17: 0.42857; 2011-11-18: 0.42857; 2011-11-19: 0.42857; 2011-11-20: 0.42857; 2011-11-21: 0.42857; 2011-11-22: 0.42857; 2011-11-23: 0.42857
51 | NEW 5/1800 x 600 Cast Insitu Endwalls and Aprons to Main Roads Std Dwgs 1304 and 1371 Complete in place, incl. Excavate, supply and construct (existing to be removed) | 5 | 1 | 2011-11-24 | 2011-11-28 | 0 | 1 | 2011-11-24: 0.2; 2011-11-25: 0.2; 2011-11-26: 0.2; 2011-11-27: 0.2; 2011-11-28: 0.2
52 | Excavate inlet and outlet at 0.5% grade with 10m base width to connect to existing drains neatly and smoothly. | 1 | 2 | 2011-11-17 | 2011-11-17 | 0 | 2 | 2011-11-17: 2
53 | Rip Rap Rock Protection in 250mm dia rock (layer 0.5m thick) to Outlet to extend 10m past culvert end and up batters a minimum of 1m - leave neat, tidy and even surface to rock. | 2 | 1 | 2011-12-01 | 2011-12-02 | 0 | 1 | 2011-12-01: 0.5; 2011-12-02: 0.5
54 | Ch 800 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-26 | 2011-10-26 | 0 | 2 | 2011-10-26: 2
55 | 4 x 450 Cast Insitu Endwall ,Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 2 | 4 | 2011-11-07 | 2011-11-08 | 0 | 4 | 2011-11-07: 2; 2011-11-08: 2
56 | Ch 1300 Extend 4/450 dia SRC Pipe Class 2 SRC, Installation to Main Roads STD DWG 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-27 | 2011-10-27 | 0 | 2 | 2011-10-27: 2
57 | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 2 | 1 | 2011-12-01 | 2011-12-02 | 0 | 1 | 2011-12-01: 0.5; 2011-12-02: 0.5
58 | Ch 1500 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-28 | 2011-10-28 | 0 | 2 | 2011-10-28: 2
59 | 1 x 375 Endwall with wings , Precast Type Complete in place, incl. Excavate, sand, supply and install. | 1 | 2 | 2011-11-09 | 2011-11-09 | 0 | 2 | 2011-11-09: 2
60 | Ch 1749.800 Extend 2/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-29 | 2011-10-29 | 0 | 2 | 2011-10-29: 2
61 | 2 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 2 | 4 | 2011-11-10 | 2011-11-11 | 0 | 4 | 2011-11-10: 2; 2011-11-11: 2
62 | Ch 1949.800 Extend 2/750 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 750 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 3 | 2011-10-30 | 2011-10-30 | 0 | 3 | 2011-10-30: 3
63 | 2 x 750 Cast Insitu Endwall ,Main Roads Std Dwg 1304 Complete in place, incl. Excavate, supply and construct | 2 | 2 | 2011-12-01 | 2011-12-02 | 0 | 2 | bar: 2011-12-01 to 2011-12-02
64 | Ch 2200 Extend 1/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-30 | 2011-10-30 | 0 | 2 | 2011-10-30: 2
65 | 1 x 375 Endwall , Precast Type with wings, Complete in place, incl. Excavate, sand, supply and install. | 1 | 1 | 2011-11-14 | 2011-11-14 | 0 | 1 | bar: 2011-11-14
66 | Ch 2720 Extend 2/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 1 | 2011-10-30 | 2011-10-30 | 0 | 1 | bar: 2011-10-30
67 | 1/600 x 300 Cast Insitu Endwall and Apron to Main Roads Std Dwgs 1304 and 1371 Complete in place, incl. Excavate, supply and construct | 2 | 5 | 2011-11-15 | 2011-11-16 | 0 | 5 | 2011-11-15: 2.5; 2011-11-16: 2.5
68 | Excavate inlet and outlet at 0.5% grade with 1.0m base width to connect to existing drains neatly and smoothly. | 1 | 2 | 2011-11-01 | 2011-11-01 | 0 | 2 | 2011-11-01: 2
71 | Schedule C - Dysart Middlemount / Dysart Bypass Intersection - Provision for Traffic and Safety including an approved Traffic Management Plan required by Council prior to commencement of site works. | 63 | 1 | 2011-11-15 | 2012-01-16 | -1.7764e-15 | 1 | 2011-11-15: 0.015873; 2011-11-16: 0.015873; 2011-11-17: 0.015873; 2011-11-18: 0.015873; 2011-11-19: 0.015873; 2011-11-20: 0.015873; 2011-11-21: 0.015873; 2011-11-22: 0.015873; 2011-11-23: 0.015873; 2011-11-24: 0.015873; 2011-11-25: 0.015873; 2011-11-26: 0.015873; 2011-11-27: 0.015873; 2011-11-28: 0.015873; 2011-11-29: 0.015873; 2011-11-30: 0.015873; 2011-12-01: 0.015873; 2011-12-02: 0.015873; 2011-12-03: 0.015873; 2011-12-04: 0.015873; 2011-12-05: 0.015873; 2011-12-06: 0.015873; 2011-12-07: 0.015873; 2011-12-08: 0.015873; 2011-12-09: 0.015873; 2011-12-10: 0.015873; 2011-12-11: 0.015873; 2011-12-12: 0.015873; 2011-12-13: 0.015873; 2011-12-14: 0.015873; 2011-12-15: 0.015873; 2011-12-16: 0.015873; 2011-12-17: 0.015873; 2011-12-18: 0.015873; 2011-12-19: 0.015873; 2011-12-20: 0.015873; 2011-12-21: 0.015873; 2011-12-22: 0.015873; 2011-12-23: 0.015873; 2011-12-24: 0.015873; 2011-12-25: 0.015873; 2011-12-26: 0.015873; 2011-12-27: 0.015873; 2011-12-28: 0.015873; 2011-12-29: 0.015873; 2011-12-30: 0.015873; 2011-12-31: 0.015873; 2012-01-01: 0.015873; 2012-01-02: 0.015873; 2012-01-03: 0.015873; 2012-01-04: 0.015873; 2012-01-05: 0.015873; 2012-01-06: 0.015873; 2012-01-07: 0.015873; 2012-01-08: 0.015873; 2012-01-09: 0.015873; 2012-01-10: 0.015873; 2012-01-11: 0.015873; 2012-01-12: 0.015873; 2012-01-13: 0.015873; 2012-01-14: 0.015873; 2012-01-15: 0.015873; 2012-01-16: 0.015873
74 | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | 1 | 1 | 2011-11-15 | 2011-11-15 | 0 | 1 | bar: 2011-11-15
81 | Clearing & Grubbing, removal of existing kerb and complete offsite disposal of Spoil inclusive of Dump Fees as required. | 2 | 1 | 2011-11-16 | 2011-11-17 | 0 | 1 | 2011-11-16: 0.5; 2011-11-17: 0.5
82 | Earthworks - excavate and place as embankment as directed - Cut to Spoil - to achieve boxed out deep to 500mm - material will be spoiled at IRC Tip. | 4 | 1 | 2011-11-18 | 2011-11-21 | 0 | 1 | 2011-11-18: 0.25; 2011-11-19: 0.25; 2011-11-20: 0.25; 2011-11-21: 0.25
83 | Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | 1 | 2 | 2011-11-22 | 2011-11-22 | 0 | 2 | 2011-11-22: 2
84 | Prepare Dysart Bypass Rd - Middlemount Rd Intersection Subgrade Surface for Gravel Pavement & for Council / MRD Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 1 | 2 | 2011-11-09 | 2011-11-09 | 0 | 2 | 2011-11-09: 2
85 | Prepare Dysart Bypass Rd - Middlemount Rd Intersection Subgrade Surface for Gravel Pavement & for Council / MRD Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 2 | 4 | 2011-12-06 | 2011-12-07 | 0 | 4 | 2011-12-06: 2; 2011-12-07: 2
86 | Prepare Base Gravel Surface for Primerseal & for Council / MRD Inspection, incl provision of compaction test results - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 1 | 4 | 2011-12-05 | 2011-12-05 | 0 | 4 | 2011-12-05: 4
87 | Prepare Base Gravel Surface for Primerseal & for Council / MRD Inspection, incl provision of compaction test results - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 2 | 1 | 2011-12-01 | 2011-12-02 | 0 | 1 | 2011-12-01: 0.5; 2011-12-02: 0.5
88 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS - Base QT Type 2.1 @ 150mm deep | 1 | 1 | 2011-11-30 | 2011-11-30 | 0 | 1 | bar: 2011-11-30
89 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS Upper Sub-Base QT Type 2.3 @ 200mm deep | 1 | 2 | 2011-11-30 | 2011-11-30 | 0 | 2 | 2011-11-30: 2
90 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS - Lower Sub-Base QT Type 2.5 @ 150mm deep | 1 | 1 | 2011-11-29 | 2011-11-29 | 0 | 1 | bar: 2011-11-29
91 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS - Base QT Type 2.1 @ 150mm deep | 2 | 1 | 2011-11-28 | 2011-11-29 | 0 | 1 | 2011-11-28: 0.5; 2011-11-29: 0.5
92 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS -Upper Sub-Base QT Type 2.3 @ 200mm deep | 4 | 1 | 2011-11-25 | 2011-11-28 | 0 | 1 | 2011-11-25: 0.25; 2011-11-26: 0.25; 2011-11-27: 0.25; 2011-11-28: 0.25
93 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS -Lower Sub-Base QT Type 2.5 @ 150mm deep | 2 | 1 | 2011-11-23 | 2011-11-24 | 0 | 1 | 2011-11-23: 0.5; 2011-11-24: 0.5
95 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 1 | 2 | 2011-12-13 | 2011-12-13 | 0 | 2 | 2011-12-13: 2
96 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 1 | 2 | 2011-12-13 | 2011-12-13 | 0 | 2 | 2011-12-13: 2
97 | Asphaltic Concrete Pavement MRD Type DG14 and 60 mm minimum thickness - complete in place. - Dysart Bypass Rd - Middlemount Rd Intersection Complete (overlaying existing seal area) | 2 | 2 | 2012-02-15 | 2012-02-16 | 0 | 2 | bar: 2012-02-15 to 2012-02-16
98 | Medians Kerb at Intersections - Type 5 Concrete Kerb in minimum 25 MPa concrete | 2 | 2 | 2012-02-06 | 2012-02-07 | 0 | 2 | bar: 2012-02-06 to 2012-02-07
99 | Street Lighting - Conduits and Bases - Electrical Mains Trenching and Conduiting including bends, draw-wire, sand, bed, backfill, warning tape: 1 x 100 dia LV (HD) + HARD COVER (Provisional Item) | 1 | 5 | 2012-02-01 | 2012-02-01 | 0 | 5 | 2012-02-01: 5
100 | Electrical Under Road Bore complete including conduit bends and draw-wire: 1 x 100 dia LV (HD) (Provisional Item) | 1 | 2 | 2011-12-13 | 2011-12-13 | 0 | 2 | 2011-12-13: 2
101 | Electrical Mains Cable Pit (Provisional Item) | 2 | 2 | 2012-02-01 | 2012-02-02 | 0 | 2 | bar: 2012-02-01 to 2012-02-02
102 | Street Light Bases Complete in Place, including supply of rag bolts and excluding Conduiting Major Pole Base (NB - ALL 10.5m POLES NEED THE LARGER BASES) | 2 | 5 | 2012-02-07 | 2012-02-08 | 0 | 5 | 2012-02-07: 2.5; 2012-02-08: 2.5
103 | Soil Management Measures inclusive of: Prepare batters and drains for hydromulch placement | 3 | 1 | 2012-02-21 | 2012-02-23 | 0 | 1 | 2012-02-21: 0.33333; 2012-02-22: 0.33333; 2012-02-23: 0.33333
104 | Soil Management Measures inclusive of: Hydromulch to all disturbed areas as directed (batters and drains) | 1 | 2 | 2012-06-01 | 2012-06-01 | 0 | 2 | 2012-06-01: 2
106 | Supply and Install New Guide Posts | 2 | 2 | 2012-01-10 | 2012-01-11 | 0 | 2 | bar: 2012-01-10 to 2012-01-11
107 | Supply and Install New Give Way Sign R1-2 | 1 | 1 | 2012-01-10 | 2012-01-10 | 0 | 1 | bar: 2012-01-10
108 | Linemarking Complete,Dysart Bypass Rd - Middlemount Rd Intersection - Reinstate existing and new lines as per drawing No 842 - R19 | 2 | 2 | 2012-06-05 | 2012-06-06 | 0 | 2 | bar: 2012-06-05 to 2012-06-06
109 | Drainage - Ch 140 Middlemount Road Culvert 1A - Extend existing 600 x 300 RCBC RHS, complete in place incl. excavate, sand, supply, lay and backfill | 2 | 2 | 2011-11-16 | 2011-11-17 | 0 | 2 | bar: 2011-11-16 to 2011-11-17
110 | Drainage - Ch 140 Middlemount Road - 1/600 x 300 Cast Insitu Endwall and Apron to Main Roads Std Dwgs complete in place | 4 | 2 | 2011-11-18 | 2011-11-21 | 0 | 2 | 2011-11-18: 0.5; 2011-11-19: 0.5; 2011-11-20: 0.5; 2011-11-21: 0.5
161 | Remove & replace unsuitable - ch0 | 1 | 2 | 2011-11-08 | 2011-11-08 | 0 | 2 | 2011-11-08: 2
162 | Addiitonal drainage items | 3 | 3 | 2011-11-01 | 2011-11-03 | 0 | 3 | bar: 2011-11-01 to 2011-11-03
168 | Stabilisation of Edges - Bypass Road | 9 | 8 | 2012-06-05 | 2012-06-13 | 0 | 8 | 2012-06-05: 0.88889; 2012-06-06: 0.88889; 2012-06-07: 0.88889; 2012-06-08: 0.88889; 2012-06-09: 0.88889; 2012-06-10: 0.88889; 2012-06-11: 0.88889; 2012-06-12: 0.88889; 2012-06-13: 0.88889
|  |  | 179 |  |  |  | 179
| EDM Data - EDM - QM | [6 empty] | 1 | 3 | 3 | 4.5 | 6 | 6 | 6 | 8 | 8 | 10 | 12 | 14 | 16 | 22 | 22 | 26.375 | 27.75 | 30.125 | 31.5 | 31.875 | 32.25 | 34.625 | 39 | 43.375 | 45.75 | 48.125 | 48.5 | 48.875 | 50.25 | 54.1409 | 58.5317 | 62.4762 | 64.1706 | 65.8651 | 67.5595 | 69.254 | 72.1984 | 73.6429 | 74.8587 | 75.8246 | 76.7905 | 77.7563 | 79.2222 | 81.2381 | 84.254 | 86.7698 | 89.2857 | 89.3016 | 89.3175 | 93.3333 | 98.3492 | 103.3651 | 109.381 | 109.3968 | 109.4127 | 109.4286 | 109.4444 | 126.4603 | 126.4762 | 126.4921 | 126.5079 | 126.5238 | 126.5397 | 126.5556 | 126.5714 | 126.5873 | 126.6032 | 126.619 | 126.6349 | 126.6508 | 126.6667 | 126.6825 | 126.6984 | 126.7143 | 126.7302 | 126.746 | 126.7619 | 126.7778 | 126.7937 | 126.8095 | 126.8254 | 126.8413 | 126.8571 | 126.873 | 126.8889 | 128.9048 | 129.9206 | 129.9365 | 129.9524 | 129.9683 | 129.9841 | 130 | 130 | 132.3333 | 132.6667 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 139 | 140 | 140 | 140 | 140 | 141 | 144.5 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 150.5238 | 154.0476 | 156.5714 | 158.4286 | 160.2857 | 162.1429 | 164.3333 | 164.6667 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 166 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 169 | 169 | 169 | 169 | 170.8889 | 172.7778 | 173.6667 | 174.5556 | 175.4444 | 176.3333 | 177.2222 | 178.1111 | 179 | 179 | 179
| TOTAL - EDM - ACTUAL DURATIONS | [6 empty] | 1 | 2 | 2 | 3 | 4 | 4 | 4 | 5 | 5 | 6 | 7 | 8 | 9 | 12 | 12 | 16 | 18 | 21 | 23 | 24 | 25 | 27 | 30 | 33 | 35 | 37 | 38 | 39 | 41 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 79 | 83 | 87 | 91 | 95 | 99 | 104 | 108 | 111 | 116 | 121 | 122 | 123 | 125 | 128 | 131 | 135 | 136 | 137 | 138 | 139 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 177 | 179 | 180 | 181 | 182 | 183 | 184 | 184 | 187 | 188 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 191 | 192 | 192 | 192 | 192 | 193 | 195 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 199 | 202 | 204 | 205 | 206 | 207 | 209 | 210 | 211 | 211 | 211 | 211 | 211 | 211 | 211 | 211 | 211 | 211 | 211 | 211 | 211 | 211 | 211 | 211 | 211 | 211 | 211 | 211 | 211 | 212 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 214 | 214 | 214 | 214 | 216 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 225 | 225
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## FINAL - EDM 50
P03 - Dysart Road
| Project Start |  |  | 2011-10-17
| Display Week |  |  | 1
[8 empty] | 2011-10-17 | [6 empty] | 2011-10-24 | [6 empty] | 2011-10-31 | [6 empty] | 2011-11-07 | [6 empty] | 2011-11-14 | [6 empty] | 2011-11-21 | [6 empty] | 2011-11-28 | [6 empty] | 2011-12-05 | [6 empty] | 2011-12-12 | [6 empty] | 2011-12-19 | [6 empty] | 2011-12-26 | [6 empty] | 2012-01-02 | [6 empty] | 2012-01-09 | [6 empty] | 2012-01-16 | [6 empty] | 2012-01-23 | [6 empty] | 2012-01-30 | [6 empty] | 2012-02-06 | [6 empty] | 2012-02-13 | [6 empty] | 2012-02-20 | [6 empty] | 2012-02-27 | [6 empty] | 2012-03-05 | [6 empty] | 2012-03-12 | [6 empty] | 2012-03-19 | [6 empty] | 2012-03-26 | [6 empty] | 2012-04-02 | [6 empty] | 2012-04-09 | [6 empty] | 2012-04-16 | [6 empty] | 2012-04-23 | [6 empty] | 2012-04-30 | [6 empty] | 2012-05-07 | [6 empty] | 2012-05-14 | [6 empty] | 2012-05-21 | [6 empty] | 2012-05-28 | [6 empty] | 2012-06-04 | [6 empty] | 2012-06-11
 | time axis 2011-10-17 to 2012-06-17
| TASK | DURn | ORININAL DUR | START | END |  | DAYS | time axis 2011-10-17 to 2012-06-17
WBS | Task Name |  |  | Start | Finish
2 | CONTRACT AWARD | 1 | 1 | 2011-10-17 | 2011-10-17 | 0 | 1 | bar: 2011-10-17
3 | PRACTICAL COMPLETION | 2 | 2 | 2012-03-15 | 2012-03-16 | 0 | 2 | bar: 2012-03-15 to 2012-03-16
5 | Schedule A - Roadworks Dysart Bypass Road Widening Preliminaries - Site establishment, Provision for Workplace Health & Safety, Site Cleanup and Dis-establishment | 245 |  | 2011-10-01 | 2012-06-01 |  |  | 2012-06-01: 0
9 | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | 2 | 3 | 2011-10-20 | 2011-10-21 | 0 | 3 | 2011-10-20: 1.5; 2011-10-21: 1.5
18 | Clearing & Grubbing and complete offsite disposal of Spoil inclusive of Dump Fees as required. | 12 | 6 | 2011-11-18 | 2011-11-29 | 0 | 6 | 2011-11-18: 3; 2011-11-29: 3
23 | Prepare Base Gravel Surface for Primerseal & for Council Inspection, incl provision of compaction test results - Bypass Road Widening Ch 18 to 2801 | 2 | 6 | 2011-12-06 | 2011-12-07 | 0 | 6 | 2011-12-06: 3; 2011-12-07: 3
27 | Primerseal complete in place (10mm stone ); spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED Bypass Road LHS Shoulder 1 metre wide Ch 510 to Ch 650 | 1 | 2 | 2011-12-08 | 2011-12-08 | 0 | 2 | 2011-12-08: 2
28 | Primerseal complete in place (10mm stone ); spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED Bypass Road Widening plus 1 metre wide shoulder RHS Ch 510 to Ch 650 | 1 | 2 | 2011-12-08 | 2011-12-08 | 0 | 2 | 2011-12-08: 2
29 | Bypass Road 7 metre section over where New RCBC culvert placement approx Ch 600 | 1 | 2 | 2011-12-08 | 2011-12-08 | 0 | 2 | 2011-12-08: 2
30 | Bitumen Seal - First Coat complete in place (16mm primerseal ) ; spray rates nominally to be 1.6 l/sqm C170 - SHOULDER WIDENING, SEAL DESIGN TO BE CONFIRMED Bypass Road Widening Ch 18 to Ch 510 | 1 | 2 | 2011-12-13 | 2011-12-13 | 0 | 2 | 2011-12-13: 2
31 | Bitumen Seal - First Coat complete in place (16mm primerseal ) ; spray rates nominally to be 1.6 l/sqm C170 - SHOULDER WIDENING, SEAL DESIGN TO BE CONFIRMED - Bypass Road Widening Ch 650 to Ch 2801 | 1 | 4 | 2011-12-13 | 2011-12-13 | 0 | 4 | 2011-12-13: 4
32 | Bitumen Seal - Second Coat complete in place (10mm second coat); spray rates nominally to be 1.2 l/sqm C170 - 7 METRE WIDE SEAL, SEAL DESIGN TO BE CONFIRMED -Bypass Road Widening Ch 18 to Ch 510 | 1 | 2 | 2011-12-13 | 2011-12-13 | 0 | 2 | 2011-12-13: 2
33 | Bitumen Seal - Second Coat complete in place (10mm second coat); spray rates nominally to be 1.2 l/sqm C170 - 7 METRE WIDE SEAL, SEAL DESIGN TO BE CONFIRMED - Bypass Road Widening Ch 650 to Ch 2801 | 1 | 3 | 2011-12-13 | 2011-12-13 | 0 | 3 | 2011-12-13: 3
34 | DG10 Asphaltic Concrete Pavement 35mm minimum thickness - complete in place including sawcut edges and neat smooth joins - Bypass Road Floodway - Ch 510 to Ch 650 (x 9 metres wide) | 3 | 2 | 2012-02-15 | 2012-02-17 | 0 | 2 | bar: 2012-02-15; 2012-02-17
38 | Soil Management Measures inclusive of: Prepare batters and drains for hydromulch placement | 7 | 13 | 2012-02-15 | 2012-02-21 | 0 | 13 | 2012-02-15: 6.5; 2012-02-21: 6.5
41 | Supply and Install New Guide Posts - allow new on widened side only and adjacent to end wall extensions | 3 | 1 | 2012-01-18 | 2012-01-20 | 0 | 1 | 2012-01-18: 0.5; 2012-01-20: 0.5
42 | Supply and Install Floodway Depth markers (G9-22-1A) | 1 | 1 | 2012-01-18 | 2012-01-18 | 0 | 1 | bar: 2012-01-18
43 | Remove Signs for widening and reinstate | 1 | 1 | 2012-01-18 | 2012-01-18 | 0 | 1 | bar: 2012-01-18
45 | Schedule B - Drainage Dysart Bypass Rd: Ch 49.400 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 dia SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay and backfi | 1 | 2 | 2011-10-24 | 2011-10-24 | 0 | 2 | 2011-10-24: 2
46 | 1 x 375 dia Endwall , Precast Type with wings Complete in place, incl. Excavate, sand, supply and install. | 1 | 1 | 2011-11-01 | 2011-11-01 | 0 | 1 | bar: 2011-11-01
47 | Ch 300 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-18 | 2011-10-18 | 0 | 2 | 2011-10-18: 2
48 | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 2 | 2 | 2011-11-03 | 2011-11-04 | 0 | 2 | bar: 2011-11-03 to 2011-11-04
49 | Ch 600 Extend 2/1800 x 600 RCBC and Add 3 New Cells 1800 x 600, Installation to Main Roads Std Dwg 1359 - Extend existing 2/1800 x 600 RCBC Complete in place, incl. removal of existing Endwalls with care, excavate, sand, supply, lay & backfill. | 16 | 6 | 2011-11-01 | 2011-11-16 | 0 | 6 | 2011-11-01: 3; 2011-11-16: 3
50 | Install NEW 3/1800 x 600 RCBC adjacent to existing lengthened Culvert Complete in place, incl. excavate, sand, supply, lay and backfill. | 7 | 3 | 2011-11-17 | 2011-11-23 | 0 | 3 | 2011-11-17: 1.5; 2011-11-23: 1.5
51 | NEW 5/1800 x 600 Cast Insitu Endwalls and Aprons to Main Roads Std Dwgs 1304 and 1371 Complete in place, incl. Excavate, supply and construct (existing to be removed) | 5 | 1 | 2011-11-24 | 2011-11-28 | 0 | 1 | 2011-11-24: 0.5; 2011-11-28: 0.5
52 | Excavate inlet and outlet at 0.5% grade with 10m base width to connect to existing drains neatly and smoothly. | 1 | 2 | 2011-11-17 | 2011-11-17 | 0 | 2 | 2011-11-17: 2
53 | Rip Rap Rock Protection in 250mm dia rock (layer 0.5m thick) to Outlet to extend 10m past culvert end and up batters a minimum of 1m - leave neat, tidy and even surface to rock. | 2 | 1 | 2011-12-01 | 2011-12-02 | 0 | 1 | 2011-12-01: 0.5; 2011-12-02: 0.5
54 | Ch 800 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-26 | 2011-10-26 | 0 | 2 | 2011-10-26: 2
55 | 4 x 450 Cast Insitu Endwall ,Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 2 | 4 | 2011-11-07 | 2011-11-08 | 0 | 4 | 2011-11-07: 2; 2011-11-08: 2
56 | Ch 1300 Extend 4/450 dia SRC Pipe Class 2 SRC, Installation to Main Roads STD DWG 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-27 | 2011-10-27 | 0 | 2 | 2011-10-27: 2
57 | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 2 | 1 | 2011-12-01 | 2011-12-02 | 0 | 1 | 2011-12-01: 0.5; 2011-12-02: 0.5
58 | Ch 1500 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-28 | 2011-10-28 | 0 | 2 | 2011-10-28: 2
59 | 1 x 375 Endwall with wings , Precast Type Complete in place, incl. Excavate, sand, supply and install. | 1 | 2 | 2011-11-09 | 2011-11-09 | 0 | 2 | 2011-11-09: 2
60 | Ch 1749.800 Extend 2/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-29 | 2011-10-29 | 0 | 2 | 2011-10-29: 2
61 | 2 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 2 | 4 | 2011-11-10 | 2011-11-11 | 0 | 4 | 2011-11-10: 2; 2011-11-11: 2
62 | Ch 1949.800 Extend 2/750 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 750 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 3 | 2011-10-30 | 2011-10-30 | 0 | 3 | 2011-10-30: 3
63 | 2 x 750 Cast Insitu Endwall ,Main Roads Std Dwg 1304 Complete in place, incl. Excavate, supply and construct | 2 | 2 | 2011-12-01 | 2011-12-02 | 0 | 2 | bar: 2011-12-01 to 2011-12-02
64 | Ch 2200 Extend 1/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-30 | 2011-10-30 | 0 | 2 | 2011-10-30: 2
65 | 1 x 375 Endwall , Precast Type with wings, Complete in place, incl. Excavate, sand, supply and install. | 1 | 1 | 2011-11-14 | 2011-11-14 | 0 | 1 | bar: 2011-11-14
66 | Ch 2720 Extend 2/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 1 | 2011-10-30 | 2011-10-30 | 0 | 1 | bar: 2011-10-30
67 | 1/600 x 300 Cast Insitu Endwall and Apron to Main Roads Std Dwgs 1304 and 1371 Complete in place, incl. Excavate, supply and construct | 2 | 5 | 2011-11-15 | 2011-11-16 | 0 | 5 | 2011-11-15: 2.5; 2011-11-16: 2.5
68 | Excavate inlet and outlet at 0.5% grade with 1.0m base width to connect to existing drains neatly and smoothly. | 1 | 2 | 2011-11-01 | 2011-11-01 | 0 | 2 | 2011-11-01: 2
71 | Schedule C - Dysart Middlemount / Dysart Bypass Intersection - Provision for Traffic and Safety including an approved Traffic Management Plan required by Council prior to commencement of site works. | 63 | 1 | 2011-11-15 | 2012-01-16 | 0 | 1 | 2011-11-15: 0.5; 2012-01-16: 0.5
74 | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | 1 | 1 | 2011-11-15 | 2011-11-15 | 0 | 1 | bar: 2011-11-15
81 | Clearing & Grubbing, removal of existing kerb and complete offsite disposal of Spoil inclusive of Dump Fees as required. | 2 | 1 | 2011-11-16 | 2011-11-17 | 0 | 1 | 2011-11-16: 0.5; 2011-11-17: 0.5
82 | Earthworks - excavate and place as embankment as directed - Cut to Spoil - to achieve boxed out deep to 500mm - material will be spoiled at IRC Tip. | 4 | 1 | 2011-11-18 | 2011-11-21 | 0 | 1 | 2011-11-18: 0.5; 2011-11-21: 0.5
83 | Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | 1 | 2 | 2011-11-22 | 2011-11-22 | 0 | 2 | 2011-11-22: 2
84 | Prepare Dysart Bypass Rd - Middlemount Rd Intersection Subgrade Surface for Gravel Pavement & for Council / MRD Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 1 | 2 | 2011-11-09 | 2011-11-09 | 0 | 2 | 2011-11-09: 2
85 | Prepare Dysart Bypass Rd - Middlemount Rd Intersection Subgrade Surface for Gravel Pavement & for Council / MRD Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 2 | 4 | 2011-12-06 | 2011-12-07 | 0 | 4 | 2011-12-06: 2; 2011-12-07: 2
86 | Prepare Base Gravel Surface for Primerseal & for Council / MRD Inspection, incl provision of compaction test results - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 1 | 4 | 2011-12-05 | 2011-12-05 | 0 | 4 | 2011-12-05: 4
87 | Prepare Base Gravel Surface for Primerseal & for Council / MRD Inspection, incl provision of compaction test results - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 2 | 1 | 2011-12-01 | 2011-12-02 | 0 | 1 | 2011-12-01: 0.5; 2011-12-02: 0.5
88 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS - Base QT Type 2.1 @ 150mm deep | 1 | 1 | 2011-11-30 | 2011-11-30 | 0 | 1 | bar: 2011-11-30
89 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS Upper Sub-Base QT Type 2.3 @ 200mm deep | 1 | 2 | 2011-11-30 | 2011-11-30 | 0 | 2 | 2011-11-30: 2
90 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS - Lower Sub-Base QT Type 2.5 @ 150mm deep | 1 | 1 | 2011-11-29 | 2011-11-29 | 0 | 1 | bar: 2011-11-29
91 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS - Base QT Type 2.1 @ 150mm deep | 2 | 1 | 2011-11-28 | 2011-11-29 | 0 | 1 | 2011-11-28: 0.5; 2011-11-29: 0.5
92 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS -Upper Sub-Base QT Type 2.3 @ 200mm deep | 4 | 1 | 2011-11-25 | 2011-11-28 | 0 | 1 | 2011-11-25: 0.5; 2011-11-28: 0.5
93 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS -Lower Sub-Base QT Type 2.5 @ 150mm deep | 2 | 1 | 2011-11-23 | 2011-11-24 | 0 | 1 | 2011-11-23: 0.5; 2011-11-24: 0.5
95 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 1 | 2 | 2011-12-13 | 2011-12-13 | 0 | 2 | 2011-12-13: 2
96 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 1 | 2 | 2011-12-13 | 2011-12-13 | 0 | 2 | 2011-12-13: 2
97 | Asphaltic Concrete Pavement MRD Type DG14 and 60 mm minimum thickness - complete in place. - Dysart Bypass Rd - Middlemount Rd Intersection Complete (overlaying existing seal area) | 2 | 2 | 2012-02-15 | 2012-02-16 | 0 | 2 | bar: 2012-02-15 to 2012-02-16
98 | Medians Kerb at Intersections - Type 5 Concrete Kerb in minimum 25 MPa concrete | 2 | 2 | 2012-02-06 | 2012-02-07 | 0 | 2 | bar: 2012-02-06 to 2012-02-07
99 | Street Lighting - Conduits and Bases - Electrical Mains Trenching and Conduiting including bends, draw-wire, sand, bed, backfill, warning tape: 1 x 100 dia LV (HD) + HARD COVER (Provisional Item) | 1 | 5 | 2012-02-01 | 2012-02-01 | 0 | 5 | 2012-02-01: 5
100 | Electrical Under Road Bore complete including conduit bends and draw-wire: 1 x 100 dia LV (HD) (Provisional Item) | 1 | 2 | 2011-12-13 | 2011-12-13 | 0 | 2 | 2011-12-13: 2
101 | Electrical Mains Cable Pit (Provisional Item) | 2 | 2 | 2012-02-01 | 2012-02-02 | 0 | 2 | bar: 2012-02-01 to 2012-02-02
102 | Street Light Bases Complete in Place, including supply of rag bolts and excluding Conduiting Major Pole Base (NB - ALL 10.5m POLES NEED THE LARGER BASES) | 2 | 5 | 2012-02-07 | 2012-02-08 | 0 | 5 | 2012-02-07: 2.5; 2012-02-08: 2.5
103 | Soil Management Measures inclusive of: Prepare batters and drains for hydromulch placement | 3 | 1 | 2012-02-21 | 2012-02-23 | 0 | 1 | 2012-02-21: 0.5; 2012-02-23: 0.5
104 | Soil Management Measures inclusive of: Hydromulch to all disturbed areas as directed (batters and drains) | 1 | 2 | 2012-06-01 | 2012-06-01 | 0 | 2 | 2012-06-01: 2
106 | Supply and Install New Guide Posts | 2 | 2 | 2012-01-10 | 2012-01-11 | 0 | 2 | bar: 2012-01-10 to 2012-01-11
107 | Supply and Install New Give Way Sign R1-2 | 1 | 1 | 2012-01-10 | 2012-01-10 | 0 | 1 | bar: 2012-01-10
108 | Linemarking Complete,Dysart Bypass Rd - Middlemount Rd Intersection - Reinstate existing and new lines as per drawing No 842 - R19 | 2 | 2 | 2012-06-05 | 2012-06-06 | 0 | 2 | bar: 2012-06-05 to 2012-06-06
109 | Drainage - Ch 140 Middlemount Road Culvert 1A - Extend existing 600 x 300 RCBC RHS, complete in place incl. excavate, sand, supply, lay and backfill | 2 | 2 | 2011-11-16 | 2011-11-17 | 0 | 2 | bar: 2011-11-16 to 2011-11-17
110 | Drainage - Ch 140 Middlemount Road - 1/600 x 300 Cast Insitu Endwall and Apron to Main Roads Std Dwgs complete in place | 4 | 2 | 2011-11-18 | 2011-11-21 | 0 | 2 | bar: 2011-11-18; 2011-11-21
161 | Remove & replace unsuitable - ch0 | 1 | 2 | 2011-11-08 | 2011-11-08 | 0 | 2 | 2011-11-08: 2
162 | Addiitonal drainage items | 3 | 3 | 2011-11-01 | 2011-11-03 | 0 | 3 | 2011-11-01: 1.5; 2011-11-03: 1.5
168 | Stabilisation of Edges - Bypass Road | 9 | 8 | 2012-06-05 | 2012-06-13 | 0 | 8 | 2012-06-05: 4; 2012-06-13: 4
|  |  | 179 |  |  |  | 179
| EDM Data - EDM - QM | [6 empty] | 1 | 3 | 3 | 4.5 | 6 | 6 | 6 | 8 | 8 | 10 | 12 | 14 | 16 | 22 | 22 | 29.5 | 29.5 | 32 | 33 | 33 | 33 | 35 | 39 | 43 | 45 | 47 | 47 | 47 | 48 | 52 | 59 | 64 | 68.5 | 68.5 | 68.5 | 70 | 72 | 74 | 75 | 75.5 | 75.5 | 75.5 | 77 | 81.5 | 84.5 | 87 | 89.5 | 89.5 | 89.5 | 93.5 | 98.5 | 103.5 | 109.5 | 109.5 | 109.5 | 109.5 | 109.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 128.5 | 129.5 | 129.5 | 129.5 | 129.5 | 129.5 | 130 | 130 | 132.5 | 132.5 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 139 | 140 | 140 | 140 | 140 | 141 | 144.5 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 155.5 | 156.5 | 157.5 | 157.5 | 157.5 | 157.5 | 164.5 | 164.5 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 166 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 169 | 169 | 169 | 169 | 174 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 179 | 179 | 179 | 179 | 179
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## FINAL - EDM 100
P03 - Dysart Road
| Project Start |  |  | 2011-10-17
| Display Week |  |  | 1
[8 empty] | 2011-10-17 | [6 empty] | 2011-10-24 | [6 empty] | 2011-10-31 | [6 empty] | 2011-11-07 | [6 empty] | 2011-11-14 | [6 empty] | 2011-11-21 | [6 empty] | 2011-11-28 | [6 empty] | 2011-12-05 | [6 empty] | 2011-12-12 | [6 empty] | 2011-12-19 | [6 empty] | 2011-12-26 | [6 empty] | 2012-01-02 | [6 empty] | 2012-01-09 | [6 empty] | 2012-01-16 | [6 empty] | 2012-01-23 | [6 empty] | 2012-01-30 | [6 empty] | 2012-02-06 | [6 empty] | 2012-02-13 | [6 empty] | 2012-02-20 | [6 empty] | 2012-02-27 | [6 empty] | 2012-03-05 | [6 empty] | 2012-03-12 | [6 empty] | 2012-03-19 | [6 empty] | 2012-03-26 | [6 empty] | 2012-04-02 | [6 empty] | 2012-04-09 | [6 empty] | 2012-04-16 | [6 empty] | 2012-04-23 | [6 empty] | 2012-04-30 | [6 empty] | 2012-05-07 | [6 empty] | 2012-05-14 | [6 empty] | 2012-05-21 | [6 empty] | 2012-05-28 | [6 empty] | 2012-06-04 | [6 empty] | 2012-06-11 | [6 empty] | 2012-06-18 | [6 empty] | 2012-06-25 | [6 empty] | 2012-07-02 | [6 empty] | 2012-07-09 | [6 empty] | 2012-07-16 | [6 empty] | 2012-07-23
 | time axis 2011-10-17 to 2012-07-29
| TASK | DURn | ORININAL DUR | START | END |  | DAYS | time axis 2011-10-17 to 2012-07-29
WBS | Task Name |  |  | Start | Finish
2 | CONTRACT AWARD | 1 | 1 | 2011-10-17 | 2011-10-17 | 0 | 1 | bar: 2011-10-17
3 | PRACTICAL COMPLETION | 2 | 2 | 2012-03-15 | 2012-03-16 | 0 | 2 | 2012-03-16: 2
5 | Schedule A - Roadworks Dysart Bypass Road Widening Preliminaries - Site establishment, Provision for Workplace Health & Safety, Site Cleanup and Dis-establishment | 245 | 2 | 2011-10-01 | 2012-06-01
9 | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | 2 | 3 | 2011-10-20 | 2011-10-21 | 0 | 3 | 2011-10-21: 3
18 | Clearing & Grubbing and complete offsite disposal of Spoil inclusive of Dump Fees as required. | 12 | 6 | 2011-11-18 | 2011-11-29 | 0 | 6 | 2011-11-29: 6
23 | Prepare Base Gravel Surface for Primerseal & for Council Inspection, incl provision of compaction test results - Bypass Road Widening Ch 18 to 2801 | 2 | 6 | 2011-12-06 | 2011-12-07 | 0 | 6 | 2011-12-07: 6
27 | Primerseal complete in place (10mm stone ); spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED Bypass Road LHS Shoulder 1 metre wide Ch 510 to Ch 650 | 1 | 2 | 2011-12-08 | 2011-12-08 | 0 | 2 | 2011-12-08: 2
28 | Primerseal complete in place (10mm stone ); spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED Bypass Road Widening plus 1 metre wide shoulder RHS Ch 510 to Ch 650 | 1 | 2 | 2011-12-08 | 2011-12-08 | 0 | 2 | 2011-12-08: 2
29 | Bypass Road 7 metre section over where New RCBC culvert placement approx Ch 600 | 1 | 2 | 2011-12-08 | 2011-12-08 | 0 | 2 | 2011-12-08: 2
30 | Bitumen Seal - First Coat complete in place (16mm primerseal ) ; spray rates nominally to be 1.6 l/sqm C170 - SHOULDER WIDENING, SEAL DESIGN TO BE CONFIRMED Bypass Road Widening Ch 18 to Ch 510 | 1 | 2 | 2011-12-13 | 2011-12-13 | 0 | 2 | 2011-12-13: 2
31 | Bitumen Seal - First Coat complete in place (16mm primerseal ) ; spray rates nominally to be 1.6 l/sqm C170 - SHOULDER WIDENING, SEAL DESIGN TO BE CONFIRMED - Bypass Road Widening Ch 650 to Ch 2801 | 1 | 4 | 2011-12-13 | 2011-12-13 | 0 | 4 | 2011-12-13: 4
32 | Bitumen Seal - Second Coat complete in place (10mm second coat); spray rates nominally to be 1.2 l/sqm C170 - 7 METRE WIDE SEAL, SEAL DESIGN TO BE CONFIRMED -Bypass Road Widening Ch 18 to Ch 510 | 1 | 2 | 2011-12-13 | 2011-12-13 | 0 | 2 | 2011-12-13: 2
33 | Bitumen Seal - Second Coat complete in place (10mm second coat); spray rates nominally to be 1.2 l/sqm C170 - 7 METRE WIDE SEAL, SEAL DESIGN TO BE CONFIRMED - Bypass Road Widening Ch 650 to Ch 2801 | 1 | 3 | 2011-12-13 | 2011-12-13 | 0 | 3 | 2011-12-13: 3
34 | DG10 Asphaltic Concrete Pavement 35mm minimum thickness - complete in place including sawcut edges and neat smooth joins - Bypass Road Floodway - Ch 510 to Ch 650 (x 9 metres wide) | 3 | 2 | 2012-02-15 | 2012-02-17 | 0 | 2 | 2012-02-17: 2
38 | Soil Management Measures inclusive of: Prepare batters and drains for hydromulch placement | 7 | 13 | 2012-02-15 | 2012-02-21 | 0 | 13 | 2012-02-21: 13
41 | Supply and Install New Guide Posts - allow new on widened side only and adjacent to end wall extensions | 3 | 1 | 2012-01-18 | 2012-01-20 | 0 | 1 | bar: 2012-01-20
42 | Supply and Install Floodway Depth markers (G9-22-1A) | 1 | 1 | 2012-01-18 | 2012-01-18 | 0 | 1 | bar: 2012-01-18
43 | Remove Signs for widening and reinstate | 1 | 1 | 2012-01-18 | 2012-01-18 | 0 | 1 | bar: 2012-01-18
45 | Schedule B - Drainage Dysart Bypass Rd: Ch 49.400 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 dia SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay and backfi | 1 | 2 | 2011-10-24 | 2011-10-24 | 0 | 2 | 2011-10-24: 2
46 | 1 x 375 dia Endwall , Precast Type with wings Complete in place, incl. Excavate, sand, supply and install. | 1 | 1 | 2011-11-01 | 2011-11-01 | 0 | 1 | bar: 2011-11-01
47 | Ch 300 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-18 | 2011-10-18 | 0 | 2 | 2011-10-18: 2
48 | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 2 | 2 | 2011-11-03 | 2011-11-04 | 0 | 2 | 2011-11-04: 2
49 | Ch 600 Extend 2/1800 x 600 RCBC and Add 3 New Cells 1800 x 600, Installation to Main Roads Std Dwg 1359 - Extend existing 2/1800 x 600 RCBC Complete in place, incl. removal of existing Endwalls with care, excavate, sand, supply, lay & backfill. | 16 | 6 | 2011-11-01 | 2011-11-16 | 0 | 6 | 2011-11-16: 6
50 | Install NEW 3/1800 x 600 RCBC adjacent to existing lengthened Culvert Complete in place, incl. excavate, sand, supply, lay and backfill. | 7 | 3 | 2011-11-17 | 2011-11-23 | 0 | 3 | 2011-11-23: 3
51 | NEW 5/1800 x 600 Cast Insitu Endwalls and Aprons to Main Roads Std Dwgs 1304 and 1371 Complete in place, incl. Excavate, supply and construct (existing to be removed) | 5 | 1 | 2011-11-24 | 2011-11-28 | 0 | 1 | bar: 2011-11-28
52 | Excavate inlet and outlet at 0.5% grade with 10m base width to connect to existing drains neatly and smoothly. | 1 | 2 | 2011-11-17 | 2011-11-17 | 0 | 2 | 2011-11-17: 2
53 | Rip Rap Rock Protection in 250mm dia rock (layer 0.5m thick) to Outlet to extend 10m past culvert end and up batters a minimum of 1m - leave neat, tidy and even surface to rock. | 2 | 1 | 2011-12-01 | 2011-12-02 | 0 | 1 | bar: 2011-12-02
54 | Ch 800 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-26 | 2011-10-26 | 0 | 2 | 2011-10-26: 2
55 | 4 x 450 Cast Insitu Endwall ,Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 2 | 4 | 2011-11-07 | 2011-11-08 | 0 | 4 | 2011-11-08: 4
56 | Ch 1300 Extend 4/450 dia SRC Pipe Class 2 SRC, Installation to Main Roads STD DWG 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-27 | 2011-10-27 | 0 | 2 | 2011-10-27: 2
57 | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 2 | 1 | 2011-12-01 | 2011-12-02 | 0 | 1 | bar: 2011-12-02
58 | Ch 1500 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-28 | 2011-10-28 | 0 | 2 | 2011-10-28: 2
59 | 1 x 375 Endwall with wings , Precast Type Complete in place, incl. Excavate, sand, supply and install. | 1 | 2 | 2011-11-09 | 2011-11-09 | 0 | 2 | 2011-11-09: 2
60 | Ch 1749.800 Extend 2/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-29 | 2011-10-29 | 0 | 2 | 2011-10-29: 2
61 | 2 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 2 | 4 | 2011-11-10 | 2011-11-11 | 0 | 4 | 2011-11-11: 4
62 | Ch 1949.800 Extend 2/750 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 750 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 3 | 2011-10-30 | 2011-10-30 | 0 | 3 | 2011-10-30: 3
63 | 2 x 750 Cast Insitu Endwall ,Main Roads Std Dwg 1304 Complete in place, incl. Excavate, supply and construct | 2 | 2 | 2011-12-01 | 2011-12-02 | 0 | 2 | 2011-12-02: 2
64 | Ch 2200 Extend 1/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-30 | 2011-10-30 | 0 | 2 | 2011-10-30: 2
65 | 1 x 375 Endwall , Precast Type with wings, Complete in place, incl. Excavate, sand, supply and install. | 1 | 1 | 2011-11-14 | 2011-11-14 | 0 | 1 | bar: 2011-11-14
66 | Ch 2720 Extend 2/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 1 | 2011-10-30 | 2011-10-30 | 0 | 1 | bar: 2011-10-30
67 | 1/600 x 300 Cast Insitu Endwall and Apron to Main Roads Std Dwgs 1304 and 1371 Complete in place, incl. Excavate, supply and construct | 2 | 5 | 2011-11-15 | 2011-11-16 | 0 | 5 | 2011-11-16: 5
68 | Excavate inlet and outlet at 0.5% grade with 1.0m base width to connect to existing drains neatly and smoothly. | 1 | 2 | 2011-11-01 | 2011-11-01 | 0 | 2 | 2011-11-01: 2
71 | Schedule C - Dysart Middlemount / Dysart Bypass Intersection - Provision for Traffic and Safety including an approved Traffic Management Plan required by Council prior to commencement of site works. | 63 | 1 | 2011-11-15 | 2012-01-16 | 0 | 1 | bar: 2012-01-16
74 | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | 1 | 1 | 2011-11-15 | 2011-11-15 | 0 | 1 | bar: 2011-11-15
81 | Clearing & Grubbing, removal of existing kerb and complete offsite disposal of Spoil inclusive of Dump Fees as required. | 2 | 1 | 2011-11-16 | 2011-11-17 | 0 | 1 | bar: 2011-11-17
82 | Earthworks - excavate and place as embankment as directed - Cut to Spoil - to achieve boxed out deep to 500mm - material will be spoiled at IRC Tip. | 4 | 1 | 2011-11-18 | 2011-11-21 | 0 | 1 | bar: 2011-11-21
83 | Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | 1 | 2 | 2011-11-22 | 2011-11-22 | 0 | 2 | 2011-11-22: 2
84 | Prepare Dysart Bypass Rd - Middlemount Rd Intersection Subgrade Surface for Gravel Pavement & for Council / MRD Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 1 | 2 | 2011-11-09 | 2011-11-09 | 0 | 2 | 2011-11-09: 2
85 | Prepare Dysart Bypass Rd - Middlemount Rd Intersection Subgrade Surface for Gravel Pavement & for Council / MRD Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 2 | 4 | 2011-12-06 | 2011-12-07 | 0 | 4 | 2011-12-07: 4
86 | Prepare Base Gravel Surface for Primerseal & for Council / MRD Inspection, incl provision of compaction test results - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 1 | 4 | 2011-12-05 | 2011-12-05 | 0 | 4 | 2011-12-05: 4
87 | Prepare Base Gravel Surface for Primerseal & for Council / MRD Inspection, incl provision of compaction test results - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 2 | 1 | 2011-12-01 | 2011-12-02 | 0 | 1 | bar: 2011-12-02
88 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS - Base QT Type 2.1 @ 150mm deep | 1 | 1 | 2011-11-30 | 2011-11-30 | 0 | 1 | bar: 2011-11-30
89 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS Upper Sub-Base QT Type 2.3 @ 200mm deep | 1 | 2 | 2011-11-30 | 2011-11-30 | 0 | 2 | 2011-11-30: 2
90 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS - Lower Sub-Base QT Type 2.5 @ 150mm deep | 1 | 1 | 2011-11-29 | 2011-11-29 | 0 | 1 | bar: 2011-11-29
91 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS - Base QT Type 2.1 @ 150mm deep | 2 | 1 | 2011-11-28 | 2011-11-29 | 0 | 1 | bar: 2011-11-29
92 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS -Upper Sub-Base QT Type 2.3 @ 200mm deep | 4 | 1 | 2011-11-25 | 2011-11-28 | 0 | 1 | bar: 2011-11-28
93 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS -Lower Sub-Base QT Type 2.5 @ 150mm deep | 2 | 1 | 2011-11-23 | 2011-11-24 | 0 | 1 | bar: 2011-11-24
95 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 1 | 2 | 2011-12-13 | 2011-12-13 | 0 | 2 | 2011-12-13: 2
96 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 1 | 2 | 2011-12-13 | 2011-12-13 | 0 | 2 | 2011-12-13: 2
97 | Asphaltic Concrete Pavement MRD Type DG14 and 60 mm minimum thickness - complete in place. - Dysart Bypass Rd - Middlemount Rd Intersection Complete (overlaying existing seal area) | 2 | 2 | 2012-02-15 | 2012-02-16 | 0 | 2 | 2012-02-16: 2
98 | Medians Kerb at Intersections - Type 5 Concrete Kerb in minimum 25 MPa concrete | 2 | 2 | 2012-02-06 | 2012-02-07 | 0 | 2 | 2012-02-07: 2
99 | Street Lighting - Conduits and Bases - Electrical Mains Trenching and Conduiting including bends, draw-wire, sand, bed, backfill, warning tape: 1 x 100 dia LV (HD) + HARD COVER (Provisional Item) | 1 | 5 | 2012-02-01 | 2012-02-01 | 0 | 5 | 2012-02-01: 5
100 | Electrical Under Road Bore complete including conduit bends and draw-wire: 1 x 100 dia LV (HD) (Provisional Item) | 1 | 2 | 2011-12-13 | 2011-12-13 | 0 | 2 | 2011-12-13: 2
101 | Electrical Mains Cable Pit (Provisional Item) | 2 | 2 | 2012-02-01 | 2012-02-02 | 0 | 2 | 2012-02-02: 2
102 | Street Light Bases Complete in Place, including supply of rag bolts and excluding Conduiting Major Pole Base (NB - ALL 10.5m POLES NEED THE LARGER BASES) | 2 | 5 | 2012-02-07 | 2012-02-08 | 0 | 5 | 2012-02-08: 5
103 | Soil Management Measures inclusive of: Prepare batters and drains for hydromulch placement | 3 | 1 | 2012-02-21 | 2012-02-23 | 0 | 1 | bar: 2012-02-23
104 | Soil Management Measures inclusive of: Hydromulch to all disturbed areas as directed (batters and drains) | 1 | 2 | 2012-06-01 | 2012-06-01 | 0 | 2 | 2012-06-01: 2
106 | Supply and Install New Guide Posts | 2 | 2 | 2012-01-10 | 2012-01-11 | 0 | 2 | 2012-01-11: 2
107 | Supply and Install New Give Way Sign R1-2 | 1 | 1 | 2012-01-10 | 2012-01-10 | 0 | 1 | bar: 2012-01-10
108 | Linemarking Complete,Dysart Bypass Rd - Middlemount Rd Intersection - Reinstate existing and new lines as per drawing No 842 - R19 | 2 | 2 | 2012-06-05 | 2012-06-06 | 0 | 2 | 2012-06-06: 2
109 | Drainage - Ch 140 Middlemount Road Culvert 1A - Extend existing 600 x 300 RCBC RHS, complete in place incl. excavate, sand, supply, lay and backfill | 2 | 2 | 2011-11-16 | 2011-11-17 | 0 | 2 | 2011-11-17: 2
110 | Drainage - Ch 140 Middlemount Road - 1/600 x 300 Cast Insitu Endwall and Apron to Main Roads Std Dwgs complete in place | 4 | 2 | 2011-11-18 | 2011-11-21 | 0 | 2 | 2011-11-21: 2
161 | Remove & replace unsuitable - ch0 | 1 | 2 | 2011-11-08 | 2011-11-08 | 0 | 2 | 2011-11-08: 2
162 | Addiitonal drainage items | 3 | 3 | 2011-11-01 | 2011-11-03 | 0 | 3 | 2011-11-03: 3
168 | Stabilisation of Edges - Bypass Road | 9 | 8 | 2012-06-05 | 2012-06-13 | 0 | 8 | 2012-06-13: 8
179
| EDM Data - EDM - QM | [6 empty] | 1 | 3 | 3 | 3 | 6 | 6 | 6 | 8 | 8 | 10 | 12 | 14 | 16 | 22 | 22 | 25 | 25 | 28 | 30 | 30 | 30 | 30 | 36 | 40 | 40 | 44 | 44 | 44 | 45 | 46 | 57 | 62 | 62 | 62 | 62 | 65 | 67 | 70 | 71 | 71 | 71 | 71 | 73 | 81 | 84 | 84 | 89 | 89 | 89 | 93 | 93 | 103 | 109 | 109 | 109 | 109 | 109 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 127 | 129 | 129 | 129 | 129 | 129 | 130 | 130 | 132 | 132 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 138 | 140 | 140 | 140 | 140 | 140 | 142 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 149 | 151 | 151 | 151 | 151 | 164 | 164 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 169 | 169 | 169 | 169 | 169 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## FINAL - EDM LOE
P03 - Dysart Road
| Project Start |  |  | 2011-10-17
| Display Week |  |  | 1
[8 empty] | 2011-10-17 | [6 empty] | 2011-10-24 | [6 empty] | 2011-10-31 | [6 empty] | 2011-11-07 | [6 empty] | 2011-11-14 | [6 empty] | 2011-11-21 | [6 empty] | 2011-11-28 | [6 empty] | 2011-12-05 | [6 empty] | 2011-12-12 | [6 empty] | 2011-12-19 | [6 empty] | 2011-12-26 | [6 empty] | 2012-01-02 | [6 empty] | 2012-01-09 | [6 empty] | 2012-01-16 | [6 empty] | 2012-01-23 | [6 empty] | 2012-01-30 | [6 empty] | 2012-02-06 | [6 empty] | 2012-02-13 | [6 empty] | 2012-02-20 | [6 empty] | 2012-02-27 | [6 empty] | 2012-03-05 | [6 empty] | 2012-03-12 | [6 empty] | 2012-03-19 | [6 empty] | 2012-03-26 | [6 empty] | 2012-04-02 | [6 empty] | 2012-04-09 | [6 empty] | 2012-04-16 | [6 empty] | 2012-04-23 | [6 empty] | 2012-04-30 | [6 empty] | 2012-05-07 | [6 empty] | 2012-05-14 | [6 empty] | 2012-05-21 | [6 empty] | 2012-05-28 | [6 empty] | 2012-06-04 | [6 empty] | 2012-06-11 | [6 empty] | 2012-06-18 | [6 empty] | 2012-06-25
 | time axis 2011-10-17 to 2012-07-01
| TASK | DURn | ORININAL DUR | START | END |  | DAYS | time axis 2011-10-17 to 2012-07-01
WBS | Task Name |  |  | Start | Finish
2 | CONTRACT AWARD | 1 | 1 | 2011-10-17 | 2011-10-17 | 0 | 1 | bar: 2011-10-17
3 | PRACTICAL COMPLETION | 2 | 2 | 2012-03-15 | 2012-03-16 | 0 | 2 | bar: 2012-03-15 to 2012-03-16
5 | Schedule A - Roadworks Dysart Bypass Road Widening Preliminaries - Site establishment, Provision for Workplace Health & Safety, Site Cleanup and Dis-establishment | 245 | 2 | 2011-10-01 | 2012-06-01
9 | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | 2 | 3 | 2011-10-20 | 2011-10-21 | 0 | 3 | bar: 2011-10-20 to 2011-10-22
18 | Clearing & Grubbing and complete offsite disposal of Spoil inclusive of Dump Fees as required. | 12 | 6 | 2011-11-18 | 2011-11-29 | 0 | 6 | bar: 2011-11-18 to 2011-11-23
23 | Prepare Base Gravel Surface for Primerseal & for Council Inspection, incl provision of compaction test results - Bypass Road Widening Ch 18 to 2801 | 2 | 6 | 2011-12-06 | 2011-12-07 | 0 | 6 | bar: 2011-12-06 to 2011-12-11
27 | Primerseal complete in place (10mm stone ); spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED Bypass Road LHS Shoulder 1 metre wide Ch 510 to Ch 650 | 1 | 2 | 2011-12-08 | 2011-12-08 | 0 | 2 | bar: 2011-12-08 to 2011-12-09
28 | Primerseal complete in place (10mm stone ); spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED Bypass Road Widening plus 1 metre wide shoulder RHS Ch 510 to Ch 650 | 1 | 2 | 2011-12-08 | 2011-12-08 | 0 | 2 | bar: 2011-12-08 to 2011-12-09
29 | Bypass Road 7 metre section over where New RCBC culvert placement approx Ch 600 | 1 | 2 | 2011-12-08 | 2011-12-08 | 0 | 2 | bar: 2011-12-08 to 2011-12-09
30 | Bitumen Seal - First Coat complete in place (16mm primerseal ) ; spray rates nominally to be 1.6 l/sqm C170 - SHOULDER WIDENING, SEAL DESIGN TO BE CONFIRMED Bypass Road Widening Ch 18 to Ch 510 | 1 | 2 | 2011-12-13 | 2011-12-13 | 0 | 2 | bar: 2011-12-13 to 2011-12-14
31 | Bitumen Seal - First Coat complete in place (16mm primerseal ) ; spray rates nominally to be 1.6 l/sqm C170 - SHOULDER WIDENING, SEAL DESIGN TO BE CONFIRMED - Bypass Road Widening Ch 650 to Ch 2801 | 1 | 4 | 2011-12-13 | 2011-12-13 | 0 | 4 | bar: 2011-12-13 to 2011-12-16
32 | Bitumen Seal - Second Coat complete in place (10mm second coat); spray rates nominally to be 1.2 l/sqm C170 - 7 METRE WIDE SEAL, SEAL DESIGN TO BE CONFIRMED -Bypass Road Widening Ch 18 to Ch 510 | 1 | 2 | 2011-12-13 | 2011-12-13 | 0 | 2 | bar: 2011-12-13 to 2011-12-14
33 | Bitumen Seal - Second Coat complete in place (10mm second coat); spray rates nominally to be 1.2 l/sqm C170 - 7 METRE WIDE SEAL, SEAL DESIGN TO BE CONFIRMED - Bypass Road Widening Ch 650 to Ch 2801 | 1 | 3 | 2011-12-13 | 2011-12-13 | 0 | 3 | bar: 2011-12-13 to 2011-12-15
34 | DG10 Asphaltic Concrete Pavement 35mm minimum thickness - complete in place including sawcut edges and neat smooth joins - Bypass Road Floodway - Ch 510 to Ch 650 (x 9 metres wide) | 3 | 2 | 2012-02-15 | 2012-02-17 | 0 | 2 | bar: 2012-02-15 to 2012-02-16
38 | Soil Management Measures inclusive of: Prepare batters and drains for hydromulch placement | 7 | 13 | 2012-02-15 | 2012-02-21 | 0 | 13 | bar: 2012-02-15 to 2012-02-27
41 | Supply and Install New Guide Posts - allow new on widened side only and adjacent to end wall extensions | 3 | 1 | 2012-01-18 | 2012-01-20 | 0 | 1 | bar: 2012-01-18
42 | Supply and Install Floodway Depth markers (G9-22-1A) | 1 | 1 | 2012-01-18 | 2012-01-18 | 0 | 1 | bar: 2012-01-18
43 | Remove Signs for widening and reinstate | 1 | 1 | 2012-01-18 | 2012-01-18 | 0 | 1 | bar: 2012-01-18
45 | Schedule B - Drainage Dysart Bypass Rd: Ch 49.400 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 dia SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay and backfi | 1 | 2 | 2011-10-24 | 2011-10-24 | 0 | 2 | bar: 2011-10-24 to 2011-10-25
46 | 1 x 375 dia Endwall , Precast Type with wings Complete in place, incl. Excavate, sand, supply and install. | 1 | 1 | 2011-11-01 | 2011-11-01 | 0 | 1 | bar: 2011-11-01
47 | Ch 300 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-18 | 2011-10-18 | 0 | 2 | bar: 2011-10-18 to 2011-10-19
48 | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 2 | 2 | 2011-11-03 | 2011-11-04 | 0 | 2 | bar: 2011-11-03 to 2011-11-04
49 | Ch 600 Extend 2/1800 x 600 RCBC and Add 3 New Cells 1800 x 600, Installation to Main Roads Std Dwg 1359 - Extend existing 2/1800 x 600 RCBC Complete in place, incl. removal of existing Endwalls with care, excavate, sand, supply, lay & backfill. | 16 | 6 | 2011-11-01 | 2011-11-16 | 0 | 6 | bar: 2011-11-01 to 2011-11-06
50 | Install NEW 3/1800 x 600 RCBC adjacent to existing lengthened Culvert Complete in place, incl. excavate, sand, supply, lay and backfill. | 7 | 3 | 2011-11-17 | 2011-11-23 | 0 | 3 | bar: 2011-11-17 to 2011-11-19
51 | NEW 5/1800 x 600 Cast Insitu Endwalls and Aprons to Main Roads Std Dwgs 1304 and 1371 Complete in place, incl. Excavate, supply and construct (existing to be removed) | 5 | 1 | 2011-11-24 | 2011-11-28 | 0 | 1 | bar: 2011-11-24
52 | Excavate inlet and outlet at 0.5% grade with 10m base width to connect to existing drains neatly and smoothly. | 1 | 2 | 2011-11-17 | 2011-11-17 | 0 | 2 | bar: 2011-11-17 to 2011-11-18
53 | Rip Rap Rock Protection in 250mm dia rock (layer 0.5m thick) to Outlet to extend 10m past culvert end and up batters a minimum of 1m - leave neat, tidy and even surface to rock. | 2 | 1 | 2011-12-01 | 2011-12-02 | 0 | 1 | bar: 2011-12-01
54 | Ch 800 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-26 | 2011-10-26 | 0 | 2 | bar: 2011-10-26 to 2011-10-27
55 | 4 x 450 Cast Insitu Endwall ,Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 2 | 4 | 2011-11-07 | 2011-11-08 | 0 | 4 | bar: 2011-11-07 to 2011-11-10
56 | Ch 1300 Extend 4/450 dia SRC Pipe Class 2 SRC, Installation to Main Roads STD DWG 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-27 | 2011-10-27 | 0 | 2 | bar: 2011-10-27 to 2011-10-28
57 | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 2 | 1 | 2011-12-01 | 2011-12-02 | 0 | 1 | bar: 2011-12-01
58 | Ch 1500 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-28 | 2011-10-28 | 0 | 2 | bar: 2011-10-28 to 2011-10-29
59 | 1 x 375 Endwall with wings , Precast Type Complete in place, incl. Excavate, sand, supply and install. | 1 | 2 | 2011-11-09 | 2011-11-09 | 0 | 2 | bar: 2011-11-09 to 2011-11-10
60 | Ch 1749.800 Extend 2/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-29 | 2011-10-29 | 0 | 2 | bar: 2011-10-29 to 2011-10-30
61 | 2 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 2 | 4 | 2011-11-10 | 2011-11-11 | 0 | 4 | bar: 2011-11-10 to 2011-11-13
62 | Ch 1949.800 Extend 2/750 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 750 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 3 | 2011-10-30 | 2011-10-30 | 0 | 3 | bar: 2011-10-30 to 2011-11-01
63 | 2 x 750 Cast Insitu Endwall ,Main Roads Std Dwg 1304 Complete in place, incl. Excavate, supply and construct | 2 | 2 | 2011-12-01 | 2011-12-02 | 0 | 2 | bar: 2011-12-01 to 2011-12-02
64 | Ch 2200 Extend 1/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 2 | 2011-10-30 | 2011-10-30 | 0 | 2 | bar: 2011-10-30 to 2011-10-31
65 | 1 x 375 Endwall , Precast Type with wings, Complete in place, incl. Excavate, sand, supply and install. | 1 | 1 | 2011-11-14 | 2011-11-14 | 0 | 1 | bar: 2011-11-14
66 | Ch 2720 Extend 2/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 1 | 2011-10-30 | 2011-10-30 | 0 | 1 | bar: 2011-10-30
67 | 1/600 x 300 Cast Insitu Endwall and Apron to Main Roads Std Dwgs 1304 and 1371 Complete in place, incl. Excavate, supply and construct | 2 | 5 | 2011-11-15 | 2011-11-16 | 0 | 5 | bar: 2011-11-15 to 2011-11-19
68 | Excavate inlet and outlet at 0.5% grade with 1.0m base width to connect to existing drains neatly and smoothly. | 1 | 2 | 2011-11-01 | 2011-11-01 | 0 | 2 | bar: 2011-11-01 to 2011-11-02
71 | Schedule C - Dysart Middlemount / Dysart Bypass Intersection - Provision for Traffic and Safety including an approved Traffic Management Plan required by Council prior to commencement of site works. | 63 | 1 | 2011-11-15 | 2012-01-16 | 0 | 1 | bar: 2011-11-15
74 | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | 1 | 1 | 2011-11-15 | 2011-11-15 | 0 | 1 | bar: 2011-11-15
81 | Clearing & Grubbing, removal of existing kerb and complete offsite disposal of Spoil inclusive of Dump Fees as required. | 2 | 1 | 2011-11-16 | 2011-11-17 | 0 | 1 | bar: 2011-11-16
82 | Earthworks - excavate and place as embankment as directed - Cut to Spoil - to achieve boxed out deep to 500mm - material will be spoiled at IRC Tip. | 4 | 1 | 2011-11-18 | 2011-11-21 | 0 | 1 | bar: 2011-11-18
83 | Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | 1 | 2 | 2011-11-22 | 2011-11-22 | 0 | 2 | bar: 2011-11-22 to 2011-11-23
84 | Prepare Dysart Bypass Rd - Middlemount Rd Intersection Subgrade Surface for Gravel Pavement & for Council / MRD Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 1 | 2 | 2011-11-09 | 2011-11-09 | 0 | 2 | bar: 2011-11-09 to 2011-11-10
85 | Prepare Dysart Bypass Rd - Middlemount Rd Intersection Subgrade Surface for Gravel Pavement & for Council / MRD Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 2 | 4 | 2011-12-06 | 2011-12-07 | 0 | 4 | bar: 2011-12-06 to 2011-12-09
86 | Prepare Base Gravel Surface for Primerseal & for Council / MRD Inspection, incl provision of compaction test results - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 1 | 4 | 2011-12-05 | 2011-12-05 | 0 | 4 | bar: 2011-12-05 to 2011-12-08
87 | Prepare Base Gravel Surface for Primerseal & for Council / MRD Inspection, incl provision of compaction test results - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 2 | 1 | 2011-12-01 | 2011-12-02 | 0 | 1 | bar: 2011-12-01
88 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS - Base QT Type 2.1 @ 150mm deep | 1 | 1 | 2011-11-30 | 2011-11-30 | 0 | 1 | bar: 2011-11-30
89 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS Upper Sub-Base QT Type 2.3 @ 200mm deep | 1 | 2 | 2011-11-30 | 2011-11-30 | 0 | 2 | bar: 2011-11-30 to 2011-12-01
90 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS - Lower Sub-Base QT Type 2.5 @ 150mm deep | 1 | 1 | 2011-11-29 | 2011-11-29 | 0 | 1 | bar: 2011-11-29
91 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS - Base QT Type 2.1 @ 150mm deep | 2 | 1 | 2011-11-28 | 2011-11-29 | 0 | 1 | bar: 2011-11-28
92 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS -Upper Sub-Base QT Type 2.3 @ 200mm deep | 4 | 1 | 2011-11-25 | 2011-11-28 | 0 | 1 | bar: 2011-11-25
93 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS -Lower Sub-Base QT Type 2.5 @ 150mm deep | 2 | 1 | 2011-11-23 | 2011-11-24 | 0 | 1 | bar: 2011-11-23
95 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 1 | 2 | 2011-12-13 | 2011-12-13 | 0 | 2 | bar: 2011-12-13 to 2011-12-14
96 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 1 | 2 | 2011-12-13 | 2011-12-13 | 0 | 2 | bar: 2011-12-13 to 2011-12-14
97 | Asphaltic Concrete Pavement MRD Type DG14 and 60 mm minimum thickness - complete in place. - Dysart Bypass Rd - Middlemount Rd Intersection Complete (overlaying existing seal area) | 2 | 2 | 2012-02-15 | 2012-02-16 | 0 | 2 | bar: 2012-02-15 to 2012-02-16
98 | Medians Kerb at Intersections - Type 5 Concrete Kerb in minimum 25 MPa concrete | 2 | 2 | 2012-02-06 | 2012-02-07 | 0 | 2 | bar: 2012-02-06 to 2012-02-07
99 | Street Lighting - Conduits and Bases - Electrical Mains Trenching and Conduiting including bends, draw-wire, sand, bed, backfill, warning tape: 1 x 100 dia LV (HD) + HARD COVER (Provisional Item) | 1 | 5 | 2012-02-01 | 2012-02-01 | 0 | 5 | bar: 2012-02-01 to 2012-02-05
100 | Electrical Under Road Bore complete including conduit bends and draw-wire: 1 x 100 dia LV (HD) (Provisional Item) | 1 | 2 | 2011-12-13 | 2011-12-13 | 0 | 2 | bar: 2011-12-13 to 2011-12-14
101 | Electrical Mains Cable Pit (Provisional Item) | 2 | 2 | 2012-02-01 | 2012-02-02 | 0 | 2 | bar: 2012-02-01 to 2012-02-02
102 | Street Light Bases Complete in Place, including supply of rag bolts and excluding Conduiting Major Pole Base (NB - ALL 10.5m POLES NEED THE LARGER BASES) | 2 | 5 | 2012-02-07 | 2012-02-08 | 0 | 5 | bar: 2012-02-07 to 2012-02-11
103 | Soil Management Measures inclusive of: Prepare batters and drains for hydromulch placement | 3 | 1 | 2012-02-21 | 2012-02-23 | 0 | 1 | bar: 2012-02-21
104 | Soil Management Measures inclusive of: Hydromulch to all disturbed areas as directed (batters and drains) | 1 | 2 | 2012-06-01 | 2012-06-01 | 0 | 2 | bar: 2012-06-01 to 2012-06-02
106 | Supply and Install New Guide Posts | 2 | 2 | 2012-01-10 | 2012-01-11 | 0 | 2 | bar: 2012-01-10 to 2012-01-11
107 | Supply and Install New Give Way Sign R1-2 | 1 | 1 | 2012-01-10 | 2012-01-10 | 0 | 1 | bar: 2012-01-10
108 | Linemarking Complete,Dysart Bypass Rd - Middlemount Rd Intersection - Reinstate existing and new lines as per drawing No 842 - R19 | 2 | 2 | 2012-06-05 | 2012-06-06 | 0 | 2 | bar: 2012-06-05 to 2012-06-06
109 | Drainage - Ch 140 Middlemount Road Culvert 1A - Extend existing 600 x 300 RCBC RHS, complete in place incl. excavate, sand, supply, lay and backfill | 2 | 2 | 2011-11-16 | 2011-11-17 | 0 | 2 | bar: 2011-11-16 to 2011-11-17
110 | Drainage - Ch 140 Middlemount Road - 1/600 x 300 Cast Insitu Endwall and Apron to Main Roads Std Dwgs complete in place | 4 | 2 | 2011-11-18 | 2011-11-21 | 0 | 2 | bar: 2011-11-18 to 2011-11-19
161 | Remove & replace unsuitable - ch0 | 1 | 2 | 2011-11-08 | 2011-11-08 | 0 | 2 | bar: 2011-11-08 to 2011-11-09
162 | Addiitonal drainage items | 3 | 3 | 2011-11-01 | 2011-11-03 | 0 | 3 | bar: 2011-11-01 to 2011-11-03
168 | Stabilisation of Edges - Bypass Road | 9 | 8 | 2012-06-05 | 2012-06-13 | 0 | 8 | bar: 2012-06-05 to 2012-06-12
179
| EDM Data - EDM - QM | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 6 | 7 | 8 | 9 | 11 | 13 | 15 | 19 | 21 | 26 | 29 | 32 | 34 | 35 | 36 | 37 | 39 | 43 | 47 | 48 | 49 | 50 | 51 | 54 | 57 | 61 | 67 | 71 | 72 | 73 | 75 | 78 | 79 | 80 | 80 | 80 | 81 | 82 | 84 | 89 | 90 | 90 | 90 | 91 | 94 | 97 | 103 | 108 | 109 | 110 | 110 | 117 | 124 | 126 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 129 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 135 | 137 | 138 | 139 | 140 | 141 | 143 | 144 | 145 | 146 | 147 | 147 | 147 | 147 | 150 | 153 | 154 | 155 | 156 | 157 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 166 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 168 | 169 | 169 | 169 | 171 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.