## Estimate
[9 empty] | 1161213.1571 |  |  | 197712.9509 | 422296.4698 | 442866.9864 | 98336.75 | 1161213.1571
WBS | Line No. | Resource Name | Unit | Type | No | Prodn | Quantity | Rate | Cost | Usage | Duration | Labour | Material | Plant | Subcontract | Total | Portfolio WBS
3 |  | Preliminary & General Items
4 | Line No 2 Item No 1.01 | Mobilisation - Demobilisation | Item |  |  |  | 1 |  | 48943.75 |  | 5 | 650 | 0 | 27995 | 20298.75 | 48943.75
| 1 | Establishment on Site
| 2 | Float | LS | P | 500 | 1 | 1 | 1 | 500 | 500 | 1 | 0 | 0 | 500 | 0 | 500 | 907
| 3 | Float | LS | P | 750 | 1 | 1 | 1 | 750 | 750 | 1 | 0 | 0 | 750 | 0 | 750 | 907
| 4 | Float | LS | P | 2250 | 1 | 1 | 1 | 2250 | 2250 | 1 | 0 | 0 | 2250 | 0 | 2250 | 907
| 5 | Float | LS | P | 350 | 1 | 1 | 1 | 350 | 350 | 1 | 0 | 0 | 350 | 0 | 350 | 907
| 6 | Float | LS | P | 350 | 1 | 1 | 1 | 350 | 350 | 1 | 0 | 0 | 350 | 0 | 350 | 907
| 7 | Float | LS | P | 200 | 1 | 1 | 1 | 200 | 200 | 1 | 0 | 0 | 200 | 0 | 200 | 907
| 8 | Float | LS | P | 200 | 1 | 1 | 1 | 200 | 200 | 1 | 0 | 0 | 200 | 0 | 200 | 907
| 9 | Float | LS | P | 13995 | 1 | 1 | 1 | 13995 | 13995 | 1 | 0 | 0 | 13995 | 0 | 13995 | 907
| 10 | Float | LS | P | 200 | 1 | 1 | 1 | 200 | 200 | 1 | 0 | 0 | 200 | 0 | 200 | 907
| 11 | Float | LS | P | 200 | 1 | 1 | 1 | 200 | 200 | 1 | 0 | 0 | 200 | 0 | 200 | 907
| 14 | Insurances
| 15 | CAR | Item | S | 12000 | 1 | 1 | 1 | 12000 | 12000 | 1 | 0 | 0 | 0 | 12000 | 12000 | 904
| 17 | WHS Levy = ).525% of GST InclusicePrice
| 18 | WHS | Item | S | 7218.75 | 1 | 1 | 1 | 7218.75 | 7218.75 | 1 | 0 | 0 | 0 | 7218.75 | 7218.75 | 904
| 20 | Establishment of Borrow Areas
| 21 | Excavator - 25T | hr | P | 9 | 1 | 1 | 130 | 1170 | 9 | 1 | 0 | 0 | 1170 | 0 | 1170 | 13
| 22 | Geotech Level One | hr | S | 9 | 1 | 1 | 120 | 1080 | 9 | 1 | 0 | 0 | 0 | 1080 | 1080 | 13
| 23 | Project Engineer | week | L | 0.2 | 1 | 1 | 3250 | 650 | 0.2 | 1 | 650 | 0 | 0 | 0 | 650 | 31
| 24 | D6 | hr | P | 9 | 1 | 1 | 185 | 1665 | 9 | 1 | 0 | 0 | 1665 | 0 | 1665 | 31
| 25 | Excavator - 25T | hr | P | 9 | 1 | 1 | 130 | 1170 | 9 | 1 | 0 | 0 | 1170 | 0 | 1170 | 31
| 26 | A25 | hr | P | 27 | 1 | 1 | 185 | 4995 | 27 | 1 | 0 | 0 | 4995 | 0 | 4995 | 31
5 | Line No 3 Item No 1.02 | Preparation and implementation of Construction Environmental Management Plan. Quality Plan, Workplace Health and Safety Plan and Works Installation Plan | Item |  |  |  | 1 |  | 20838.9998 |  | 5 | 13212 | 3999.9998 | 3627 | 0 | 20838.9998
| 1 | Preparation of Plans
| 2 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 | 1 | 1 | 3250 | 0 | 0 | 0 | 3250 | 901
| 4 | Implimentation of Plans
| 5 | Project Supervisor | week | L | 1 | 1 | 1 | 3350 | 3350 | 1 | 1 | 3350 | 0 | 0 | 0 | 3350 | 902
| 6 | Labour | hr | L | 3 | 1 | 18 | 38 | 2052 | 54 | 18 | 2052 | 0 | 0 | 0 | 2052 | 151
| 7 | CAT297 | hr | P | 1 | 1 | 18 | 46.5 | 837 | 18 | 18 | 0 | 0 | 837 | 0 | 837 | 151
| 8 | Silt Fence | m | M | 1000 | 1 | 1 | 2 | 2000 |  |  | 0 | 2000 | 0 | 0 | 2000 | 151
| 9 | Pickets | each | M | 333.3333 | 1 | 1 | 6 | 1999.9998 |  |  | 0 | 1999.9998 | 0 | 0 | 1999.9998 | 151
| 11 | Maintenance
| 12 | Labour | hr | L | 120 | 1 | 1 | 38 | 4560 | 120 | 1 | 4560 | 0 | 0 | 0 | 4560 | 151
| 13 | CAT297 | hr | P | 60 | 1 | 1 | 46.5 | 2790 | 60 | 1 | 0 | 0 | 2790 | 0 | 2790 | 151
6 | Line No 4 Item No 1.03 | Site Inspections for approval of construction phases | Item |  |  |  | 1 |  | 6500 |  | 1 | 6500 | 0 | 0 | 0 | 6500
| 1 | Project Engineer | week | L | 2 | 1 | 1 | 3250 | 6500 | 2 | 1 | 6500 | 0 | 0 | 0 | 6500 | 901
| Line No 5 Item No 1.04 | Provision of 'As-Constructed' Drawings including survey | Item |  |  |  | 1 |  | 20230 |  | 1 | 17020 | 0 | 0 | 3210 | 20230
| 1 | Survey
| 2 | Surveyor | hr | L | 52 | 1 | 1 | 185 | 9620 | 52 | 1 | 9620 | 0 | 0 | 0 | 9620 | 11
| 3 | Surveyor | hr | L | 40 | 1 | 1 | 185 | 7400 | 40 | 1 | 7400 | 0 | 0 | 0 | 7400 | 11
| 4 | Geotechnical Testing
| 5 | Field Density | each | S | 50 | 1 | 1 | 45 | 2250 | 50 | 1 | 0 | 0 | 0 | 2250 | 2250 | 13
| 6 | Geotech Level One | hr | S | 8 | 1 | 1 | 120 | 960 | 8 | 1 | 0 | 0 | 0 | 960 | 960 | 13
7 |  | Cell Construction - Earthworks
8 | Line No 9 Item No 2.01 | Trim, Grade and compact the former waste layer | m2 |  |  |  | 20000 |  | 69435.5556 |  | 12 | 9162.2222 | 0 | 60273.3333 | 0 | 69435.5556
| 1 | Strip Vegetation & Topsoil
| 2 | Assume a total depth of 150mm of vegetation & topsoil. Strip with a D6 into stockpile. Bulk away with 25T & A25's to area requiring levelling.
| 3 | D6 | hr | P | 1 | 150 | 3000 | 185 | 3700 | 20 | 20 | 0 | 0 | 3700 | 0 | 3700 | 31
8.1 | 4 | Excavator - 25T | hr | P | 1 | 90 | 3000 | 130 | 4333.3333 | 33.3333 | 33.3333 | 0 | 0 | 4333.3333 | 0 | 4333.3333 | 31
| 5 | Labour | hr | L | 1 | 90 | 3000 | 38 | 1266.6667 | 33.3333 | 33.3333 | 1266.6667 | 0 | 0 | 0 | 1266.6667 | 31
| 8 | Grade & Shape clay under Topsoil
| 9 | Use a grader, and a spotter with dual grade laser.
8.2 | 10 | Grader | hr | P | 1 | 200 | 20000 | 135 | 13500 | 100 | 100 | 0 | 0 | 13500 | 0 | 13500 | 59
| 11 | Labour | hr | L | 1 | 200 | 20000 | 38 | 3800 | 100 | 100 | 3800 | 0 | 0 | 0 | 3800 | 59
| 13 | Import 700 cum to balance cut: Excavation & carting at other items.
8.3 | 14 | Grader | hr | P | 1 | 90 | 700 | 135 | 1050 | 7.7778 | 7.7778 | 0 | 0 | 1050 | 0 | 1050 | 51
| 15 | PF Roller Wet - No OP | hr | P | 1 | 90 | 700 | 58 | 451.1111 | 7.7778 | 7.7778 | 0 | 0 | 451.1111 | 0 | 451.1111 | 51
| 16 | Labour | hr | L | 1 | 90 | 700 | 38 | 295.5556 | 7.7778 | 7.7778 | 295.5556 | 0 | 0 | 0 | 295.5556 | 51
| 17 | Water Cart - Hire | hr | P | 1 | 90 | 700 | 95 | 738.8889 | 7.7778 | 7.7778 | 0 | 0 | 738.8889 | 0 | 738.8889 | 51
| 19 | Conmpact existing to 95%
| 20 | Use a PF Roller, WC. Follow the grader around so the PF marks can be cut out.
8.4 | 21 | PF Roller | day | P | 1 | 200 | 20000 | 365 | 36500 | 100 | 100 | 0 | 0 | 36500 | 0 | 36500 | 59
| 22 | Labour | hr | L | 1 | 200 | 20000 | 38 | 3800 | 100 | 100 | 3800 | 0 | 0 | 0 | 3800 | 59
9 | Line No 10 Item No 2.02 | High energy impact compact the graded surface of waste | m2 |  |  |  | 20000 |  | 31754.12 |  | 2 | 5382 | 492.12 | 0 | 25880 | 31754.12
| 1 | This will take 3 days to complete
| 3 | Broons - Day One | day | S | 1 | 1 | 1 | 15400 | 15400 | 1 | 1 | 0 | 0 | 0 | 15400 | 15400 | 510
| 4 | Broons - Day Two + | day | S | 2 | 1 | 1 | 5240 | 10480 | 2 | 1 | 0 | 0 | 0 | 10480 | 10480 | 510
| 6 | DN100 uPVC PN18 | m | M | 36 | 1 | 1 | 13.67 | 492.12 |  |  | 0 | 492.12 | 0 | 0 | 492.12 | 510
| 7 | Surveyor | hr | L | 18 | 1 | 1 | 185 | 3330 | 18 | 1 | 3330 | 0 | 0 | 0 | 3330 | 11
| 9 | Labour | hr | L | 54 | 1 | 1 | 38 | 2052 | 54 | 1 | 2052 | 0 | 0 | 0 | 2052 | 510
10 | Line No 11 Item No 2.03 | Excavate, select, lay, grade and compact the decomposed granite | m3 |  |  |  | 7100 |  | 72223.4649 |  | 7 | 7734.2602 | 0 | 64489.2047 | 0 | 72223.4649
| 1 | Cut To Fill
10.1 | 2 | Excavator - 25T | hr | P | 1 | 166.667 | 7100 | 130 | 5537.9889 | 42.5999 | 42.5999 | 0 | 0 | 5537.9889 | 0 | 5537.9889 | 51
| 3 | A25 | hr | P | 3 | 166.667 | 7100 | 185 | 23642.9527 | 127.7997 | 42.5999 | 0 | 0 | 23642.9527 | 0 | 23642.9527 | 51
| 4 | D6 | hr | P | 1 | 166.667 | 7100 | 185 | 7880.9842 | 42.5999 | 42.5999 | 0 | 0 | 7880.9842 | 0 | 7880.9842 | 51
| 5 | Water Cart - Hire | hr | P | 2 | 166.667 | 7100 | 95 | 8093.9838 | 85.1998 | 42.5999 | 0 | 0 | 8093.9838 | 0 | 8093.9838 | 51
| 6 | PF Roller Wet - No OP | hr | P | 1 | 166.667 | 7100 | 58 | 2470.7951 | 42.5999 | 42.5999 | 0 | 0 | 2470.7951 | 0 | 2470.7951 | 51
| 7 | Labour | hr | L | 2 | 166.667 | 7100 | 38 | 3237.5935 | 85.1998 | 42.5999 | 3237.5935 | 0 | 0 | 0 | 3237.5935 | 51
| 9 | Trim Profile
10.2 | 10 | Grader | hr | P | 1 | 300 | 17750 | 135 | 7987.5 | 59.1667 | 59.1667 | 0 | 0 | 7987.5 | 0 | 7987.5 | 59
| 11 | SD Roller - Wet (No Op) | hr | P | 1 | 300 | 17750 | 55 | 3254.1667 | 59.1667 | 59.1667 | 0 | 0 | 3254.1667 | 0 | 3254.1667 | 59
| 12 | Water Cart - Hire | hr | P | 1 | 300 | 17750 | 95 | 5620.8333 | 59.1667 | 59.1667 | 0 | 0 | 5620.8333 | 0 | 5620.8333 | 59
| 13 | Labour | hr | L | 2 | 300 | 17750 | 38 | 4496.6667 | 118.3333 | 59.1667 | 4496.6667 | 0 | 0 | 0 | 4496.6667 | 59
11 | Line No 12 Item No 2.04 | Construct, shape and compact the bunds, including anchor trenches | m3 |  |  |  | 3100 |  | 43112.1111 |  | 4 | 5294.6667 | 0 | 37817.4444 | 0 | 43112.1111
| 1 | Excavate Material from borrow areas
11.1 | 2 | Excavator - 25T | hr | P | 1 | 90 | 3100 | 130 | 4477.7778 | 34.4444 | 34.4444 | 0 | 0 | 4477.7778 | 0 | 4477.7778 | 51
| 3 | A25 | hr | P | 2 | 90 | 3100 | 185 | 12744.4444 | 68.8889 | 34.4444 | 0 | 0 | 12744.4444 | 0 | 12744.4444 | 51
| 6 | Stockpile material on approved area
| 8 | Construct Embankments as drawn including 95% compaction & trimming
| 9 | Place with the dozer and compact with a PF. Trim faces with the dozer between pushing out & Grader at end.
| 10 | D6 | hr | P | 1 | 90 | 3100 | 185 | 6372.2222 | 34.4444 | 34.4444 | 0 | 0 | 6372.2222 | 0 | 6372.2222 | 51
| 11 | PF Roller Wet - No OP | hr | P | 1 | 90 | 3100 | 58 | 1997.7778 | 34.4444 | 34.4444 | 0 | 0 | 1997.7778 | 0 | 1997.7778 | 51
| 12 | Water Cart - Hire | hr | P | 1 | 90 | 3100 | 95 | 3272.2222 | 34.4444 | 34.4444 | 0 | 0 | 3272.2222 | 0 | 3272.2222 | 51
| 13 | Labour | hr | L | 3 | 90 | 3100 | 38 | 3926.6667 | 103.3333 | 34.4444 | 3926.6667 | 0 | 0 | 0 | 3926.6667 | 51
| 14 | Final Trim & Pick up trimmings
| 15 | Grader | hr | P | 27 | 1 | 1 | 135 | 3645 | 27 | 1 | 0 | 0 | 3645 | 0 | 3645 | 59
| 16 | Excavator - 25T | hr | P | 4 | 1 | 1 | 130 | 520 | 4 | 1 | 0 | 0 | 520 | 0 | 520 | 59
| 17 | A25 | hr | P | 8 | 1 | 1 | 185 | 1480 | 8 | 1 | 0 | 0 | 1480 | 0 | 1480 | 59
| 20 | Anchor Trenches for HDPE, including Backfilling. (250m x .6 x .6) = 90cum
11.2 | 22 | Excavator - 25T | hr | P | 1 | 50 | 550 | 130 | 1430 | 11 | 11 | 0 | 0 | 1430 | 0 | 1430 | 222
11.3 | 24 | CAT297 | hr | P | 1 | 10 | 120 | 46.5 | 558 | 12 | 12 | 0 | 0 | 558 | 0 | 558 | 222
11.4 | 25 | Labour | hr | L | 3 | 10 | 120 | 38 | 1368 | 36 | 12 | 1368 | 0 | 0 | 0 | 1368 | 222
| 26 | Trench Roller | hr | P | 1 | 10 | 120 | 15 | 180 | 12 | 12 | 0 | 0 | 180 | 0 | 180 | 222
| 27 | Water Cart - Hire | hr | P | 1 | 10 | 120 | 95 | 1140 | 12 | 12 | 0 | 0 | 1140 | 0 | 1140 | 222
12 | Line No 13 Item No 2.05 | Construct, shape and compact the intercell bunds, including anchor trenches and the plywood | m3 |  |  |  | 3200 |  | 49669.8889 |  | 4 | 5421.3333 | 5500 | 38748.5556 | 0 | 49669.8889
| 1 | Excavate Material from borrow areas
12.1 | 2 | Excavator - 25T | hr | P | 1 | 90 | 3200 | 130 | 4622.2222 | 35.5556 | 35.5556 | 0 | 0 | 4622.2222 | 0 | 4622.2222 | 51
| 3 | A25 | hr | P | 2 | 90 | 3200 | 185 | 13155.5556 | 71.1111 | 35.5556 | 0 | 0 | 13155.5556 | 0 | 13155.5556 | 51
| 6 | Stockpile material on approved area
| 8 | Construct Embankments as drawn including 95% compaction & trimming
| 9 | Place with the dozer and compact with a PF. Trim faces with the dozer between pushing out & Grader at end.
| 10 | D6 | hr | P | 1 | 90 | 3200 | 185 | 6577.7778 | 35.5556 | 35.5556 | 0 | 0 | 6577.7778 | 0 | 6577.7778 | 51
| 11 | PF Roller Wet - No OP | hr | P | 1 | 90 | 3200 | 58 | 2062.2222 | 35.5556 | 35.5556 | 0 | 0 | 2062.2222 | 0 | 2062.2222 | 51
| 12 | Water Cart - Hire | hr | P | 1 | 90 | 3200 | 95 | 3377.7778 | 35.5556 | 35.5556 | 0 | 0 | 3377.7778 | 0 | 3377.7778 | 51
| 13 | Labour | hr | L | 3 | 90 | 3200 | 38 | 4053.3333 | 106.6667 | 35.5556 | 4053.3333 | 0 | 0 | 0 | 4053.3333 | 51
| 14 | Final Trim & Pick up trimmings
| 15 | Grader | hr | P | 27 | 1 | 1 | 135 | 3645 | 27 | 1 | 0 | 0 | 3645 | 0 | 3645 | 59
| 16 | Excavator - 25T | hr | P | 4 | 1 | 1 | 130 | 520 | 4 | 1 | 0 | 0 | 520 | 0 | 520 | 59
| 17 | A25 | hr | P | 8 | 1 | 1 | 185 | 1480 | 8 | 1 | 0 | 0 | 1480 | 0 | 1480 | 59
| 20 | Anchor Trenches for HDPE, including Backfilling. (250m x .6 x .6) = 90cum
12.2 | 21 | Qty to excavate from trenches |  |  |  |  | 550
| 22 | Excavator - 25T | hr | P | 1 | 50 | 550 | 130 | 1430 | 11 | 11 | 0 | 0 | 1430 | 0 | 1430 | 222
12.3 | 23 | Qty Backfill = 120 m3 |  |  |  |  | 120
12.4 | 24 | CAT297 | hr | P | 1 | 10 | 120 | 46.5 | 558 | 12 | 12 | 0 | 0 | 558 | 0 | 558 | 222
| 25 | Labour | hr | L | 3 | 10 | 120 | 38 | 1368 | 36 | 12 | 1368 | 0 | 0 | 0 | 1368 | 222
| 26 | Trench Roller | hr | P | 1 | 10 | 120 | 15 | 180 | 12 | 12 | 0 | 0 | 180 | 0 | 180 | 222
| 27 | Water Cart - Hire | hr | P | 1 | 10 | 120 | 95 | 1140 | 12 | 12 | 0 | 0 | 1140 | 0 | 1140 | 222
| 28 | Form Ply | m² | M | 1 | 1 | 550 | 10 | 5500 |  |  | 0 | 5500 | 0 | 0 | 5500 | 222
13 | Line No 14 Item No 2.06 | Supply, lay, grade and compact the gravel drainage layer | m3 |  |  |  | 4300 |  | 189376.1208 |  | 10 | 11742.1056 | 159637.5 | 17996.5153 | 0 | 189376.1208
Density of Agg = 1.35t/m3. Place at 600 t/day.
| 1 | 40mm Drainage Agg | ton | M | 1 | 1 | 5805 | 27.5 | 159637.5 |  |  | 0 | 159637.5 | 0 | 0 | 159637.5 | QMD40
13.1 | 2 | CAT297 | hr | P | 1 | 66.6667 | 5805 | 46.5 | 4048.9875 | 87.075 | 87.075 | 0 | 0 | 4048.9875 | 0 | 4048.9875 | 224
| 3 | Labour | hr | L | 3 | 66.6667 | 5805 | 38 | 9926.55 | 261.225 | 87.075 | 9926.55 | 0 | 0 | 0 | 9926.55 | 224
| 4 | Excavator - 25T | hr | P | 1 | 66.6667 | 5805 | 130 | 11319.75 | 87.075 | 87.075 | 0 | 0 | 11319.75 | 0 | 11319.75 | 224
13.2 | 5 | SD Roller - Wet (No Op) | hr | P | 1 | 300 | 14333.3333 | 55 | 2627.7778 | 47.7778 | 47.7778 | 0 | 0 | 2627.7778 | 0 | 2627.7778 | 224
| 6 | Labour | hr | L | 1 | 300 | 14333.3333 | 38 | 1815.5556 | 47.7778 | 47.7778 | 1815.5556 | 0 | 0 | 0 | 1815.5556 | 224
14 | Line No 15 Item No 2.07 | Supply, lay, grade and compact the gravel around the leachate pipes | m3 |  |  |  | 150 |  | 7821.1437 |  | 1 | 409.6083 | 6783.75 | 627.7854 | 0 | 7821.1437
| 1 | 20mm Drainage Agg | ton | M | 1 | 1 | 202.5 | 33.5 | 6783.75 |  |  | 0 | 6783.75 | 0 | 0 | 6783.75 | QMD40
14.1 | 2 | CAT297 | hr | P | 1 | 66.6667 | 202.5 | 46.5 | 141.2437 | 3.0375 | 3.0375 | 0 | 0 | 141.2437 | 0 | 141.2437 | 224
| 3 | Labour | hr | L | 3 | 66.6667 | 202.5 | 38 | 346.275 | 9.1125 | 3.0375 | 346.275 | 0 | 0 | 0 | 346.275 | 224
| 4 | Excavator - 25T | hr | P | 1 | 66.6667 | 202.5 | 130 | 394.875 | 3.0375 | 3.0375 | 0 | 0 | 394.875 | 0 | 394.875 | 224
14.2 | 5 | SD Roller - Wet (No Op) | hr | P | 1 | 300 | 500 | 55 | 91.6667 | 1.6667 | 1.6667 | 0 | 0 | 91.6667 | 0 | 91.6667 | 224
| 6 | Labour | hr | L | 1 | 300 | 500 | 38 | 63.3333 | 1.6667 | 1.6667 | 63.3333 | 0 | 0 | 0 | 63.3333 | 224
15 |  | Interim Channel Construction - Earthworks
16 | Line No 19 Item No 3.01 | Construct and shape the internal channel with clay material from site | m |  |  |  | 420 |  | 20541 |  | 3 | 2194.5 | 0 | 18346.5 | 0 | 20541
| 1 | Excavate Material from borrow areas
16.1 | 2 | Qty * 4.125 = Qty of clay to be imported / compacted as lining |  |  |  |  | 1732.5
16.2 | 3 | Excavator - 25T | hr | P | 1 | 90 | 1732.5 | 130 | 2502.5 | 19.25 | 19.25 | 0 | 0 | 2502.5 | 0 | 2502.5 | 51
| 4 | A25 | hr | P | 2 | 90 | 1732.5 | 185 | 7122.5 | 38.5 | 19.25 | 0 | 0 | 7122.5 | 0 | 7122.5 | 51
| 7 | Stockpile material on approved area
| 9 | Construct Embankments as drawn including 95% compaction & trimming
| 10 | Place with the dozer and compact with a PF. Trim faces with the dozer between pushing out & Grader at end.
| 11 | D6 | hr | P | 1 | 90 | 1732.5 | 185 | 3561.25 | 19.25 | 19.25 | 0 | 0 | 3561.25 | 0 | 3561.25 | 51
| 12 | PF Roller Wet - No OP | hr | P | 1 | 90 | 1732.5 | 58 | 1116.5 | 19.25 | 19.25 | 0 | 0 | 1116.5 | 0 | 1116.5 | 51
| 13 | Water Cart - Hire | hr | P | 1 | 90 | 1732.5 | 95 | 1828.75 | 19.25 | 19.25 | 0 | 0 | 1828.75 | 0 | 1828.75 | 51
| 14 | Labour | hr | L | 3 | 90 | 1732.5 | 38 | 2194.5 | 57.75 | 19.25 | 2194.5 | 0 | 0 | 0 | 2194.5 | 51
| 15 | Final Trim & Pick up trimmings
| 16 | Grader | hr | P | 9 | 1 | 1 | 135 | 1215 | 9 | 1 | 0 | 0 | 1215 | 0 | 1215 | 59
| 17 | Excavator - 25T | hr | P | 2 | 1 | 1 | 130 | 260 | 2 | 1 | 0 | 0 | 260 | 0 | 260 | 59
| 18 | A25 | hr | P | 4 | 1 | 1 | 185 | 740 | 4 | 1 | 0 | 0 | 740 | 0 | 740 | 59
17 | Line No 20 Item No 3.02 | Construct and shape the interim channel with soil material from site | m |  |  |  | 260 |  | 13559.6667 |  | 2 | 1358.5 | 0 | 12201.1667 | 0 | 13559.6667
| 1 | Excavate Material from borrow areas
17.1 | 2 | Qty * 4.125 = Qty of clay to be imported / compacted as lining |  |  |  |  | 1072.5
17.2 | 3 | Excavator - 25T | hr | P | 1 | 90 | 1072.5 | 130 | 1549.1667 | 11.9167 | 11.9167 | 0 | 0 | 1549.1667 | 0 | 1549.1667 | 51
| 4 | A25 | hr | P | 2 | 90 | 1072.5 | 185 | 4409.1667 | 23.8333 | 11.9167 | 0 | 0 | 4409.1667 | 0 | 4409.1667 | 51
| 7 | Stockpile material on approved area
| 9 | Construct Embankments as drawn including 95% compaction & trimming
| 10 | Place with the dozer and compact with a PF. Trim faces with the dozer between pushing out & Grader at end.
| 11 | D6 | hr | P | 1 | 90 | 1072.5 | 185 | 2204.5833 | 11.9167 | 11.9167 | 0 | 0 | 2204.5833 | 0 | 2204.5833 | 51
| 12 | PF Roller Wet - No OP | hr | P | 1 | 90 | 1072.5 | 58 | 691.1667 | 11.9167 | 11.9167 | 0 | 0 | 691.1667 | 0 | 691.1667 | 51
| 13 | Water Cart - Hire | hr | P | 1 | 90 | 1072.5 | 95 | 1132.0833 | 11.9167 | 11.9167 | 0 | 0 | 1132.0833 | 0 | 1132.0833 | 51
| 14 | Labour | hr | L | 3 | 90 | 1072.5 | 38 | 1358.5 | 35.75 | 11.9167 | 1358.5 | 0 | 0 | 0 | 1358.5 | 51
| 15 | Final Trim & Pick up trimmings
| 16 | Grader | hr | P | 9 | 1 | 1 | 135 | 1215 | 9 | 1 | 0 | 0 | 1215 | 0 | 1215 | 59
| 17 | Excavator - 25T | hr | P | 2 | 1 | 1 | 130 | 260 | 2 | 1 | 0 | 0 | 260 | 0 | 260 | 59
| 18 | A25 | hr | P | 4 | 1 | 1 | 185 | 740 | 4 | 1 | 0 | 0 | 740 | 0 | 740 | 59
18 |  | Leachate Pond Construction - Earthworks
19 | Line No 25 Item No 4.01 | Strip, shape and compact the floor of the pond | m2 |  |  |  | 2000 |  | 6690 |  | 2 | 886.6667 | 0 | 5803.3333 | 0 | 6690
| 1 | Strip Vegetation & Topsoil
| 2 | Assume a total depth of 150mm of vegetation & topsoil. Strip with a D6 into stockpile. Bulk away with 25T & A25's to area requiring levelling.
| 3 | D6 | hr | P | 1 | 150 | 300 | 185 | 370 | 2 | 2 | 0 | 0 | 370 | 0 | 370 | 31
19.1 | 4 | Excavator - 25T | hr | P | 1 | 90 | 300 | 130 | 433.3333 | 3.3333 | 3.3333 | 0 | 0 | 433.3333 | 0 | 433.3333 | 31
| 5 | Labour | hr | L | 1 | 90 | 300 | 38 | 126.6667 | 3.3333 | 3.3333 | 126.6667 | 0 | 0 | 0 | 126.6667 | 31
| 8 | Grade & Shape clay under Topsoil
| 9 | Use a grader, and a spotter with dual grade laser.
19.2 | 10 | Grader | hr | P | 1 | 200 | 2000 | 135 | 1350 | 10 | 10 | 0 | 0 | 1350 | 0 | 1350 | 59
| 11 | Labour | hr | L | 1 | 200 | 2000 | 38 | 380 | 10 | 10 | 380 | 0 | 0 | 0 | 380 | 59
| 15 | Conmpact existing to 95%
| 16 | Use a PF Roller, WC. Follow the grader around so the PF marks can be cut out.
| 17 | PF Roller | day | P | 1 | 200 | 2000 | 365 | 3650 | 10 | 10 | 0 | 0 | 3650 | 0 | 3650 | 59
| 18 | Labour | hr | L | 1 | 200 | 2000 | 38 | 380 | 10 | 10 | 380 | 0 | 0 | 0 | 380 | 59
20 | Line No 26 Item No 4.02 | Construct, shape and compact the embankment, including anchor trenches | m3 |  |  |  | 2000 |  | 27266.5556 |  | 3 | 3901.3333 | 0 | 23365.2222 | 0 | 27266.5556
| 1 | Excavate Material from borrow areas
20.1 | 2 | Excavator - 25T | hr | P | 1 | 90 | 2000 | 130 | 2888.8889 | 22.2222 | 22.2222 | 0 | 0 | 2888.8889 | 0 | 2888.8889 | 51
| 3 | A25 | hr | P | 2 | 90 | 2000 | 185 | 8222.2222 | 44.4444 | 22.2222 | 0 | 0 | 8222.2222 | 0 | 8222.2222 | 51
| 6 | Stockpile material on approved area
| 8 | Construct Embankments as drawn including 95% compaction & trimming
| 9 | Place with the dozer and compact with a PF. Trim faces with the dozer between pushing out & Grader at end.
| 10 | D6 | hr | P | 1 | 90 | 2000 | 185 | 4111.1111 | 22.2222 | 22.2222 | 0 | 0 | 4111.1111 | 0 | 4111.1111 | 51
| 11 | PF Roller Wet - No OP | hr | P | 1 | 90 | 2000 | 58 | 1288.8889 | 22.2222 | 22.2222 | 0 | 0 | 1288.8889 | 0 | 1288.8889 | 51
| 12 | Water Cart - Hire | hr | P | 1 | 90 | 2000 | 95 | 2111.1111 | 22.2222 | 22.2222 | 0 | 0 | 2111.1111 | 0 | 2111.1111 | 51
| 13 | Labour | hr | L | 3 | 90 | 2000 | 38 | 2533.3333 | 66.6667 | 22.2222 | 2533.3333 | 0 | 0 | 0 | 2533.3333 | 51
| 14 | Final Trim & Pick up trimmings
| 15 | Grader | hr | P | 9 | 1 | 1 | 135 | 1215 | 9 | 1 | 0 | 0 | 1215 | 0 | 1215 | 59
| 16 | Excavator - 25T | hr | P | 2 | 1 | 1 | 130 | 260 | 2 | 1 | 0 | 0 | 260 | 0 | 260 | 59
| 17 | A25 | hr | P | 4 | 1 | 1 | 185 | 740 | 4 | 1 | 0 | 0 | 740 | 0 | 740 | 59
| 20 | Anchor Trenches for HDPE, including Backfilling. (250m x .6 x .6) = 90cum
20.2 | 21 | trench length = 250m |  |  |  |  | 250
| 22 | Excavator - 25T | hr | P | 1 | 50 | 250 | 130 | 650 | 5 | 5 | 0 | 0 | 650 | 0 | 650 | 222
20.3 | 23 | Backfill qty = 120 m3 |  |  |  |  | 120
20.4 | 24 | CAT297 | hr | P | 1 | 10 | 120 | 46.5 | 558 | 12 | 12 | 0 | 0 | 558 | 0 | 558 | 222
| 25 | Labour | hr | L | 3 | 10 | 120 | 38 | 1368 | 36 | 12 | 1368 | 0 | 0 | 0 | 1368 | 222
| 26 | Trench Roller | hr | P | 1 | 10 | 120 | 15 | 180 | 12 | 12 | 0 | 0 | 180 | 0 | 180 | 222
| 27 | Water Cart - Hire | hr | P | 1 | 10 | 120 | 95 | 1140 | 12 | 12 | 0 | 0 | 1140 | 0 | 1140 | 222
21 | Line No 27 Item No 4.03 | Supply and install the securuty fence and access gates | m |  |  |  | 300 |  | 2970 |  | 5 | 0 | 0 | 0 | 2970 | 2970
| 1 | Security Fence | m | S | 1 | 6.6667 | 300 | 66 | 2970 | 45 | 45 | 0 | 0 | 0 | 2970 | 2970 | 131
22 |  | Sedimentation Pond Construction - Earthworks
23 | Line No 31 Item No 5.01 | Strip, excavate, shape and compact the floor of the pond | m2 |  |  |  | 2800 |  | 9366 |  | 2 | 1241.3333 | 0 | 8124.6667 | 0 | 9366
| 1 | Strip Vegetation & Topsoil
| 2 | Assume a total depth of 150mm of vegetation & topsoil. Strip with a D6 into stockpile. Bulk away with 25T & A25's to area requiring levelling.
| 3 | D6 | hr | P | 1 | 150 | 420 | 185 | 518 | 2.8 | 2.8 | 0 | 0 | 518 | 0 | 518 | 31
23.1 | 4 | Excavator - 25T | hr | P | 1 | 90 | 420 | 130 | 606.6667 | 4.6667 | 4.6667 | 0 | 0 | 606.6667 | 0 | 606.6667 | 31
| 5 | Labour | hr | L | 1 | 90 | 420 | 38 | 177.3333 | 4.6667 | 4.6667 | 177.3333 | 0 | 0 | 0 | 177.3333 | 31
| 8 | Grade & Shape clay under Topsoil
| 9 | Use a grader, and a spotter with dual grade laser.
23.2 | 10 | Grader | hr | P | 1 | 200 | 2800 | 135 | 1890 | 14 | 14 | 0 | 0 | 1890 | 0 | 1890 | 59
| 11 | Labour | hr | L | 1 | 200 | 2800 | 38 | 532 | 14 | 14 | 532 | 0 | 0 | 0 | 532 | 59
| 15 | Conmpact existing to 95%
| 16 | Use a PF Roller, WC. Follow the grader around so the PF marks can be cut out.
| 17 | PF Roller | day | P | 1 | 200 | 2800 | 365 | 5110 | 14 | 14 | 0 | 0 | 5110 | 0 | 5110 | 59
| 18 | Labour | hr | L | 1 | 200 | 2800 | 38 | 532 | 14 | 14 | 532 | 0 | 0 | 0 | 532 | 59
24 | Line No 32 Item No 5.02 | Construct, shape and compact the embankment | m3 |  |  |  | 1500 |  | 18081.6667 |  | 2 | 1900 | 0 | 16181.6667 | 0 | 18081.6667
| 1 | Excavate Material from borrow areas
24.1 | 2 | Excavator - 25T | hr | P | 1 | 90 | 1500 | 130 | 2166.6667 | 16.6667 | 16.6667 | 0 | 0 | 2166.6667 | 0 | 2166.6667 | 51
| 3 | A25 | hr | P | 2 | 90 | 1500 | 185 | 6166.6667 | 33.3333 | 16.6667 | 0 | 0 | 6166.6667 | 0 | 6166.6667 | 51
| 7 | Stockpile material on approved area
| 9 | Construct Embankments as drawn including 95% compaction & trimming
| 10 | Place with the dozer and compact with a PF. Trim faces with the dozer between pushing out & Grader at end.
| 11 | D6 | hr | P | 1 | 90 | 1500 | 185 | 3083.3333 | 16.6667 | 16.6667 | 0 | 0 | 3083.3333 | 0 | 3083.3333 | 51
| 12 | PF Roller Wet - No OP | hr | P | 1 | 90 | 1500 | 58 | 966.6667 | 16.6667 | 16.6667 | 0 | 0 | 966.6667 | 0 | 966.6667 | 51
| 13 | Water Cart - Hire | hr | P | 1 | 90 | 1500 | 95 | 1583.3333 | 16.6667 | 16.6667 | 0 | 0 | 1583.3333 | 0 | 1583.3333 | 51
| 14 | Labour | hr | L | 3 | 90 | 1500 | 38 | 1900 | 50 | 16.6667 | 1900 | 0 | 0 | 0 | 1900 | 51
| 15 | Final Trim & Pick up trimmings
| 16 | Grader | hr | P | 9 | 1 | 1 | 135 | 1215 | 9 | 1 | 0 | 0 | 1215 | 0 | 1215 | 59
| 17 | Excavator - 25T | hr | P | 2 | 1 | 1 | 130 | 260 | 2 | 1 | 0 | 0 | 260 | 0 | 260 | 59
| 18 | A25 | hr | P | 4 | 1 | 1 | 185 | 740 | 4 | 1 | 0 | 0 | 740 | 0 | 740 | 59
25 | Line No 33 Item No 5.03 | Construct the spillways, including scour protection | Item |  |  |  | 1 |  | 1670.5 |  | 1 | 228 | 662.5 | 780 | 0 | 1670.5
| 1 | Gabion Rock | tonne | M | 1 | 1 | 25 | 26.5 | 662.5 |  |  | 0 | 662.5 | 0 | 0 | 662.5 | QMR
| 2 | Excavator - 25T | hr | P | 6 | 1 | 1 | 130 | 780 | 6 | 1 | 0 | 0 | 780 | 0 | 780 | 221
| 3 | Labour | hr | L | 6 | 1 | 1 | 38 | 228 | 6 | 1 | 228 | 0 | 0 | 0 | 228 | 221
External Channel Construction - Earthworks
26 | Line No 37 Item No 6.01 | Excavate, grade and shape the external channel | m |  |  |  | 230 |  | 1449 |  | 1 | 0 | 0 | 1449 | 0 | 1449
| 1 | Excavator - 25T | hr | P | 1 | 50 | 230 | 130 | 598 | 4.6 | 4.6 | 0 | 0 | 598 | 0 | 598 | 59
| 2 | A25 | hr | P | 1 | 50 | 230 | 185 | 851 | 4.6 | 4.6 | 0 | 0 | 851 | 0 | 851 | 59
27 |  | Reprofile the external area
28 | Line No 41 Item No 7.01 | Excavate material for site and lay on the areas to be re-profiled | m2 |  |  |  | 20000 |  | 27766.6667 |  | 8 | 5066.6667 | 0 | 22700 | 0 | 27766.6667
| 1 | Use stripped topsoil from ponds & cell. in excess of 750 cum. Use D6 to level stockpiles & grader, WC & SD Roller to profile.
| 2 | D6 | hr | P | 1 | 150 | 3000 | 185 | 3700 | 20 | 20 | 0 | 0 | 3700 | 0 | 3700 | 51
| 3 | Grader | hr | P | 1 | 300 | 20000 | 135 | 9000 | 66.6667 | 66.6667 | 0 | 0 | 9000 | 0 | 9000 | 51
| 4 | Water Cart - Hire | hr | P | 1 | 300 | 20000 | 95 | 6333.3333 | 66.6667 | 66.6667 | 0 | 0 | 6333.3333 | 0 | 6333.3333 | 51
| 5 | SD Roller - Wet (No Op) | hr | P | 1 | 300 | 20000 | 55 | 3666.6667 | 66.6667 | 66.6667 | 0 | 0 | 3666.6667 | 0 | 3666.6667 | 51
| 6 | Labour | hr | L | 2 | 300 | 20000 | 38 | 5066.6667 | 133.3333 | 66.6667 | 5066.6667 | 0 | 0 | 0 | 5066.6667 | 51
29 | Line No 42 Item No 7.02 | Grade and shape the areas | m2 |  |  |  | 20000 |  | 24066.6667 |  | 8 | 5066.6667 | 0 | 19000 | 0 | 24066.6667
| 1 | Grader | hr | P | 1 | 300 | 20000 | 135 | 9000 | 66.6667 | 66.6667 | 0 | 0 | 9000 | 0 | 9000 | 59
| 2 | Water Cart - Hire | hr | P | 1 | 300 | 20000 | 95 | 6333.3333 | 66.6667 | 66.6667 | 0 | 0 | 6333.3333 | 0 | 6333.3333 | 59
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 300 | 20000 | 55 | 3666.6667 | 66.6667 | 66.6667 | 0 | 0 | 3666.6667 | 0 | 3666.6667 | 59
| 4 | Labour | hr | L | 2 | 300 | 20000 | 38 | 5066.6667 | 133.3333 | 66.6667 | 5066.6667 | 0 | 0 | 0 | 5066.6667 | 59
30 |  | Access Tracks
31 | Line No 46 Item No 8.01 | Construct the two access tracks in gravel pavement | m2 |  |  |  | 2400 |  | 36204.9284 |  | 2 | 1805.751 | 29884.8 | 4514.3774 | 0 | 36204.9284
| 1 | CBR45 | tonne | M | 1 | 1 | 1056 | 28.3 | 29884.8 |  |  | 0 | 29884.8 | 0 | 0 | 29884.8 | QM2.3
| 2 | Grader | hr | P | 1 | 66.667 | 1056 | 135 | 2138.3893 | 15.8399 | 15.8399 | 0 | 0 | 2138.3893 | 0 | 2138.3893 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 66.667 | 1056 | 55 | 871.1956 | 15.8399 | 15.8399 | 0 | 0 | 871.1956 | 0 | 871.1956 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 66.667 | 1056 | 95 | 1504.7925 | 15.8399 | 15.8399 | 0 | 0 | 1504.7925 | 0 | 1504.7925 | 62
| 5 | Labour | hr | L | 3 | 66.667 | 1056 | 38 | 1805.751 | 47.5198 | 15.8399 | 1805.751 | 0 | 0 | 0 | 1805.751 | 62
32 |  | Supply & Placement of Geocomposites
33 | Line No 50 Item No 9.01 | Supply and Placement of the Geocomposite Clay Liner (GCL) | m2 |  |  |  | 15200 |  | 140573.1568 |  | 11 | 11222.252 | 116553.6 | 12797.3049 | 0 | 140573.1568
Allow 6.5% for wastage & overlaps
| 1 | GCL | m² | M | 1 | 1 | 16188 | 7.2 | 116553.6 |  |  | 0 | 116553.6 | 0 | 0 | 116553.6 | 223
33.1 | 2 | Excavator - 25T | hr | P | 1 | 164.444 | 16188 | 130 | 12797.3049 | 98.4408 | 98.4408 | 0 | 0 | 12797.3049 | 0 | 12797.3049 | 223
| 3 | Labour | hr | L | 3 | 164.444 | 16188 | 38 | 11222.252 | 295.3224 | 98.4408 | 11222.252 | 0 | 0 | 0 | 11222.252 | 223
34 | Line No 51 Item No 9.02 | Supply and Placement of the Geotextile Protection | m2 |  |  |  | 15200 |  | 50804.5921 |  | 11 | 11064.1921 | 39740.4 | 0 | 0 | 50804.5921
Allow 5% for wastage & overlaps
| 1 | A64 | m² | M | 1 | 1 | 15960 | 2.49 | 39740.4 |  |  | 0 | 39740.4 | 0 | 0 | 39740.4 | 161
| 2 | Labour | hr | L | 3 | 164.444 | 15960 | 38 | 11064.1921 | 291.1629 | 97.0543 | 11064.1921 | 0 | 0 | 0 | 11064.1921 | 161
35 | Line No 52 Item No 9.03 | Supply and Placement of the Geotextile Separation | m2 |  |  |  | 15200 |  | 27502.9921 |  | 11 | 11064.1921 | 16438.8 | 0 | 0 | 27502.9921
| 1 | A24 | m² | M | 1 | 1 | 15960 | 1.03 | 16438.8 |  |  | 0 | 16438.8 | 0 | 0 | 16438.8 | 162
| 2 | Labour | hr | L | 3 | 164.444 | 15960 | 38 | 11064.1921 | 291.1629 | 97.0543 | 11064.1921 | 0 | 0 | 0 | 11064.1921 | 162
36 | Line No 53 Item No 9.04 | Supply and Placement of the HDPE Liner (Leachate Pond) | m2 |  |  |  | 3400 |  | 26553 |  | 1 | 0 | 0 | 0 | 26553 | 26553
| 1 | HDPE Liner | Item | S | 1 | 1 | 1 | 26553 | 26553 | 1 | 1 | 0 | 0 | 0 | 26553 | 26553 | 222
37 |  | Pipeworks
38 | Line No 57 Item No 10.01 | Supply and Placement of the perforated collection pipes | m |  |  |  | 550 |  | 21419 |  | 5 | 4484 | 12595 | 2340 | 2000 | 21419
| 1 | PN10 : 200 DiaPE100 | m | M | 1 | 1 | 550 | 22.9 | 12595 |  |  | 0 | 12595 | 0 | 0 | 12595 | SPF
| 3 | Drill Holes - 7,350 holes required. at 20 sec / hole = 41 hours.
| 4 | Labour | hr | L | 2 | 1 | 41 | 38 | 3116 | 82 | 41 | 3116 | 0 | 0 | 0 | 3116 | 91
| 5 | Welding
| 6 | PE Welder | each | S | 1 | 1 | 40 | 50 | 2000 | 40 | 40 | 0 | 0 | 0 | 2000 | 2000 | 91
| 7 | Placement
| 8 | Excavator - 25T | hr | P | 1 | 1 | 18 | 130 | 2340 | 18 | 18 | 0 | 0 | 2340 | 0 | 2340 | 91
| 9 | Labour | hr | L | 2 | 1 | 18 | 38 | 1368 | 36 | 18 | 1368 | 0 | 0 | 0 | 1368 | 91
39 | Line No 58 Item No 10.02 | Supply and palcement of the non-perforated collection pipes, including liner penetration and clean out risers | m |  |  |  | 80 |  | 6097 |  | 2 | 988 | 3789 | 520 | 800 | 6097
| 1 | PN10 : 200 DiaPE100 | m | M | 1 | 1 | 80 | 22.9 | 1832 |  |  | 0 | 1832 | 0 | 0 | 1832 | SPF
| 2 | PE Welder | each | S | 1 | 1 | 6 | 50 | 300 | 6 | 6 | 0 | 0 | 0 | 300 | 300 | 91
| 3 | Placement
| 4 | Excavator - 25T | hr | P | 1 | 1 | 4 | 130 | 520 | 4 | 4 | 0 | 0 | 520 | 0 | 520 | 91
| 5 | Labour | hr | L | 2 | 1 | 4 | 38 | 304 | 8 | 4 | 304 | 0 | 0 | 0 | 304 | 91
| 6 | Junctions
| 7 | MDPE Junctions | each | M | 1 | 1 | 5 | 391.4 | 1957 |  |  | 0 | 1957 | 0 | 0 | 1957 | 91
| 8 | PE Welder | each | S | 1 | 1 | 10 | 50 | 500 | 10 | 10 | 0 | 0 | 0 | 500 | 500 | 91
| 9 | Labour | hr | L | 2 | 1 | 9 | 38 | 684 | 18 | 9 | 684 | 0 | 0 | 0 | 684 | 91
40 | Line No 59 Item No 10.03 | Supply and Placement of the non-perforated delivery pipe | m |  |  |  | 110 |  | 4255 |  | 2 | 456 | 2519 | 780 | 500 | 4255
| 1 | PN10 : 200 DiaPE100 | m | M | 1 | 1 | 110 | 22.9 | 2519 |  |  | 0 | 2519 | 0 | 0 | 2519 | SPF
| 3 | Welding
| 4 | PE Welder | each | S | 1 | 1 | 10 | 50 | 500 | 10 | 10 | 0 | 0 | 0 | 500 | 500 | 91
| 5 | Placement
| 6 | Excavator - 25T | hr | P | 1 | 1 | 6 | 130 | 780 | 6 | 6 | 0 | 0 | 780 | 0 | 780 | 91
| 7 | Labour | hr | L | 2 | 1 | 6 | 38 | 456 | 12 | 6 | 456 | 0 | 0 | 0 | 456 | 91
1026742.5464
PROJECT OVERHEADS (TO BE SPREAD ACROSS ABOVE ITEMS)
41 | Line No. | Resource Name | Unit |  | No | Production | Quantity | Rate |  |  |  |  | Material | Plant | Subcontract | Total
42 | Line No OH 1 Item No | Project Supervision | item |  |  |  | 1 |  | 47350 |  | 11 | 36850 | 0 | 0 | 10500 | 47350
| 1 | Project Supervisor | week | L | 1 | 1 | 11 | 3350 | 36850 | 11 | 11 | 36850 | 0 | 0 | 0 | 36850 | 902
| 2 | Accommodation | day | S | 1 | 1 | 84 | 125 | 10500 | 84 | 84 | 0 | 0 | 0 | 10500 | 10500 | 911
43 | Line No OH 2 Item No | Project Engineering | item |  |  |  | 1 |  | 13000 |  | 1 | 13000 | 0 | 0 | 0 | 13000
| 1 | Project Engineer | week | L | 4 | 1 | 1 | 3250 | 13000 | 4 | 1 | 13000 | 0 | 0 | 0 | 13000 | 901
44 | Line No OH 3 Item No | Small Tools | item |  |  |  | 1 |  | 2500 |  | 0 | 0 | 2500 | 0 | 0 | 2500
| 1 | Small Tools | Item | M | 2500 | 1 | 1 | 1 | 2500 |  |  | 0 | 2500 | 0 | 0 | 2500 | 905
45 | Line No OH 4 Item No | Site Ammenities | item |  |  |  | 1 |  | 15000 |  | 1 | 0 | 0 | 15000 | 0 | 15000
| 1 | Crib Facilities | week | P | 12 | 1 | 1 | 1250 | 15000 | 12 | 1 | 0 | 0 | 15000 | 0 | 15000 | 903
46 | Line No OH 5 Item No | Dual Grade Laser | item |  |  |  | 1 |  | 3324 |  | 1 | 0 | 0 | 3324 | 0 | 3324
| 1 | Dual Grade Laser | week | P | 12 | 1 | 1 | 277 | 3324 | 12 | 1 | 0 | 0 | 3324 | 0 | 3324 | 905
47 | Line No OH 6 Item No | Retention Costs | Item |  |  |  | 1 |  | 5625 |  | 5625 | 0 | 0 | 0 | 5625 | 5625
| 1 | Retention Costs | Item | S | 1 | 1 | 5625 | 1 | 5625 | 5625 | 5625 | 0 | 0 | 0 | 5625 | 5625 | 904
VARIATIONS
48 | VAR 01 | Leachate pond spillway redesign | each |  | 835.25 |  | 80 |  | 21704.5045 |  | 3.003 | 114.1141 | 21200 | 390.3904 | 0 | 21704.5045
| 1 | Gabion Rock | tonne | M | 1 | 1 | 800 | 26.5 | 21200 |  |  | 0 | 21200 | 0 | 0 | 21200 | QMR
48.1 | 2 | Excavator - 25T | hr | P | 1 | 0.333 | 1 | 130 | 390.3904 | 3.003 | 3.003 | 0 | 0 | 390.3904 | 0 | 390.3904 | 221
| 3 | Labour | hr | L | 1 | 0.333 | 1 | 38 | 114.1141 | 3.003 | 3.003 | 114.1141 | 0 | 0 | 0 | 114.1141 | 221
49 | VAR02 | Additional deco material required to build up the main cell to bottom of GCL layer. | m³ |  | 5.5709 |  | 4019 |  | 22528.7278 |  | 22.3278 | 1696.9111 | 0 | 20831.8167 | 0 | 22528.7278
| 1 | Cut To Fill
49.1 | 2 | Excavator - 25T | hr | P | 1 | 180 | 4019 | 130 | 2902.6111 | 22.3278 | 22.3278 | 0 | 0 | 2902.6111 | 0 | 2902.6111 | 51
| 3 | A25 | hr | P | 3 | 180 | 4019 | 185 | 12391.9167 | 66.9833 | 22.3278 | 0 | 0 | 12391.9167 | 0 | 12391.9167 | 51
| 5 | Water Cart - Hire | hr | P | 2 | 180 | 4019 | 95 | 4242.2778 | 44.6556 | 22.3278 | 0 | 0 | 4242.2778 | 0 | 4242.2778 | 51
| 6 | PF Roller Wet - No OP | hr | P | 1 | 180 | 4019 | 58 | 1295.0111 | 22.3278 | 22.3278 | 0 | 0 | 1295.0111 | 0 | 1295.0111 | 51
| 7 | Labour | hr | L | 2 | 180 | 4019 | 38 | 1696.9111 | 44.6556 | 22.3278 | 1696.9111 | 0 | 0 | 0 | 1696.9111 | 51
51 | VAR04 | Replace marine plywood above the anchor tenches of intercell bunds with LDPE detection tape. | each |  | 3600 |  | -447 |  | -4470 |  | 1 | 0 | 0 | -4470 | 0 | -4470
51.1 | 2 | Form Ply | hr | P | 1 | 1 | -447 | 10 | -4470 | -447 | -447 | 0 | 0 | -4470 | 0 | -4470 | 222
52 | VAR05 | Removal and replacement of rubbish material in external channels | each |  | 8000 |  | 1450 |  | 7908.3784 |  | 7.8378 | 595.6757 | 0 | 7312.7027 | 0 | 7908.3784
52.1 | 2 | Excavator - 25T | hr | P | 1 | 185 | 1450 | 130 | 1018.9189 | 7.8378 | 7.8378 | 0 | 0 | 1018.9189 | 0 | 1018.9189 | 51
| 3 | A25 | hr | P | 3 | 185 | 1450 | 185 | 4350 | 23.5135 | 7.8378 | 0 | 0 | 4350 | 0 | 4350 | 51
| 5 | Water Cart - Hire | hr | P | 2 | 185 | 1450 | 95 | 1489.1892 | 15.6757 | 7.8378 | 0 | 0 | 1489.1892 | 0 | 1489.1892 | 51
| 6 | PF Roller Wet - No OP | hr | P | 1 | 185 | 1450 | 58 | 454.5946 | 7.8378 | 7.8378 | 0 | 0 | 454.5946 | 0 | 454.5946 | 51
| 7 | Labour | hr | L | 2 | 185 | 1450 | 38 | 595.6757 | 15.6757 | 7.8378 | 595.6757 | 0 | 0 | 0 | 595.6757 | 51

## Resources
| Resource Name | Description | Type | Unit | Currency | Base Rate
LABOUR | Labour | Labour | L | hr | AUD | 38
| Project Engineer | Project Engineer - Weekly Rate | L | week | AUD | 3250
| Project Supervisor | Project Supervisor | L | week | AUD | 3350
| Surveyor | Survey Team | L | hr | AUD | 185
MATERIAL RESOURCES | 20mm Drainage Agg |  | M | ton | AUD | 33.5
| 40mm Drainage Agg |  | M | ton | AUD | 27.5
| A24 | A24 - Bidum | M | m² | AUD | 1.03
| A64 | A64 Bidum | M | m² | AUD | 2.49
| CBR45 | CBR45 Road Base | M | tonne | AUD | 28.3
| DN100 uPVC PN18 |  | M | m | AUD | 13.67
| Form Ply |  | M | m² | AUD | 10
| GCL |  | M | m² | AUD | 7.2
| Gabion Rock | Gabion Rock (150 - 300) | M | tonne | AUD | 26.5
| MDPE Junctions |  | M | each | AUD | 391.4
| PN10 : 200 DiaPE100 | DN200 - PE100 MDPE Pipe | M | m | AUD | 22.9
| Pickets | Star Pickets | M | each | AUD | 6
| Silt Fence | Silt Fence | M | m | AUD | 2
| Small Tools |  | M | Item | AUD | 1
PLANT RESOURCES | A25 |  | P | hr | AUD | 185
| CAT297 | CAT297C MTL - No Operator | P | hr | AUD | 46.5
| Crib Facilities | Site Office & Tiolet, 1 Pump out during project. | P | week | AUD | 1250
| D6 | D6 Dozer | P | hr | AUD | 185
| Dual Grade Laser |  | P | week | AUD | 277
| Excavator - 25T | 25T Excavator - Wet Hire | P | hr | AUD | 130
| Float |  | P | LS | AUD | 1
| Grader | Grader - Wet Hire | P | hr | AUD | 135
| PF Roller | Pad Foot Roller - Dry | P | day | AUD | 365
| PF Roller Wet - No OP |  | P | hr | AUD | 58
| SD Roller - Wet (No Op) | SD Roller Wet Hire - No Operator | P | hr | AUD | 55
| Trench Roller |  | P | hr | AUD | 15
| Water Cart - Hire | Water Cart Hire | P | hr | AUD | 95
SUB-CONTRACT RESOURCES | Accommodation | Accommodation & 3 meals Rate | S | day | AUD | 125
| Broons - Day One | Broons Impact Roller First day hire | S | day | AUD | 15400
| Broons - Day Two + | Broons Impact Roller - Daily hire after day one | S | day | AUD | 5240
| CAR | CAR Insurance | S | Item | AUD | 1
| Field Density |  | S | each | AUD | 45
| Geotech Level One |  | S | hr | AUD | 120
| HDPE Liner |  | S | Item | AUD | 26553
| PE Welder |  | S | each | AUD | 50
| Retention Costs |  | S | Item | AUD | 1
| Security Fence | Security Fence - Three Strand Barb & Crank | S | m | AUD | 66
| WHS | WHS Insurance / Levy | S | Item | AUD | 1

## Model Inputs
WBS | DESCRIPTION - QTY & PRODUCTION VARIABLES | MODEL INPUT | TYPE | UOM
4 | Mobilisation - Demobilisation | 5 | Q | Item
5 | Preparation and implementation of Construction Environmental Management Plan. Quality Plan, Workplace Health and Safety Plan and Works Installation Plan | 5 | Q | Item
6 | Site Inspections for approval of construction phases | 1 | Q | Item
8 | Trim, Grade and compact the former waste layer | 20000 | P | m2
8.1 | Excavator - 25T | 90 | P | hr
8.2 | Grader | 200 | P | hr
8.3 | Grader | 700 | P | hr
8.4 | PF Roller | 200 | P | day
9 | High energy impact compact the graded surface of waste | 2 | Q | m2
10 | Excavate, select, lay, grade and compact the decomposed granite | 7100 | Q | m3
10.1 | Excavator - 25T | 166.667 | P | hr
10.2 | Grader | 300 | P | hr
11 | Construct, shape and compact the bunds, including anchor trenches | 3100 | Q | m3
11.1 | Excavator - 25T | 90 | P | hr
11.2 | Excavator - 25T | 550 | P | hr
11.3 | CAT297 | 10 | P | hr
11.4 | Labour | 120 | P | hr
12 | Construct, shape and compact the intercell bunds, including anchor trenches and the plywood | 3200 | Q | m3
12.1 | Excavator - 25T | 90 | P | hr
12.2 | Qty to excavate from trenches | 550 | P | 0%
12.3 | Qty Backfill = 120 m3 | 120 | P | 0%
12.4 | CAT297 | 10 | P | hr
13 | Supply, lay, grade and compact the gravel drainage layer | 4300 | Q | m3
13.1 | CAT297 | 66.6667 | P | hr
13.2 | SD Roller - Wet (No Op) | 300 | P | hr
14 | Supply, lay, grade and compact the gravel around the leachate pipes | 150 | Q | m3
14.1 | CAT297 | 66.6667 | P | hr
14.2 | SD Roller - Wet (No Op) | 300 | P | hr
16 | Construct and shape the internal channel with clay material from site | 420 | Q | m
16.1 | Qty * 4.125 = Qty of clay to be imported / compacted as lining | 1732.5 | P | 0%
16.2 | Excavator - 25T | 90 | P | hr
17 | Construct and shape the interim channel with soil material from site | 260 | Q | m
17.1 | Qty * 4.125 = Qty of clay to be imported / compacted as lining | 1072.5 | P | 0%
17.2 | Excavator - 25T | 90 | P | hr
19 | Strip, shape and compact the floor of the pond | 2000 | Q | m2
19.1 | Excavator - 25T | 90 | P | hr
19.2 | Grader | 200 | P | hr
20 | Construct, shape and compact the embankment, including anchor trenches | 2000 | Q | m3
20.1 | Excavator - 25T | 90 | P | hr
20.2 | trench length = 250m | 250 | P | 0%
20.3 | Backfill qty = 120 m3 | 120 | P | 0%
20.4 | CAT297 | 10 | P | hr
21 | Supply and install the securuty fence and access gates | 300 | Q | m
23 | Strip, excavate, shape and compact the floor of the pond | 2800 | Q | m2
23.1 | Excavator - 25T | 90 | P | hr
23.2 | Grader | 200 | P | hr
24 | Construct, shape and compact the embankment | 1500 | Q | m3
24.1 | Excavator - 25T | 90 | P | hr
25 | Construct the spillways, including scour protection | 1 | Q | Item
26 | Excavate, grade and shape the external channel | 230 | Q | m
28 | Excavate material for site and lay on the areas to be re-profiled | 20000 | Q | m2
29 | Grade and shape the areas | 20000 | Q | m2
31 | Construct the two access tracks in gravel pavement | 2400 | Q | m2
33 | Supply and Placement of the Geocomposite Clay Liner (GCL) | 15200 | Q | m2
33.1 | Excavator - 25T | 164.444 | P | hr
34 | Supply and Placement of the Geotextile Protection | 15200 | Q | m2
35 | Supply and Placement of the Geotextile Separation | 15200 | Q | m2
36 | Supply and Placement of the HDPE Liner (Leachate Pond) | 1 | Q | m2
38 | Supply and Placement of the perforated collection pipes | 550 | Q | m
39 | Supply and palcement of the non-perforated collection pipes, including liner penetration and clean out risers | 80 | Q | m
40 | Supply and Placement of the non-perforated delivery pipe | 110 | Q | m
48 | Leachate pond spillway redesign | 80 | Q | each
48.1 | Excavator - 25T | 0.333 | P | hr
49 | Additional deco material required to build up the main cell to bottom of GCL layer. | 4019 | Q | m³
49.1 | Excavator - 25T | 180 | P | hr
51 | Replace marine plywood above the anchor tenches of intercell bunds with LDPE detection tape. | -447 | Q | each
52 | Removal and replacement of rubbish material in external channels | 1450 | Q | each
52.1 | Excavator - 25T | 185 | P | hr

## Non-Work Days
Non-Working Calendar 2011 - 2015 (Queensland - Australia)
| 2011-01-01 |  | 2012-01-01 |  | 2013-01-01 |  | 2014-01-01 |  | 2015-01-01
| 2011-01-08 | 2011-01-09 | 2012-01-14 | 2012-01-15 | 2013-01-19 | 2013-01-20 | 2014-01-18 | 2014-01-19 | 2015-01-17 | 2015-01-18
| 2011-01-01 | 2011-01-02 |  | 2012-01-01 | 2013-01-05 | 2013-01-06 | 2014-01-04 | 2014-01-05 | 2015-01-03 | 2015-01-04
| 2011-01-08 | 2011-01-09 | 2012-01-07 | 2012-01-08 | 2013-01-12 | 2013-01-13 | 2014-01-11 | 2014-01-12 | 2015-01-10 | 2015-01-11
| 2011-01-15 | 2011-01-16 | 2012-01-14 | 2012-01-15 | 2013-01-19 | 2013-01-20 | 2014-01-18 | 2014-01-19 | 2015-01-17 | 2015-01-18
| 2011-01-22 | 2011-01-23 | 2012-01-21 | 2012-01-22 | 2013-01-26 | 2013-01-27 | 2014-01-25 | 2014-01-26 | 2015-01-24 | 2015-01-25
| 2011-01-29 | 2011-01-30 | 2012-01-28 | 2012-01-29 | 2013-02-02 | 2013-02-03 | 2014-02-01 | 2014-02-02 | 2015-01-31 | 2015-02-01
| 2011-02-05 | 2011-02-06 | 2012-02-04 | 2012-02-05 | 2013-02-09 | 2013-02-10 | 2014-02-08 | 2014-02-09 | 2015-02-07 | 2015-02-08
| 2011-02-12 | 2011-02-13 | 2012-02-11 | 2012-02-12 | 2013-02-16 | 2013-02-17 | 2014-02-15 | 2014-02-16 | 2015-02-14 | 2015-02-15
| 2011-02-19 | 2011-02-20 | 2012-02-18 | 2012-02-19 | 2013-02-23 | 2013-02-24 | 2014-02-22 | 2014-02-23 | 2015-02-21 | 2015-02-22
| 2011-02-26 | 2011-02-27 | 2012-02-25 | 2012-02-26 | 2013-03-02 | 2013-03-03 | 2014-03-01 | 2014-03-02 | 2015-02-28 | 2015-03-01
| 2011-03-05 | 2011-03-06 | 2012-03-03 | 2012-03-04 | 2013-03-09 | 2013-03-10 | 2014-03-08 | 2014-03-09 | 2015-03-07 | 2015-03-08
| 2011-03-12 | 2011-03-13 | 2012-03-10 | 2012-03-11 | 2013-03-16 | 2013-03-17 | 2014-03-15 | 2014-03-16 | 2015-03-14 | 2015-03-15
| 2011-03-19 | 2011-03-20 | 2012-03-17 | 2012-03-18 | 2013-03-23 | 2013-03-24 | 2014-03-22 | 2014-03-23 | 2015-03-21 | 2015-03-22
| 2011-03-26 | 2011-03-27 | 2012-03-24 | 2012-03-25 | 2013-03-30 | 2013-03-31 | 2014-03-29 | 2014-03-30 | 2015-03-28 | 2015-03-29
| 2011-04-02 | 2011-04-03 | 2012-03-31 | 2012-04-01 | 2013-04-06 | 2013-04-07 | 2014-04-05 | 2014-04-06 | 2015-04-04 | 2015-04-05
| 2011-04-09 | 2011-04-10 | 2012-04-07 | 2012-04-08 | 2013-04-13 | 2013-04-14 | 2014-04-12 | 2014-04-13 | 2015-04-11 | 2015-04-12
| 2011-04-16 | 2011-04-17 | 2012-04-14 | 2012-04-15 | 2013-04-20 | 2013-04-21 | 2014-04-19 | 2014-04-20 | 2015-04-18 | 2015-04-19
| 2011-04-23 | 2011-04-24 | 2012-04-21 | 2012-04-22 | 2013-04-27 | 2013-04-28 | 2014-04-26 | 2014-04-27 | 2015-04-25 | 2015-04-26
| 2011-04-30 | 2011-05-01 | 2012-04-28 | 2012-04-29 | 2013-05-04 | 2013-05-05 | 2014-05-03 | 2014-05-04 | 2015-05-02 | 2015-05-03
| 2011-05-07 | 2011-05-08 | 2012-05-05 | 2012-05-06 | 2013-05-11 | 2013-05-12 | 2014-05-10 | 2014-05-11 | 2015-05-09 | 2015-05-10
| 2011-05-14 | 2011-05-15 | 2012-05-12 | 2012-05-13 | 2013-05-18 | 2013-05-19 | 2014-05-17 | 2014-05-18 | 2015-05-16 | 2015-05-17
| 2011-05-21 | 2011-05-22 | 2012-05-19 | 2012-05-20 | 2013-05-25 | 2013-05-26 | 2014-05-24 | 2014-05-25 | 2015-05-23 | 2015-05-24
| 2011-05-28 | 2011-05-29 | 2012-05-26 | 2012-05-27 | 2013-06-01 | 2013-06-02 | 2014-05-31 | 2014-06-01 | 2015-05-30 | 2015-05-31
| 2011-06-04 | 2011-06-05 | 2012-06-02 | 2012-06-03 | 2013-06-08 | 2013-06-09 | 2014-06-07 | 2014-06-08 | 2015-06-06 | 2015-06-07
| 2011-06-11 | 2011-06-12 | 2012-06-09 | 2012-06-10 | 2013-06-15 | 2013-06-16 | 2014-06-14 | 2014-06-15 | 2015-06-13 | 2015-06-14
| 2011-06-18 | 2011-06-19 | 2012-06-16 | 2012-06-17 | 2013-06-22 | 2013-06-23 | 2014-06-21 | 2014-06-22 | 2015-06-20 | 2015-06-21
| 2011-06-25 | 2011-06-26 | 2012-06-23 | 2012-06-24 | 2013-06-29 | 2013-06-30 | 2014-06-28 | 2014-06-29 | 2015-06-27 | 2015-06-28
| 2011-07-02 | 2011-07-03 | 2012-06-30 | 2012-07-01 | 2013-07-06 | 2013-07-07 | 2014-07-05 | 2014-07-06 | 2015-07-04 | 2015-07-05
| 2011-07-09 | 2011-07-10 | 2012-07-07 | 2012-07-08 | 2013-07-13 | 2013-07-14 | 2014-07-12 | 2014-07-13 | 2015-07-11 | 2015-07-12
| 2011-07-16 | 2011-07-17 | 2012-07-14 | 2012-07-15 | 2013-07-20 | 2013-07-21 | 2014-07-19 | 2014-07-20 | 2015-07-18 | 2015-07-19
| 2011-07-23 | 2011-07-24 | 2012-07-21 | 2012-07-22 | 2013-07-27 | 2013-07-28 | 2014-07-26 | 2014-07-27 | 2015-07-25 | 2015-07-26
| 2011-07-30 | 2011-07-31 | 2012-07-28 | 2012-07-29 | 2013-08-03 | 2013-08-04 | 2014-08-02 | 2014-08-03 | 2015-08-01 | 2015-08-02
| 2011-08-06 | 2011-08-07 | 2012-08-04 | 2012-08-05 | 2013-08-10 | 2013-08-11 | 2014-08-09 | 2014-08-10 | 2015-08-08 | 2015-08-09
| 2011-08-13 | 2011-08-14 | 2012-08-11 | 2012-08-12 | 2013-08-17 | 2013-08-18 | 2014-08-16 | 2014-08-17 | 2015-08-15 | 2015-08-16
| 2011-08-20 | 2011-08-21 | 2012-08-18 | 2012-08-19 | 2013-08-24 | 2013-08-25 | 2014-08-23 | 2014-08-24 | 2015-08-22 | 2015-08-23
| 2011-08-27 | 2011-08-28 | 2012-08-25 | 2012-08-26 | 2013-08-31 | 2013-09-01 | 2014-08-30 | 2014-08-31 | 2015-08-29 | 2015-08-30
| 2011-09-03 | 2011-09-04 | 2012-09-01 | 2012-09-02 | 2013-09-07 | 2013-09-08 | 2014-09-06 | 2014-09-07 | 2015-09-05 | 2015-09-06
| 2011-09-10 | 2011-09-11 | 2012-09-08 | 2012-09-09 | 2013-09-14 | 2013-09-15 | 2014-09-13 | 2014-09-14 | 2015-09-12 | 2015-09-13
| 2011-09-17 | 2011-09-18 | 2012-09-15 | 2012-09-16 | 2013-09-21 | 2013-09-22 | 2014-09-20 | 2014-09-21 | 2015-09-19 | 2015-09-20
| 2011-09-24 | 2011-09-25 | 2012-09-22 | 2012-09-23 | 2013-09-28 | 2013-09-29 | 2014-09-27 | 2014-09-28 | 2015-09-26 | 2015-09-27
| 2011-10-01 | 2011-10-02 | 2012-09-29 | 2012-09-30 | 2013-10-05 | 2013-10-06 | 2014-10-04 | 2014-10-05 | 2015-10-03 | 2015-10-04
| 2011-10-08 | 2011-10-09 | 2012-10-06 | 2012-10-07 | 2013-10-12 | 2013-10-13 | 2014-10-11 | 2014-10-12 | 2015-10-10 | 2015-10-11
| 2011-10-15 | 2011-10-16 | 2012-10-13 | 2012-10-14 | 2013-10-19 | 2013-10-20 | 2014-10-18 | 2014-10-19 | 2015-10-17 | 2015-10-18
| 2011-10-22 | 2011-10-23 | 2012-10-20 | 2012-10-21 | 2013-10-26 | 2013-10-27 | 2014-10-25 | 2014-10-26 | 2015-10-24 | 2015-10-25
| 2011-10-29 | 2011-10-30 | 2012-10-27 | 2012-10-28 | 2013-11-02 | 2013-11-03 | 2014-11-01 | 2014-11-02 | 2015-10-31 | 2015-11-01
| 2011-11-05 | 2011-11-06 | 2012-11-03 | 2012-11-04 | 2013-11-09 | 2013-11-10 | 2014-11-08 | 2014-11-09 | 2015-11-07 | 2015-11-08
| 2011-11-12 | 2011-11-13 | 2012-11-10 | 2012-11-11 | 2013-11-16 | 2013-11-17 | 2014-11-15 | 2014-11-16 | 2015-11-14 | 2015-11-15
| 2011-11-19 | 2011-11-20 | 2012-11-17 | 2012-11-18 | 2013-11-23 | 2013-11-24 | 2014-11-22 | 2014-11-23 | 2015-11-21 | 2015-11-22
| 2011-11-26 | 2011-11-27 | 2012-11-24 | 2012-11-25 | 2013-11-30 | 2013-12-01 | 2014-11-29 | 2014-11-30 | 2015-11-28 | 2015-11-29
| 2011-12-03 | 2011-12-04 | 2012-12-01 | 2012-12-02 | 2013-12-07 | 2013-12-08 | 2014-12-06 | 2014-12-07 | 2015-12-05 | 2015-12-06
| 2011-12-10 | 2011-12-11 | 2012-12-08 | 2012-12-09 | 2013-12-14 | 2013-12-15 | 2014-12-13 | 2014-12-14 | 2015-12-12 | 2015-12-13
| 2011-12-17 | 2011-12-18 | 2012-12-15 | 2012-12-16 | 2013-12-21 | 2013-12-22 | 2014-12-20 | 2014-12-21 | 2015-12-19 | 2015-12-20
| 2011-12-24 | 2011-12-25 | 2012-12-22 | 2012-12-23 | 2013-12-28 | 2013-12-29 | 2014-12-27 | 2014-12-28 | 2015-12-26 | 2015-12-27
| 2011-12-31 |  | 2012-12-29 | 2012-12-30
Christmas Day | 2011-12-25 | 2011-12-23 | 2012-12-25 | 2012-01-02 | 2013-12-25 | 2013-01-02 | 2014-12-25 | 2014-01-02 | 2015-12-25 | 2015-01-02
Boxing Day | 2011-12-27 | 2011-12-24 | 2012-12-26 | 2012-01-03 | 2013-12-26 | 2013-01-03 | 2014-12-26 | 2014-01-03 | 2015-12-26 | 2015-01-05
New Years Day | 2011-01-01 | 2011-12-28 | 2012-01-01 | 2012-01-04 | 2013-01-01 | 2013-01-04 | 2014-01-01 | 2014-12-22 | 2015-01-01 | 2015-01-06
Australia Day | 2011-01-26 | 2011-12-29 | 2013-01-26 | 2012-01-05 | 2013-01-28 | 2013-12-23 | 2014-01-27 | 2014-12-23 | 2015-01-26 | 2015-01-07
Good Friday | 2011-04-22 | 2011-12-30 | 2012-04-06 | 2012-01-06 | 2013-03-29 | 2013-12-24 | 2014-04-18 | 2014-12-24 | 2015-04-03 | 2015-01-08
Easter Monday | 2011-04-25 |  | 2012-04-09 | 2012-12-24 | 2013-04-01 | 2013-12-27 | 2014-04-21 | 2014-12-29 | 2015-04-06 | 2015-01-09
ANZAC Day | 2011-04-26 |  | 2012-04-25 | 2012-12-27 | 2013-04-25 | 2013-12-30 | 2014-04-25 | 2014-12-30 | 2015-04-27 | 2015-12-24
Labour Day | 2011-05-02 |  | 2012-05-07 | 2012-12-28 | 2013-06-10 | 2013-12-31 | 2014-10-06 | 2014-12-31 | 2015-10-05 | 2015-12-27
Queen's Birthday | 2011-06-13 |  | 2012-06-11 | 2012-12-31 | 2013-10-07 |  | 2014-06-09 |  | 2015-06-08 | 2015-12-28
2015-12-29
2015-12-30
2015-12-31
|  | Xmas S/D | 2012-12-28: Xmas S/D; 2013-12-31: Xmas S/D; 2014-12-31: Xmas S/D; 2015-12-27: Xmas S/D
Work Hours Per Day |  | 9
Start Date |  | 2011-04-07

## Program Links
WBS | Task | Duration | WBS Predecessors | WBS Successors | Budget | %C Claim 01 | %C Claim 02 | %C Claim 03
1 | Contract Award | 0 |  | 5 | 0
2 | Practical Completion | 0 | 36,21,41,31,29,35,6 |  | 0
3 | Preliminary & General Items | 0 |  |  | 0
4 | Mobilisation - Demobilisation | 5 | 5 | 6,8,16,19,23 | 48943.75 | 70% | 80% | 100%
5 | Preparation and implementation of Construction Environmental Management Plan. Quality Plan, Workplace Health and Safety Plan and Works Installation Plan | 5 | 1 | 4 | 20838.9998 | 50% | 60% | 100%
6 | Site Inspections for approval of construction phases | 1 | 4 | 2 | 6500 | 25% | 50% | 100%
7 | Cell Construction - Earthworks | 0 |  |  | 0
8 | Trim, Grade and compact the former waste layer | 12 | 4 | 9 | 69435.5556 | 100% | 100% | 100%
9 | High energy impact compact the graded surface of waste | 2 | 8 | 10 | 31754.12 | 0% | 100% | 100%
10 | Excavate, select, lay, grade and compact the decomposed granite | 7 | 9 | 11,42 | 72223.4649 | 0% | 40% | 100%
11 | Construct, shape and compact the bunds, including anchor trenches | 4 | 10,42 | 12,16 | 43112.1111 | 0% | 40% | 100%
12 | Construct, shape and compact the intercell bunds, including anchor trenches and the plywood | 4 | 11 | 13,28,33,43 | 49669.8889 | 0% | 40% | 100%
13 | Supply, lay, grade and compact the gravel drainage layer | 10 | 12,43,33 | 14 | 189376.1208 | 0% | 0% | 100%
14 | Supply, lay, grade and compact the gravel around the leachate pipes | 1 | 13,38,40 | 35 | 7821.1437 | 0% | 0% | 100%
15 | Interim Channel Construction - Earthworks | 0 |  |  | 0
16 | Construct and shape the internal channel with clay material from site | 3 | 4,11 | 17,44 | 20541 | 0% | 0% | 100%
17 | Construct and shape the interim channel with soil material from site | 2 | 16,44 | 29 | 13559.6667 | 0% | 0% | 100%
18 | Leachate Pond Construction - Earthworks | 0 |  |  | 0
19 | Strip, shape and compact the floor of the pond | 2 | 4 | 20 | 6690 | 100% | 100% | 100%
20 | Construct, shape and compact the embankment, including anchor trenches | 3 | 19 | 21,23,36 | 27266.5556 | 70% | 100% | 100%
21 | Supply and install the securuty fence and access gates | 5 | 20 | 2 | 2970 | 0% | 0% | 100%
22 | Sedimentation Pond Construction - Earthworks | 0 |  |  | 0
23 | Strip, excavate, shape and compact the floor of the pond | 2 | 4,20 | 24 | 9366 | 50% | 100% | 100%
24 | Construct, shape and compact the embankment | 2 | 23 | 25 | 18081.6667 | 0% | 100% | 100%
25 | Construct the spillways, including scour protection | 1 | 24 | 41 | 1670.5 | 0% | 0% | 100%
26 | Excavate, grade and shape the external channel | 1 | 44 |  | 1449 | 0% | 0% | 100%
27 | Reprofile the external area | 0 |  |  | 0
28 | Excavate material for site and lay on the areas to be re-profiled | 8 | 12 | 29,31 | 27766.6667 | 0% | 0% | 100%
29 | Grade and shape the areas | 8 | 28,17 | 2 | 24066.6667 | 0% | 0% | 100%
30 | Access Tracks | 0 |  |  | 0
31 | Construct the two access tracks in gravel pavement | 2 | 28 | 2 | 36204.9284 | 0% | 0% | 100%
32 | Supply & Placement of Geocomposites | 0 |  |  | 0
33 | Supply and Placement of the Geocomposite Clay Liner (GCL) | 11 | 12 | 34,38,13 | 140573.1568 | 0% | 0% | 100%
34 | Supply and Placement of the Geotextile Protection | 11 | 33 | 35 | 50804.5921 | 0% | 0% | 100%
35 | Supply and Placement of the Geotextile Separation | 11 | 34,14 | 2 | 27502.9921 | 0% | 0% | 100%
36 | Supply and Placement of the HDPE Liner (Leachate Pond) | 1 | 20 | 2 | 26553 | 0% | 100% | 100%
37 | Pipeworks | 0 |  |  | 0
38 | Supply and Placement of the perforated collection pipes | 5 | 33 | 39,14 | 21419 | 0% | 50% | 100%
39 | Supply and palcement of the non-perforated collection pipes, including liner penetration and clean out risers | 2 | 38 | 40 | 6097 | 0% | 50% | 100%
40 | Supply and Placement of the non-perforated delivery pipe | 2 | 39 | 14 | 4255 | 0% | 50% | 100%
48 | Leachate pond spillway redesign | 3.003 | 25 | 2 | 21704.5045 | 0% | 0% | 100%
49 | Additional deco material required to build up the main cell to bottom of GCL layer. | 22.3278 | 10 | 11 | 22528.7278 | 0% | 0% | 100%
51 | Replace marine plywood above the anchor tenches of intercell bunds with LDPE detection tape. | 1 | 12 | 13 | -4470 | 0% | 0% | 100%
52 | Removal and replacement of rubbish material in external channels | 7.8378 | 16 | 17,26 | 7908.3784 | 0% | 0% | 100%

## Budget & Revenue
WBS | Item No | Description | Unit | Tender Budget | Tender Quantity | Contract Quantity | Tender Rate | Tender Total | Contract Total | Qty Claim 01 | % Claim 01 | Qty Claim 02 | % Claim 02 | Qty Claim 03 | % Claim 03 | Revenue Claim 01 | Revenue Claim 02 | Revenue Claim 03
Contract Items
3 | 1 | Preliminary and General Items |  | 0
4 | 1.01 | Mobilisation - Demobilisation | Item | 48943.75 | 1 | 1 | 58842 | 58842 | 58842 | 0.7 | 70% | 0.8 | 80% | 1 | 100% | 41189.4 | 47073.6 | 58842
5 | 1.02 | Preparation and implementation of Construction Environmental Management Plan. Quality Plan, Workplace Health and Safety Plan and Works Installation Plan | Item | 20838.9998 | 1 | 1 | 25053 | 25053 | 25053 | 0.5 | 50% | 0.6 | 60% | 1 | 100% | 12526.5 | 15031.8 | 25053
6 | 1.03 | Site Inspections for approval of construction phases | Item | 6500 | 1 | 1 | 7815 | 7815 | 7815 | 0.25 | 25% | 0.5 | 50% | 1 | 100% | 1953.75 | 3907.5 | 7815
| 1.04 | Provision of 'As-Constructed' Drawings including survey | Item |  | 1 | 1 | 24321 | 24321 | 24321 |  | 0% | 0.25 | 25% | 1 | 100% | 0 | 6080.25 | 24321
|  | Sub-total 1 - Preliminary and General Items | [5 empty] | 116031
7 | 2 | Cell Construction - Earthworks |  | 0
8 | 2.01 | Trim, Grade and compact the former waste layer | m2 | 69435.5556 | 20000 | 20000 | 4.17 | 83400 | 83400 | 20000 | 100% | 20000 | 100% | 20000 | 100% | 83400 | 83400 | 83400
9 | 2.02 | High energy impact compact the graded surface of waste | m2 | 31754.12 | 20000 | 20000 | 1.91 | 38200 | 38200 |  | 0% | 20000 | 100% | 20000 | 100% | 0 | 38200 | 38200
10 | 2.03 | Excavate, select, lay, grade and compact the decomposed granite | m3 | 72223.4649 | 7100 | 7100 | 12.23 | 86833 | 86833 |  | 0% | 2840 | 40% | 7100 | 100% | 0 | 34733.2 | 86833
11 | 2.04 | Construct, shape and compact the bunds, including anchor trenches | m3 | 43112.1111 | 3100 | 3100 | 16.72 | 51832 | 51832 |  | 0% | 1240 | 40% | 3100 | 100% | 0 | 20732.8 | 51832
12 | 2.05 | Construct, shape and compact the intercell bunds, including anchor trenches and the plywood | m3 | 49669.8889 | 3200 | 3200 | 18.66 | 59712 | 59712 |  | 0% | 1280 | 40% | 3200 | 100% | 0 | 23884.8 | 59712
13 | 2.06 | Supply, lay, grade and compact the gravel drainage layer | m3 | 189376.1208 | 4300 | 4300 | 52.94 | 227642 | 227642 |  | 0% |  | 0% | 4300 | 100% | 0 | 0 | 227642
14 | 2.07 | Supply, lay, grade and compact the gravel around the leachate pipes | m3 | 7821.1437 | 150 | 150 | 62.68 | 9402 | 9402 |  | 0% |  | 0% | 150 | 100% | 0 | 0 | 9402
|  | Sub-total 2 - Cell Construction - Earthworks | [5 empty] | 557021
15 | 3 | Interim Channel Construction - Earthworks |  | 0
16 | 3.01 | Construct and shape the internal channel with clay material from site | m | 20541 | 420 | 420 | 58.8 | 24696 | 24696 |  | 0% |  | 0% | 420 | 100% | 0 | 0 | 24696
17 | 3.02 | Construct and shape the interim channel with soil material from site | m | 13559.6667 | 260 | 260 | 62.7 | 16302 | 16302 |  | 0% |  | 0% | 260 | 100% | 0 | 0 | 16302
|  | Sub-total - Internal Channel Construction - Earthworks | [5 empty] | 40998
18 | 4 | Leachate Pond Construction - Earthworks |  | 0
19 | 4.01 | Strip, shape and compact the floor of the pond | m2 | 6690 | 2000 | 2000 | 4.02 | 8040 | 8040 | 2000 | 100% | 2000 | 100% | 2000 | 100% | 8040 | 8040 | 8040
20 | 4.02 | Construct, shape and compact the embankment, including anchor trenches | m3 | 27266.5556 | 2000 | 2000 | 16.39 | 32780 | 32780 | 1400 | 70% | 2000 | 100% | 2000 | 100% | 22946 | 32780 | 32780
21 | 4.03 | Supply and install the securuty fence and access gates | m | 2970 | 300 | 300 | 79.35 | 23805 | 23805 |  | 0% |  | 0% | 300 | 100% | 0 | 0 | 23805
|  | Sub-total 4 - Leachate Pond Construction - Earthworks | [5 empty] | 64625
22 | 5 | Sedimentation Pond Construction - Earthworks |  | 0
23 | 5.01 | Strip, excavate, shape and compact the floor of the pond | m2 | 9366 | 2800 | 2800 | 4.02 | 11256 | 11256 | 1400 | 50% | 2800 | 100% | 2800 | 100% | 5628 | 11256 | 11256
24 | 5.02 | Construct, shape and compact the embankment | m3 | 18081.6667 | 1500 | 1500 | 14.49 | 21735 | 21735 |  | 0% | 1500 | 100% | 1500 | 100% | 0 | 21735 | 21735
25 | 5.03 | Construct the spillways, including scour protection | Item | 1670.5 | 1 | 1 | 2008 | 2008 | 2008 |  | 0% |  | 0% | 1 | 100% | 0 | 0 | 2008
|  | Sub-total 5 - Sedimentation Pond Construction - Earthworks | [5 empty] | 34999
| 6 | External Channel Construction - Earthworks
26 | 6.01 | Excavate, grade and shape the external channel | m | 1449 | 230 | 230 | 7.57 | 1741.1 | 1741.1 |  | 0% |  | 0% | 230 | 100% | 0 | 0 | 1741.1
|  | Sub-total 6 - External Channel Construction - Earthworks | [5 empty] | 1741.1
27 | 7 | Re-profile the external area |  | 0
28 | 7.01 | Excavate material for site and lay on the areas to be re-profiled | m2 | 27766.6667 | 20000 | 20000 | 1.67 | 33400 | 33400 |  | 0% |  | 0% | 20000 | 100% | 0 | 0 | 33400
29 | 7.02 | Grade and shape the areas | m2 | 24066.6667 | 20000 | 20000 | 1.45 | 29000 | 29000 |  | 0% |  | 0% | 20000 | 100% | 0 | 0 | 29000
|  | Sub-total 7 - External Channel Construction - Earthworks | [5 empty] | 62400
30 | 8 | Access Tracks |  | 0
31 | 8.01 | Construct the two access tracks in gravel pavement | m2 | 36204.9284 | 2400 | 2400 | 18.13 | 43512 | 43512 |  | 0% |  | 0% | 2400 | 100% | 0 | 0 | 43512
|  | Sub-total 8 - Access Tracks | [5 empty] | 43512
32 | 9 | Supply and Placement of the Geocomposites |  | 0
33 | 9.01 | Supply and Placement of the Geocomposite Clay Liner (GCL) | m2 | 140573.1568 | 15200 | 15200 | 11.12 | 169024 | 169024 |  | 0% |  | 0% | 15200 | 100% | 0 | 0 | 169024
34 | 9.02 | Supply and Placement of the Geotextile Protection | m2 | 50804.5921 | 15200 | 15200 | 4.02 | 61104 | 61104 |  | 0% |  | 0% | 15200 | 100% | 0 | 0 | 61104
35 | 9.03 | Supply and Placement of the Geotextile Separation | m2 | 27502.9921 | 15200 | 15200 | 2.18 | 33136 | 33136 |  | 0% |  | 0% | 15200 | 100% | 0 | 0 | 33136
36 | 9.04 | Supply and Placement of the HDPE Liner (Leachate Pond) | m2 | 26553 | 3400 | 3400 | 9.39 | 31926 | 31926 |  | 0% | 3400 | 100% | 3400 | 100% | 0 | 31926 | 31926
|  | Sub-total 9 - Supply and Placement of Geocomposites | [5 empty] | 295190
37 | 10 | Pipeworks |  | 0
38 | 10.01 | Supply and Placement of the perforated collection pipes | m | 21419 | 550 | 550 | 46.82 | 25751 | 25751 |  | 0% | 275 | 50% | 550 | 100% | 0 | 12875.5 | 25751
39 | 10.02 | Supply and palcement of the non-perforated collection pipes, including liner penetration and clean out risers | m | 6097 | 80 | 80 | 91.62 | 7329.6 | 7329.6 |  | 0% | 40 | 50% | 80 | 100% | 0 | 3664.8 | 7329.6
40 | 10.03 | Supply and Placement of the non-perforated delivery pipe | m | 4255 | 110 | 110 | 46.5 | 5115 | 5115 |  | 0% | 55 | 50% | 110 | 100% | 0 | 2557.5 | 5115
|  | Sub-total 10 - Pipeworks | [5 empty] | 38195.6
Variations
48 | VAR 01 | Leachate pond spillway redesign | each | 21704.5045 | 1 | 1 | 1004 | 1004 | 1004 |  | 0% |  | 0% | 1 | 100% | 0 | 0 | 1004
49 | VAR02 | Additional deco material required to build up the main cell to bottom of GCL layer. | m³ | 22528.7278 | 4019 | 4019 | 12.23 | 49152.37 | 49152.37 |  | 0% |  | 0% | 4019 | 100% | 0 | 0 | 49152.37
| VAR03 | Removal of concrete and other waste material near leachate pond. | each |  | 1 | 1 |  |  |  |  | 0% |  | 0% | 1 | 100% | 0 | 0 | 0
51 | VAR04 | Replace marine plywood above the anchor tenches of intercell bunds with LDPE detection tape. | each | -4470 | 1 | 1 | -4473.2 | -4473.2 | -4473.2 |  | 0% |  | 0% | 1 | 100% | 0 | 0 | -4473.2
52 | VAR05 | Removal and replacement of rubbish material in external channels | each | 7908.3784 | 1 | 1 | 10206.9 | 10206.9 | 10206.9 |  | 0% |  | 0% | 1 | 100% | 0 | 0 | 10206.9
|  | Subtotal, excluding GST | [5 empty] | 1310602.77
|  | Total all contract items, variations and sundry items (including GST) |  | 1054184.1571 |  |  |  | 1441663.047 | [7 empty] | 175683.65 | 397878.75 | 1310602.77

## Portfolio WBS
[29 empty] | ** | 100 | hrs | 159.45 | 15945 | 15945 | 312.6471 | 51 | 0 | 0 | 10 | #DIV/0! | 4.5 | 698 | 1406.9118 | 8160
Portfolio WBS | Description | Quantity | Unit | Budget | BAC Rate | Final Qty | Final Cost | Final Rate |  |  | 2011-04-01 |  |  |  |  | 2011-05-01 |  |  |  |  | 2011-06-01 |  |  |  |  | 2011-07-01
|  | SQ |  | BAC |  | AQ | AC |  | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV
11 | Survey - Construction | 110 | hrs | 20350 | 185 | 103 | 19038.5 | 184.8398 | 20 | 3700 | 16 | 2954.4 | 3161.165 | 40 | 7400 | 59.5 | 11016.8 | 11755.5825 | 70 | 12950 | 91 | 16842.3 | 17979.1262 | 110 | 20350 | 103 | 19038.5 | 20350
13 | QA Testing | 1 | item | 5460 | 5460 | 1 | 11878.85 | 11878.85 | 0 | 0 | 0 | 0 | 0 | 0.5 | 2730 | 0.65 | 7389.85 | 3549 | 1 | 5460 | 0.65 | 7389.85 | 3549 | 1 | 5460 | 1 | 11878.85 | 5460
31 | Strip Topsoil to Stockpile | 2500 | m3 | 20012 | 8.0048 | 2500 | 8287.17 | 3.3149 | 2500 | 20012 | 2500 | 8287.17 | 20012 | 2500 | 20012 | 2500 | 8287.17 | 20012 | 2500 | 20012 | 2500 | 8287.17 | 20012 | 2500 | 20012 | 2500 | 8287.17 | 20012
51 | Cut to Fill | 22919 | m3 | 244936.5155 | 10.6871 | 22919 | 292965.585 | 12.7827 | 0 | 0 | 1400 | 34066.54 | 14961.871 | 16000 | 170992.8116 | 12500 | 169440.325 | 133588.134 | 22919 | 244936.5155 | 22919 | 292965.585 | 244936.5155 | 22919 | 244936.5155 | 22919 | 292965.585 | 244936.5155
59 | Trim unpaved areas - footpaths, batters, drains etc | 86600 | m2 | 138448.8333 | 1.5987 | 86600 | 105179.34 | 1.2145 | 10000 | 15987.1632 | 5000 | 6900 | 7993.5816 | 45000 | 71942.2344 | 49500 | 62115 | 79136.4579 | 86600 | 138448.8333 | 82500 | 99312.8 | 131894.0964 | 86600 | 138448.8333 | 86600 | 105179.34 | 138448.8333
62 | Place & Compact Gravel | 1056 | tonne | 6320.1284 | 5.985 | 641 | 3632.5 | 5.6669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056 | 6320.1284 | 641 | 3632.5 | 6320.1284 | 1056 | 6320.1284 | 641 | 3632.5 | 6320.1284
91 | InstallLeachate Pipes | 740 | m | 14825 | 20.0338 | 740 | 11473.04 | 15.5041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 740 | 14825 | 245 | 3235.4 | 4908.277 | 740 | 14825 | 740 | 11473.04 | 14825
131 | Fencing Sub-contractors | 300 | m | 2970 | 9.9 | 300 | 18430 | 61.4333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 2970 | 300 | 18430 | 2970 | 300 | 2970 | 300 | 18430 | 2970
151 | Supply & Place Silt fences & protective devices | 1 | item | 14238.9998 | 14238.9998 | 0 | 0 | 0 | 1 | 14238.9998 | 0 |  | 0 | 1 | 14238.9998 | 0 |  | 14238.9998 | 1 | 14238.9998 | 0 |  | 14238.9998 | 1 | 14238.9998 | 0 |  | 14238.9998
161 | Supply & Place A64 Protection Geotextile | 15960 | m2 | 50804.5921 | 3.1832 | 15960 | 48447.015 | 3.0355 | 0 | 0 | 0 | 0 | 0 | 7500 | 23874.3384 | 0 | 0 | 0 | 15960 | 50804.5921 | 12550 | 38097 | 39949.7262 | 15960 | 50804.5921 | 15960 | 48447.015 | 50804.5921
162 | Supply & Place A24 Separation Geotextile | 15960 | m2 | 27502.9921 | 1.7232 | 15960 | 16222.5 | 1.0164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15960 | 27502.9921 | 15960 | 16222.5 | 27502.9921 | 15960 | 27502.9921 | 15960 | 16222.5 | 27502.9921
191 | Dayworks |  |  |  | 0 | 1 | 7230 | 7230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7230 | 0 | 0 | 0 | 1 | 7230 | 0
221 | Construct Spillway | 1 | item | 1512.5045 | 1512.5045 | 1 | 1180.15 | 1180.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1512.5045 | 1 | 1180.15 | 1512.5045 | 1 | 1512.5045 | 1 | 1180.15 | 1512.5045
222 | Supply & Install HDPE Liner | 3400 | m2 | 40831 | 12.0091 | 3400 | 36108.2 | 10.6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2880 | 30608.2 | 34586.2588 | 3400 | 40831 | 3400 | 36108.2 | 40831 | 3400 | 40831 | 3400 | 36108.2 | 40831
223 | Supply & Place GCL Liner | 16118 | m2 | 140573.1568 | 8.7215 | 16118 | 141962.25 | 8.8077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16118 | 140573.1568 | 3100 | 28403.76 | 27036.6538 | 16118 | 140573.1568 | 16118 | 141962.25 | 140573.1568
224 | Place Drainage Gravel | 6008 | tonne | 30776.0146 | 5.1225 | 6656 | 11791.5 | 1.7716 | 0 | 0 | 0 | 0 | 0 | 2000 | 10245.0115 | 0 | 0 | 0 | 6008 | 30776.0146 | 4000 | 6132 | 18495.2011 | 6008 | 30776.0146 | 6656 | 11791.5 | 30776.0146
510 | High Energy Compaction | 20000 | m2 | 28424.12 | 1.4212 | 20000 | 25880 | 1.294 | 0 | 0 | 0 | 0 | 0 | 20000 | 28424.12 | 20000 | 25880 | 28424.12 | 20000 | 28424.12 | 20000 | 25880 | 28424.12 | 20000 | 28424.12 | 20000 | 25880 | 28424.12
901 | Project Management | 7.2 | week | 22750 | 3159.7222 | 0.5 | 1359.33 | 2718.66 | 2 | 6319.4444 | 0.4 | 954.33 | 18200 | 4 | 12638.8889 | 0.4 | 954.33 | 18200 | 7.2 | 22750 | 1 | 1359.33 | 45500 | 7.2 | 22750 | 0.5 | 1359.33 | 22750
902 | Project Supervision | 12 | week | 40200 | 3350 | 16 | 42014.91 | 2625.9319 | 3 | 10050 | 3.3 | 8554.76 | 8291.25 | 6 | 20100 | 8.8 | 22594.225 | 22110 | 12 | 40200 | 14.5 | 37978.995 | 36431.25 | 12 | 40200 | 16 | 42014.91 | 40200
903 | Project Facilities | 12 | week | 15000 | 1250 | 16 | 12881.8 | 805.1125 | 3 | 3750 | 3.6 | 2875.04 | 3375 | 6 | 7500 | 9.9 | 8006.04 | 9281.25 | 12 | 15000 | 13.8 | 11155.56 | 12937.5 | 12 | 15000 | 16 | 12881.8 | 15000
904 | Project Insurance, Fees & Levies | 1 | item | 24843.75 | 24843.75 | 1 | 6981.2 | 6981.2 | 0.75 | 18632.8125 | 0.9 | 4736.04 | 22359.375 | 1 | 24843.75 | 0.9 | 4736.04 | 22359.375 | 1 | 24843.75 | 0.98 | 5129.73 | 24346.875 | 1 | 24843.75 | 1 | 6981.2 | 24843.75
905 | Small Tools | 1 | item | 5824 | 5824 | 1 | 614.9 | 614.9 | 0.25 | 1456 | 0.01 | 68.4 | 58.24 | 0.75 | 4368 | 0.06 | 349.82 | 349.44 | 1 | 5824 | 1 | 614.9 | 5824 | 1 | 5824 | 1 | 614.9 | 5824
907 | Site Establishment | 1 | item | 18995 | 18995 | 1 | 27660.31 | 27660.31 | 0.25 | 4748.75 | 0.25 | 8330.655 | 4748.75 | 1 | 18995 | 0.9 | 23383.375 | 17095.5 | 1 | 18995 | 0.95 | 25178.49 | 18045.25 | 1 | 18995 | 1 | 27660.31 | 18995
910 | Site de-Establishment | 1 | item | 0 | 0 | 1 | 2117.6 | 2117.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2117.6 | 0
911 | Accommodation | 84 | days | 10500 | 125 | 84 | 4579.81 | 54.5215 | 24 | 3000 | 24 | 1040 | 3000 | 48 | 6000 | 48 | 3191.24 | 6000 | 72 | 9000 | 72 | 4231.24 | 9000 | 84 | 10500 | 84 | 4579.81 | 10500
QM2.3 | CBR 45 | 1056 | tonne | 29884.8 | 28.3 | 641 | 14753.12 | 23.0158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056 | 29884.8 | 641 | 14753.12 | 29884.8 | 1056 | 29884.8 | 641 | 14753.12 | 29884.8
QMD40 | 40mm Drainage Aggregate | 6008 | tonne | 166421.25 | 27.6999 | 6656 | 187089.96 | 28.1085 | 0 | 0 | 0 | 0 | 0 | 2000 | 55399.8835 | 0 | 0 | 0 | 6008 | 166421.25 | 5313 | 150155.81 | 132841.9623 | 6008 | 166421.25 | 6656 | 187089.96 | 166421.25
QMR | Rock | 37 | tonne | 21862.5 | 590.8784 | 62 | 1741.04 | 28.0813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 21862.5 | 62 | 1741.04 | 21862.5 | 37 | 21862.5 | 62 | 1741.04 | 21862.5
SPF | Supply HDPE Leachate Pipe | 740 | m | 16946 | 22.9 | 740 | 23479.5 | 31.7291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 740 | 23479.5 | 16946 | 740 | 16946 | 740 | 23479.5 | 16946 | 740 | 16946 | 740 | 23479.5 | 16946
| Totals |  |  | 1161213.1571 |  |  | 1084980.08 |  |  | 101895.1699 |  | 78767.335 | 106161.2327 |  | 499705.0381 |  | 401431.915 | 437632.118 |  | 1152313.1571 |  | 885126.93 | 984180.4784 |  | 1161213.1571 |  | 1084980.08 | 1161213.1571
|  | PV | EV | AC
| 2011-04-01 | 101895.1699 | 106161.2327 | 78767.335
| 2011-05-01 | 499705.0381 | 437632.118 | 401431.915
| 2011-06-01 | 1152313.1571 | 984180.4784 | 885126.93
| 2011-07-01 | 1161213.1571 | 1161213.1571 | 1084980.08
Note on CI1: Brett Thiele: Agreed 51 hrs @ $160 / hr.

## Actual Costs
Date | Description | Resource | Unit | Quantity | Rate | BOQ No. | Total | Portfolio WBS | 1080 | Portfolio WBS | TOTAL | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01
Portfolio WBS 011
2011-04-27 | Pin Point Surveys Pty Ltd | Surveyor | hr | 1 | 2954.4 | OH | 2954.4 | 11 |  | 11 | 19038.5 | 0 | 2954.4 | 11016.8 | 16842.3 | 19038.5
2011-05-27 | Survey Team | Surveyor | hr | 1 | 8062.4 | OH | 8062.4 | 11 |  | 13 | 11878.85 | 0 | 0 | 7389.85 | 7389.85 | 11878.85
2011-06-26 | Survey Team - Inv 706 | Surveyor | hr | 1 | 5825.5 | 1.04 | 5825.5 | 11 |  | 31 | 8287.17 | 0 | 8287.17 | 8287.17 | 8287.17 | 8287.17
2011-07-25 | Survey Team - Inv 715 | Surveyor | hr | 1 | 2196.2 | 1.04 | 2196.2 | 11 |  | 51 | 292965.585 | 0 | 34066.54 | 169440.325 | 292965.585 | 292965.585
| Subtotal for 011 | [5 empty] | 19038.5 |  |  | 510 | 25880 | 0 | 0 | 25880 | 25880 | 25880
[10 empty] | 59 | 105179.34 | 0 | 6900 | 62115 | 99312.8 | 105179.34
| Portfolio WBS 013 | [8 empty] | 62 | 3632.5 | 0 | 0 | 0 | 3632.5 | 3632.5
2011-05-05 | Inv 9529 | Field Density | ITEM | 1 | 1157.94 | 1.01 | 1157.94 | 13 |  | 91 | 11473.04 | 0 | 0 | 0 | 3235.4 | 11473.04
2011-05-11 | Inv 9583 | Field Density | ITEM | 1 | 579.96 | 1.01 | 579.96 | 13 |  | 131 | 18430 | 0 | 0 | 0 | 18430 | 18430
2011-05-11 | Inv 9582 | Field Density | ITEM | 1 | 1012.95 | 1.01 | 1012.95 | 13 |  | 161 | 48447.015 | 0 | 0 | 0 | 38097 | 48447.015
2011-05-18 | Inv 9652 | Field Density | ITEM | 1 | 1030 | 1.01 | 1030 | 13 |  | 162 | 16222.5 | 0 | 0 | 0 | 16222.5 | 16222.5
2011-05-31 | Inv 9863 | Field Density | ITEM | 1 | 1726 | 1.01 | 1726 | 13 |  | 191 | 7230 | 0 | 0 | 0 | 7230 | 7230
2011-05-31 | Inv 9825 | Field Density | ITEM | 1 | 1158 | 1.01 | 1158 | 13 |  | 221 | 1180.15 | 0 | 0 | 0 | 1180.15 | 1180.15
2011-05-31 | Inv 9826 | Field Density | ITEM | 1 | 725 | 1.01 | 725 | 13 |  | 222 | 36108.2 | 0 | 0 | 30608.2 | 36108.2 | 36108.2
2011-07-05 | Inv 10346 | Field Density | ITEM | 1 | 1158 | 1.01 | 1158 | 13 |  | 223 | 141962.25 | 0 | 0 | 0 | 28403.76 | 141962.25
2011-07-11 | Inv 10356 | Field Density | ITEM | 1 | 1883 | 1.01 | 1883 | 13 |  | 224 | 11791.5 | 0 | 0 | 0 | 6132 | 11791.5
2011-07-11 | Inv 10355 | Field Density | ITEM | 1 | 1448 | 1.01 | 1448 | 13 |  | 901 | 1359.33 | 594.33 | 954.33 | 954.33 | 1359.33 | 1359.33
| Subtotal for 013 | [5 empty] | 11878.85 |  |  | 902 | 42014.91 | 0 | 8554.76 | 22594.225 | 37978.995 | 42014.91
[10 empty] | 903 | 12881.8 | 0 | 2875.04 | 8006.04 | 11155.56 | 12881.8
| Portfolio WBS 031 | [8 empty] | 904 | 6981.2 | 0 | 4736.04 | 4736.04 | 5129.73 | 6981.2
2011-04-13 | 25T Excavator Hire - Dry Hire | Shannon's Excavations | hr | 9.5 | 85 | 4.01 | 807.5 | 31 |  | 905 | 614.9 | 0 | 68.4 | 349.82 | 614.9 | 614.9
2011-04-13 | Dozer Hire | Graham McDowall | hr | 10 | 165 | 4.01 | 1650 | 31 |  | 907 | 27660.31 | 0 | 8330.655 | 23383.375 | 25178.49 | 27660.31
2011-04-14 | Dozer Hire | Graham McDowall | hr | 9.5 | 165 | 4.01 | 1567.5 | 31 |  | 910 | 2117.6 | 0 | 0 | 0 | 0 | 2117.6
2011-04-14 | 25T Excavator Hire - Dry Hire | Shannon's Excavations | hr | 9.5 | 85 | 4.01 | 807.5 | 31 |  | 911 | 4579.81 | 0 | 1040 | 3191.24 | 4231.24 | 4579.81
2011-04-15 | Dozer Hire | Graham McDowall | hr | 8 | 165 | 4.01 | 1320 | 31 |  | QM2.3 | 14753.12 | 0 | 0 | 0 | 14753.12 | 14753.12
2011-04-15 | 25T Excavator Hire - Dry Hire | Shannon's Excavations | hr | 4.5 | 85 | 4.01 | 382.5 | 31 |  | QMD40 | 187089.96 | 0 | 0 | 0 | 150155.81 | 187089.96
2011-04-18 | Truck Driver | Labour | hr | 1.5 | 39.18 | 5.01 | 58.77 | 31 |  | QMR | 1741.04 | 0 | 0 | 0 | 1741.04 | 1741.04
2011-04-18 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 1.5 | 65 | 5.01 | 97.5 | 31 |  | SPF | 23479.5 | 0 | 0 | 23479.5 | 23479.5 | 23479.5
2011-04-19 | Truck Driver | Labour | hr | 5 | 39.18 | 5.01 | 195.9 | 31
2011-04-19 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 5 | 65 | 5.01 | 325 | 31 |  | TOTAL | 1084980.08 | 594.33 | 78767.335 | 401431.915 | 885126.93 | 1084980.08
2011-04-19 | 25T Excavator Hire | Shannon's Excavations | hr | 5 | 130 | 5.01 | 650 | 31
2011-04-19 | Tipper Hire | Michael J Biles | hr | 5 | 85 | 5.01 | 425 | 31
| Subtotal for 031 | [5 empty] | 8287.17
Portfolio WBS 051
2011-04-18 | Tipper Hire | Michael J Biles | hr | 5 | 85 | 4.02 | 425 | 51
2011-04-18 | Labour | Labour | hr | 9.5 | 32.2 | 4.02 | 305.9 | 51
2011-04-18 | Dozer Hire | Graham McDowall | hr | 9.5 | 165 | 4.02 | 1567.5 | 51
2011-04-18 | 25T Excavator Hire | Shannon's Excavations | hr | 9.5 | 130 | 4.02 | 1235 | 51
2011-04-18 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 4.02 | 283.5 | 51
2011-04-19 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 4.02 | 283.5 | 51
2011-04-19 | 25T Excavator Hire | Shannon's Excavations | hr | 4.5 | 130 | 4.02 | 585 | 51
2011-04-19 | Tipper Hire | Michael J Biles | hr | 4.5 | 85 | 4.02 | 382.5 | 51
2011-04-19 | Dozer Hire | Graham McDowall | hr | 10 | 165 | 4.02 | 1650 | 51
2011-04-19 | Labour | Labour | hr | 9.5 | 32.2 | 4.02 | 305.9 | 51
2011-04-19 | Truck Driver | Labour | hr | 4.5 | 39.18 | 4.02 | 176.31 | 51
2011-04-19 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 4.5 | 65 | 4.02 | 292.5 | 51
2011-04-19 | Labour | Labour | hr | 9.5 | 32.2 | 4.02 | 305.9 | 51
2011-04-20 | Dozer Hire | Graham McDowall | hr | 10 | 165 | 4.02 | 1650 | 51
2011-04-20 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 9.5 | 65 | 4.02 | 617.5 | 51
2011-04-20 | 25T Excavator Hire | Shannon's Excavations | hr | 9.5 | 130 | 4.02 | 1235 | 51
2011-04-20 | Tipper Hire | Michael J Biles | hr | 9.5 | 85 | 4.02 | 807.5 | 51
2011-04-20 | Labour | Labour | hr | 9.5 | 32.2 | 4.02 | 305.9 | 51
2011-04-20 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 4.02 | 283.5 | 51
2011-04-20 | Truck Driver | Labour | hr | 9.5 | 39.18 | 4.02 | 372.21 | 51
2011-04-20 | Labour | Labour | hr | 9.5 | 32.2 | 4.02 | 305.9 | 51
2011-04-21 | Dozer Hire | Graham McDowall | hr | 8.5 | 165 | 5.02 | 1402.5 | 51
2011-04-21 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 8 | 65 | 5.02 | 520 | 51
2011-04-21 | Tipper Hire | Michael J Biles | hr | 8 | 85 | 5.02 | 680 | 51
2011-04-21 | Tipper Hire | AG Laidlaw Tipper Hire | hr | 8 | 80 | 5.02 | 640 | 51
2011-04-21 | 25T Excavator Hire | Shannon's Excavations | hr | 8 | 130 | 5.02 | 1040 | 51
2011-04-21 | Truck Driver | Labour | hr | 8 | 39.18 | 5.02 | 313.44 | 51
2011-04-21 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 5.02 | 283.5 | 51
2011-04-21 | Labour | Labour | hr | 8 | 32.2 | 5.02 | 257.6 | 51
2011-04-21 | Labour | Labour | hr | 8 | 32.2 | 5.02 | 257.6 | 51
2011-04-27 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8.5 | 42.79 | 5.02 | 363.715 | 51
2011-04-27 | Labour | Labour | hr | 8.5 | 39.18 | 5.02 | 333.03 | 51
2011-04-27 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 8.5 | 65 | 5.02 | 552.5 | 51
2011-04-27 | 25T Excavator Hire | Shannon's Excavations | hr | 8.5 | 130 | 5.02 | 1105 | 51
2011-04-27 | Tipper Hire | Michael J Biles | hr | 8.5 | 85 | 5.02 | 722.5 | 51
2011-04-27 | Truck Driver | Labour | hr | 8.5 | 39.18 | 5.02 | 333.03 | 51
2011-04-27 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 5.02 | 283.5 | 51
2011-04-27 | Labour | Labour | hr | 8.5 | 32.2 | 5.02 | 273.7 | 51
2011-04-27 | Labour | Labour | hr | 9.5 | 32.2 | 5.02 | 305.9 | 51
2011-04-28 | Labour | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-04-28 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-04-28 | 25T Excavator Hire | Shannon's Excavations | hr | 9.5 | 130 | 2.03 | 1235 | 51
2011-04-28 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 5.5 | 65 | 2.03 | 357.5 | 51
2011-04-28 | Tipper Hire | Michael J Biles | hr | 9.5 | 85 | 2.03 | 807.5 | 51
2011-04-28 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 2.03 | 406.505 | 51
2011-04-28 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-04-28 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 2.03 | 283.5 | 51
2011-04-28 | Truck Driver | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-04-29 | Labour | Labour | hr | 10 | 32.2 | 2.03 | 322 | 51
2011-04-29 | Truck Driver | Labour | hr | 8 | 39.18 | 2.03 | 313.44 | 51
2011-04-29 | Labour | Labour | hr | 8 | 32.2 | 2.03 | 257.6 | 51
2011-04-29 | Labour | Labour | hr | 8 | 39.18 | 2.03 | 313.44 | 51
2011-04-29 | Tipper Hire | Michael J Biles | hr | 8 | 85 | 2.03 | 680 | 51
2011-04-29 | 25T Excavator Hire | Shannon's Excavations | hr | 8 | 130 | 2.03 | 1040 | 51
2011-04-29 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8 | 42.79 | 2.03 | 342.32 | 51
2011-04-29 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 8 | 65 | 2.03 | 520 | 51
2011-04-29 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 2.03 | 283.5 | 51
2011-04-30 | Labour | Labour | hr | 6 | 39.18 | 2.03 | 235.08 | 51
2011-04-30 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-04-30 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 2.03 | 283.5 | 51
2011-04-30 | 25T Excavator Hire | Shannon's Excavations | hr | 6 | 130 | 2.03 | 780 | 51
2011-04-30 | Tipper Hire | Michael J Biles | hr | 6 | 85 | 2.03 | 510 | 51
2011-04-30 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 6 | 65 | 2.03 | 390 | 51
2011-05-03 | Truck Driver | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-03 | Tipper Hire | Michael J Biles | hr | 9.5 | 85 | 2.03 | 807.5 | 51
2011-05-03 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 2.03 | 406.505 | 51
2011-05-03 | Labour | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-03 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-03 | 25T Excavator Hire | Shannon's Excavations | hr | 9.5 | 130 | 2.03 | 1235 | 51
2011-05-03 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-03 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 9.5 | 65 | 2.03 | 617.5 | 51
2011-05-04 | Tipper - Allciv Water Cart | Tipper - Allciv | hr | 9.5 | 42.79 | 2.03 | 406.505 | 51
2011-05-04 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 9.5 | 65 | 2.03 | 617.5 | 51
2011-05-04 | 25T Excavator Hire | Shannon's Excavations | hr | 9.5 | 130 | 2.03 | 1235 | 51
2011-05-04 | Labour | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-04 | Truck Driver | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-04 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-04 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-04 | Tipper Hire | Michael J Biles | hr | 9.5 | 85 | 2.03 | 807.5 | 51
2011-05-05 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-05 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-05 | Tipper Hire | Michael J Biles | hr | 9.5 | 85 | 2.03 | 807.5 | 51
2011-05-05 | 25T Excavator Hire | Shannon's Excavations | hr | 9.5 | 130 | 2.03 | 1235 | 51
2011-05-05 | Tipper - Allciv Water Cart | Tipper - Allciv | hr | 9.5 | 42.79 | 2.03 | 406.505 | 51
2011-05-05 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 9.5 | 65 | 2.03 | 617.5 | 51
2011-05-05 | Truck Driver | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-05 | Labour | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-06 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 8 | 65 | 2.03 | 520 | 51
2011-05-06 | Tipper - Allciv Water Cart | Tipper - Allciv | hr | 8 | 42.79 | 2.03 | 342.32 | 51
2011-05-06 | Tipper Hire | Michael J Biles | hr | 8 | 85 | 2.03 | 680 | 51
2011-05-06 | 25T Excavator Hire | Shannon's Excavations | hr | 8 | 85 | 2.03 | 680 | 51
2011-05-06 | Labour | Labour | hr | 8 | 32.2 | 2.03 | 257.6 | 51
2011-05-06 | Truck Driver | Labour | hr | 8 | 39.18 | 2.03 | 313.44 | 51
2011-05-06 | Labour | Labour | hr | 8 | 32.2 | 2.03 | 257.6 | 51
2011-05-06 | Labour | Labour | hr | 8.5 | 39.18 | 2.03 | 333.03 | 51
2011-05-07 | 1.6T Mini Excavator - Wet Hire | Excavator - 8T | hr | 1 | 305.45 | 2.03 | 305.45 | 51
2011-05-09 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-09 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-09 | Truck Driver | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-09 | Labour | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-09 | Tipper Hire | Michael J Biles | hr | 9.5 | 85 | 2.03 | 807.5 | 51
2011-05-09 | Labour Hire - People Resourcing | Labour | hr | 9.5 | 43.4 | 2.03 | 412.3 | 51
2011-05-09 | 25T Excavator Hire | Shannon's Excavations | hr | 9.5 | 130 | 2.03 | 1235 | 51
2011-05-09 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 9.5 | 65 | 2.03 | 617.5 | 51
2011-05-09 | Tipper - Allciv Water Cart | Tipper - Allciv | hr | 9.5 | 42.79 | 2.03 | 406.505 | 51
2011-05-10 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 9.5 | 65 | 2.03 | 617.5 | 51
2011-05-10 | Tipper - Allciv Water Cart | Tipper - Allciv | hr | 3 | 42.79 | 2.03 | 128.37 | 51
2011-05-10 | Labour | Labour | hr | 3 | 39.18 | 2.03 | 117.54 | 51
2011-05-10 | 25T Excavator Hire | Shannon's Excavations | hr | 6 | 130 | 2.03 | 780 | 51
2011-05-10 | Labour Hire - People Resourcing | Labour | hr | 9.5 | 43.4 | 2.03 | 412.3 | 51
2011-05-10 | Tipper Hire | Michael J Biles | hr | 9.5 | 85 | 2.03 | 807.5 | 51
2011-05-10 | 25T Excavator Hire - Dry Hire | Shannon's Excavations | hr | 3.5 | 85 | 2.03 | 297.5 | 51
2011-05-10 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-10 | Truck Driver | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-10 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-11 | 25T Excavator Hire | Shannon's Excavations | hr | 9.5 | 130 | 2.03 | 1235 | 51
2011-05-11 | Tipper Hire | Michael J Biles | hr | 9.5 | 85 | 2.03 | 807.5 | 51
2011-05-11 | Labour Hire - People Resourcing | Labour | hr | 9.5 | 43.4 | 2.03 | 412.3 | 51
2011-05-11 | Truck Driver | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-11 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-11 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-11 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 9.5 | 65 | 2.03 | 617.5 | 51
2011-05-12 | Truck Driver | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-12 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 2.03 | 406.505 | 51
2011-05-12 | Labour | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-12 | 25T Excavator Hire | Shannon's Excavations | hr | 9.5 | 130 | 2.03 | 1235 | 51
2011-05-12 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 9.5 | 65 | 2.03 | 617.5 | 51
2011-05-12 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-12 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-12 | Tipper Hire | Michael J Biles | hr | 9.5 | 85 | 2.03 | 807.5 | 51
2011-05-12 | Labour Hire - People Resourcing | Labour | hr | 9.5 | 43.4 | 2.03 | 412.3 | 51
2011-05-13 | 25T Excavator Hire | Shannon's Excavations | hr | 8 | 130 | 2.03 | 1040 | 51
2011-05-13 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 8 | 65 | 2.03 | 520 | 51
2011-05-13 | Labour Hire - People Resourcing | Labour | hr | 8 | 43.4 | 2.03 | 347.2 | 51
2011-05-13 | Tipper Hire | Michael J Biles | hr | 8 | 85 | 2.03 | 680 | 51
2011-05-13 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8 | 42.79 | 2.03 | 342.32 | 51
2011-05-13 | Labour | Labour | hr | 8 | 32.2 | 2.03 | 257.6 | 51
2011-05-13 | Truck Driver | Labour | hr | 8 | 39.18 | 2.03 | 313.44 | 51
2011-05-13 | Labour | Labour | hr | 8 | 39.18 | 2.03 | 313.44 | 51
2011-05-13 | Labour | Labour | hr | 8 | 32.2 | 2.03 | 257.6 | 51
2011-05-14 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 6 | 42.79 | 2.03 | 256.74 | 51
2011-05-14 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 6 | 65 | 2.03 | 390 | 51
2011-05-14 | Labour | Labour | hr | 6 | 39.18 | 2.03 | 235.08 | 51
2011-05-14 | Labour Hire - People Resourcing | Labour | hr |  | 43.4 | 2.03 |  | 51
2011-05-14 | Labour | Labour | hr |  | 32.2 | 2.03 |  | 51
2011-05-14 | Labour | Labour | hr |  | 32.2 | 2.03 |  | 51
2011-05-14 | Truck Driver | Labour | hr | 6 | 39.18 | 2.03 | 235.08 | 51
2011-05-14 | 25T Excavator Hire | Shannon's Excavations | hr | 6 | 130 | 2.03 | 780 | 51
2011-05-14 | Tipper Hire | Michael J Biles | hr | 6 | 85 | 2.03 | 510 | 51
2011-05-16 | Labour | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-16 | Labour | Labour | hr | 9.5 | 41.83 | 2.03 | 397.385 | 51
2011-05-16 | Labour | Labour | hr | 5.5 | 32.2 | 2.03 | 177.1 | 51
2011-05-16 | Labour Hire - People Resourcing | Labour | hr | 9.5 | 43.4 | 2.03 | 412.3 | 51
2011-05-16 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 9.5 | 65 | 2.03 | 617.5 | 51
2011-05-16 | 25T Excavator Hire | Shannon's Excavations | hr | 9.5 | 130 | 2.03 | 1235 | 51
2011-05-16 | Tipper Hire | Michael J Biles | hr | 9.5 | 85 | 2.03 | 807.5 | 51
2011-05-16 | Truck Driver | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-16 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 2.03 | 406.505 | 51
2011-05-16 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 2.5 | 50 | 2.03 | 125 | 51
2011-05-16 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-17 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 2.03 | 406.505 | 51
2011-05-17 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-17 | Truck Driver | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-17 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-17 | Labour | Labour | hr | 9.5 | 41.83 | 2.03 | 397.385 | 51
2011-05-17 | Labour | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-17 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 9.5 | 65 | 2.03 | 617.5 | 51
2011-05-17 | Labour Hire - People Resourcing | Labour | hr | 9.5 | 43.4 | 2.03 | 412.3 | 51
2011-05-17 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 9.5 | 50 | 2.03 | 475 | 51
2011-05-17 | 25T Excavator Hire | Shannon's Excavations | hr | 9.5 | 130 | 2.03 | 1235 | 51
2011-05-17 | Tipper Hire | Michael J Biles | hr | 9.5 | 85 | 2.03 | 807.5 | 51
2011-05-18 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 2.03 | 406.505 | 51
2011-05-18 | Labour Hire - People Resourcing | Labour | hr | 9.5 | 43.4 | 2.03 | 412.3 | 51
2011-05-18 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 9.5 | 65 | 2.03 | 617.5 | 51
2011-05-18 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 9.5 | 50 | 2.03 | 475 | 51
2011-05-18 | 25T Excavator Hire | Shannon's Excavations | hr | 9.5 | 130 | 2.03 | 1235 | 51
2011-05-18 | Labour | Labour | hr | 9.5 | 41.83 | 2.03 | 397.385 | 51
2011-05-18 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-18 | Truck Driver | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-18 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-18 | Labour | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-18 | Tipper Hire | Michael J Biles | hr | 9.5 | 85 | 2.03 | 807.5 | 51
2011-05-19 | Tipper Hire | Michael J Biles | hr | 9.5 | 85 | 2.03 | 807.5 | 51
2011-05-19 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-19 | Truck Driver | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-19 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 9.5 | 50 | 2.03 | 475 | 51
2011-05-19 | Labour Hire - People Resourcing | Labour | hr | 9.5 | 43.4 | 2.03 | 412.3 | 51
2011-05-19 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-19 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 9.5 | 65 | 2.03 | 617.5 | 51
2011-05-19 | 25T Excavator Hire | Shannon's Excavations | hr | 9.5 | 130 | 2.03 | 1235 | 51
2011-05-19 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 2.03 | 406.505 | 51
2011-05-19 | Labour | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-19 | Labour | Labour | hr | 9.5 | 41.83 | 2.03 | 397.385 | 51
2011-05-20 | 25T Excavator Hire | Shannon's Excavations | hr | 8 | 130 | 2.03 | 1040 | 51
2011-05-20 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 8 | 65 | 2.03 | 520 | 51
2011-05-20 | Tipper Hire | Michael J Biles | hr | 8 | 85 | 2.03 | 680 | 51
2011-05-20 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 8 | 50 | 2.03 | 400 | 51
2011-05-20 | Labour Hire - People Resourcing | Labour | hr | 8 | 43.4 | 2.03 | 347.2 | 51
2011-05-20 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4 | 42.79 | 2.03 | 171.16 | 51
2011-05-20 | Labour | Labour | hr | 7 | 32.2 | 2.03 | 225.4 | 51
2011-05-20 | Truck Driver | Labour | hr | 8 | 39.18 | 2.03 | 313.44 | 51
2011-05-20 | Labour | Labour | hr | 8 | 32.2 | 2.03 | 257.6 | 51
2011-05-20 | Labour | Labour | hr | 8 | 41.83 | 2.03 | 334.64 | 51
2011-05-20 | Labour | Labour | hr | 4 | 39.18 | 2.03 | 156.72 | 51
2011-05-23 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 9.5 | 50 | 2.03 | 475 | 51
2011-05-23 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 9.5 | 65 | 2.03 | 617.5 | 51
2011-05-23 | Labour | Labour | hr | 9.5 | 41.83 | 2.03 | 397.385 | 51
2011-05-23 | Labour Hire - People Resourcing | Labour | hr | 9.5 | 43.4 | 2.03 | 412.3 | 51
2011-05-23 | Tipper Hire | Michael J Biles | hr | 9.5 | 85 | 2.03 | 807.5 | 51
2011-05-23 | 25T Excavator Hire | Shannon's Excavations | hr | 9.5 | 130 | 2.03 | 1235 | 51
2011-05-23 | Truck Driver | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-24 | Truck Driver | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-24 | Tipper Hire | Michael J Biles | hr | 9.5 | 85 | 2.03 | 807.5 | 51
2011-05-24 | Labour Hire - People Resourcing | Labour | hr |  | 43.4 | 2.03 |  | 51
2011-05-24 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 9.5 | 50 | 2.03 | 475 | 51
2011-05-24 | 25T Excavator Hire | Shannon's Excavations | hr | 9.5 | 130 | 2.03 | 1235 | 51
2011-05-24 | Labour | Labour | hr | 9.5 | 41.83 | 2.03 | 397.385 | 51
2011-05-24 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 9.5 | 65 | 2.03 | 617.5 | 51
2011-05-25 | Pad Foot Roller - Coates Hire | PF Roller | hr | 17 | 365 | 2.03 | 6205 | 51
2011-05-25 | SD Roller - Coates Hire | SD Roller | hr | 15 | 365 | 2.03 | 5475 | 51
2011-05-25 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 9.5 | 50 | 2.03 | 475 | 51
2011-05-25 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 9.5 | 65 | 2.03 | 617.5 | 51
2011-05-25 | Labour | Labour | hr | 9.5 | 41.83 | 2.03 | 397.385 | 51
2011-05-25 | Truck Driver | Labour | hr | 9.5 | 39.18 | 2.03 | 372.21 | 51
2011-05-25 | Labour Hire - People Resourcing | Labour | hr | 9.5 | 43.4 | 2.03 | 412.3 | 51
2011-05-25 | Tipper Hire | Michael J Biles | hr | 9.5 | 85 | 2.03 | 807.5 | 51
2011-05-25 | 25T Excavator Hire | Shannon's Excavations | hr | 9.5 | 130 | 2.03 | 1235 | 51
2011-05-25 | Pad Foot Roller - Flexihire | PF Roller | hr | 14 | 365 | 2.03 | 5110 | 51
2011-05-25 | Hire of Laser Scoop | Scraper - RATE ONLY |  | 1 | 17730 | 2.03 | 17730 | 51
2011-05-26 | 25T Excavator Hire | Shannon's Excavations | hr | 9.5 | 130 | 2.03 | 1235 | 51
2011-05-26 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-26 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 9.5 | 50 | 2.03 | 475 | 51
2011-05-26 | Labour | Labour | hr | 9.5 | 32.2 | 2.03 | 305.9 | 51
2011-05-26 | Tipper Hire | Hurst Backhoe Hire | hr | 9.5 | 85 | 2.03 | 807.5 | 51
2011-05-26 | Tipper Hire | Michael J Biles | hr | 9.5 | 85 | 2.03 | 807.5 | 51
2011-05-26 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-05-26 | Labour | Labour | hr | 9.5 | 41.83 | 2.03 | 397.385 | 51
2011-05-26 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-05-26 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-05-26 | Labour Hire - People Resourcing | Labour | hr | 9.5 | 43.4 | 2.03 | 412.3 | 51
2011-05-27 | Tipper Hire | Hurst Backhoe Hire | hr | 8 | 85 | 2.03 | 680 | 51
2011-05-27 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-05-27 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-05-27 | Tipper Hire | Michael J Biles | hr | 8 | 85 | 2.03 | 680 | 51
2011-05-27 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-05-27 | Labour Hire - People Resourcing | Labour | hr | 8 | 43.4 | 2.03 | 347.2 | 51
2011-05-27 | Labour | Labour | hr | 8 | 32.2 | 2.03 | 257.6 | 51
2011-05-27 | 25T Excavator Hire | Shannon's Excavations | hr | 8 | 130 | 2.03 | 1040 | 51
2011-05-27 | Labour | Labour | hr | 8 | 41.83 | 2.03 | 334.64 | 51
2011-05-27 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 8 | 50 | 2.03 | 400 | 51
2011-05-27 | Labour | Labour | hr | 8 | 32.2 | 2.03 | 257.6 | 51
2011-05-28 | Tipper Hire | Michael J Biles | hr | 6 | 85 | 2.03 | 510 | 51
2011-05-28 | 25T Excavator Hire | Shannon's Excavations | hr | 6 | 130 | 2.03 | 780 | 51
2011-05-28 | Labour | Labour | hr | 6 | 41.83 | 2.03 | 250.98 | 51
2011-05-28 | Tipper Hire | Hurst Backhoe Hire | hr | 6 | 85 | 2.03 | 510 | 51
2011-05-28 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 6 | 50 | 2.03 | 300 | 51
2011-05-28 | Labour Hire - People Resourcing | Labour | hr | 6 | 43.4 | 2.03 | 260.4 | 51
2011-05-31 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-05-31 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-05-31 | Tipper Hire | Hurst Backhoe Hire | hr | 10 | 85 | 2.03 | 850 | 51
2011-05-31 | Tipper Hire | Quag Contracting | hr | 4 | 80 | 2.03 | 320 | 51
2011-05-31 | Bobcat - Dry Hire Coates Hire | Bobcat | hr | 1 | 255 | 2.03 | 255 | 51
2011-05-31 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-05-31 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 10 | 50 | 2.03 | 500 | 51
2011-05-31 | Labour | Labour | hr | 10 | 41.83 | 2.03 | 418.3 | 51
2011-05-31 | Labour | Labour | hr | 10 | 32.2 | 2.03 | 322 | 51
2011-05-31 | Labour | Labour | hr | 10 | 32.2 | 2.03 | 322 | 51
2011-05-31 | Labour Hire - People Resourcing | Labour | hr | 10 | 43.4 | 2.03 | 434 | 51
2011-05-31 | Tipper Hire | Michael J Biles | hr | 10 | 85 | 2.03 | 850 | 51
2011-05-31 | 25T Excavator Hire | Shannon's Excavations | hr | 10 | 130 | 2.03 | 1300 | 51
2011-06-01 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-01 | Tipper Hire | Hurst Backhoe Hire | hr | 10 | 85 | 2.03 | 850 | 51
2011-06-01 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 10 | 50 | 2.03 | 500 | 51
2011-06-01 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-01 | Tipper Hire | Quag Contracting | hr | 10 | 80 | 2.03 | 800 | 51
2011-06-01 | Bobcat - Dry Hire Coates Hire | Bobcat | hr | 1 | 255 | 2.03 | 255 | 51
2011-06-01 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-01 | Labour Hire - People Resourcing | Labour | hr | 10 | 43.4 | 2.03 | 434 | 51
2011-06-01 | Labour | Labour | hr | 10 | 41.83 | 2.03 | 418.3 | 51
2011-06-01 | Labour | Labour | hr | 10 | 32.2 | 2.03 | 322 | 51
2011-06-01 | Labour | Labour | hr | 10 | 32.2 | 2.03 | 322 | 51
2011-06-01 | 25T Excavator Hire | Shannon's Excavations | hr | 10 | 130 | 2.03 | 1300 | 51
2011-06-01 | Grader Hire | Scott McKenzie | hr | 5 | 145 | 2.03 | 725 | 51
2011-06-01 | Tipper Hire | Michael J Biles | hr | 10 | 85 | 2.03 | 850 | 51
2011-06-01 | Dozer Hire | Graham McDowall | hr | 5 | 165 | 2.03 | 825 | 51
2011-06-02 | Tipper Hire | Michael J Biles | hr | 10 | 85 | 2.03 | 850 | 51
2011-06-02 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 10 | 50 | 2.03 | 500 | 51
2011-06-02 | Tipper Hire | Hurst Backhoe Hire | hr | 10 | 85 | 2.03 | 850 | 51
2011-06-02 | Labour | Labour | hr | 10 | 32.2 | 2.03 | 322 | 51
2011-06-02 | Labour | Labour | hr | 10 | 41.83 | 2.03 | 418.3 | 51
2011-06-02 | 25T Excavator Hire | Shannon's Excavations | hr | 10 | 130 | 2.03 | 1300 | 51
2011-06-02 | Bobcat - Dry Hire Coates Hire | Bobcat | hr | 1 | 255 | 2.03 | 255 | 51
2011-06-02 | Tipper Hire | Quag Contracting | hr | 10 | 80 | 2.03 | 800 | 51
2011-06-02 | Labour Hire | Labour | hr | 10 | 38 | 2.03 | 380 | 51
2011-06-02 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-02 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-02 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-03 | Tipper Hire | Michael J Biles | hr | 10 | 85 | 2.03 | 850 | 51
2011-06-03 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 10 | 50 | 2.03 | 500 | 51
2011-06-03 | Tipper Hire | Hurst Backhoe Hire | hr | 10 | 85 | 2.03 | 850 | 51
2011-06-03 | Labour | Labour | hr | 10 | 32.2 | 2.03 | 322 | 51
2011-06-03 | Labour | Labour | hr | 10 | 41.83 | 2.03 | 418.3 | 51
2011-06-03 | 25T Excavator Hire | Shannon's Excavations | hr | 10 | 130 | 2.03 | 1300 | 51
2011-06-03 | Bobcat - Dry Hire Coates Hire | Bobcat | hr | 1 | 255 | 2.03 | 255 | 51
2011-06-03 | Tipper Hire | Quag Contracting | hr | 7.5 | 80 | 2.03 | 600 | 51
2011-06-03 | Labour Hire | Labour | hr | 10 | 38 | 2.03 | 380 | 51
2011-06-03 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-03 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-03 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-04 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-04 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-04 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-04 | Labour Hire | Labour | hr | 8 | 38 | 2.03 | 304 | 51
2011-06-04 | Tipper Hire | Quag Contracting | hr | 8 | 80 | 2.03 | 640 | 51
2011-06-04 | 25T Excavator Hire | Shannon's Excavations | hr | 8 | 130 | 2.03 | 1040 | 51
2011-06-04 | Labour | Labour | hr | 8 | 41.83 | 2.03 | 334.64 | 51
2011-06-04 | Tipper Hire | Michael J Biles | hr | 8 | 85 | 2.03 | 680 | 51
2011-06-04 | Tipper Hire | Hurst Backhoe Hire | hr | 8 | 85 | 2.03 | 680 | 51
2011-06-04 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 8 | 50 | 2.03 | 400 | 51
2011-06-06 | Labour Hire - People Resourcing | Labour | hr | 4 | 43.4 | 2.03 | 173.6 | 51
2011-06-06 | 25T Excavator Hire | Shannon's Excavations | hr | 10 | 130 | 2.03 | 1300 | 51
2011-06-06 | Tipper Hire | Michael J Biles | hr | 10 | 85 | 2.03 | 850 | 51
2011-06-06 | Labour Hire | Labour | hr | 10 | 38 | 2.03 | 380 | 51
2011-06-06 | Tipper Hire | Quag Contracting | hr | 10 | 80 | 2.03 | 800 | 51
2011-06-06 | Tipper Hire | Hurst Backhoe Hire | hr | 10 | 85 | 2.03 | 850 | 51
2011-06-06 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 2.03 | 255 | 51
2011-06-06 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-06 | Labour | Labour | hr | 10 | 41.83 | 2.03 | 418.3 | 51
2011-06-06 | Labour | Labour | hr | 1 | 32.2 | 2.03 | 32.2 | 51
2011-06-06 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 10 | 50 | 2.03 | 500 | 51
2011-06-06 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-06 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 2.03 | 283.5 | 51
2011-06-07 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 10 | 50 | 2.03 | 500 | 51
2011-06-07 | Labour | Labour | hr | 10 | 32.2 | 2.03 | 322 | 51
2011-06-07 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 2.03 | 255 | 51
2011-06-07 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-07 | Labour | Labour | hr | 10 | 41.83 | 2.03 | 418.3 | 51
2011-06-07 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-07 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 2.03 | 283.5 | 51
2011-06-07 | Tipper Hire | Michael J Biles | hr | 10 | 85 | 2.03 | 850 | 51
2011-06-07 | Labour Hire - People Resourcing | Labour | hr | 10 | 43.4 | 2.03 | 434 | 51
2011-06-07 | 25T Excavator Hire | Shannon's Excavations | hr | 10 | 130 | 2.03 | 1300 | 51
2011-06-07 | Tipper Hire x 2 | Quag Contracting | hr | 20 | 80 | 2.03 | 1600 | 51
2011-06-07 | Tipper Hire | Hurst Backhoe Hire | hr | 10 | 85 | 2.03 | 850 | 51
2011-06-07 | Labour Hire | Labour | hr | 10 | 38 | 2.03 | 380 | 51
2011-06-07 | Labour | Labour | hr | 1 | 32.2 | 2.03 | 32.2 | 51
2011-06-08 | 25T Excavator Hire | Shannon's Excavations | hr | 10 | 130 | 2.03 | 1300 | 51
2011-06-08 | Tipper Hire | Michael J Biles | hr | 10 | 85 | 2.03 | 850 | 51
2011-06-08 | Dozer Hire | Graham McDowall | hr | 10 | 165 | 2.03 | 1650 | 51
2011-06-08 | Grader Hire | Scott McKenzie | hr | 10 | 145 | 2.03 | 1450 | 51
2011-06-08 | Labour Hire - People Resourcing | Labour | hr | 10 | 43.4 | 2.03 | 434 | 51
2011-06-08 | Tipper Hire | Hurst Backhoe Hire | hr | 10 | 85 | 2.03 | 850 | 51
2011-06-08 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 2.03 | 255 | 51
2011-06-08 | Labour | Labour | hr | 10 | 32.2 | 2.03 | 322 | 51
2011-06-08 | Labour | Labour | hr | 10 | 41.83 | 2.03 | 418.3 | 51
2011-06-08 | Labour | Labour | hr | 10 | 32.2 | 2.03 | 322 | 51
2011-06-08 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-08 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 10 | 50 | 2.03 | 500 | 51
2011-06-08 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-08 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 2.03 | 283.5 | 51
2011-06-08 | Tipper Hire x 2 | Quag Contracting | hr | 13 | 80 | 2.03 | 1040 | 51
2011-06-08 | Labour Hire | Labour | hr | 10 | 38 | 2.03 | 380 | 51
2011-06-09 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-09 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 10 | 50 | 2.03 | 500 | 51
2011-06-09 | Truck Driver | Labour | hr | 12 | 39.18 | 2.03 | 470.16 | 51
2011-06-09 | 25T Excavator Hire | Shannon's Excavations | hr | 10 | 130 | 2.03 | 1300 | 51
2011-06-09 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-09 | Labour Hire | Labour | hr | 10 | 38 | 2.03 | 380 | 51
2011-06-09 | Tipper Hire | Hurst Backhoe Hire | hr | 10 | 85 | 2.03 | 850 | 51
2011-06-09 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 2.03 | 283.5 | 51
2011-06-09 | Grader Hire | Scott McKenzie | hr | 10 | 145 | 2.03 | 1450 | 51
2011-06-09 | Tipper Hire | Quag Contracting | hr | 10 | 80 | 2.03 | 800 | 51
2011-06-09 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 2.03 | 255 | 51
2011-06-09 | Posi Track Hire | Bowen Posi Track & Tipper | hr | 7 | 90 | 2.03 | 630 | 51
2011-06-09 | Tipper Hire | Michael J Biles | hr | 10 | 85 | 2.03 | 850 | 51
2011-06-09 | Dozer Hire | Graham McDowall | hr | 10 | 165 | 2.03 | 1650 | 51
2011-06-10 | Tipper Hire | Hurst Backhoe Hire | hr | 8 | 85 | 2.03 | 680 | 51
2011-06-10 | Tipper Hire | Quag Contracting | hr | 8 | 80 | 2.03 | 640 | 51
2011-06-10 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 2.03 | 255 | 51
2011-06-10 | Dozer Hire | Graham McDowall | hr | 8 | 165 | 2.03 | 1320 | 51
2011-06-10 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-10 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 2.03 | 283.5 | 51
2011-06-10 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-10 | Labour | Labour | hr | 8 | 32.2 | 2.03 | 257.6 | 51
2011-06-10 | 25T Excavator Hire | Shannon's Excavations | hr | 8 | 130 | 2.03 | 1040 | 51
2011-06-10 | Labour | Labour | hr | 3 | 41.83 | 2.03 | 125.49 | 51
2011-06-10 | Truck Driver | Labour | hr | 10 | 39.18 | 2.03 | 391.8 | 51
2011-06-10 | Tipper Hire | Michael J Biles | hr | 3 | 85 | 2.03 | 255 | 51
2011-06-10 | Labour | Labour | hr | 3 | 32.2 | 2.03 | 96.6 | 51
2011-06-10 | Labour Hire | Labour | hr | 8 | 38 | 2.03 | 304 | 51
2011-06-10 | Grader Hire | Scott McKenzie | hr | 8 | 145 | 2.03 | 1160 | 51
2011-06-14 | Grader Hire | Scott McKenzie | hr | 10 | 145 | 2.03 | 1450 | 51
2011-06-14 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-14 | 25T Excavator Hire | Shannon's Excavations | hr | 9.5 | 130 | 2.03 | 1235 | 51
2011-06-14 | Posi Track Hire | Bowen Posi Track & Tipper | hr | 6 | 90 | 2.03 | 540 | 51
2011-06-14 | Tipper Hire | Hurst Backhoe Hire | hr | 9.5 | 85 | 2.03 | 807.5 | 51
2011-06-14 | Inv 3274 | Flex Drive Pump | day | 1 | 77.27 | 2.03 | 77.27 | 51
2011-06-14 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 2.03 | 255 | 51
2011-06-14 | Tipper Hire | Michael J Biles | hr | 10 | 85 | 2.03 | 850 | 51
2011-06-14 | Labour Hire | Labour | hr | 10 | 38 | 2.03 | 380 | 51
2011-06-14 | Dozer Hire | Graham McDowall | hr | 10 | 165 | 2.03 | 1650 | 51
2011-06-14 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 2.03 | 283.5 | 51
2011-06-14 | Tipper Hire | Quag Contracting | hr | 5 | 80 | 2.03 | 400 | 51
2011-06-15 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 2.03 | 283.5 | 51
2011-06-15 | Grader Hire | Scott McKenzie | hr | 5 | 145 | 2.03 | 725 | 51
2011-06-15 | Tipper Hire | Quag Contracting | hr | 10 | 80 | 2.03 | 800 | 51
2011-06-15 | Tipper Hire | Hurst Backhoe Hire | hr | 10 | 85 | 2.03 | 850 | 51
2011-06-15 | 25T Excavator Hire | Shannon's Excavations | hr | 10 | 130 | 2.03 | 1300 | 51
2011-06-15 | Tipper Hire | Michael J Biles | hr | 10 | 85 | 2.03 | 850 | 51
2011-06-15 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-15 | Labour Hire | Labour | hr | 10 | 38 | 2.03 | 380 | 51
2011-06-16 | Posi Track Hire | Bowen Posi Track & Tipper | hr | 4.5 | 90 | 2.03 | 405 | 51
2011-06-16 | Tipper Hire | Michael J Biles | hr | 8 | 85 | 2.03 | 680 | 51
2011-06-16 | 25T Excavator Hire | Shannon's Excavations | hr | 8 | 130 | 2.03 | 1040 | 51
2011-06-16 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-16 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 2.03 | 283.5 | 51
2011-06-16 | Tipper Hire | Hurst Backhoe Hire | hr | 8 | 85 | 2.03 | 680 | 51
2011-06-16 | Labour Hire | Labour | hr | 10 | 38 | 2.03 | 380 | 51
2011-06-16 | Tipper Hire | Quag Contracting | hr | 8 | 80 | 2.03 | 640 | 51
2011-06-17 | Tipper Hire | Hurst Backhoe Hire | hr | 6 | 85 | 2.03 | 510 | 51
2011-06-17 | 25T Excavator Hire | Shannon's Excavations | hr | 6 | 130 | 2.03 | 780 | 51
2011-06-17 | Tipper Hire | Michael J Biles | hr | 6 | 85 | 2.03 | 510 | 51
2011-06-17 | Labour Hire | Labour | hr | 8 | 38 | 2.03 | 304 | 51
2011-06-17 | Tipper Hire | Quag Contracting | hr | 6 | 80 | 2.03 | 480 | 51
2011-06-17 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-17 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 2.03 | 283.5 | 51
2011-06-18 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 2.03 | 255 | 51
2011-06-18 | Labour Hire - People Resourcing | Labour | hr | 4 | 43.4 | 2.03 | 173.6 | 51
2011-06-18 | Tipper Hire | Michael J Biles | hr | 4 | 85 | 2.03 | 340 | 51
2011-06-18 | 25T Excavator Hire | Shannon's Excavations | hr | 4 | 130 | 2.03 | 520 | 51
2011-06-18 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 2.03 | 283.5 | 51
2011-06-18 | Tipper Hire | Hurst Backhoe Hire | hr | 4 | 85 | 2.03 | 340 | 51
2011-06-18 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-20 | Tipper Hire | Michael J Biles | hr | 8 | 85 | 2.03 | 680 | 51
2011-06-20 | Dozer Hire | Graham McDowall | hr | 8 | 165 | 2.03 | 1320 | 51
2011-06-20 | Labour Hire | Labour | hr | 10 | 38 | 2.03 | 380 | 51
2011-06-20 | Tipper Hire | Hurst Backhoe Hire | hr | 8 | 85 | 2.03 | 680 | 51
2011-06-20 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-20 | 25T Excavator Hire | Shannon's Excavations | hr | 8 | 130 | 2.03 | 1040 | 51
2011-06-20 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 2.03 | 283.5 | 51
2011-06-21 | Dozer Hire | Graham McDowall | hr | 10 | 165 | 2.03 | 1650 | 51
2011-06-21 | Labour Hire | Labour | hr | 10 | 38 | 2.03 | 380 | 51
2011-06-21 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-21 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 2.03 | 283.5 | 51
2011-06-22 | Tipper Hire | Michael J Biles | hr | 2 | 85 | 2.03 | 170 | 51
2011-06-22 | Dozer Hire | Graham McDowall | hr | 10 | 165 | 2.03 | 1650 | 51
2011-06-22 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 2.03 | 283.5 | 51
2011-06-22 | Labour Hire | Labour | hr | 5 | 38 | 2.03 | 190 | 51
2011-06-22 | Tipper Hire | Hurst Backhoe Hire | hr | 2 | 85 | 2.03 | 170 | 51
2011-06-22 | 25T Excavator Hire | Shannon's Excavations | hr | 2 | 130 | 2.03 | 260 | 51
2011-06-22 | SD Roller - Dry Coates | SD Roller | day | 0.5 | 365 | 2.03 | 182.5 | 51
2011-06-23 | Labour Hire | Labour | hr | 10 | 38 | 2.03 | 380 | 51
2011-06-23 | Labour | Labour | hr | 10 | 41.83 | 2.03 | 418.3 | 51
2011-06-23 | Labour | Labour | hr | 10 | 32.2 | 2.03 | 322 | 51
2011-06-23 | Dozer Hire | Graham McDowall | hr | 10 | 165 | 2.03 | 1650 | 51
2011-06-23 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-23 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 2.03 | 283.5 | 51
2011-06-23 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 1 | 385 | 2.03 | 385 | 51
2011-06-24 | Tipper Hire | Michael J Biles | hr | 8 | 85 | 2.03 | 680 | 51
2011-06-24 | Dozer Hire | Graham McDowall | hr | 8 | 165 | 2.03 | 1320 | 51
2011-06-24 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 2 | 50 | 2.03 | 100 | 51
2011-06-24 | 25T Excavator Hire | Shannon's Excavations | hr | 3 | 130 | 2.03 | 390 | 51
2011-06-24 | Labour Hire | Labour | hr | 5 | 38 | 2.03 | 190 | 51
2011-06-24 | Tipper Hire | Hurst Backhoe Hire | hr | 8 | 85 | 2.03 | 680 | 51
2011-06-24 | Grader Hire | Scott McKenzie | hr | 4 | 135 | 2.03 | 540 | 51
2011-06-24 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-24 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 2.03 | 283.5 | 51
2011-06-27 | Dozer Hire | Graham McDowall | hr | 10 | 165 | 2.03 | 1650 | 51
2011-06-27 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 2.03 | 283.5 | 51
2011-06-27 | 25T Excavator Hire | Shannon's Excavations | hr | 10 | 130 | 2.03 | 1300 | 51
2011-06-27 | Labour Hire | Labour | hr | 2 | 38 | 2.03 | 76 | 51
2011-06-27 | Tipper Hire | Hurst Backhoe Hire | hr | 5.5 | 85 | 2.03 | 467.5 | 51
2011-06-27 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-28 | Labour Hire | Labour | hr | 2 | 38 | 2.03 | 76 | 51
2011-06-28 | Pad Foot Roller - Coates Hire | PF Roller | day | 1 | 283.5 | 2.03 | 283.5 | 51
2011-06-28 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-28 | Tipper Hire | Hurst Backhoe Hire | hr | 1 | 85 | 2.03 | 85 | 51
2011-06-28 | Dozer Hire | Graham McDowall | hr | 6 | 165 | 2.03 | 990 | 51
2011-06-28 | Tipper Hire | Michael J Biles | hr | 4.5 | 85 | 2.03 | 382.5 | 51
2011-06-28 | 25T Excavator Hire | Shannon's Excavations | hr | 9 | 130 | 2.03 | 1170 | 51
2011-06-29 | Labour Hire | Labour | hr | 2 | 38 | 2.03 | 76 | 51
2011-06-29 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 51
2011-06-29 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 4 | 50 | 2.03 | 200 | 51
2011-06-29 | Tipper Hire | Michael J Biles | hr | 3 | 45 | 2.03 | 135 | 51
2011-06-29 | Labour Hire - People Resourcing | Labour | hr | 10 | 43.4 | 2.03 | 434 | 51
2011-06-29 | 25T Excavator Hire | Shannon's Excavations | hr | 9 | 130 | 2.03 | 1170 | 51
2011-06-29 | 25T Excavator Hire | Shannon's Excavations | hr | 1 | 130 | 2.03 | 130 | 51
2011-06-30 | Tipper Hire | Michael J Biles | hr | 5 | 45 | 2.03 | 225 | 51
2011-06-30 | Labour Hire - People Resourcing | Labour | hr | 5 | 43.4 | 2.03 | 217 | 51
2011-06-30 | Labour | Labour | hr | 5 | 32.2 | 2.03 | 161 | 51
2011-06-30 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 0.5 | 385 | 2.03 | 192.5 | 51
| Subtotal for 051 | [5 empty] | 292965.585
Portfolio WBS 0510
2011-05-12 | Broons Impact Roller First day hire | Broons - Day One | day | 1 | 15400 | 2.02 | 15400 | 510
2011-05-12 | Broons Impact Roller - Daily hire after day one | Broons - Day Two + | day | 2 | 5240 | 2.02 | 10480 | 510
| Subtotal for 0510 | [5 empty] | 25880
Portfolio WBS 059
2011-04-27 | Dozer Hire | Graham McDowall | hr | 9.5 | 165 | 4.02 | 1567.5 | 59
2011-04-28 | Dozer Hire | Graham McDowall | hr | 9.5 | 165 | 4.02 | 1567.5 | 59
2011-04-28 | Grader Hire | Scott McKenzie | hr | 9.5 | 135 | 4.02 | 1282.5 | 59
2011-04-29 | Grader Hire | Scott McKenzie | hr | 8 | 135 | 4.02 | 1080 | 59
2011-04-29 | Dozer Hire | Graham McDowall | hr | 8.5 | 165 | 4.02 | 1402.5 | 59
2011-05-03 | Grader Hire | Scott McKenzie | hr | 9.5 | 135 | 5.03 | 1282.5 | 59
2011-05-03 | Dozer Hire | Graham McDowall | hr | 9.5 | 165 | 5.03 | 1567.5 | 59
2011-05-04 | Dozer Hire | Graham McDowall | hr | 9.5 | 165 | 2.03 | 1567.5 | 59
2011-05-04 | Grader Hire | Scott McKenzie | hr | 9.5 | 135 | 2.03 | 1282.5 | 59
2011-05-05 | Grader Hire | Scott McKenzie | hr | 9.5 | 135 | 2.03 | 1282.5 | 59
2011-05-05 | Dozer Hire | Graham McDowall | hr | 9.5 | 165 | 2.03 | 1567.5 | 59
2011-05-06 | Dozer Hire | Graham McDowall | hr | 8 | 165 | 2.03 | 1320 | 59
2011-05-06 | Grader Hire | Scott McKenzie | hr | 8 | 135 | 2.03 | 1080 | 59
2011-05-09 | Dozer Hire | Graham McDowall | hr | 9.5 | 165 | 2.03 | 1567.5 | 59
2011-05-09 | Grader Hire | Scott McKenzie | hr | 9.5 | 135 | 2.03 | 1282.5 | 59
2011-05-10 | Grader Hire | Scott McKenzie | hr | 9.5 | 135 | 2.03 | 1282.5 | 59
2011-05-10 | Dozer Hire | Graham McDowall | hr | 9.5 | 165 | 2.03 | 1567.5 | 59
2011-05-11 | Grader Hire | Scott McKenzie | hr | 9.5 | 135 | 2.03 | 1282.5 | 59
2011-05-11 | Dozer Hire | Graham McDowall | hr | 9.5 | 165 | 2.03 | 1567.5 | 59
2011-05-12 | Dozer Hire | Graham McDowall | hr | 9.5 | 165 | 2.03 | 1567.5 | 59
2011-05-12 | Grader Hire | Scott McKenzie | hr | 9.5 | 135 | 2.03 | 1282.5 | 59
2011-05-13 | Grader Hire | Scott McKenzie | hr | 8 | 135 | 2.03 | 1080 | 59
2011-05-13 | Dozer Hire | Graham McDowall | hr | 8 | 165 | 2.03 | 1320 | 59
2011-05-14 | Grader Hire | Scott McKenzie | hr |  | 135 | 2.03 |  | 59
2011-05-14 | Dozer Hire | Graham McDowall | hr |  | 165 | 2.03 |  | 59
2011-05-16 | Grader Hire | Scott McKenzie | hr | 9.5 | 135 | 2.03 | 1282.5 | 59
2011-05-16 | Dozer Hire | Graham McDowall | hr | 9.5 | 165 | 2.03 | 1567.5 | 59
2011-05-17 | Dozer Hire | Graham McDowall | hr | 9.5 | 165 | 2.03 | 1567.5 | 59
2011-05-17 | Grader Hire | Scott McKenzie | hr | 9.5 | 135 | 2.03 | 1282.5 | 59
2011-05-18 | Grader Hire | Scott McKenzie | hr | 9.5 | 135 | 2.03 | 1282.5 | 59
2011-05-18 | Dozer Hire | Graham McDowall | hr | 9.5 | 165 | 2.03 | 1567.5 | 59
2011-05-19 | Grader Hire | Scott McKenzie | hr | 9.5 | 135 | 2.03 | 1282.5 | 59
2011-05-19 | Dozer Hire | Graham McDowall | hr | 9.5 | 165 | 2.03 | 1567.5 | 59
2011-05-20 | Grader Hire | Scott McKenzie | hr | 7 | 135 | 2.03 | 945 | 59
2011-05-20 | Dozer Hire | Graham McDowall | hr | 8 | 165 | 2.03 | 1320 | 59
2011-05-23 | Dozer Hire | Graham McDowall | hr | 9.5 | 165 | 2.03 | 1567.5 | 59
2011-05-23 | Grader Hire | Scott McKenzie | hr | 9.5 | 135 | 2.03 | 1282.5 | 59
2011-05-24 | Dozer Hire | Graham McDowall | hr | 9.5 | 165 | 2.03 | 1567.5 | 59
2011-05-24 | Grader Hire | Scott McKenzie | hr | 9.5 | 135 | 2.03 | 1282.5 | 59
2011-05-25 | Grader Hire | Scott McKenzie | hr | 9.5 | 135 | 2.03 | 1282.5 | 59
2011-05-25 | Dozer Hire | Graham McDowall | hr | 9.5 | 165 | 2.03 | 1567.5 | 59
2011-05-26 | Grader Hire | Scott McKenzie | hr | 9.5 | 135 | 2.03 | 1282.5 | 59
2011-05-26 | Dozer Hire | Graham McDowall | hr | 9.5 | 165 | 2.03 | 1567.5 | 59
2011-05-27 | Grader Hire | Scott McKenzie | hr | 8 | 135 | 2.03 | 1080 | 59
2011-05-27 | Dozer Hire | Graham McDowall | hr | 8 | 165 | 2.03 | 1320 | 59
2011-05-31 | Grader Hire | Scott McKenzie | hr | 10 | 135 | 2.03 | 1350 | 59
2011-05-31 | Dozer Hire | Graham McDowall | hr | 10 | 165 | 2.03 | 1650 | 59
2011-06-01 | Grader Hire | Scott McKenzie | hr | 5 | 145 | 2.03 | 725 | 59
2011-06-01 | Dozer Hire | Graham McDowall | hr | 5 | 165 | 2.03 | 825 | 59
2011-06-02 | Grader Hire | Scott McKenzie | hr | 10 | 135 | 2.03 | 1350 | 59
2011-06-02 | Dozer Hire | Graham McDowall | hr | 10 | 165 | 2.03 | 1650 | 59
2011-06-03 | Dozer Hire | Graham McDowall | hr | 10 | 165 | 2.03 | 1650 | 59
2011-06-03 | Grader Hire | Scott McKenzie | hr | 10 | 135 | 2.03 | 1350 | 59
2011-06-04 | Grader Hire | Scott McKenzie | hr | 8 | 135 | 2.03 | 1080 | 59
2011-06-04 | Dozer Hire | Graham McDowall | hr | 8 | 165 | 2.03 | 1320 | 59
2011-06-06 | Grader Hire | Scott McKenzie | hr | 10 | 145 | 2.03 | 1450 | 59
2011-06-06 | Dozer Hire | Graham McDowall | hr | 10 | 165 | 2.03 | 1650 | 59
2011-06-07 | Dozer Hire | Graham McDowall | hr | 10 | 165 | 2.03 | 1650 | 59
2011-06-07 | Grader Hire | Scott McKenzie | hr | 10 | 145 | 2.03 | 1450 | 59
2011-06-15 | Dozer Hire | Graham McDowall | hr | 10 | 165 | 2.03 | 1650 | 59
2011-06-15 | Grader Hire | Scott McKenzie | hr | 5 | 145 | 2.03 | 725 | 59
2011-06-16 | Grader Hire | Scott McKenzie | hr | 10 | 145 | 2.03 | 1450 | 59
2011-06-16 | Dozer Hire | Graham McDowall | hr | 10 | 165 | 2.03 | 1650 | 59
2011-06-17 | Grader Hire | Scott McKenzie | hr | 8 | 145 | 2.03 | 1160 | 59
2011-06-17 | Dozer Hire | Graham McDowall | hr | 8 | 165 | 2.03 | 1320 | 59
2011-06-20 | Grader Hire | Scott McKenzie | hr | 10 | 145 | 2.03 | 1450 | 59
2011-06-21 | Grader Hire | Scott McKenzie | hr | 10 | 145 | 2.03 | 1450 | 59
2011-06-22 | Grader Hire | Scott McKenzie | hr | 10 | 145 | 2.03 | 1450 | 59
2011-06-23 | Grader Hire | Scott McKenzie | hr | 10 | 135 | 2.03 | 1350 | 59
2011-06-24 | 25T Excavator Hire | Shannon's Excavations | hr | 5 | 130 | 2.03 | 650 | 59
2011-06-27 | Grader Hire | Scott McKenzie | hr | 4 | 135 | 2.03 | 540 | 59
2011-06-28 | Grader Hire | Scott McKenzie | hr | 2 | 135 | 2.03 | 270 | 59
2011-06-29 | Grader Hire | Scott McKenzie | hr | 10 | 135 | 2.03 | 1350 | 59
2011-06-30 | 25T Excavator Hire | Shannon's Excavations | hr | 10 | 130 | 2.03 | 1300 | 59
2011-06-30 | Labour Hire | Labour | hr | 10 | 38 | 2.03 | 380 | 59
2011-06-30 | Grader Hire | Scott McKenzie | hr | 10 | 135 | 2.03 | 1350 | 59
2011-06-30 | 15T Excavator - Cat Rentals | Excavator - 15T | hr | 0.5 | 385 | 2.03 | 192.5 | 59
2011-06-30 | Labour | Labour | hr | 10 | 41.83 | 2.03 | 418.3 | 59
2011-06-30 | Labour | Labour | hr | 10 | 32.2 | 2.03 | 322 | 59
2011-06-30 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 2.03 | 255 | 59
2011-06-30 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 2.03 | 365 | 59
2011-07-01 | 25T Excavator Hire | Shannon's Excavations | hr | 4 | 130 | 6.01 | 520 | 59
2011-07-01 | Tipper Hire | Michael J Biles | hr | 4 | 85 | 6.01 | 340 | 59
2011-07-01 | Grader Hire | Scott McKenzie | hr | 4 | 135 | 6.01 | 540 | 59
2011-07-01 | Labour Hire | Labour | hr | 4 | 38 | 6.01 | 152 | 59
2011-07-01 | Labour Hire - People Resourcing | Labour | hr | 8 | 43.4 | 6.01 | 347.2 | 59
2011-07-01 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 0.5 | 385 | 6.01 | 192.5 | 59
2011-07-01 | Labour | Labour | hr | 8 | 32.2 | 6.01 | 257.6 | 59
2011-07-01 | Labour | Labour | hr | 8 | 32.2 | 6.01 | 257.6 | 59
2011-07-01 | Labour | Labour | hr | 8 | 41.83 | 6.01 | 334.64 | 59
2011-07-01 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 6.01 | 255 | 59
2011-07-01 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 6.01 | 365 | 59
2011-07-04 | 25T Excavator Hire | Shannon's Excavations | hr | 6 | 130 | 6.01 | 780 | 59
2011-07-05 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 7.02 | 365 | 59
2011-07-05 | Labour Hire | Labour | hr | 10 | 38 | 7.02 | 380 | 59
2011-07-07 | 25T Excavator Hire | Shannon's Excavations | hr | 3 | 130 | 7.02 | 390 | 59
2011-07-08 | 25T Excavator Hire | Shannon's Excavations | hr | 3 | 130 | 7.02 | 390 | 59
| Subtotal for 059 | [5 empty] | 105179.34
Portfolio WBS 062
2011-06-24 | Grader Hire | Scott McKenzie | hr | 5.5 | 135 | 8.01 | 742.5 | 62
2011-06-24 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 6 | 50 | 8.01 | 300 | 62
2011-06-27 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 6 | 50 | 8.01 | 300 | 62
2011-06-27 | Grader Hire | Scott McKenzie | hr | 6 | 135 | 8.01 | 810 | 62
2011-06-28 | Grader Hire | Scott McKenzie | hr | 8 | 135 | 8.01 | 1080 | 62
2011-06-28 | Dry Hire Water Truck | Scott McKenzie - Tipper | hr | 8 | 50 | 8.01 | 400 | 62
| Subtotal for 062 | [5 empty] | 3632.5
Portfolio WBS 091
2011-06-02 | Labour | Labour | hr | 10 | 32.2 | 10.01 | 322 | 91
2011-06-02 | Labour Hire - People Resourcing | Labour | hr | 10 | 43.4 | 10.01 | 434 | 91
2011-06-03 | Labour Hire - People Resourcing | Labour | hr | 10 | 43.4 | 10.01 | 434 | 91
2011-06-03 | Labour | Labour | hr | 10 | 32.2 | 10.01 | 322 | 91
2011-06-04 | Labour Hire - People Resourcing | Labour | hr | 8 | 43.4 | 10.01 | 347.2 | 91
2011-06-04 | Labour | Labour | hr | 8 | 32.2 | 10.01 | 257.6 | 91
2011-06-06 | Labour | Labour | hr | 10 | 32.2 | 10.01 | 322 | 91
2011-06-06 | Labour | Labour | hr | 9 | 32.2 | 10.01 | 289.8 | 91
2011-06-07 | Labour | Labour | hr | 9 | 32.2 | 10.01 | 289.8 | 91
2011-06-30 | Labour Hire - People Resourcing | Labour | hr | 5 | 43.4 | 10.01 | 217 | 91
2011-07-05 | 0.5 Tonne MPA 20 | Cement | tonne | 1 | 292.18 | 10.01 | 292.18 | 91
2011-07-14 | Inv 1038953 | Poly Welder | item | 1 | 7945.46 | 10.01 | 7945.46 | 91
| Subtotal for 091 | [5 empty] | 11473.04
Portfolio WBS 131
2011-06-30 | Fencing - Inv 43 | Fencing |  | 1 | 18430 | 4.03 | 18430 | 131
| Subtotal for 131 | [5 empty] | 18430
Portfolio WBS 161
2011-06-01 | A64 Bidum | A64 | m2 | 15300 | 2.49 | 9.02 | 38097 | 161
2011-07-04 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 9.02 | 255 | 161
2011-07-04 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 1 | 385 | 9.02 | 385 | 161
2011-07-04 | Labour Hire | Labour | hr | 10 | 38 | 9.02 | 380 | 161
2011-07-04 | Labour | Labour | hr | 10 | 32.2 | 9.02 | 322 | 161
2011-07-04 | Labour | Labour | hr | 10 | 41.83 | 9.02 | 418.3 | 161
2011-07-04 | Labour | Labour | hr | 10 | 32.2 | 9.02 | 322 | 161
2011-07-04 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 9.02 | 365 | 161
2011-07-05 | Labour | Labour | hr | 5 | 32.2 | 9.02 | 161 | 161
2011-07-05 | Labour | Labour | hr | 5 | 41.83 | 9.02 | 209.15 | 161
2011-07-05 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 0.5 | 385 | 9.02 | 192.5 | 161
2011-07-05 | Labour | Labour | hr | 5 | 32.2 | 9.02 | 161 | 161
2011-07-05 | Bobcat - Coates | Bobcat | hr | 0.5 | 255 | 9.02 | 127.5 | 161
2011-07-06 | Labour Hire - People Resourcing | Labour | hr | 5 | 43.4 | 9.02 | 217 | 161
2011-07-06 | Labour | Labour | hr | 5 | 32.2 | 9.02 | 161 | 161
2011-07-06 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 0.5 | 385 | 9.02 | 192.5 | 161
2011-07-06 | Labour | Labour | hr | 5 | 32.2 | 9.02 | 161 | 161
2011-07-06 | Bobcat - Coates | Bobcat | hr | 0.5 | 255 | 9.02 | 127.5 | 161
2011-07-06 | SD Roller - Dry Coates | SD Roller | day | 0.5 | 365 | 9.02 | 182.5 | 161
2011-07-06 | Labour | Labour | hr | 5 | 41.83 | 9.02 | 209.15 | 161
2011-07-07 | Labour Hire - People Resourcing | Labour | hr | 10.5 | 43.4 | 9.02 | 455.7 | 161
2011-07-07 | Tipper Hire | Michael J Biles | hr | 5 | 95 | 9.02 | 475 | 161
2011-07-07 | Labour Hire | Labour | hr | 10.5 | 38 | 9.02 | 399 | 161
2011-07-07 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 9.02 | 365 | 161
2011-07-07 | Labour | Labour | hr | 10.5 | 41.83 | 9.02 | 439.215 | 161
2011-07-07 | Labour | Labour | hr | 11 | 32.2 | 9.02 | 354.2 | 161
2011-07-07 | Labour | Labour | hr | 10.5 | 32.2 | 9.02 | 338.1 | 161
2011-07-07 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 1 | 385 | 9.02 | 385 | 161
2011-07-07 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 9.02 | 255 | 161
2011-07-08 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 1 | 385 | 9.02 | 385 | 161
2011-07-08 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 9.02 | 255 | 161
2011-07-08 | Labour Hire | Labour | hr | 10.5 | 38 | 9.02 | 399 | 161
2011-07-08 | Labour Hire - People Resourcing | Labour | hr | 10.5 | 43.4 | 9.02 | 455.7 | 161
2011-07-08 | Tipper Hire | Michael J Biles | hr | 5 | 95 | 9.02 | 475 | 161
2011-07-08 | SD Roller - Dry Coates | SD Roller | day | 1 | 365 | 9.02 | 365 | 161
| Subtotal for 161 | [5 empty] | 48447.015
Portfolio WBS 162
2011-06-01 | A24 - Bidum | A24 | m2 | 15750 | 1.03 | 9.03 | 16222.5 | 162
| Subtotal for 162 | [5 empty] | 16222.5
Portfolio WBS 191
2011-06-20 | Tipper Hire | Michael J Biles | hr | 2 | 85 | VAR | 170 | 191
2011-06-20 | Dozer Hire | Graham McDowall | hr | 2 | 165 | VAR | 330 | 191
2011-06-20 | Tipper Hire | Hurst Backhoe Hire | hr | 2 | 85 | VAR | 170 | 191
2011-06-20 | 25T Excavator Hire | Shannon's Excavations | hr | 2 | 130 | VAR | 260 | 191
2011-06-21 | Tipper Hire | Michael J Biles | hr | 7 | 85 | VAR | 595 | 191
2011-06-21 | Tipper Hire | Hurst Backhoe Hire | hr | 7 | 85 | VAR | 595 | 191
2011-06-21 | 25T Excavator Hire | Shannon's Excavations | hr | 7 | 130 | VAR | 910 | 191
2011-06-22 | Tipper Hire | Hurst Backhoe Hire | hr | 6 | 85 | VAR | 510 | 191
2011-06-22 | Tipper Hire | Michael J Biles | hr | 6 | 85 | VAR | 510 | 191
2011-06-22 | 25T Excavator Hire | Shannon's Excavations | hr | 6 | 130 | VAR | 780 | 191
2011-06-23 | Tipper Hire | Michael J Biles | hr | 8 | 85 | VAR | 680 | 191
2011-06-23 | 25T Excavator Hire | Shannon's Excavations | hr | 8 | 130 | VAR | 1040 | 191
2011-06-23 | Tipper Hire | Hurst Backhoe Hire | hr | 8 | 85 | VAR | 680 | 191
| Subtotal for 191 | [5 empty] | 7230
Portfolio WBS 221
2011-06-10 | Labour | Labour | hr | 5 | 32.2 | 5.03 | 161 | 221
2011-06-10 | Tipper Hire | Michael J Biles | hr | 5 | 85 | 5.03 | 425 | 221
2011-06-10 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 1 | 385 | 5.03 | 385 | 221
2011-06-10 | Labour | Labour | hr | 5 | 41.83 | 5.03 | 209.15 | 221
| Subtotal for 221 | [5 empty] | 1180.15
Portfolio WBS 222
2011-05-18 | Inv 29943 | Trencher | item | 1 | 2052.6 | 9.04 | 2052.6 | 222
2011-05-20 | Labour | Labour | hr | 1 | 32.2 | 9.04 | 32.2 | 222
2011-05-20 | Grader Hire | Scott McKenzie | hr | 1 | 135 | 9.04 | 135 | 222
2011-05-23 | Labour | Labour | hr | 9.5 | 32.2 | 9.04 | 305.9 | 222
2011-05-23 | Labour | Labour | hr | 9.5 | 32.2 | 9.04 | 305.9 | 222
2011-05-24 | Labour | Labour | hr | 9.5 | 32.2 | 9.04 | 305.9 | 222
2011-05-24 | Labour | Labour | hr | 9.5 | 32.2 | 9.04 | 305.9 | 222
2011-05-25 | Labour | Labour | hr | 9.5 | 32.2 | 9.04 | 305.9 | 222
2011-05-25 | Inv 1758 | HDPE Liner | item | 1 | 26553 | 9.04 | 26553 | 222
2011-05-25 | Labour | Labour | hr | 9.5 | 32.2 | 9.04 | 305.9 | 222
2011-06-01 | Inv CD201120980 - Bond for Rental Equipment | HDPE Liner | item | 1 | 5000 | 9.01 | 5000 | 222
2011-06-01 | Hire of Equipment | Miscellaneous Items | item | 1 | 500 | 9.01 | 500 | 222
| Subtotal for 222 | [5 empty] | 36108.2
Portfolio WBS 223
2011-06-02 | 2 x Flim Polythene Rolls | GCL | item | 2 | 90 | 9.01 | 180 | 223
2011-06-09 | Labour | Labour | hr | 10.5 | 32.2 | 9.01 | 338.1 | 223
2011-06-09 | Labour | Labour | hr | 10 | 41.83 | 9.01 | 418.3 | 223
2011-06-09 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 1 | 385 | 9.01 | 385 | 223
2011-06-09 | Labour | Labour | hr | 10.5 | 32.2 | 9.01 | 338.1 | 223
2011-06-09 | Labour Hire - People Resourcing | Labour | hr | 10.5 | 43.4 | 9.01 | 455.7 | 223
2011-06-10 | Labour Hire - People Resourcing | Labour | hr | 8 | 43.4 | 9.01 | 347.2 | 223
2011-06-14 | Labour Hire - People Resourcing | Labour | hr | 10 | 43.4 | 9.01 | 434 | 223
2011-06-14 | Labour | Labour | hr | 10 | 32.2 | 9.01 | 322 | 223
2011-06-14 | Labour | Labour | hr | 10 | 41.83 | 9.01 | 418.3 | 223
2011-06-14 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 1 | 385 | 9.01 | 385 | 223
2011-06-14 | Labour | Labour | hr | 10 | 32.2 | 9.01 | 322 | 223
2011-06-15 | Labour | Labour | hr | 10 | 41.83 | 9.01 | 418.3 | 223
2011-06-15 | Labour | Labour | hr | 10 | 32.2 | 9.01 | 322 | 223
2011-06-15 | Labour | Labour | hr | 10 | 32.2 | 9.01 | 322 | 223
2011-06-15 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 9.01 | 255 | 223
2011-06-15 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 1 | 385 | 9.01 | 385 | 223
2011-06-15 | Labour Hire - People Resourcing | Labour | hr | 10 | 43.4 | 9.01 | 434 | 223
2011-06-16 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 9.01 | 255 | 223
2011-06-16 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 1 | 385 | 9.01 | 385 | 223
2011-06-16 | Labour Hire - People Resourcing | Labour | hr | 10 | 43.4 | 9.01 | 434 | 223
2011-06-16 | Labour | Labour | hr | 10 | 41.83 | 9.01 | 418.3 | 223
2011-06-16 | Labour | Labour | hr | 10 | 32.2 | 9.01 | 322 | 223
2011-06-16 | Labour | Labour | hr | 10 | 32.2 | 9.01 | 322 | 223
2011-06-17 | Labour | Labour | hr | 8 | 41.83 | 9.01 | 334.64 | 223
2011-06-17 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 9.01 | 255 | 223
2011-06-17 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 1 | 385 | 9.01 | 385 | 223
2011-06-17 | Labour Hire - People Resourcing | Labour | hr | 8 | 43.4 | 9.01 | 347.2 | 223
2011-06-17 | Labour | Labour | hr | 8 | 32.2 | 9.01 | 257.6 | 223
2011-06-17 | Labour | Labour | hr | 8 | 32.2 | 9.01 | 257.6 | 223
2011-06-18 | 25T Excavator Hire | Shannon's Excavations | hr | 2 | 130 | 9.01 | 260 | 223
2011-06-18 | Labour Hire - People Resourcing | Labour | hr | 2 | 43.4 | 9.01 | 86.8 | 223
2011-06-18 | Tipper Hire | Hurst Backhoe Hire | hr | 2 | 85 | 9.01 | 170 | 223
2011-06-18 | Tipper Hire | Michael J Biles | hr | 2 | 85 | 9.01 | 170 | 223
2011-06-18 | Labour | Labour | hr | 6 | 32.2 | 9.01 | 193.2 | 223
2011-06-18 | Labour | Labour | hr | 6 | 41.83 | 9.01 | 250.98 | 223
2011-06-18 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 1 | 385 | 9.01 | 385 | 223
2011-06-20 | Labour | Labour | hr | 10 | 41.83 | 9.01 | 418.3 | 223
2011-06-20 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 9.01 | 255 | 223
2011-06-20 | Labour | Labour | hr | 10 | 32.2 | 9.01 | 322 | 223
2011-06-20 | Labour | Labour | hr | 10 | 32.2 | 9.01 | 322 | 223
2011-06-20 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 1 | 385 | 9.01 | 385 | 223
2011-06-20 | Labour Hire - People Resourcing | Labour | hr | 10 | 43.4 | 9.01 | 434 | 223
2011-06-21 | Labour | Labour | hr | 10 | 41.83 | 9.01 | 418.3 | 223
2011-06-21 | Labour | Labour | hr | 10 | 32.2 | 9.01 | 322 | 223
2011-06-21 | Labour | Labour | hr | 10 | 32.2 | 9.01 | 322 | 223
2011-06-21 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 9.01 | 255 | 223
2011-06-21 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 1 | 385 | 9.01 | 385 | 223
2011-06-21 | Labour Hire - People Resourcing | Labour | hr | 10 | 43.4 | 9.01 | 434 | 223
2011-06-22 | Labour Hire - People Resourcing | Labour | hr | 10 | 43.4 | 9.01 | 434 | 223
2011-06-22 | Labour Hire | Labour | hr | 5 | 38 | 9.01 | 190 | 223
2011-06-22 | SD Roller - Dry Coates | SD Roller | day | 0.5 | 365 | 9.01 | 182.5 | 223
2011-06-22 | Labour | Labour | hr | 10 | 41.83 | 9.01 | 418.3 | 223
2011-06-22 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 9.01 | 255 | 223
2011-06-22 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 1 | 385 | 9.01 | 385 | 223
2011-06-22 | Labour | Labour | hr | 10 | 32.2 | 9.01 | 322 | 223
2011-06-22 | Labour | Labour | hr | 10 | 32.2 | 9.01 | 322 | 223
2011-06-24 | Labour | Labour | hr | 9.5 | 32.2 | 9.01 | 305.9 | 223
2011-06-24 | Labour | Labour | hr | 8 | 32.2 | 9.01 | 257.6 | 223
2011-06-24 | Labour Hire - People Resourcing | Labour | hr | 10 | 43.4 | 9.01 | 434 | 223
2011-06-24 | Labour | Labour | hr | 8 | 41.83 | 9.01 | 334.64 | 223
2011-06-24 | Labour Hire | Labour | hr | 3 | 38 | 9.01 | 114 | 223
2011-06-24 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 1 | 385 | 9.01 | 385 | 223
2011-06-24 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 9.01 | 255 | 223
2011-06-27 | Labour Hire - People Resourcing | Labour | hr | 10 | 43.4 | 9.01 | 434 | 223
2011-06-27 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 9.01 | 255 | 223
2011-06-27 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 1 | 385 | 9.01 | 385 | 223
2011-06-27 | Labour Hire | Labour | hr | 8 | 38 | 9.01 | 304 | 223
2011-06-27 | Labour | Labour | hr | 10 | 41.83 | 9.01 | 418.3 | 223
2011-06-27 | Labour | Labour | hr | 10 | 32.2 | 9.01 | 322 | 223
2011-06-27 | Labour | Labour | hr | 10 | 32.2 | 9.01 | 322 | 223
2011-06-28 | Labour | Labour | hr | 10 | 41.83 | 9.01 | 418.3 | 223
2011-06-28 | Labour Hire | Labour | hr | 8 | 38 | 9.01 | 304 | 223
2011-06-28 | Labour | Labour | hr | 10 | 32.2 | 9.01 | 322 | 223
2011-06-28 | Labour | Labour | hr | 10 | 32.2 | 9.01 | 322 | 223
2011-06-28 | Tipper Hire | Michael J Biles | hr | 4 | 85 | 9.01 | 340 | 223
2011-06-28 | Labour Hire - People Resourcing | Labour | hr | 10 | 43.4 | 9.01 | 434 | 223
2011-06-28 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 9.01 | 255 | 223
2011-06-28 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 1 | 385 | 9.01 | 385 | 223
2011-06-28 | Tipper Hire | Hurst Backhoe Hire | hr | 4 | 85 | 9.01 | 340 | 223
2011-06-29 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 1 | 385 | 9.01 | 385 | 223
2011-06-29 | Labour | Labour | hr | 10 | 32.2 | 9.01 | 322 | 223
2011-06-29 | Labour Hire | Labour | hr | 8 | 38 | 9.01 | 304 | 223
2011-06-29 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 9.01 | 255 | 223
2011-06-29 | Labour | Labour | hr | 10 | 41.83 | 9.01 | 418.3 | 223
2011-06-29 | Labour | Labour | hr | 10 | 32.2 | 9.01 | 322 | 223
2011-07-05 | Labour | Labour | hr | 5 | 32.2 | 9.01 | 161 | 223
2011-07-05 | Labour | Labour | hr | 5 | 41.83 | 9.01 | 209.15 | 223
2011-07-05 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 0.5 | 115 | 9.01 | 57.5 | 223
2011-07-05 | Bobcat - Coates | Bobcat | hr | 0.5 | 255 | 9.01 | 127.5 | 223
2011-07-05 | Labour | Labour | hr | 5 | 32.2 | 9.01 | 161 | 223
2011-07-06 | 11T Excavator - Cat Rentals | Excavator - 15T | hr | 0.5 | 115 | 9.01 | 57.5 | 223
2011-07-06 | Labour | Labour | hr | 5 | 32.2 | 9.01 | 161 | 223
2011-07-06 | Bobcat - Coates | Bobcat | hr | 0.5 | 255 | 9.01 | 127.5 | 223
2011-07-06 | Labour | Labour | hr | 5 | 41.83 | 9.01 | 209.15 | 223
2011-07-06 | Labour | Labour | hr | 5 | 32.2 | 9.01 | 161 | 223
2011-07-06 | SD Roller - Dry Coates | SD Roller | day | 0.5 | 365 | 9.01 | 182.5 | 223
2011-07-06 | Labour Hire - People Resourcing | Labour | hr | 5 | 43.4 | 9.01 | 217 | 223
2011-07-06 | Labour Hire | Labour | hr | 5 | 38 | 9.01 | 190 | 223
2011-07-07 | Inv CD201200419 | Bidim | m2 | 4200 | 1.03 | 9.01 | 4326 | 223
2011-07-08 | Inv CD201200507 - Undercoat | GCL | drum | 20 | 25 | 9.01 | 500 | 223
2011-07-08 | Inv CD201200507 - Topcoat | GCL | drum | 20 | 25 | 9.01 | 500 | 223
2011-07-08 | Inv CD201200507 | GCL | m2 | 16450 | 6.45 | 9.01 | 106102.5 | 223
2011-07-08 | Inv CD201200507 - Slings | GCL | ea | 200 | 25 | 9.01 | 5000 | 223
2011-07-31 | Credit for Bond on Equipment | GCL | item | 1 | -4891.81 | 9.01 | -4891.81 | 223
| Subtotal for 223 | [5 empty] | 141962.25
Portfolio WBS 224
2011-06-16 | Tipper Hire | Hurst Backhoe Hire | hr | 2 | 85 | 2.06 | 170 | 224
2011-06-16 | Tipper Hire | Quag Contracting | hr | 2 | 80 | 2.06 | 160 | 224
2011-06-16 | Tipper Hire | Michael J Biles | hr | 2 | 85 | 2.06 | 170 | 224
2011-06-16 | 25T Excavator Hire | Shannon's Excavations | hr | 2 | 130 | 2.06 | 260 | 224
2011-06-17 | Tipper Hire | Quag Contracting | hr | 1.75 | 80 | 2.06 | 140 | 224
2011-06-17 | Tipper Hire | Hurst Backhoe Hire | hr | 2 | 85 | 2.06 | 170 | 224
2011-06-17 | Tipper Hire | Michael J Biles | hr | 2 | 85 | 2.06 | 170 | 224
2011-06-17 | 25T Excavator Hire | Shannon's Excavations | hr | 2 | 130 | 2.06 | 260 | 224
2011-06-21 | Tipper Hire | Hurst Backhoe Hire | hr | 3 | 85 | 2.06 | 255 | 224
2011-06-21 | Tipper Hire | Michael J Biles | hr | 3 | 85 | 2.06 | 255 | 224
2011-06-21 | 25T Excavator Hire | Shannon's Excavations | hr | 3 | 130 | 2.06 | 390 | 224
2011-06-22 | Tipper Hire | Hurst Backhoe Hire | hr | 2 | 85 | 2.06 | 170 | 224
2011-06-22 | 25T Excavator Hire | Shannon's Excavations | hr | 2 | 130 | 2.06 | 260 | 224
2011-06-22 | Tipper Hire | Michael J Biles | hr | 2 | 85 | 2.06 | 170 | 224
2011-06-23 | 25T Excavator Hire | Shannon's Excavations | hr | 2 | 130 | 2.06 | 260 | 224
2011-06-23 | Tipper Hire | Michael J Biles | hr | 2 | 85 | 2.06 | 170 | 224
2011-06-23 | Bobcat - Coates | Bobcat | hr | 1 | 255 | 2.06 | 255 | 224
2011-06-23 | Tipper Hire | Hurst Backhoe Hire | hr | 1 | 85 | 2.06 | 85 | 224
2011-06-23 | Labour Hire - People Resourcing | Labour | hr | 10 | 43.4 | 2.06 | 434 | 224
2011-06-23 | Labour | Labour | hr | 10 | 32.2 | 2.06 | 322 | 224
2011-06-29 | Tipper Hire | Hurst Backhoe Hire | hr | 5 | 85 | 2.06 | 425 | 224
2011-06-29 | Tipper Hire | Michael J Biles | hr | 7 | 85 | 2.06 | 595 | 224
2011-06-30 | Tipper Hire | Michael J Biles | hr | 5 | 85 | 2.06 | 425 | 224
2011-06-30 | Labour | Labour | hr | 5 | 32.2 | 2.06 | 161 | 224
2011-07-01 | Tipper Hire | Michael J Biles | hr | 4 | 45 | 2.06 | 180 | 224
2011-07-01 | 15T Excavator - Cat Rentals | Excavator - 15T | hr | 0.5 | 385 | 2.06 | 192.5 | 224
2011-07-01 | Grader Hire | Scott McKenzie | hr | 4 | 135 | 2.06 | 540 | 224
2011-07-01 | 25T Excavator Hire | Shannon's Excavations | hr | 4 | 130 | 2.06 | 520 | 224
2011-07-01 | Labour Hire | Labour | hr | 4 | 38 | 2.06 | 152 | 224
2011-07-06 | Labour Hire | Labour | hr | 5 | 38 | 2.06 | 190 | 224
2011-07-06 | 25T Excavator Hire | Shannon's Excavations | hr | 6 | 130 | 2.06 | 780 | 224
2011-07-06 | Tipper Hire | Michael J Biles | hr | 6 | 95 | 2.06 | 570 | 224
2011-07-07 | Tipper Hire | Michael J Biles | hr | 6.5 | 85 | 2.06 | 552.5 | 224
2011-07-07 | 25T Excavator Hire | Shannon's Excavations | hr | 5.5 | 130 | 2.06 | 715 | 224
2011-07-08 | 25T Excavator Hire | Shannon's Excavations | hr | 5.5 | 130 | 2.06 | 715 | 224
2011-07-08 | Tipper Hire | Michael J Biles | hr | 6.5 | 85 | 2.06 | 552.5 | 224
| Subtotal for 224 | [5 empty] | 11791.5
Portfolio WBS 901
2011-03-02 | Project Technical Officer | Project Technical Officer | hr | 3 | 36.02 | 1.02 | 108.06 | 901
2011-03-14 | Project Technical Officer | Project Technical Officer | hr | 5.5 | 36.02 | 1.02 | 198.11 | 901
2011-03-15 | Project Technical Officer | Project Technical Officer | hr | 5.5 | 36.02 | 1.02 | 198.11 | 901
2011-03-24 | Project Technical Officer | Project Technical Officer | hr | 2.5 | 36.02 | 1.02 | 90.05 | 901
2011-04-21 | Work Place Health & Safety Officer | WHSO | week | 8 | 45 | 1.02 | 360 | 901
2011-06-02 | Work Place Health & Safety Officer | WHSO | week | 7 | 45 | 1.02 | 315 | 901
2011-06-17 | Work Place Health & Safety Officer | WHSO | week | 2 | 45 | 1.02 | 90 | 901
| Subtotal for 901 | [5 empty] | 1359.33
Portfolio WBS 902
2011-04-07 | Project Supervisor | Project Supervisor | hr | 9.5 | 68.99 | OH | 655.405 | 902
2011-04-11 | Project Supervisor | Project Supervisor | hr | 9.5 | 68.99 | OH | 655.405 | 902
2011-04-12 | Project Supervisor | Project Supervisor | hr | 12 | 68.99 | OH | 827.88 | 902
2011-04-13 | Project Supervisor | Project Supervisor | hr | 10 | 68.99 | OH | 689.9 | 902
2011-04-14 | Project Supervisor | Project Supervisor | hr | 9.5 | 68.99 | OH | 655.405 | 902
2011-04-15 | Project Supervisor | Project Supervisor | hr | 8 | 68.99 | OH | 551.92 | 902
2011-04-18 | Project Supervisor | Project Supervisor | hr | 9.5 | 68.99 | OH | 655.405 | 902
2011-04-19 | Project Supervisor | Project Supervisor | hr | 9.5 | 68.99 | OH | 655.405 | 902
2011-04-20 | Project Supervisor | Project Supervisor | hr | 10 | 68.99 | OH | 689.9 | 902
2011-04-21 | Project Supervisor | Project Supervisor | hr | 8.5 | 68.99 | OH | 586.415 | 902
2011-04-27 | Project Supervisor | Project Supervisor | hr | 9.5 | 68.99 | OH | 655.405 | 902
2011-04-28 | Project Supervisor | Project Supervisor | hr | 10 | 68.99 | OH | 689.9 | 902
2011-04-29 | Project Supervisor | Project Supervisor | hr | 8.5 | 68.99 | OH | 586.415 | 902
2011-05-03 | Project Supervisor | Project Supervisor | hr | 10 | 68.99 | OH | 689.9 | 902
2011-05-04 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-05-05 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-05-06 | Project Supervisor | Project Supervisor | hr | 8.5 | 68.99 | OH | 586.415 | 902
2011-05-09 | Project Supervisor | Project Supervisor | hr | 10 | 68.99 | OH | 689.9 | 902
2011-05-10 | Project Supervisor | Project Supervisor | hr | 10 | 68.99 | OH | 689.9 | 902
2011-05-11 | Project Supervisor | Project Supervisor | hr | 10.5 | 68.99 | OH | 724.395 | 902
2011-05-12 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-05-13 | Project Supervisor | Project Supervisor | hr | 9 | 68.99 | OH | 620.91 | 902
2011-05-14 | Project Supervisor | Project Supervisor | hr |  | 68.99 | OH |  | 902
2011-05-16 | Project Supervisor | Project Supervisor | hr | 10 | 68.99 | OH | 689.9 | 902
2011-05-17 | Project Supervisor | Project Supervisor | hr | 10.5 | 68.99 | OH | 724.395 | 902
2011-05-18 | Project Supervisor | Project Supervisor | hr | 10.5 | 68.99 | OH | 724.395 | 902
2011-05-19 | Project Supervisor | Project Supervisor | hr | 10.5 | 68.99 | OH | 724.395 | 902
2011-05-20 | Project Supervisor | Project Supervisor | hr | 9.5 | 68.99 | OH | 655.405 | 902
2011-05-23 | Project Supervisor | Project Supervisor | hr | 10 | 68.99 | OH | 689.9 | 902
2011-05-24 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-05-25 | Project Supervisor | Project Supervisor | hr | 10 | 68.99 | OH | 689.9 | 902
2011-05-26 | Project Supervisor | Project Supervisor | hr | 10.5 | 68.99 | OH | 724.395 | 902
2011-05-27 | Project Supervisor | Project Supervisor | hr | 9 | 68.99 | OH | 620.91 | 902
2011-05-31 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-06-01 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-06-02 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-06-03 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-06-06 | Project Supervisor | Project Supervisor | hr | 10.5 | 68.99 | OH | 724.395 | 902
2011-06-07 | Project Supervisor | Project Supervisor | hr | 10.5 | 68.99 | OH | 724.395 | 902
2011-06-08 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-06-09 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-06-10 | Project Supervisor | Project Supervisor | hr | 9 | 68.99 | OH | 620.91 | 902
2011-06-14 | Project Supervisor | Project Supervisor | hr | 10.5 | 68.99 | OH | 724.395 | 902
2011-06-15 | Project Supervisor | Project Supervisor | hr | 10.5 | 68.99 | OH | 724.395 | 902
2011-06-16 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-06-17 | Project Supervisor | Project Supervisor | hr | 9 | 68.99 | OH | 620.91 | 902
2011-06-20 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-06-21 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-06-22 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-06-23 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-06-24 | Project Supervisor | Project Supervisor | hr | 9 | 68.99 | OH | 620.91 | 902
2011-06-27 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-06-28 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-06-29 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-06-30 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-07-01 | Project Supervisor | Project Supervisor | hr | 9 | 68.99 | OH | 620.91 | 902
2011-07-04 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-07-05 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-07-06 | Project Supervisor | Project Supervisor | hr | 11 | 68.99 | OH | 758.89 | 902
2011-07-07 | Project Supervisor | Project Supervisor | hr | 11.5 | 68.99 | OH | 793.385 | 902
2011-07-08 | Project Supervisor | Project Supervisor | hr | 5 | 68.99 | OH | 344.95 | 902
| Subtotal for 902 | [5 empty] | 42014.91
Portfolio WBS 903
2011-04-15 | Spill Kit - 120Ltr Bin Medium | Spillkit | item | 1 | 649.63 | OH | 649.63 | 903
2011-04-18 | Neverfail Springwater - Inv 773863 | Water - Bottled Costs | item | 1 | 89.13 | OH | 89.13 | 903
2011-04-30 | Site Office & Lunchroom 15/4/11 to 30/4/11 Coates inv 8194574 | Crib Facilities | item | 1 | 435 | OH | 435 | 903
2011-04-30 | Inv 8194566 - 15/4/11 to 30/4/11 plus delivery | Generator | item | 1 | 1701.28 | OH | 1701.28 | 903
2011-05-04 | Temporary Fencing - 18/4/11 to 18/8/11 | Fencing | item | 1 | 1931 | OH | 1931 | 903
2011-05-09 | Purchase of Container Inv 117746 | Container | item | 1 | 3200 | OH | 3200 | 903
2011-06-30 | Generator Hire - Inv 8437843 | Generator | month | 1 | 2249.52 | OH | 2249.52 | 903
2011-06-30 | Site Office & Tiolet, 1 Pump out during project. Inv 8437852 | Crib Facilities | week | 1 | 900 | OH | 900 | 903
2011-07-06 | 5 x Corflute Signs | Signs - General | item | 1 | 113.64 | OH | 113.64 | 903
2011-07-07 | Inv 58 - Connect & Dis connect crib facilities | Electrician | item | 1 | 430 | OH | 430 | 903
2011-07-13 | Hire of Generator & Transport Costs- Inv 8505863 | Generator | week | 1 | 537.6 | OH | 537.6 | 903
2011-07-18 | Site Office & Lunch Room, Cleaning Fees - Inv 8519781 | Crib Facilities | week | 1 | 570 | OH | 570 | 903
2011-07-22 | Temporary Fencing - Cost for 3 Damaged Blocks | Fencing | item | 3 | 25 | OH | 75 | 903
| Subtotal for 903 | [5 empty] | 12881.8
Portfolio WBS 904
2011-04-14 | PL Insurance - Constructionl Risk Insurance | PL | each | 1 | 4246.75 | 1.01 | 4246.75 | 904
2011-04-30 | Coates Hire Inv 8194566 Damage Waiver Fees | Insurances | each | 1 | 151.41 | 1.01 | 151.41 | 904
2011-04-30 | Damage Waiver Fees for Office Lunch Room - Coates Inv 8194574 | Insurances | each | 1 | 54.38 | 1.01 | 54.38 | 904
2011-04-30 | Damage Waiver Fees - Coates Inv 8194583 | Insurances | each | 1 | 283.5 | 1.01 | 283.5 | 904
2011-06-30 | Damage Waiver Fees - Inv 8437843 | Insurances | each | 1 | 281.19 | 1.01 | 281.19 | 904
2011-06-30 | Insurances, fees & levies - Inv 8437852 | Insurances | each | 1 | 112.5 | 1.01 | 112.5 | 904
2011-07-13 | Damage Waiver fees - Inv 8505954 | Insurances | each | 1 | 141.75 | 1.01 | 141.75 | 904
2011-07-13 | Damage Waiver fees - Inv 8505863 | Insurances | each | 1 | 54.08 | 1.01 | 54.08 | 904
2011-07-18 | Damage Waiver Fees - Inv 8519781 | Insurances | each | 1 | 26.26 | 1.01 | 26.26 | 904
2011-07-31 | Damage Waiver Fee - inv 8563273 | Insurances | each | 1 | 159.38 | 1.01 | 159.38 | 904
2011-07-31 | Insurances, fees & levies Inv 8885150 | Insurances | each | 1 | 1470 | 1.01 | 1470 | 904
| Subtotal for 904 | [5 empty] | 6981.2
Portfolio WBS 905
2011-04-11 | Ariel Booster | Small Tools | item | 1 | 25.45 | OH | 25.45 | 905
2011-04-15 | Padlocks | Small Tools | item | 1 | 42.95 | OH | 42.95 | 905
2011-05-18 | Tape, Brooms & Broom Handles | Small Tools | item | 1 | 53.59 | OH | 53.59 | 905
2011-05-31 | Settlement Plates | Small Tools | item | 1 | 227.83 | OH | 227.83 | 905
2011-06-01 | Hammer Drill - Inv 11187541 | Small Tools | item | 1 | 112.73 | OH | 112.73 | 905
2011-06-02 | Hand Saw | Small Tools | item | 1 | 18.04 | OH | 18.04 | 905
2011-06-08 | Various miscellanoeus items | Small Tools | item | 1 | 134.31 | OH | 134.31 | 905
| Subtotal for 905 | [5 empty] | 614.9
Portfolio WBS 907
2011-04-11 | Items for Unit - Atr | Miscellaneous Items | item | 1 | 106.83 | OH | 106.83 | 907
2011-04-11 | Dozer Hire | Graham McDowall | hr | 4 | 165 | OH | 660 | 907
2011-04-12 | Dozer Hire | Graham McDowall | hr | 8 | 165 | OH | 1320 | 907
2011-04-12 | Float 25T Excavator to Kirknie | Float | item | 1 | 2400 | OH | 2400 | 907
2011-04-13 | Float Dozer to Kirknie | Graham McDowall | item | 1 | 700 | OH | 700 | 907
2011-04-18 | Safety glasses, gloves, sunscreen & Insect repellant | Miscellaneous Items | item | 1 | 125.79 | OH | 125.79 | 907
2011-04-19 | Miscellaneous items - safety signs, cable ties, spray & mark etc | Small Tools | item | 1 | 152.38 | OH | 152.38 | 907
2011-04-20 | Locks & Chain | Small Tools | item | 1 | 25.92 | OH | 25.92 | 907
2011-04-20 | Bins, Batteries and Fire Extinguishers | Small Tools | item | 1 | 176.43 | OH | 176.43 | 907
2011-04-27 | Flashing Light for Ford Ranger Ute | Small Tools | item | 1 | 149.67 | OH | 149.67 | 907
2011-04-27 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 2.5 | 42.79 | OH | 106.975 | 907
2011-04-27 | Labour | Labour | hr | 2.5 | 39.18 | OH | 97.95 | 907
2011-04-28 | Miscellaneous items spray & mark etc | Small Tools | item | 1 | 68.71 | OH | 68.71 | 907
2011-04-28 | 8 Wheel Tipper Hire - Iveco | PR & HT Gourlay | hr | 4 | 65 | OH | 260 | 907
2011-04-30 | Delivery of Office & Lunch Room | Float | item | 1 | 980 | OH | 980 | 907
2011-04-30 | Delivery costs - Coates Inv 8194583 | Float | LS | 1 | 1000 | OH | 1000 | 907
2011-05-02 | Float Grader to Kirknie Landfill | Float | item | 1 | 460 | OH | 460 | 907
2011-05-12 | Site Establishment Costs | Site Establishment Costs | item | 1 | 13995 | OH | 13995 | 907
2011-05-16 | Spray & Mark | Miscellaneous Items | item | 1 | 39.3 | OH | 39.3 | 907
2011-05-19 | Spray & Mark - Pink | Miscellaneous Items | item | 1 | 58.42 | OH | 58.42 | 907
2011-05-24 | Deliver container to site - Inv 1026 | Float | item | 1 | 500 | OH | 500 | 907
2011-06-01 | Marker Paint | Miscellaneous Items | item | 1 | 55.58 | OH | 55.58 | 907
2011-06-08 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 18.5 | 42.79 | OH | 791.615 | 907
2011-06-08 |  | Plant Float - Allciv | hr | 18.5 | 7 | OH | 129.5 | 907
2011-06-08 | Labour | Labour | hr | 18.5 | 39.18 | OH | 724.83 | 907
2011-06-17 | Miscellaneous items Spray Mark, Gloves Cable ties | Miscellaneous Items | item | 1 | 93.59 | OH | 93.59 | 907
2011-07-07 | Float charges 11T Excavator to Dysart | Float | item | 1 | 1800 | OH | 1800 | 907
2011-07-08 | De-Establishment - Move container to Airlie Beach Inv 1157 | Float | item | 1 | 681.82 | OH | 681.82 | 907
| Subtotal for 907 | [5 empty] | 27660.31
Portfolio WBS 910
2011-07-08 | Labour | Labour | hr | 4 | 32.2 | OH | 128.8 | 910
2011-07-08 | Labour | Labour | hr | 4 | 32.2 | OH | 128.8 | 910
2011-07-13 | Pick fee - Inv 8505954 | Float | item | 1 | 520 | OH | 520 | 910
2011-07-18 | Pick up fees Inv 8519781 | Float | item | 1 | 980 | OH | 980 | 910
2011-07-31 | Pick up fee - Skid Steer - Inv 8563273 | Float | item | 1 | 360 | OH | 360 | 910
| Subtotal for 910 | [5 empty] | 2117.6
Portfolio WBS 911
2011-04-18 | 2 weeks Accommodation | Accommodation | week | 2 | 220 | OH | 440 | 911
2011-04-20 | 2 Weeks Accommodation - 161 11th Ave Home Hill | Accommodation | week | 2 | 300 | OH | 600 | 911
2011-05-09 | 2 weeks Accommodation | Accommodation | week | 2 | 220 | OH | 440 | 911
2011-05-09 | 2 Weeks Accommodation 161 11th Ave Home Hill | Accommodation | week | 2 | 300 | OH | 600 | 911
2011-05-11 | Accommodation - Electricity for Unit 1/6 Clayton St Ayr | Accommodation | item | 1 | 71.24 | OH | 71.24 | 911
2011-05-23 | 2 Weeks Accommodation - 161 11th Avenue Home hill | Accommodation | week | 2 | 300 | OH | 600 | 911
2011-05-23 | 2 weeks Accommodation | Accommodation | week | 2 | 220 | OH | 440 | 911
2011-06-06 | 2 Weeks Accommodation - 161 11th Ave Home Hill | Accommodation | week | 2 | 300 | OH | 600 | 911
2011-06-06 | 2 weeks Accommodation | Accommodation | week | 2 | 220 | OH | 440 | 911
2011-07-06 | Accommodation - 161 11th Ave Home Hill | Accommodation | week | 1 | 128.57 | OH | 128.57 | 911
2011-07-06 | Accommodation 1/6 Clayton Street Ayr | Accommodation | week | 1 | 220 | OH | 220 | 911
| Subtotal for 911 | [5 empty] | 4579.81
Portfolio WBS QM2.3
2011-06-30 | Inv 18463 | 2.3 Gravel | tonne | 641.44 | 15.5 | 8.01 | 9942.32 | QM2.3
2011-06-30 | Inv 18463 | Cartage of Material | tonne | 641.44 | 7.5 | 8.01 | 4810.8 | QM2.3
| Subtotal for QM2.3 | [5 empty] | 14753.12
Portfolio WBS QMD40
2011-06-30 | Inv 18463 | 20mm Drainage Agg | tonne | 594.06 | 26 | 2.07 | 15445.56 | QMD40
2011-06-30 | Inv 18463 | 40mm Drainage Agg | tonne | 4719.58 | 20 | 2.06 | 94391.6 | QMD40
2011-06-30 | Inv 18463 | Cartage of Material | tonne | 594.06 | 7.5 | 2.07 | 4455.45 | QMD40
2011-06-30 | Inv 18463 | Cartage of Material | tonne | 62.18 | 7.5 | 2.06 | 466.35 | QMD40
2011-06-30 | Inv 18463 - Cartage Fees | Cartage of Material | tonne | 4719.58 | 7.5 | 2.06 | 35396.85 | QMD40
2011-07-29 | Inv 18642 - Ballast 1-7/7/11 | 40mm Drainage Agg | tonne | 1343.06 | 20 | 2.06 | 26861.2 | QMD40
2011-07-29 | Cartage - Inv 18642 | Cartage of Material | tonne | 1343.06 | 7.5 | 2.06 | 10072.95 | QMD40
| Subtotal for QMD40 | [5 empty] | 187089.96
Portfolio WBS QMR
2011-06-30 | Inv 18463 | 300m Rock | tonne | 62.18 | 28 | 5.03 | 1741.04 | QMR
| Subtotal for QMR | [5 empty] | 1741.04
Portfolio WBS SPF
2011-05-19 | Inv 18801 | Pipes - Various | item | 1 | 23479.5 | 10.01 | 23479.5 | SPF
| Subtotal for SPF | [5 empty] | 23479.5
| Grand Total | [5 empty] | 1084980.08