## Estimate
[9 empty] | 806368.6647 |  |  | 188502.7718 | 153519.292 | 389982.1544 | 74364.4464 | 806368.6647
WBS | Line No. | Resource Name | Unit | Type | No | Prodn | Quantity | Rate | Cost | Usage | Duration | Labour | Material | Plant | Subcontract | Total | Portfolio WBS
3 |  | PRELIMINARIES
4 | 1 | Stabilising | Item |  |  | 44.44 | 20085.2 | 29.7173 | 596877.3687 |  | 48 | 150930.2645 | 116121.1491 | 276500.3025 | 53325.6526 | 596877.3687
4.01 | 1 | Cement | tonne | M | 1 | 0.012 | 253.0735 | 375 | 94902.57 |  |  | 0 | 94902.57 | 0 | 0 | 94902.57 | CSA
| 4 | Stabilising Crew |  |  | 1
| 5 | Project Supervisor | hr | L | 1 | 1999.8 | 20085.2 | 3350 | 33646.0746 | 10.0436 | 10.0436 | 33646.0746 | 0 | 0 | 0 | 33646.0746 | 902
4.02 | 6 | CAT297 | hr | P | 1 | 44.44 | 20085.2 | 46.5 | 21016.2421 | 451.9622 | 451.9622 | 0 | 0 | 21016.2421 | 0 | 21016.2421 | 68
| 7 | UD Spreader | hr | P | 1 | 44.44 | 20085.2 | 21.61 | 9766.9031 | 451.9622 | 451.9622 | 0 | 0 | 9766.9031 | 0 | 9766.9031 | 68
| 8 | Water Cart - Hire | hr | P | 1 | 44.44 | 20085.2 | 95 | 42936.4086 | 451.9622 | 451.9622 | 0 | 0 | 42936.4086 | 0 | 42936.4086 | 68
| 9 | Grader | hr | P | 1 | 44.44 | 20085.2 | 160 | 72313.9514 | 451.9622 | 451.9622 | 0 | 0 | 72313.9514 | 0 | 72313.9514 | 68
| 10 | NH Grader | hr | P | 1 | 44.44 | 20085.2 | 25.78 | 11651.5854 | 451.9622 | 451.9622 | 0 | 0 | 11651.5854 | 0 | 11651.5854 | 68
| 11 | SD Roller - Wet (No Op) | hr | P | 1 | 44.44 | 20085.2 | 55 | 24857.9208 | 451.9622 | 451.9622 | 0 | 0 | 24857.9208 | 0 | 24857.9208 | 68
|  | Traffic Ute | hr | S | 1 | 44.44 | 20085.2 | 25 | 11299.0549 | 451.9622 | 451.9622 | 0 | 0 | 0 | 11299.0549 | 11299.0549 | 68
|  | Traffic Lights | day | P | 1 | 400 | 20085.2 | 125 | 6276.625 | 50.213 | 50.213 | 0 | 0 | 6276.625 | 0 | 6276.625 | 68
|  | Plant Float - Allciv | hr | P | 1 | 44.44 | 20085.2 | 7 | 3163.7354 | 451.9622 | 451.9622 | 0 | 0 | 3163.7354 | 0 | 3163.7354 | 68
|  | Tipper | hr | P | 1 | 44.44 | 20085.2 | 120 | 54235.4635 | 451.9622 | 451.9622 | 0 | 0 | 54235.4635 | 0 | 54235.4635 | 68
|  | Labour | hr | L | 4 | 44.44 | 20085.2 | 51.9 | 93827.3519 | 1807.8488 | 451.9622 | 93827.3519 | 0 | 0 | 0 | 93827.3519 | 68
Accommodation Requirements
|  | Accommodation | day | S | 1 | 1 | 311.3081 | 135 | 42026.5977 | 311.3081 | 311.3081 | 0 | 0 | 0 | 42026.5977 | 42026.5977 | 911
Holding Seals CRS60
|  | Paveline | hr | P | 1 | 44.44 | 20085.2 | 67 | 30281.4671 | 451.9622 | 451.9622 | 0 | 0 | 30281.4671 | 0 | 30281.4671 | 64
|  | Labour | hr | L | 1 | 44.44 | 20085.2 | 51.9 | 23456.838 | 451.9622 | 451.9622 | 23456.838 | 0 | 0 | 0 | 23456.838 | 64
4.03 |  | 10 mm Aggregate | tonne | M | 1 | 120 | 301.278 | 37 | 11147.286 |  |  | 0 | 11147.286 | 0 | 0 | 11147.286 | 64
4.04 |  | 7 mm Aggregate | tonne | M | 1 | 140 | 258.2383 | 39 | 10071.2931 |  |  | 0 | 10071.2931 | 0 | 0 | 10071.2931 | 64
5 | PV01 | VARIATION - Emulsion Used for Training | Day |  |  |  | 2560 | 1.4 | -3584 |  | 0 | 0 | -3584 | 0 | 0 | -3584
| 1 | CRS60 Emulsion | hr | M | 1 | 1 | -2560 | 1.4 | -3584 |  |  | 0 | -3584 | 0 | 0 | -3584 | 64
6 | PV02 | VARIATION - Additional Stabilising North of Mine Access Road | Item |  |  | 44.44 | 5000 | 29.9201 | 149600.2959 |  | 12 | 37572.5073 | 28907.1429 | 68831.8519 | 14288.7939 | 149600.2959
6.01 | 1 | Cement | tonne | M | 1 | 0.012 | 63 | 375 | 23625 |  |  | 0 | 23625 | 0 | 0 | 23625 | CSA
| 4 | Stabilising Crew |  |  | 1
| 5 | Project Supervisor | hr | L | 1 | 1999.8 | 5000 | 3350 | 8375.8376 | 2.5003 | 2.5003 | 8375.8376 | 0 | 0 | 0 | 8375.8376 | 902
6.02 | 6 | CAT297 | hr | P | 1 | 44.44 | 5000 | 46.5 | 5231.7732 | 112.5113 | 112.5113 | 0 | 0 | 5231.7732 | 0 | 5231.7732 | 68
| 7 | UD Spreader | hr | P | 1 | 44.44 | 5000 | 21.61 | 2431.3681 | 112.5113 | 112.5113 | 0 | 0 | 2431.3681 | 0 | 2431.3681 | 68
| 8 | Water Cart - Hire | hr | P | 1 | 44.44 | 5000 | 95 | 10688.5689 | 112.5113 | 112.5113 | 0 | 0 | 10688.5689 | 0 | 10688.5689 | 68
| 9 | Grader | hr | P | 1 | 44.44 | 5000 | 160 | 18001.8002 | 112.5113 | 112.5113 | 0 | 0 | 18001.8002 | 0 | 18001.8002 | 68
| 10 | NH Grader | hr | P | 1 | 44.44 | 5000 | 25.78 | 2900.5401 | 112.5113 | 112.5113 | 0 | 0 | 2900.5401 | 0 | 2900.5401 | 68
| 11 | SD Roller - Wet (No Op) | hr | P | 1 | 44.44 | 5000 | 55 | 6188.1188 | 112.5113 | 112.5113 | 0 | 0 | 6188.1188 | 0 | 6188.1188 | 68
|  | Traffic Ute | hr | S | 1 | 44.44 | 5000 | 25 | 2812.7813 | 112.5113 | 112.5113 | 0 | 0 | 0 | 2812.7813 | 2812.7813 | 68
|  | Traffic Lights | day | P | 1 | 400 | 5000 | 125 | 1562.5 | 12.5 | 12.5 | 0 | 0 | 1562.5 | 0 | 1562.5 | 68
|  | Plant Float - Allciv | hr | P | 1 | 44.44 | 5000 | 7 | 787.5788 | 112.5113 | 112.5113 | 0 | 0 | 787.5788 | 0 | 787.5788 | 68
|  | Tipper | hr | P | 1 | 44.44 | 5000 | 120 | 13501.3501 | 112.5113 | 112.5113 | 0 | 0 | 13501.3501 | 0 | 13501.3501 | 68
|  | Labour | hr | L | 4 | 44.44 | 5000 | 51.9 | 23357.3357 | 450.045 | 112.5113 | 23357.3357 | 0 | 0 | 0 | 23357.3357 | 68
Accommodation Requirements
|  | Accommodation | day | S | 1 | 1 | 85.0075 | 135 | 11476.0126 | 85.0075 | 85.0075 | 0 | 0 | 0 | 11476.0126 | 11476.0126 | 911
Holding Seals CRS60
|  | Paveline | hr | P | 1 | 44.44 | 5000 | 67 | 7538.2538 | 112.5113 | 112.5113 | 0 | 0 | 7538.2538 | 0 | 7538.2538 | 64
|  | Labour | hr | L | 1 | 44.44 | 5000 | 51.9 | 5839.3339 | 112.5113 | 112.5113 | 5839.3339 | 0 | 0 | 0 | 5839.3339 | 64
6.03 |  | 10 mm Aggregate | tonne | M | 1 | 120 | 75 | 37 | 2775 |  |  | 0 | 2775 | 0 | 0 | 2775 | 64
6.04 |  | 7 mm Aggregate | tonne | M | 1 | 140 | 64.2857 | 39 | 2507.1429 |  |  | 0 | 2507.1429 | 0 | 0 | 2507.1429 | 64
7 | PV03 | VARIATION - Clearing Table Drains | Day |  |  |  | 20 | 2570 | 51400 |  | 20 | 0 | 0 | 44650 | 6750 | 51400
| 1 | Excavator - 15T | hr | P | 1 | 1 | 190 | 115 | 21850 | 190 | 190 | 0 | 0 | 21850 | 0 | 21850 | 191
| 2 | Tipper | hr | P | 1 | 1 | 190 | 120 | 22800 | 190 | 190 | 0 | 0 | 22800 | 0 | 22800 | 191
|  | Accommodation | d | S | 1 | 1 | 50 | 135 | 6750 | 50 | 50 | 0 | 0 | 0 | 6750 | 6750 | 911
8 | PV04 | VARIATION - Supply Additional Materials | Item |  |  |  | 1 | 21.5 | 5375 |  |  | 0 | 5375 | 0 | 0 | 5375
8.01 | 1 | CBR80 | tonne | M | 1 | 1 | 250 | 21.5 | 5375 |  |  | 0 | 5375 | 0 | 0 | 5375 | QM2.3
9 | PV05 | VARIATION - Supply Additional Materials | Item |  |  |  | 1 | 33.5 | 6700 |  |  | 0 | 6700 | 0 | 0 | 6700
9.01 | 1 | Sealing Aggregate 7/10 | tonne | M | 1 | 1 | 200 | 33.5 | 6700 |  |  | 0 | 6700 | 0 | 0 | 6700 | QMR

## Resources
| Resource Name | Type | Unit | Currency | Base Rate
Labour Resources | Project Supervisor | L | week | AUD | 3350
| Labour | L | hr | AUD | 51.9
Material Resources | Cement | M | tonne | AUD | 375
| 10 mm Aggregate | M | tonne | AUD | 37
| 7 mm Aggregate | M | tonne | AUD | 39
| CBR80 | M | tonne | AUD | 21.5
| CRS60 Emulsion | M | litre | AUD | 1.4
| Sealing Aggregate 7/10 | M | tonne | AUD | 33.5
Plant Resources | CAT297 | P | hr | AUD | 46.5
| UD Spreader | P | hr | AUD | 21.61
| Water Cart - Hire | P | hr | AUD | 95
| Grader | P | hr | AUD | 160
| NH Grader | P | hr | AUD | 25.78
| SD Roller - Wet (No Op) | P | hr | AUD | 55
| Traffic Lights | P | day | AUD | 125
| Plant Float - Allciv | P | hr | AUD | 7
| Tipper | P | hr | AUD | 120
| Paveline | P | hr | AUD | 67
| Excavator - 15T | P | hr | AUD | 115
Sub-Contract Resources | Traffic Ute | S | hr | AUD | 25
| Accommodation | S | day | AUD | 135

## Model Inputs
WBS | Description | Model Input | Type | UOM
4 | Stabilising | 20085.2 | Q | m2
4.01 | Cement | 12 | P | kq/m2
4.02 | CAT297 | 44.44 | P | m2/hr
4.03 | 10 mm Aggregate | 120 | P | m2/m3
4.04 | 7 mm Aggregate | 140 | P | m2/m3
5 | VARIATION - Emulsion Used for Training | 2560 | Q | litre
6 | VARIATION - Additional Stabilising North of Mine Access Road | 5000 | Q | m2
6.01 | Cement | 12 | P | kq/m2
6.02 | CAT297 | 44.44 | P | m2/hr
6.03 | 10 mm Aggregate | 120 | P | m2/m3
6.04 | 7 mm Aggregate | 140 | P | m2/m3
7 | VARIATION - Clearing Table Drains | 20 | Q | days
8.01 | CBR80 | 250 | Q | tonne
9.01 | Sealing Aggregate 7/10 | 200 | Q | tonne

## Non-Work Days
Non-Working Calendar 2011 - 2015 (Queensland - Australia)
| 2011-01-01 |  | 2012-01-01 |  | 2013-01-01 |  | 2014-01-01 |  | 2015-01-01
| 2011-01-08 | 2011-01-09 | 2012-01-14 | 2012-01-15 | 2013-01-19 | 2013-01-20 | 2014-01-18 | 2014-01-19 | 2015-01-17 | 2015-01-18
| 2011-01-01 | 2011-01-02 |  | 2012-01-01 | 2013-01-05 | 2013-01-06 | 2014-01-04 | 2014-01-05 | 2015-01-03 | 2015-01-04
| 2011-01-08 | 2011-01-09 | 2012-01-07 | 2012-01-08 | 2013-01-12 | 2013-01-13 | 2014-01-11 | 2014-01-12 | 2015-01-10 | 2015-01-11
| 2011-01-15 | 2011-01-16 | 2012-01-14 | 2012-01-15 | 2013-01-19 | 2013-01-20 | 2014-01-18 | 2014-01-19 | 2015-01-17 | 2015-01-18
| 2011-01-22 | 2011-01-23 | 2012-01-21 | 2012-01-22 | 2013-01-26 | 2013-01-27 | 2014-01-25 | 2014-01-26 | 2015-01-24 | 2015-01-25
| 2011-01-29 | 2011-01-30 | 2012-01-28 | 2012-01-29 | 2013-02-02 | 2013-02-03 | 2014-02-01 | 2014-02-02 | 2015-01-31 | 2015-02-01
| 2011-02-05 | 2011-02-06 | 2012-02-04 | 2012-02-05 | 2013-02-09 | 2013-02-10 | 2014-02-08 | 2014-02-09 | 2015-02-07 | 2015-02-08
| 2011-02-12 | 2011-02-13 | 2012-02-11 | 2012-02-12 | 2013-02-16 | 2013-02-17 | 2014-02-15 | 2014-02-16 | 2015-02-14 | 2015-02-15
| 2011-02-19 | 2011-02-20 | 2012-02-18 | 2012-02-19 | 2013-02-23 | 2013-02-24 | 2014-02-22 | 2014-02-23 | 2015-02-21 | 2015-02-22
| 2011-02-26 | 2011-02-27 | 2012-02-25 | 2012-02-26 | 2013-03-02 | 2013-03-03 | 2014-03-01 | 2014-03-02 | 2015-02-28 | 2015-03-01
| 2011-03-05 | 2011-03-06 | 2012-03-03 | 2012-03-04 | 2013-03-09 | 2013-03-10 | 2014-03-08 | 2014-03-09 | 2015-03-07 | 2015-03-08
| 2011-03-12 | 2011-03-13 | 2012-03-10 | 2012-03-11 | 2013-03-16 | 2013-03-17 | 2014-03-15 | 2014-03-16 | 2015-03-14 | 2015-03-15
| 2011-03-19 | 2011-03-20 | 2012-03-17 | 2012-03-18 | 2013-03-23 | 2013-03-24 | 2014-03-22 | 2014-03-23 | 2015-03-21 | 2015-03-22
| 2011-03-26 | 2011-03-27 | 2012-03-24 | 2012-03-25 | 2013-03-30 | 2013-03-31 | 2014-03-29 | 2014-03-30 | 2015-03-28 | 2015-03-29
| 2011-04-02 | 2011-04-03 | 2012-03-31 | 2012-04-01 | 2013-04-06 | 2013-04-07 | 2014-04-05 | 2014-04-06 | 2015-04-04 | 2015-04-05
| 2011-04-09 | 2011-04-10 | 2012-04-07 | 2012-04-08 | 2013-04-13 | 2013-04-14 | 2014-04-12 | 2014-04-13 | 2015-04-11 | 2015-04-12
| 2011-04-16 | 2011-04-17 | 2012-04-14 | 2012-04-15 | 2013-04-20 | 2013-04-21 | 2014-04-19 | 2014-04-20 | 2015-04-18 | 2015-04-19
| 2011-04-23 | 2011-04-24 | 2012-04-21 | 2012-04-22 | 2013-04-27 | 2013-04-28 | 2014-04-26 | 2014-04-27 | 2015-04-25 | 2015-04-26
| 2011-04-30 | 2011-05-01 | 2012-04-28 | 2012-04-29 | 2013-05-04 | 2013-05-05 | 2014-05-03 | 2014-05-04 | 2015-05-02 | 2015-05-03
| 2011-05-07 | 2011-05-08 | 2012-05-05 | 2012-05-06 | 2013-05-11 | 2013-05-12 | 2014-05-10 | 2014-05-11 | 2015-05-09 | 2015-05-10
| 2011-05-14 | 2011-05-15 | 2012-05-12 | 2012-05-13 | 2013-05-18 | 2013-05-19 | 2014-05-17 | 2014-05-18 | 2015-05-16 | 2015-05-17
| 2011-05-21 | 2011-05-22 | 2012-05-19 | 2012-05-20 | 2013-05-25 | 2013-05-26 | 2014-05-24 | 2014-05-25 | 2015-05-23 | 2015-05-24
| 2011-05-28 | 2011-05-29 | 2012-05-26 | 2012-05-27 | 2013-06-01 | 2013-06-02 | 2014-05-31 | 2014-06-01 | 2015-05-30 | 2015-05-31
| 2011-06-04 | 2011-06-05 | 2012-06-02 | 2012-06-03 | 2013-06-08 | 2013-06-09 | 2014-06-07 | 2014-06-08 | 2015-06-06 | 2015-06-07
| 2011-06-11 | 2011-06-12 | 2012-06-09 | 2012-06-10 | 2013-06-15 | 2013-06-16 | 2014-06-14 | 2014-06-15 | 2015-06-13 | 2015-06-14
| 2011-06-18 | 2011-06-19 | 2012-06-16 | 2012-06-17 | 2013-06-22 | 2013-06-23 | 2014-06-21 | 2014-06-22 | 2015-06-20 | 2015-06-21
| 2011-06-25 | 2011-06-26 | 2012-06-23 | 2012-06-24 | 2013-06-29 | 2013-06-30 | 2014-06-28 | 2014-06-29 | 2015-06-27 | 2015-06-28
| 2011-07-02 | 2011-07-03 | 2012-06-30 | 2012-07-01 | 2013-07-06 | 2013-07-07 | 2014-07-05 | 2014-07-06 | 2015-07-04 | 2015-07-05
| 2011-07-09 | 2011-07-10 | 2012-07-07 | 2012-07-08 | 2013-07-13 | 2013-07-14 | 2014-07-12 | 2014-07-13 | 2015-07-11 | 2015-07-12
| 2011-07-16 | 2011-07-17 | 2012-07-14 | 2012-07-15 | 2013-07-20 | 2013-07-21 | 2014-07-19 | 2014-07-20 | 2015-07-18 | 2015-07-19
| 2011-07-23 | 2011-07-24 | 2012-07-21 | 2012-07-22 | 2013-07-27 | 2013-07-28 | 2014-07-26 | 2014-07-27 | 2015-07-25 | 2015-07-26
| 2011-07-30 | 2011-07-31 | 2012-07-28 | 2012-07-29 | 2013-08-03 | 2013-08-04 | 2014-08-02 | 2014-08-03 | 2015-08-01 | 2015-08-02
| 2011-08-06 | 2011-08-07 | 2012-08-04 | 2012-08-05 | 2013-08-10 | 2013-08-11 | 2014-08-09 | 2014-08-10 | 2015-08-08 | 2015-08-09
| 2011-08-13 | 2011-08-14 | 2012-08-11 | 2012-08-12 | 2013-08-17 | 2013-08-18 | 2014-08-16 | 2014-08-17 | 2015-08-15 | 2015-08-16
| 2011-08-20 | 2011-08-21 | 2012-08-18 | 2012-08-19 | 2013-08-24 | 2013-08-25 | 2014-08-23 | 2014-08-24 | 2015-08-22 | 2015-08-23
| 2011-08-27 | 2011-08-28 | 2012-08-25 | 2012-08-26 | 2013-08-31 | 2013-09-01 | 2014-08-30 | 2014-08-31 | 2015-08-29 | 2015-08-30
| 2011-09-03 | 2011-09-04 | 2012-09-01 | 2012-09-02 | 2013-09-07 | 2013-09-08 | 2014-09-06 | 2014-09-07 | 2015-09-05 | 2015-09-06
| 2011-09-10 | 2011-09-11 | 2012-09-08 | 2012-09-09 | 2013-09-14 | 2013-09-15 | 2014-09-13 | 2014-09-14 | 2015-09-12 | 2015-09-13
| 2011-09-17 | 2011-09-18 | 2012-09-15 | 2012-09-16 | 2013-09-21 | 2013-09-22 | 2014-09-20 | 2014-09-21 | 2015-09-19 | 2015-09-20
| 2011-09-24 | 2011-09-25 | 2012-09-22 | 2012-09-23 | 2013-09-28 | 2013-09-29 | 2014-09-27 | 2014-09-28 | 2015-09-26 | 2015-09-27
| 2011-10-01 | 2011-10-02 | 2012-09-29 | 2012-09-30 | 2013-10-05 | 2013-10-06 | 2014-10-04 | 2014-10-05 | 2015-10-03 | 2015-10-04
| 2011-10-08 | 2011-10-09 | 2012-10-06 | 2012-10-07 | 2013-10-12 | 2013-10-13 | 2014-10-11 | 2014-10-12 | 2015-10-10 | 2015-10-11
| 2011-10-15 | 2011-10-16 | 2012-10-13 | 2012-10-14 | 2013-10-19 | 2013-10-20 | 2014-10-18 | 2014-10-19 | 2015-10-17 | 2015-10-18
| 2011-10-22 | 2011-10-23 | 2012-10-20 | 2012-10-21 | 2013-10-26 | 2013-10-27 | 2014-10-25 | 2014-10-26 | 2015-10-24 | 2015-10-25
| 2011-10-29 | 2011-10-30 | 2012-10-27 | 2012-10-28 | 2013-11-02 | 2013-11-03 | 2014-11-01 | 2014-11-02 | 2015-10-31 | 2015-11-01
| 2011-11-05 | 2011-11-06 | 2012-11-03 | 2012-11-04 | 2013-11-09 | 2013-11-10 | 2014-11-08 | 2014-11-09 | 2015-11-07 | 2015-11-08
| 2011-11-12 | 2011-11-13 | 2012-11-10 | 2012-11-11 | 2013-11-16 | 2013-11-17 | 2014-11-15 | 2014-11-16 | 2015-11-14 | 2015-11-15
| 2011-11-19 | 2011-11-20 | 2012-11-17 | 2012-11-18 | 2013-11-23 | 2013-11-24 | 2014-11-22 | 2014-11-23 | 2015-11-21 | 2015-11-22
| 2011-11-26 | 2011-11-27 | 2012-11-24 | 2012-11-25 | 2013-11-30 | 2013-12-01 | 2014-11-29 | 2014-11-30 | 2015-11-28 | 2015-11-29
| 2011-12-03 | 2011-12-04 | 2012-12-01 | 2012-12-02 | 2013-12-07 | 2013-12-08 | 2014-12-06 | 2014-12-07 | 2015-12-05 | 2015-12-06
| 2011-12-10 | 2011-12-11 | 2012-12-08 | 2012-12-09 | 2013-12-14 | 2013-12-15 | 2014-12-13 | 2014-12-14 | 2015-12-12 | 2015-12-13
| 2011-12-17 | 2011-12-18 | 2012-12-15 | 2012-12-16 | 2013-12-21 | 2013-12-22 | 2014-12-20 | 2014-12-21 | 2015-12-19 | 2015-12-20
| 2011-12-24 | 2011-12-25 | 2012-12-22 | 2012-12-23 | 2013-12-28 | 2013-12-29 | 2014-12-27 | 2014-12-28 | 2015-12-26 | 2015-12-27
| 2011-12-31 |  | 2012-12-29 | 2012-12-30
Christmas Day | 2011-12-25 | 2011-12-23 | 2012-12-25 | 2012-01-02 | 2013-12-25 | 2013-01-02 | 2014-12-25 | 2014-01-02 | 2015-12-25 | 2015-01-02
Boxing Day | 2011-12-27 | 2011-12-24 | 2012-12-26 | 2012-01-03 | 2013-12-26 | 2013-01-03 | 2014-12-26 | 2014-01-03 | 2015-12-26 | 2015-01-05
New Years Day | 2011-01-01 | 2011-12-28 | 2012-01-01 | 2012-01-04 | 2013-01-01 | 2013-01-04 | 2014-01-01 | 2014-12-22 | 2015-01-01 | 2015-01-06
Australia Day | 2011-01-26 | 2011-12-29 | 2013-01-26 | 2012-01-05 | 2013-01-28 | 2013-12-23 | 2014-01-27 | 2014-12-23 | 2015-01-26 | 2015-01-07
Good Friday | 2011-04-22 | 2011-12-30 | 2012-04-06 | 2012-01-06 | 2013-03-29 | 2013-12-24 | 2014-04-18 | 2014-12-24 | 2015-04-03 | 2015-01-08
Easter Monday | 2011-04-25 |  | 2012-04-09 | 2012-12-24 | 2013-04-01 | 2013-12-27 | 2014-04-21 | 2014-12-29 | 2015-04-06 | 2015-01-09
ANZAC Day | 2011-04-26 |  | 2012-04-25 | 2012-12-27 | 2013-04-25 | 2013-12-30 | 2014-04-25 | 2014-12-30 | 2015-04-27 | 2015-12-24
Labour Day | 2011-05-02 |  | 2012-05-07 | 2012-12-28 | 2013-06-10 | 2013-12-31 | 2014-10-06 | 2014-12-31 | 2015-10-05 | 2015-12-27
Queen's Birthday | 2011-06-13 |  | 2012-06-11 | 2012-12-31 | 2013-10-07 |  | 2014-06-09 |  | 2015-06-08 | 2015-12-28
2015-12-29
2015-12-30
2015-12-31
|  | Xmas S/D | 2012-12-28: Xmas S/D; 2013-12-31: Xmas S/D; 2014-12-31: Xmas S/D; 2015-12-27: Xmas S/D
Work Hours Per Day |  | 9.5

## Program Links
WBS | Description | Duration | Predessors | Successors | Budget | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01
ENSURE BELOW IS PASTED INTO ROW 3 OF MS-PROJECT
3 | PRELIMINARIES | 0 |  |  | 0
4 | Stabilising | 48 |  | 6,8FF,7FF | 596877.3687 | 25.26% | 48.27% | 53.12% | 63.56% | 106%
5 | VARIATION - Emulsion Used for Training | 0 |  |  | -3584 | 0% | 100% | 100% | 100% | 100%
6 | VARIATION - Additional Stabilising North of Mine Access Road | 12 | 4 | 8FF,9FF,10 | 149600.2959 | 0% | 0% | 25.78% | 25.78% | 25.78%
7 | VARIATION - Clearing Table Drains | 20 | 4FF |  | 51400 | 15% | 70% | 100% | 112.5% | 137.5%
8 | VARIATION - Supply Additional Materials | 0 | 6FF,4FF |  | 5375 | 29.03% | 48.66% | 68.92% | 83.06% | 83.06%
9 | VARIATION - Supply Additional Materials | 0 | 6FF |  | 6700 | 0% | 52.63% | 131.6% | 186.8% | 349%
10 | Practical Completion | 0 | 6

## Budget & Revenue
WBS | Item No | Description | Unit | SQ | AQ | Budget Rate | Original Budget | Final Budget | Contract Sell Rate | Contract Sell Total | 2011-06-01 | %C Jun-11 | 2011-07-01 | %C Jul-11 | 2011-08-01 | %C Aug-11 | 2011-09-01 | %C Sep-11 | 2011-10-01 | %C Oct-11 | Revenue Jun-11 | Revenue Jul-11 | Revenue Aug-11 | Revenue Sep-11 | Revenue Oct-11
Contract Items
SARAJI ROAD
4 |  | Stabilising Works: 3% cement by mass & CRS60 10/7 holding seal | sqm | 20085 | 21280.2 | 29.7173 | 596877.3687 | 596871.4253 | 35 | 744807 | 5074 | 25.26% | 9695 | 48.27% | 10669 | 53.12% | 12767 | 63.56% | 21280.2 | 106% | 177590 | 339325 | 373415 | 446845 | 744807
|  | TOTALS Original Works |  |  |  |  | 596877.3687 | 596871.4253 |  | 744807
Variations
5 | VO1 | Emulsion Used By Allciv for Training | litre | 2560 | 2560 | 1.4 | -3584 | -3584 | -1.4 | -3584 |  | 0% | 2560 | 100% | 2560 | 100% | 2560 | 100% | 2560 | 100% | 0 | -3584 | -3584 | -3584 | -3584
6 | V02 | Additional Stabilising works North of Saraji Mine | m² | 5000 | 1289 | 29.9201 | 149600.2959 | 38566.9563 | 35 | 45115 |  | 0% |  | 0% | 1289 | 25.78% | 1289 | 25.78% | 1289 | 25.78% | 0 | 0 | 45115 | 45115 | 45115
7 | V03 | Clearing Table Drains | day | 20 | 27.5 | 2570 | 51400 | 70675 | 5035 | 138462.5 | 3 | 15% | 14 | 70% | 20 | 100% | 22.5 | 112.5% | 27.5 | 137.5% | 15105 | 70490 | 100700 | 113287.5 | 138462.5
8 | V04 | Supply Additional Road Base Gravel | tonne | 250 | 207.65 | 21.5 | 5375 | 4464.475 | 21.5 | 4464.475 | 72.58 | 29.03% | 121.65 | 48.66% | 172.29 | 68.92% | 207.65 | 83.06% | 207.65 | 83.06% | 1560.47 | 2615.475 | 3704.235 | 4464.475 | 4464.475
9 | V05 | Supply Sealing Aggregate 7/10 mm | tonne | 200 | 697.98 | 33.5 | 6700 | 23382.33 | 33.5 | 23382.33 |  | 0% | 105.26 | 52.63% | 263.23 | 131.6% | 373.5 | 186.8% | 697.98 | 349% | 0 | 3526.21 | 8818.205 | 12512.25 | 23382.33
|  | TOTALS Variations |  |  |  |  | 209491.2959 | 133504.7613 |  | 207840.305
|  | Total contract items and variations |  |  |  |  | 806368.6647 | 730376.1866 |  | 952647.305 |  | 194255.47 |  | 412372.685 |  | 528168.44 |  | 618640.225 |  | 952647.305 | 194255.47 | 412372.685 | 528168.44 | 618640.225 | 952647.305

## Portfolio WBS
Cost Code | Description | Quantity | Unit | Original Budget Rate | BAC | Final Qty | Final Cost | Final Rate |  |  |  | 2011-05-01 |  |  |  |  | 2011-06-01 |  |  |  |  | 2011-07-01 |  |  |  |  | 2011-08-01 |  |  |  |  | 2011-09-01 |  |  |  |  | 2011-10-01 |  |  |  |  | 2011-11-01 |  |  |  |  | 2012-09-01
| Totals, all cost codes | SQ |  |  | 944430.8 | AQ | AC |  | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV
13 | QA Testing | 0 | item | 0 | 0 | 1 | 4750 | 4750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65 | 3340 | 0 | 0 | 0 | 0.85 | 4150 | 0 | 0 | 0 | 0.95 | 4750 | 0 | 0 | 0 | 1 | 4750 | 0 | 0 | 0 | 1 | 4750 | 0 | 0 | 0 | 1 | 4750 | 0 | 0 | 0 | 1 | 4750 | 0
62 | Purchase Water - IRC | 0 | item | 0 | 0 | 1 | 420 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | 0
64 | Sweep & Prime / Primer seal or Seal | 26280 | m2 | 3.4259 | 90032.6149 | 26280 | 118730 | 4.5179 | 4250 | 14560.069 | 0 | 0 | 0 | 8500 | 29120.138 | 530 | 6043.09 | 1815.7263 | 12750 | 43680.207 | 9695 | 51022.95 | 33214.0868 | 17000 | 58240.276 | 9695 | 58886.44 | 33214.0868 | 21280 | 72903.1219 | 17000 | 92080.09 | 58240.276 | 26280 | 90032.6149 | 26280 | 139834.145 | 90032.6149 | 26280 | 90032.6149 | 26280 | 139834.145 | 90032.6149 | 26280 | 90032.6149 | 26280 | 145851.255 | 90032.6149
68 | Insitu Stabilisation | 26280 | m2 | 16.6974 | 438808.9573 | 26280 | 223782 | 8.5153 | 4250 | 70964.1579 | 1875 | 22621.735 | 31307.7167 | 8500 | 141928.3157 | 5074 | 61006.81 | 84722.8558 | 12750 | 212892.4736 | 9695 | 94361.75 | 161881.7672 | 17000 | 283856.6314 | 14500 | 128050.49 | 242113.0092 | 21280 | 355321.7128 | 21280 | 183805.215 | 355321.7128 | 26280 | 438808.9573 | 26280 | 223781.7 | 438808.9573 | 26280 | 438808.9573 | 26280 | 223781.7 | 438808.9573 | 26280 | 438808.9573 | 26280 | 223781.7 | 438808.9573
191 | Dayworks - Cleaning Drains | 27.5 | day | 1623.6364 | 44650 | 27.5 | 92723 | 3371.7455 | 4 | 6494.5455 | 1.2 | 4751.28 | 1948.3636 | 8 | 12989.0909 | 3 | 6267.435 | 4870.9091 | 12 | 19483.6364 | 14 | 25325.07 | 22730.9091 | 16 | 25978.1818 | 20 | 60299.05 | 32472.7273 | 20 | 32472.7273 | 22.5 | 66781.515 | 36531.8182 | 24 | 38967.2727 | 26 | 90202.42 | 42214.5455 | 27.5 | 44650 | 27.5 | 91621.18 | 44650 | 27.5 | 44650 | 27.5 | 94517.63 | 44650
902 | Project Supervision | 53 | day | 792.8663 | 42021.9122 | 139 | 93792 | 674.7626 | 8 | 6342.9301 | 18 | 11964.15 | 5441.6865 | 16 | 12685.8603 | 35 | 23843.9 | 10581.057 | 24 | 19028.7904 | 72 | 48482.1 | 21766.7459 | 32 | 25371.7206 | 87 | 59050.25 | 26301.4846 | 40 | 31714.6507 | 117 | 78901.65 | 35370.9621 | 48 | 38057.5809 | 134 | 90848.15 | 40510.3326 | 53 | 42021.9122 | 139 | 90848.15 | 42021.9122 | 53 | 42021.9122 | 139 | 93792.495 | 42021.9122
905 | Small Tools | 0 | item | 0 | 0 | 1 | 5698 | 5698 | 0 | 0 | 0.05 | 359.35 | 0 | 0 | 0 | 0.15 | 826.85 | 0 | 0 | 0 | 0.15 | 826.85 | 0 | 0 | 0 | 0.75 | 5140.48 | 0 | 0 | 0 | 0.9 | 5259.45 | 0 | 0 | 0 | 1 | 5697.75 | 0 | 0 | 0 | 1 | 5697.75 | 0 | 0 | 0 | 1 | 5697.75 | 0
907 | Site Relocations (Along Road) | 0 | month | 0 | 0 | 6 | 39399 | 6566.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6991.78 | 0 | 0 | 0 | 2 | 15375.72 | 0 | 0 | 0 | 3 | 22977.305 | 0 | 0 | 0 | 4 | 28856.15 | 0 | 0 | 0 | 5 | 36682.5 | 0 | 0 | 0 | 6 | 36682.5 | 0 | 0 | 0 | 6 | 39398.615 | 0
911 | Accommodation | 580 | nights | 103.8838 | 60252.6103 | 499 | 67367 | 135.004 | 41 | 4259.2362 | 67 | 9078.12 | 8090.0298 | 124 | 12881.5925 | 164 | 22107.29 | 19802.4611 | 207 | 21503.9488 | 359 | 48479.02 | 43348.0703 | 290 | 30126.3051 | 378 | 50970 | 45642.2579 | 373 | 38748.6614 | 455 | 60399.53 | 54939.7548 | 456 | 47371.0177 | 499 | 67366.89 | 60252.6103 | 580 | 60252.6103 | 499 | 67366.89 | 60252.6103 | 580 | 60252.6103 | 499 | 67366.89 | 60252.6103
CSA | Cement Powder (Stabilising) | 335 | tonne | 353.8136 | 118527.57 | 325 | 109135 | 335.8 | 54.1762 | 19168.2714 | 41 | 13825 | 14952.7088 | 108.3524 | 38336.5428 | 123 | 41195 | 44858.1265 | 162.5285 | 57504.8142 | 202 | 68055 | 73669.4435 | 216.7047 | 76673.0856 | 202 | 68055 | 73669.4435 | 271.2633 | 95976.6625 | 284 | 95705 | 103574.8612 | 335 | 118527.57 | 325 | 109135 | 118527.57 | 335 | 118527.57 | 325 | 109135 | 118527.57 | 335 | 118527.57 | 325 | 109135 | 118527.57
QM2.3 | Road Base | 178 | tonne | 30.1966 | 5375 | 207.65 | 3838 | 18.483 | 25 | 754.9157 | 0 | 0 | 0 | 50 | 1509.8315 | 72.58 | 1033.29 | 1878.7262 | 75 | 2264.7472 | 121.65 | 3163.725 | 3148.8984 | 100 | 3019.6629 | 172.29 | 3400.01 | 4459.7098 | 125 | 3774.5787 | 207.65 | 3400.01 | 5375 | 150 | 4529.4944 | 207.65 | 3838.46 | 5375 | 178 | 5375 | 207.65 | 3838.46 | 5375 | 178 | 5375 | 207.65 | 3838.46 | 5375
QMR | Sealing Aggregate (10/7) | 1290 | tonne | 5.1938 | 6700 | 1290 | 52649 | 40.8132 | 208.6187 | 1083.5236 | 0 | 0 | 0 | 417.2374 | 2167.0472 | 89 | 0 | 462.2481 | 625.8562 | 3250.5708 | 237 | 0 | 1230.9302 | 834.4749 | 4334.0944 | 317 | 0 | 1646.4341 | 1044.5662 | 5425.2664 | 586 | 6462.59 | 3043.5659 | 1290 | 6700 | 1290 | 26038.82 | 6700 | 1290 | 6700 | 1290 | 26038.82 | 6700 | 1290 | 6700 | 1290 | 26038.82 | 6700
| Totals, all cost codes |  |  |  | 806368.6647 |  | 813335 |  |  | 123627.6494 |  | 62599.635 | 61740.5055 |  | 251618.4189 |  | 172655.445 | 168992.11 |  | 379609.1884 |  | 359242.185 | 360990.8514 |  | 507599.9579 |  | 461579.025 | 459519.1532 |  | 636337.3816 |  | 626401.2 | 652397.9509 |  | 782994.5079 |  | 798175.835 | 802421.6305 |  | 806368.6647 |  | 799594.595 | 806368.6647 |  | 806368.6647 |  | 814588.615 | 806368.6647
|  | PV | EV | AC
| 2011-05-01 | 123627.6494 | 61740.5055 | 62599.635
| 2011-06-01 | 251618.4189 | 168992.11 | 172655.445
| 2011-07-01 | 379609.1884 | 360990.8514 | 359242.185
| 2011-08-01 | 507599.9579 | 459519.1532 | 461579.025
| 2011-09-01 | 636337.3816 | 652397.9509 | 626401.2
| 2011-10-01 | 782994.5079 | 802421.6305 | 798175.835
| 2011-11-01 | 806368.6647 | 806368.6647 | 799594.595
| 2012-09-01 | 806368.6647 | 806368.6647 | 814588.615

## Actual Costs
Date | Description | Resource | Unit | Quantity | Rate | Total | Cost Code | Supplier | Portfoliol WBS | TOTAL | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01
| Cost Code 013 | [7 empty] | 13 | 4750 | 0 | 3340 | 4150 | 4750 | 4750 | 4750 | 4750 | 4750 | 4750 | 4750 | 4750 | 4750 | 4750 | 4750 | 4750 | 4750 | 4750 | 0
2011-06-30 | Inv 69103445 | Field Density |  | 1 | 3340 | 3340 | 13 | Bowler Geotechnical | 62 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 0
2011-07-29 | Inv 69121257 | Field Density |  | 1 | 810 | 810 | 13 | Bowler Geotechnical | 64 | 145851.255 | 0 | 6043.09 | 51022.95 | 58886.44 | 92080.09 | 139834.145 | 139834.145 | 139834.145 | 139834.145 | 139834.145 | 139834.145 | 139834.145 | 139834.145 | 139834.145 | 139834.145 | 139834.145 | 145851.255 | 0
2011-08-26 | Inv 69121531 | Field Density |  | 1 | 600 | 600 | 13 | Bowler Geotechnical | 68 | 223781.7 | 22621.735 | 61006.81 | 94361.75 | 128050.49 | 183805.215 | 223781.7 | 223781.7 | 223781.7 | 223781.7 | 223781.7 | 223781.7 | 223781.7 | 223781.7 | 223781.7 | 223781.7 | 223781.7 | 223781.7 | 0
| Subtotal for 013 |  |  |  |  | 4750 |  |  | 191 | 94517.63 | 4751.28 | 6267.435 | 25325.07 | 60299.05 | 66781.515 | 90202.42 | 91621.18 | 91621.18 | 91621.18 | 91621.18 | 91621.18 | 91621.18 | 91621.18 | 91621.18 | 91621.18 | 91621.18 | 94517.63 | 0
[9 empty] | 902 | 93792.495 | 11964.15 | 23843.9 | 48482.1 | 59050.25 | 78901.65 | 90848.15 | 90848.15 | 90848.15 | 90848.15 | 90848.15 | 90848.15 | 90848.15 | 90848.15 | 90848.15 | 90848.15 | 90848.15 | 93792.495 | 0
[9 empty] | 905 | 5697.75 | 359.35 | 826.85 | 826.85 | 5140.48 | 5259.45 | 5697.75 | 5697.75 | 5697.75 | 5697.75 | 5697.75 | 5697.75 | 5697.75 | 5697.75 | 5697.75 | 5697.75 | 5697.75 | 5697.75 | 0
| Cost Code 062 | [7 empty] | 907 | 39398.615 | 0 | 6991.78 | 15375.72 | 22977.305 | 28856.15 | 36682.5 | 36682.5 | 36682.5 | 36682.5 | 36682.5 | 36682.5 | 36682.5 | 36682.5 | 36682.5 | 36682.5 | 36682.5 | 39398.615 | 0
2012-01-11 | Inv No 71014 | Water Usage |  | 1 | 420 | 420 | 62 | Isaac Regioal Council | 911 | 67366.89 | 9078.12 | 22107.29 | 48479.02 | 50970 | 60399.53 | 67366.89 | 67366.89 | 67366.89 | 67366.89 | 67366.89 | 67366.89 | 67366.89 | 67366.89 | 67366.89 | 67366.89 | 67366.89 | 67366.89 | 0
| Subtotal for 062 |  |  |  |  | 420 |  |  | CSA | 109135 | 13825 | 41195 | 68055 | 68055 | 95705 | 109135 | 109135 | 109135 | 109135 | 109135 | 109135 | 109135 | 109135 | 109135 | 109135 | 109135 | 109135 | 0
[9 empty] | QM2.3 | 3838.46 | 0 | 1033.29 | 3163.725 | 3400.01 | 3400.01 | 3838.46 | 3838.46 | 3838.46 | 3838.46 | 3838.46 | 3838.46 | 3838.46 | 3838.46 | 3838.46 | 3838.46 | 3838.46 | 3838.46 | 0
| Cost Code 064 | [7 empty] | QMR | 26038.82 | 0 | 0 | 0 | 0 | 6462.59 | 26038.82 | 26038.82 | 26038.82 | 26038.82 | 26038.82 | 26038.82 | 26038.82 | 26038.82 | 26038.82 | 26038.82 | 26038.82 | 26038.82 | 0
2011-06-04 | 10 mm sealing aggregate - Inv 2198 | 10 mm Aggregate |  | 69.83 | 33.5 | 2339.305 | 64 | Crushing Insudtries Aust |  | 814588.615 | 62599.635 | 172655.445 | 359242.185 | 461579.025 | 626401.2 | 798175.835 | 799594.595 | 799594.595 | 800014.595 | 800014.595 | 800014.595 | 800014.595 | 800014.595 | 800014.595 | 800014.595 | 800014.595 | 814588.615 | 0
2011-06-27 | Purchase Poly Tank - Emulsion | Poly Tank |  | 1 | 2209.09 | 2209.09 | 64 | Middlemount Rural | [19 empty] | 0
2011-06-30 | 10 mm sealing aggregate Inv 2173 | 10 mm Aggregate |  | 38.65 | 33.5 | 1294.775 | 64 | Crushing Insudtries Aust | [19 empty] | 0
2011-06-30 | 6 x Loose Stones Signs | Signs - General |  | 6 | 33.32 | 199.92 | 64 | Artcraft | [19 empty] | 0
2011-07-01 | Labour | Labour | hr | 10.5 | 39.39 | 413.595 | 64 | [20 empty] | 0
2011-07-01 | Sealing Truck | Paveline Truck | hr | 11.5 | 50 | 575 | 64 | [20 empty] | 0
2011-07-01 | Labour | Labour | hr | 11.5 | 30 | 345 | 64
2011-07-01 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 11 | 42.79 | 470.69 | 64
2011-07-01 |  | Plant Float - Allciv | hr | 11 | 7 | 77 | 64
2011-07-01 | Labour | Labour | hr | 11.5 | 32.2 | 370.3 | 64
2011-07-01 | Truck Driver | Labour | hr | 11 | 39.18 | 430.98 | 64
2011-07-02 | Labour | Labour | hr | 6 | 39.39 | 236.34 | 64
2011-07-02 | Stand Down SD Roller | Bomag 124DH (Stand Down) | hr | 6.5 | 10.75 | 69.875 | 64
2011-07-02 | Labour | Labour | hr | 9.5 | 32.2 | 305.9 | 64
2011-07-02 | Truck Driver | Labour | hr | 11.5 | 39.18 | 450.57 | 64
2011-07-02 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 11 | 42.79 | 470.69 | 64
2011-07-02 | Labour | Labour | hr | 9.5 | 30 | 285 | 64
2011-07-02 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 64
2011-07-02 |  | Plant Float - Allciv | hr | 11 | 7 | 77 | 64
2011-07-02 | Sealing Truck | Paveline Truck | hr | 9.5 | 50 | 475 | 64
2011-07-03 | Labour | Labour | hr | 9.5 | 39.39 | 374.205 | 64
2011-07-03 | Stand Down SD Roller | Bomag 124DH (Stand Down) | hr | 7.5 | 10.75 | 80.625 | 64
2011-07-03 | Labour | Labour | hr | 9.5 | 32.2 | 305.9 | 64
2011-07-03 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 64
2011-07-03 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9 | 42.79 | 385.11 | 64
2011-07-03 | Labour | Labour | hr | 10.5 | 30 | 315 | 64
2011-07-03 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 64
2011-07-03 |  | Plant Float - Allciv | hr | 9 | 7 | 63 | 64
2011-07-03 | Sealing Truck | Paveline Truck | hr | 10.5 | 50 | 525 | 64
2011-07-04 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 64
2011-07-04 | Labour | Labour | hr | 10 | 39.39 | 393.9 | 64
2011-07-04 | Labour | Labour | hr | 10 | 30 | 300 | 64
2011-07-04 | Labour | Labour | hr | 10 | 32.2 | 322 | 64
2011-07-04 |  | Plant Float - Allciv | hr | 9 | 7 | 63 | 64
2011-07-04 | Sealing Truck | Paveline Truck | hr | 10 | 50 | 500 | 64
2011-07-04 | Stand Down SD Roller | Bomag 124DH (Stand Down) | hr | 7.5 | 10.75 | 80.625 | 64
2011-07-04 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9 | 42.79 | 385.11 | 64
2011-07-04 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 64
2011-07-04 | 10 mm sealing aggregate - Inv 2198 | 10 mm Aggregate |  | 69.83 | 33.5 | 2339.305 | 64 | Crushing Insudtries Aust
2011-07-05 |  | Plant Float - Allciv | hr | 9 | 7 | 63 | 64
2011-07-05 | Sealing Truck | Paveline Truck | hr | 10.5 | 50 | 525 | 64
2011-07-05 | Labour | Labour | hr | 10.5 | 30 | 315 | 64
2011-07-05 | Labour | Labour | hr | 2 | 39.39 | 78.78 | 64
2011-07-05 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 64
2011-07-05 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9 | 42.79 | 385.11 | 64
2011-07-05 | Stand Down SD Roller | Bomag 124DH (Stand Down) | hr | 7.5 | 10.75 | 80.625 | 64
2011-07-05 | 10 mm sealing aggregate - Inv 2227 | 10 mm Aggregate |  | 7.75 | 33.5 | 259.625 | 64 | Crushing Insudtries Aust
2011-07-13 | Stand Down SD Roller | Bomag 124DH (Stand Down) | hr | 7 | 10.75 | 75.25 | 64
2011-07-13 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 64
2011-07-13 | Labour | Labour | hr | 4.5 | 39.39 | 177.255 | 64
2011-07-13 | Labour | Labour | hr | 9.5 | 32.2 | 305.9 | 64
2011-07-13 | Labour | Labour | hr | 9.5 | 30 | 285 | 64
2011-07-13 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 64
2011-07-13 |  | Traffic Lights | day | 0.5 | 125 | 62.5 | 64
2011-07-13 | Sealing Truck | Paveline Truck | hr | 9.5 | 50 | 475 | 64
2011-07-13 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 64
2011-07-13 | 10 mm sealing aggregate - Inv 2268 | 10 mm Aggregate |  | 16.2 | 33.5 | 542.7 | 64 | Crushing Insudtries Aust
2011-07-14 | Work Place Health & Safety Officer | WHSO | week | 10 | 45 | 450 | 64
2011-07-14 | Stand Down SD Roller | Bomag 124DH (Stand Down) | hr | 7 | 10.75 | 75.25 | 64
2011-07-14 | Labour | Labour | hr | 10 | 39.39 | 393.9 | 64
2011-07-14 | Labour | Labour | hr | 10 | 32.2 | 322 | 64
2011-07-14 | Labour | Labour | hr | 10 | 30 | 300 | 64
2011-07-14 | Sealing Truck | Paveline Truck | hr | 9.5 | 50 | 475 | 64
2011-07-14 | Labour Hire | Labour | hr | 3.5 | 45 | 157.5 | 64
2011-07-14 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 64
2011-07-14 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 64
2011-07-14 | Labour | Labour | hr | 5 | 32.2 | 161 | 64
2011-07-15 | Labour | Labour | hr | 3 | 32.2 | 96.6 | 64
2011-07-15 | Work Place Health & Safety Officer | WHSO | week | 3 | 45 | 135 | 64
2011-07-15 | Labour | Labour | hr | 3 | 39.39 | 118.17 | 64
2011-07-15 | Labour | Labour | hr | 3 | 32.2 | 96.6 | 64
2011-07-15 | Labour | Labour | hr | 3.5 | 30 | 105 | 64
2011-07-15 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 64
2011-07-15 | SD Roller - Cat Rentals | SD Roller | day | 1 | 365 | 365 | 64
2011-07-15 | Sealing Truck | Paveline Truck | hr | 9.5 | 50 | 475 | 64
2011-07-18 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 64
2011-07-18 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9 | 42.79 | 385.11 | 64
2011-07-18 | Sealing Truck | Paveline Truck | hr | 5 | 50 | 250 | 64
2011-07-18 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 64
2011-07-18 | Labour | Labour | hr | 5 | 30 | 150 | 64
2011-07-18 | Stand Down SD Roller | Bomag 124DH (Stand Down) | hr | 2 | 10.75 | 21.5 | 64
2011-07-18 | Truck Driver | Labour | hr | 10.5 | 39.18 | 411.39 | 64
2011-07-18 | Labour | Labour | hr | 5 | 32.2 | 161 | 64
2011-07-18 | Labour | Labour | hr | 4 | 39.39 | 157.56 | 64
2011-07-18 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 64
2011-07-18 | Labour | Labour | hr | 4 | 32.2 | 128.8 | 64
2011-07-19 | Sealing Truck | Paveline Truck | hr | 5 | 50 | 250 | 64
2011-07-19 |  | Traffic Lights | day | 1 | 125 | 125 | 64
2011-07-19 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 64
2011-07-19 | 10 mm sealing aggregate - Inv 2316 | 10 mm Aggregate |  | 33.11 | 33.5 | 1109.185 | 64 | Crushing Insudtries Aust
2011-07-19 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 64
2011-07-19 | Labour | Labour | hr | 5 | 30 | 150 | 64
2011-07-19 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 64
2011-07-19 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 64
2011-07-19 | Labour | Labour | hr | 5 | 32.2 | 161 | 64
2011-07-19 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 7.5 | 42.79 | 320.925 | 64
2011-07-19 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 64
2011-07-19 | Labour | Labour | hr | 5 | 32.2 | 161 | 64
2011-07-20 |  | Traffic Lights | day | 1 | 125 | 125 | 64
2011-07-20 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 64
2011-07-20 | Sealing Truck | Paveline Truck | hr | 8.5 | 50 | 425 | 64
2011-07-20 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 64
2011-07-20 | Labour | Labour | hr | 5 | 30 | 150 | 64
2011-07-20 | Labour | Labour | hr | 5.5 | 39.39 | 216.645 | 64
2011-07-20 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 64
2011-07-20 | Labour | Labour | hr | 5 | 32.2 | 161 | 64
2011-07-20 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 7.5 | 42.79 | 320.925 | 64
2011-07-20 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 64
2011-07-20 | Labour | Labour | hr | 5.5 | 32.2 | 177.1 | 64
2011-07-21 |  | Traffic Lights | day | 1 | 125 | 125 | 64
2011-07-21 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 64
2011-07-21 | Sealing Truck | Paveline Truck | hr | 8.5 | 50 | 425 | 64
2011-07-21 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 64
2011-07-21 | Labour | Labour | hr | 5 | 30 | 150 | 64
2011-07-21 | Labour | Labour | hr | 4.5 | 39.39 | 177.255 | 64
2011-07-21 | Truck Driver | Labour | hr | 5.5 | 39.18 | 215.49 | 64
2011-07-21 | Labour | Labour | hr | 5 | 32.2 | 161 | 64
2011-07-21 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 7.5 | 42.79 | 320.925 | 64
2011-07-21 | Truck Driver | Labour | hr | 4 | 39.18 | 156.72 | 64
2011-07-21 | Labour | Labour | hr | 5.5 | 32.2 | 177.1 | 64
2011-07-22 |  | Traffic Lights | day | 1 | 125 | 125 | 64
2011-07-22 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 64
2011-07-22 | Sealing Truck | Paveline Truck | hr | 8.5 | 50 | 425 | 64
2011-07-22 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 64
2011-07-22 | Labour | Labour | hr | 5 | 30 | 150 | 64
2011-07-22 | Labour | Labour | hr | 4.5 | 39.39 | 177.255 | 64
2011-07-22 | Truck Driver | Labour | hr | 5.5 | 39.18 | 215.49 | 64
2011-07-22 | Labour | Labour | hr | 4 | 32.2 | 128.8 | 64
2011-07-22 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 7.5 | 42.79 | 320.925 | 64
2011-07-22 | Truck Driver | Labour | hr | 4 | 39.18 | 156.72 | 64
2011-07-22 | Labour | Labour | hr | 5.5 | 32.2 | 177.1 | 64
2011-07-23 |  | Traffic Lights | day | 1 | 125 | 125 | 64
2011-07-23 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 64
2011-07-23 | Sealing Truck | Paveline Truck | hr | 8.5 | 50 | 425 | 64
2011-07-23 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 64
2011-07-23 | Labour | Labour | hr | 5 | 30 | 150 | 64
2011-07-23 | Labour | Labour | hr | 5.5 | 39.39 | 216.645 | 64
2011-07-23 | Truck Driver | Labour | hr | 5.5 | 39.18 | 215.49 | 64
2011-07-23 | Labour | Labour | hr | 5 | 32.2 | 161 | 64
2011-07-23 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 7.5 | 42.79 | 320.925 | 64
2011-07-23 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 64
2011-07-23 | Labour | Labour | hr | 5.5 | 32.2 | 177.1 | 64
2011-07-24 |  | Traffic Lights | day | 1 | 125 | 125 | 64
2011-07-24 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 64
2011-07-24 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 7.5 | 42.79 | 320.925 | 64
2011-07-24 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 64
2011-07-24 | Labour | Labour | hr | 4 | 30 | 120 | 64
2011-07-24 | Sealing Truck | Paveline Truck | hr | 8.5 | 50 | 425 | 64
2011-07-24 | Truck Driver | Labour | hr | 4 | 39.18 | 156.72 | 64
2011-07-24 | Labour | Labour | hr | 4 | 32.2 | 128.8 | 64
2011-07-24 | 10 mm sealing aggregate - Inv 2342 | 10 mm Aggregate |  | 41.26 | 33.5 | 1382.21 | 64 | Crushing Insudtries Aust
2011-07-24 | Truck Driver | Labour | hr | 4 | 39.18 | 156.72 | 64
2011-07-24 | Labour | Labour | hr | 4 | 32.2 | 128.8 | 64
2011-07-24 | Labour | Labour | hr | 4 | 39.39 | 157.56 | 64
2011-07-25 | Labour | Labour | hr | 4 | 32.2 | 128.8 | 64
2011-07-25 | Truck Driver | Labour | hr | 4 | 39.18 | 156.72 | 64
2011-07-25 | Labour | Labour | hr | 4 | 39.39 | 157.56 | 64
2011-07-25 | Labour | Labour | hr | 4 | 32.2 | 128.8 | 64
2011-07-25 | Truck Driver | Labour | hr | 4 | 39.18 | 156.72 | 64
2011-07-25 | Sealing Truck | Paveline Truck | hr | 8.5 | 50 | 425 | 64
2011-07-25 | Labour | Labour | hr | 5 | 30 | 150 | 64
2011-07-25 | 10 mm sealing aggregate - Inv 2359 | 10 mm Aggregate |  | 13.77 | 33.5 | 461.295 | 64 | Crushing Insudtries Aust
2011-07-25 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 7.5 | 42.79 | 320.925 | 64
2011-07-25 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 64
2011-07-25 |  | Traffic Lights | day | 1 | 125 | 125 | 64
2011-07-26 |  | Traffic Lights | day | 1 | 125 | 125 | 64
2011-07-26 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 64
2011-07-26 | Labour | Labour | hr | 6 | 30 | 180 | 64
2011-07-26 | Sealing Truck | Paveline Truck | hr | 8.5 | 50 | 425 | 64
2011-07-26 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 7.5 | 42.79 | 320.925 | 64
2011-07-26 | Truck Driver | Labour | hr | 4 | 39.18 | 156.72 | 64
2011-07-26 | Labour | Labour | hr | 4 | 32.2 | 128.8 | 64
2011-07-26 | Labour | Labour | hr | 4 | 39.39 | 157.56 | 64
2011-07-26 | Truck Driver | Labour | hr | 4 | 39.18 | 156.72 | 64
2011-07-26 | Labour | Labour | hr | 4 | 32.2 | 128.8 | 64
2011-07-27 | Labour | Labour | hr | 7 | 39.39 | 275.73 | 64
2011-07-27 | Labour | Labour | hr | 7 | 32.2 | 225.4 | 64
2011-07-27 | Labour | Labour | hr | 5.5 | 32.2 | 177.1 | 64
2011-07-27 | Truck Driver | Labour | hr | 5.5 | 39.18 | 215.49 | 64
2011-07-27 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 64
2011-07-27 | Sealing Truck | Paveline Truck | hr | 6 | 50 | 300 | 64
2011-07-27 | Labour | Labour | hr | 6 | 30 | 180 | 64
2011-07-27 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 7.5 | 42.79 | 320.925 | 64
2011-07-27 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 64
2011-08-19 | Labour | Labour | hr | 5.5 | 32.2 | 177.1 | 64
2011-08-19 | Labour | Labour | hr | 9.5 | 30 | 285 | 64
2011-08-20 | 10 mm sealing aggregate Inv -2563 | 10 mm Aggregate |  | 24.28 | 33.5 | 813.38 | 64 | Crushing Insudtries Aust
2011-08-20 | 10 mm sealing aggregate Inv 2564 | 10 mm Aggregate |  | 24.37 | 21.5 | 523.955 | 64 | Crushing Insudtries Aust
2011-08-20 | Labour | Labour | hr | 5 | 32.2 | 161 | 64
2011-08-20 | Labour | Labour | hr | 10 | 30 | 300 | 64
2011-08-20 | Labour | Labour | hr | 9.5 | 30 | 285 | 64
2011-08-21 | Sealing Truck | Paveline Truck | hr | 3 | 50 | 150 | 64
2011-08-22 | 10 mm sealing aggregate Inv 2625 | 10 mm Aggregate |  | 16.15 | 33.5 | 541.025 | 64 | Crushing Insudtries Aust
2011-08-22 | Labour | Labour | hr | 5 | 32.2 | 161 | 64
2011-08-22 | Labour | Labour | hr | 5 | 32.2 | 161 | 64
2011-08-22 | Labour | Labour | hr | 5 | 30 | 150 | 64
2011-08-22 | Sealing Truck | Paveline Truck | hr | 5 | 50 | 250 | 64
2011-08-23 | Labour | Labour | hr | 5 | 32.2 | 161 | 64
2011-08-23 | Labour | Labour | hr | 5 | 32.2 | 161 | 64
2011-08-23 | Labour | Labour | hr | 5 | 30 | 150 | 64
2011-08-23 | Sealing Truck | Paveline Truck | hr | 5 | 50 | 250 | 64
2011-08-24 | Sealing Truck | Paveline Truck | hr | 5 | 50 | 250 | 64
2011-08-24 | Labour | Labour | hr | 5 | 30 | 150 | 64
2011-08-24 | 10 mm sealing aggregate Inv- 2575 | 10 mm Aggregate |  | 22.4 | 33.5 | 750.4 | 64 | Crushing Insudtries Aust
2011-08-24 | Labour | Labour | hr | 5 | 32.2 | 161 | 64
2011-08-24 | Labour | Labour | hr | 5 | 32.2 | 161 | 64
2011-08-31 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 64
2011-08-31 | 10 mm sealing aggregate Inv 2612 | 10 mm Aggregate |  | 18.76 | 33.5 | 628.46 | 64 | Crushing Insudtries Aust
2011-08-31 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 64
2011-08-31 | Sealing Truck | Paveline Truck | hr | 0.5 | 50 | 25 | 64
2011-08-31 | Labour | Labour | hr | 5 | 32.2 | 161 | 64
2011-08-31 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 64
2011-08-31 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 64
2011-08-31 | Labour | Labour | hr | 5 | 32.2 | 161 | 64
2011-09-01 | Sealing Truck | Paveline Truck | hr | 4 | 50 | 200 | 64
2011-09-01 | Labour | Labour | hr | 4.5 | 32.2 | 144.9 | 64
2011-09-01 | Labour | Labour | hr | 5 | 32.2 | 161 | 64
2011-09-02 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-02 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-02 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-02 | Sealing Truck | Paveline Truck | hr | 4.5 | 50 | 225 | 64
2011-09-02 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-02 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 64
2011-09-02 | Inv - 2638 | 10 mm Aggregate |  | 28.68 | 33.5 | 960.78 | 64 | Crushing Insudtries Aust
2011-09-02 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-03 | Labour | Labour | hr | 9.5 | 32.2 | 305.9 | 64
2011-09-03 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 64
2011-09-03 | Labour | Labour | hr | 9.5 | 39.39 | 374.205 | 64
2011-09-03 | Sealing Truck | Paveline Truck | hr | 4 | 50 | 200 | 64
2011-09-03 | Labour | Labour | hr | 10 | 32.2 | 322 | 64
2011-09-07 | Tipper 3T - Kennards Hire | Tipper 3T | day | 0.5 | 213.4 | 106.7 | 64
2011-09-07 | inv - 2663 | Primer Seal - 10mm |  | 11.96 | 33.5 | 400.66 | 64 | Crushing Insudtries Aust
2011-09-07 | Labour | Labour | hr | 6 | 32.2 | 193.2 | 64
2011-09-07 | Truck Driver | Labour | hr | 6 | 39.18 | 235.08 | 64
2011-09-07 | Sealing Truck | Paveline Truck | hr | 3 | 50 | 150 | 64
2011-09-07 | Labour | Labour | hr | 5 | 32.2 | 161 | 64
2011-09-08 | Tipper 3T - Kennards Hire | Tipper 3T | day | 0.5 | 213.4 | 106.7 | 64
2011-09-08 | Sealing Truck | Paveline Truck | hr | 2 | 50 | 100 | 64
2011-09-14 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-14 | Sealing Truck | Paveline Truck | hr | 4.5 | 50 | 225 | 64
2011-09-14 | 10 mm sealing aggregate Inv 2698 | 10 mm Aggregate |  | 9.08 | 33.5 | 304.18 | 64 | Crushing Insudtries Aust
2011-09-14 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-14 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 64
2011-09-14 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-16 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-16 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-16 | Sealing Truck | Paveline Truck | hr | 4 | 50 | 200 | 64
2011-09-16 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-16 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-16 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-16 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 64
2011-09-17 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 64
2011-09-17 | Labour | Labour | hr | 10 | 32.2 | 322 | 64
2011-09-17 | Labour | Labour | hr | 10 | 39.39 | 393.9 | 64
2011-09-17 | Truck Driver | Labour | hr | 10 | 39.18 | 391.8 | 64
2011-09-17 | Sealing Truck | Paveline Truck | hr | 10 | 50 | 500 | 64
2011-09-17 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 64
2011-09-17 |  | Plant Float - Allciv | hr | 8.5 | 7 | 59.5 | 64
2011-09-17 | Labour | Labour | hr | 10 | 32.2 | 322 | 64
2011-09-17 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7.5 | 66.07 | 495.525 | 64
2011-09-18 | 10 mm sealing aggregate Inv - 2716 | 10 mm Aggregate |  | 61.69 | 33.5 | 2066.615 | 64 | Crushing Insudtries Aust
2011-09-19 | Labour | Labour | hr | 9 | 32.2 | 289.8 | 64
2011-09-19 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 64
2011-09-19 | Labour | Labour | hr | 9 | 32.2 | 289.8 | 64
2011-09-19 | Truck Driver | Labour | hr | 9 | 39.18 | 352.62 | 64
2011-09-19 |  | Plant Float - Allciv | hr | 8.5 | 7 | 59.5 | 64
2011-09-19 | Sealing Truck | Paveline Truck | hr | 9 | 50 | 450 | 64
2011-09-19 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 64
2011-09-19 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8.5 | 42.79 | 363.715 | 64
2011-09-20 |  | Plant Float - Allciv | hr | 8.5 | 7 | 59.5 | 64
2011-09-20 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8.5 | 42.79 | 363.715 | 64
2011-09-27 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-27 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-27 |  | Plant Float - Allciv | hr | 5.5 | 7 | 38.5 | 64
2011-09-27 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5.5 | 42.79 | 235.345 | 64
2011-09-27 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-27 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 64
2011-09-27 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-27 | 7mm Primer Seal Inv - 2765 | 10 mm Aggregate |  | 36.99 | 33.5 | 1239.165 | 64 | Crushing Insudtries Aust
2011-09-28 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5.5 | 42.79 | 235.345 | 64
2011-09-28 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-28 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-28 |  | Plant Float - Allciv | hr | 5.5 | 7 | 38.5 | 64
2011-09-28 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-28 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-28 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 64
2011-09-28 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-29 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5.5 | 42.79 | 235.345 | 64
2011-09-29 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-29 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-29 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-29 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 64
2011-09-29 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-29 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-29 |  | Plant Float - Allciv | hr | 5.5 | 7 | 38.5 | 64
2011-09-30 |  | Plant Float - Allciv | hr | 5.5 | 7 | 38.5 | 64
2011-09-30 | SD Roller - Dry from the ( 31/08/2011 to 30/09/2011 ) Inv - 7771117 | Multi Roller |  | 1 | 10010 | 10010 | 64 | Tutt Bryant Hire
2011-09-30 | Sealing Truck | Paveline Truck | hr | 5 | 50 | 250 | 64
2011-09-30 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-30 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5.5 | 42.79 | 235.345 | 64
2011-09-30 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-30 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-30 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-09-30 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 64
2011-09-30 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-01 | Truck Driver | Labour | hr | 4.5 | 39.18 | 176.31 | 64
2011-10-01 | Labour | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2011-10-01 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 64
2011-10-01 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2011-10-01 | Sealing Truck | Paveline Truck | hr | 5 | 50 | 250 | 64
2011-10-01 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 64
2011-10-01 | Multi Roller Hire | Multi Roller | day | 0.5 | 365 | 182.5 | 64
2011-10-01 | Labour | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2011-10-01 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2011-10-01 | Labour | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2011-10-02 | Multi Roller Hire | Multi Roller | day | 0.5 | 365 | 182.5 | 64
2011-10-02 | Labour | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2011-10-02 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2011-10-02 | Labour | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2011-10-02 | Labour | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2011-10-02 | Truck Driver | Labour | hr | 4.5 | 39.18 | 176.31 | 64
2011-10-02 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 64
2011-10-02 | Sealing Truck | Paveline Truck | hr | 5 | 50 | 250 | 64
2011-10-02 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2011-10-02 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 64
2011-10-03 | Labour | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2011-10-03 | Tipper (Wet Hire) Inv - 13095422 | Tipper |  | 1 | 1940.02 | 1940.02 | 64 | Kennards Hire
2011-10-03 | Truck Driver | Labour | hr | 4.5 | 39.18 | 176.31 | 64
2011-10-03 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 64
2011-10-03 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 64
2011-10-03 | Sealing Truck | Paveline Truck | hr | 4 | 50 | 200 | 64
2011-10-03 | 10 mm sealing aggregate Inv - 2805 | 10 mm Aggregate |  | 108.4 | 33.5 | 3631.4 | 64 | Crushing Insudtries Aust
2011-10-03 | Multi Roller Hire | Multi Roller | day | 0.5 | 365 | 182.5 | 64
2011-10-03 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2011-10-03 | Labour | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2011-10-03 | Labour | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2011-10-03 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2011-10-04 | Labour | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2011-10-05 | From the ( 31/08/2011 to 30/09/2011 ) Inv - 7771116 | Traffic Lights |  | 1 | 3174.6 | 3174.6 | 64 | Tutt Bryant Hire
2011-10-06 | 10 mm sealing aggregatem INv - 2840 | 10 mm Aggregate |  | 77.23 | 33.5 | 2587.205 | 64 | Crushing Insudtries Aust
2011-10-06 | truck and trailer hire | Michael Biles ( dog) | hr | 4 | 130 | 520 | 64
2011-10-12 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-12 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-12 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-12 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-12 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-12 |  | Traffic Lights | day | 0.5 | 125 | 62.5 | 64
2011-10-12 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-12 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 64
2011-10-12 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-12 | Tipper 3T - Kennards Hire | Tipper 3T | day | 5 | 213.4 | 1067 | 64
2011-10-12 | Multi Roller Hire | Multi Roller | day | 4 | 365 | 1460 | 64
2011-10-12 | Sealing Truck | Paveline Truck | hr | 4 | 50 | 200 | 64
2011-10-13 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-13 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-13 | Tipper 3T - Kennards Hire | Tipper 3T | day | 5 | 213.4 | 1067 | 64
2011-10-13 | Sealing Truck | Paveline Truck | hr | 4 | 50 | 200 | 64
2011-10-13 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-13 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 64
2011-10-13 | 7mm/10mmm Con Agg, Dock 29823.29840,29865. Inv - 2878 | 10 mm Aggregate |  | 26.8 | 33.5 | 897.8 | 64 | Crushing Insudtries Aust
2011-10-13 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-13 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-13 | Multi Roller Hire | Multi Roller | day | 4 | 365 | 1460 | 64
2011-10-13 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-13 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-14 | Multi Roller Hire | Multi Roller | day | 4 | 365 | 1460 | 64
2011-10-14 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-14 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 64
2011-10-14 | Sealing Truck | Paveline Truck | hr | 4 | 50 | 200 | 64
2011-10-14 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-14 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-14 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-14 | Tipper 3T - Kennards Hire | Tipper 3T | day | 5 | 213.4 | 1067 | 64
2011-10-14 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-14 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-14 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-15 | Labour | Labour | hr | 4 | 35.35 | 141.4 | 64
2011-10-15 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 64
2011-10-15 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 64
2011-10-15 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 64
2011-10-15 | Labour | Labour | hr | 4 | 35.35 | 141.4 | 64
2011-10-15 | Truck Driver | Labour | hr | 4 | 39.18 | 156.72 | 64
2011-10-15 | Tipper 3T - Kennards Hire | Tipper 3T | day | 5 | 213.4 | 1067 | 64
2011-10-15 | Sealing Truck | Paveline Truck | hr | 4 | 50 | 200 | 64
2011-10-15 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 64
2011-10-15 | Multi Roller Hire | Multi Roller | day | 4 | 365 | 1460 | 64
2011-10-16 | Tipper 3T - Kennards Hire | Tipper 3T | day | 5 | 213.4 | 1067 | 64
2011-10-16 | 10 mm sealing aggregate Dock No 29886,29888,29892,29893,29894 Inv - 2907 | 10 mm Aggregate |  | 38.71 | 33.5 | 1296.785 | 64 | Crushing Insudtries Aust
2011-10-17 | Tipper (Wet Hire) Inv- 13132038 | Insurances |  | 1 | 327.28 | 327.28 | 64 | Kennards Hire
2011-10-17 | Hire of Trafic Lights (sola) Inv- 7771849 | Traffic Lights |  | 1 | 847 | 847 | 64 | Tutt Bryant Hire
2011-10-17 | Tipper (Wet Hire) Inv - 13132038 | Tipper |  | 1 | 1612.73 | 1612.73 | 64 | Kennards Hire
2011-10-24 | SD Roller - Dry Inv - 6000030975 | SD Roller |  | 1 | 5892.48 | 5892.48 | 64 | Hastings Deering
2011-10-28 | 10 mm sealing aggregate Inv - 2778 | 10 mm Aggregate |  | 19.13 | 33.5 | 640.855 | 64 | Crushing Insudtries Aust
2011-10-31 | Tipper (Wet Hire) 2 Tonne Inv - 13169436 | Tipper |  | 1 | 1940 | 1940 | 64 | Kennards Hire
2012-09-17 | Sealing Truck | Paveline Truck | hr | 10 | 50 | 500 | 64
2012-09-17 | Allciv - Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 64
2012-09-18 | Allciv - Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2012-09-18 | Sealing Truck | Paveline Truck | hr | 10 | 50 | 500 | 64
2012-09-18 | Allciv - Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 64
2012-09-18 | Labour | Labour | hr | 6 | 35.35 | 212.1 | 64
2012-09-18 | Allciv - Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 64
2012-09-18 | Allciv - Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 64
2012-09-18 | Labour | Labour | hr | 2 | 35.35 | 70.7 | 64
2012-09-18 | Allciv - Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 64
2012-09-19 | Labour | Labour | hr | 4 | 35.35 | 141.4 | 64
2012-09-19 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 3.5 | 42.79 | 149.765 | 64
2012-09-19 | Allciv - Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 64
2012-09-19 | Allciv - Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 64
2012-09-19 | Allciv - Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 64
2012-09-19 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 64
2012-09-19 | Labour | Labour | hr | 3 | 35.35 | 106.05 | 64
2012-09-19 | Sealing Truck | Paveline Truck | hr | 11 | 50 | 550 | 64
2012-09-19 | Allciv - Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 64
2012-09-19 | Allciv - Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 64
2012-09-20 | Allciv - Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 64
2012-09-20 | Allciv - Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 64
2012-09-26 | Allciv - Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 64
2012-09-26 | Allciv - Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 64
2012-09-26 | Allciv - Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 64
2012-09-26 | Allciv - Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 64
| Subtotal for 064 |  |  |  |  | 145851.255
Cost Code 066
| Subtotal for 066 |  |  |  |  | 1471.67
Cost Code 068
2011-05-23 | Truck Driver | Labour | hr | 15 | 39.18 | 587.7 | 68
2011-05-23 | Labour | Labour | hr | 10 | 30 | 300 | 68
2011-05-23 | Labour | Labour | hr | 12 | 32.2 | 386.4 | 68
2011-05-24 | Labour | Labour | hr | 11 | 32.2 | 354.2 | 68
2011-05-24 |  | Plant Float - Allciv | hr | 6 | 7 | 42 | 68
2011-05-24 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-05-24 | Labour | Labour | hr | 9.5 | 30 | 285 | 68
2011-05-24 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 6 | 42.79 | 256.74 | 68
2011-05-24 | Truck Driver | Labour | hr | 11 | 39.18 | 430.98 | 68
2011-05-25 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 2 | 26.46 | 52.92 | 68
2011-05-25 |  | Plant Float - Allciv | hr | 3 | 7 | 21 | 68
2011-05-25 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 3.5 | 66.07 | 231.245 | 68
2011-05-25 | New Holland Compact Grader - No Operator | NH Grader | hr | 1.5 | 25.78 | 38.67 | 68
2011-05-25 | Truck Driver | Labour | hr | 10.5 | 39.18 | 411.39 | 68
2011-05-25 | Labour | Labour | hr | 10.5 | 32.2 | 338.1 | 68
2011-05-25 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 68
2011-05-25 | Labour | Labour | hr | 10.5 | 30 | 315 | 68
2011-05-25 | UD Spreader Truck - No Driver | UD Spreader | hr | 3.5 | 21.61 | 75.635 | 68
2011-05-25 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-05-25 |  | Traffic Lights | day | 1 | 125 | 125 | 68
2011-05-26 | Labour | Labour | hr | 10 | 30 | 300 | 68
2011-05-26 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-05-26 |  | Traffic Lights | day | 1 | 125 | 125 | 68
2011-05-26 | Truck Driver | Labour | hr | 8.5 | 39.18 | 333.03 | 68
2011-05-26 | UD Spreader Truck - No Driver | UD Spreader | hr | 6.5 | 21.61 | 140.465 | 68
2011-05-26 |  | Plant Float - Allciv | hr | 3 | 7 | 21 | 68
2011-05-26 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 6.5 | 26.46 | 171.99 | 68
2011-05-26 | Labour | Labour | hr | 10 | 32.2 | 322 | 68
2011-05-26 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 6.5 | 66.07 | 429.455 | 68
2011-05-26 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 68
2011-05-26 | New Holland Compact Grader - No Operator | NH Grader | hr | 6.5 | 25.78 | 167.57 | 68
2011-05-27 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 68
2011-05-27 |  | Traffic Lights | day | 1 | 125 | 125 | 68
2011-05-27 | Labour | Labour | hr | 9.5 | 32.2 | 305.9 | 68
2011-05-27 | Labour | Labour | hr | 9.5 | 30 | 285 | 68
2011-05-27 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 68
2011-05-27 | UD Spreader Truck - No Driver | UD Spreader | hr | 6.5 | 21.61 | 140.465 | 68
2011-05-27 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-05-27 | New Holland Compact Grader - No Operator | NH Grader | hr | 6.5 | 25.78 | 167.57 | 68
2011-05-27 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 6.5 | 26.46 | 171.99 | 68
2011-05-27 |  | Plant Float - Allciv | hr | 3 | 7 | 21 | 68
2011-05-27 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 6.5 | 66.07 | 429.455 | 68
2011-05-28 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 68
2011-05-28 | Labour | Labour | hr | 9.5 | 32.2 | 305.9 | 68
2011-05-28 | UD Spreader Truck - No Driver | UD Spreader | hr | 6.5 | 21.61 | 140.465 | 68
2011-05-28 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 6.5 | 66.07 | 429.455 | 68
2011-05-28 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-05-28 |  | Traffic Lights | day | 1 | 125 | 125 | 68
2011-05-28 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 6.5 | 26.46 | 171.99 | 68
2011-05-28 | Labour | Labour | hr | 9.5 | 30 | 285 | 68
2011-05-28 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 68
2011-05-28 |  | Plant Float - Allciv | hr | 3 | 7 | 21 | 68
2011-05-28 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 68
2011-05-29 | Labour | Labour | hr | 10 | 30 | 300 | 68
2011-05-29 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 68
2011-05-29 | Truck Driver | Labour | hr | 10 | 39.18 | 391.8 | 68
2011-05-29 | Labour | Labour | hr | 10 | 32.2 | 322 | 68
2011-05-29 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 68
2011-05-29 |  | Plant Float - Allciv | hr | 3 | 7 | 21 | 68
2011-05-29 |  | Traffic Lights | day | 1 | 125 | 125 | 68
2011-05-29 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-05-29 | UD Spreader Truck - No Driver | UD Spreader | hr | 6.5 | 21.61 | 140.465 | 68
2011-05-29 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 7 | 26.46 | 185.22 | 68
2011-05-29 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 6.5 | 66.07 | 429.455 | 68
2011-05-29 | Repairs to Skid Steer Inv MKY258144 | Repairs & Maint |  | 1 | 129.47 | 129.47 | 68 | Pirtek
2011-05-30 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 68
2011-05-30 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-05-30 | Labour | Labour | hr | 10.5 | 32.2 | 338.1 | 68
2011-05-30 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 7 | 26.46 | 185.22 | 68
2011-05-30 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 68
2011-05-30 | Labour | Labour | hr | 10.5 | 30 | 315 | 68
2011-05-30 | UD Spreader Truck - No Driver | UD Spreader | hr | 6.5 | 21.61 | 140.465 | 68
2011-05-30 |  | Traffic Lights | day | 1 | 125 | 125 | 68
2011-05-30 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 6.5 | 66.07 | 429.455 | 68
2011-05-30 | Dry Hire - Cat Rentals | Grader 120H | day | 1 | 536.95 | 536.95 | 68
2011-05-30 |  | Plant Float - Allciv | hr | 3 | 7 | 21 | 68
2011-05-30 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8 | 42.79 | 342.32 | 68
2011-05-31 | Tipper Hire | PR & HT Gourlay | hr | 10.5 | 65 | 682.5 | 68
2011-05-31 | UD Spreader Truck - No Driver | UD Spreader | hr | 6.5 | 21.61 | 140.465 | 68
2011-05-31 | Labour | Labour | hr | 10.5 | 30 | 315 | 68
2011-05-31 | Truck Driver | Labour | hr | 10.5 | 39.18 | 411.39 | 68
2011-05-31 | Labour | Labour | hr | 10.5 | 32.2 | 338.1 | 68
2011-05-31 |  | Traffic Lights | day | 1 | 125 | 125 | 68
2011-05-31 | Dry Hire - Cat Rentals | Grader 120H | day | 1 | 536.95 | 536.95 | 68
2011-05-31 | Truck Driver | Labour | hr | 10.5 | 39.18 | 411.39 | 68
2011-05-31 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 7 | 26.46 | 185.22 | 68
2011-05-31 | Inv 1961 | 2.3 Roadbase |  | 11.97 | 21.5 | 257.355 | 68 | Crushing Insudtries Aust
2011-05-31 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8 | 42.79 | 342.32 | 68
2011-05-31 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-05-31 | Inv 1940 | 2.3 Roadbase |  | 24.54 | 21.5 | 527.61 | 68 | Crushing Insudtries Aust
2011-05-31 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 6.5 | 66.07 | 429.455 | 68
2011-06-01 | Tipper Hire | PR & HT Gourlay | hr | 9 | 65 | 585 | 68
2011-06-01 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9 | 42.79 | 385.11 | 68
2011-06-01 | Labour | Labour | hr | 9 | 30 | 270 | 68
2011-06-01 | Truck Driver | Labour | hr | 9 | 39.18 | 352.62 | 68
2011-06-01 | Truck Driver | Labour | hr | 9 | 39.18 | 352.62 | 68
2011-06-01 | Labour | Labour | hr | 9 | 32.2 | 289.8 | 68
2011-06-02 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 68
2011-06-02 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 68
2011-06-03 | Truck Driver | Labour | hr | 10.5 | 39.18 | 411.39 | 68
2011-06-03 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10.5 | 42.79 | 449.295 | 68
2011-06-13 | Truck Driver | Labour | hr | 4 | 39.18 | 156.72 | 68
2011-06-13 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 68
2011-06-14 | Labour | Labour | hr | 7 | 30 | 210 | 68
2011-06-14 | Labour | Labour | hr | 7 | 32.2 | 225.4 | 68
2011-06-14 | Truck Driver | Labour | hr | 11 | 39.18 | 430.98 | 68
2011-06-14 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 11 | 42.79 | 470.69 | 68
2011-06-16 | Dry Hire - Cat Rentals | Grader 120H | day | 1 | 536.95 | 536.95 | 68
2011-06-16 | Labour | Labour | hr | 10 | 30 | 300 | 68
2011-06-16 |  | Traffic Lights | day | 1 | 125 | 125 | 68
2011-06-16 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7 | 66.07 | 462.49 | 68
2011-06-16 | UD Spreader Truck - No Driver | UD Spreader | hr | 7 | 21.61 | 151.27 | 68
2011-06-16 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-06-16 | Labour | Labour | hr | 10 | 32.2 | 322 | 68
2011-06-16 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8.5 | 42.79 | 363.715 | 68
2011-06-16 | Truck Driver | Labour | hr | 10 | 39.18 | 391.8 | 68
2011-06-16 | SD Roller - Cat Rentals | SD Roller | day | 1 | 267.84 | 267.84 | 68
2011-06-16 | Labour | Labour | hr | 10 | 39.39 | 393.9 | 68
2011-06-17 | Truck Driver | Labour | hr | 11 | 39.18 | 430.98 | 68
2011-06-17 | Labour | Labour | hr | 11 | 39.39 | 433.29 | 68
2011-06-17 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9 | 42.79 | 385.11 | 68
2011-06-17 | Dry Hire - Cat Rentals | Grader 120H | day | 1 | 536.95 | 536.95 | 68
2011-06-17 | SD Roller - Cat Rentals | SD Roller | day | 1 | 267.84 | 267.84 | 68
2011-06-17 | Labour | Labour | hr | 11 | 32.2 | 354.2 | 68
2011-06-17 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-06-17 |  | Traffic Lights | day | 1 | 125 | 125 | 68
2011-06-17 | Labour | Labour | hr | 11 | 30 | 330 | 68
2011-06-17 |  | Plant Float - Allciv | hr | 9 | 7 | 63 | 68
2011-06-17 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7.5 | 66.07 | 495.525 | 68
2011-06-17 | UD Spreader Truck - No Driver | UD Spreader | hr | 7.5 | 21.61 | 162.075 | 68
2011-06-18 | Labour | Labour | hr | 10 | 30 | 300 | 68
2011-06-18 |  | Traffic Lights | day | 1 | 125 | 125 | 68
2011-06-18 | Labour | Labour | hr | 10 | 32.2 | 322 | 68
2011-06-18 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-06-18 | SD Roller - Cat Rentals | SD Roller | day | 1 | 267.84 | 267.84 | 68
2011-06-18 | Dry Hire - Cat Rentals | Grader 120H | day | 1 | 536.95 | 536.95 | 68
2011-06-18 |  | Plant Float - Allciv | hr | 8.5 | 7 | 59.5 | 68
2011-06-18 | Labour | Labour | hr | 10 | 39.39 | 393.9 | 68
2011-06-18 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8.5 | 42.79 | 363.715 | 68
2011-06-18 | UD Spreader Truck - No Driver | UD Spreader | hr | 7.5 | 21.61 | 162.075 | 68
2011-06-18 | Truck Driver | Labour | hr | 10 | 39.18 | 391.8 | 68
2011-06-18 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7.5 | 66.07 | 495.525 | 68
2011-06-19 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-06-20 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 7 | 42.79 | 299.53 | 68
2011-06-20 | Labour | Labour | hr | 9 | 39.39 | 354.51 | 68
2011-06-20 | Truck Driver | Labour | hr | 9 | 39.18 | 352.62 | 68
2011-06-20 | Labour | Labour | hr | 9 | 32.2 | 289.8 | 68
2011-06-20 | SD Roller - Cat Rentals | SD Roller | day | 1 | 365 | 365 | 68
2011-06-20 | Dry Hire - Cat Rentals | Grader 120H | day | 1 | 536.95 | 536.95 | 68
2011-06-20 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-06-20 | Labour | Labour | hr | 9 | 30 | 270 | 68
2011-06-20 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7 | 66.07 | 462.49 | 68
2011-06-20 |  | Plant Float - Allciv | hr | 7 | 7 | 49 | 68
2011-06-20 |  | Traffic Lights | day | 1 | 125 | 125 | 68
2011-06-20 | UD Spreader Truck - No Driver | UD Spreader | hr | 7 | 21.61 | 151.27 | 68
2011-06-21 | UD Spreader Truck - No Driver | UD Spreader | hr | 7 | 21.61 | 151.27 | 68
2011-06-21 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7 | 66.07 | 462.49 | 68
2011-06-21 |  | Traffic Lights | day | 1 | 125 | 125 | 68
2011-06-21 | SD Roller - Cat Rentals | SD Roller | day | 1 | 365 | 365 | 68
2011-06-21 | Dry Hire - Cat Rentals | Grader 120H | day | 1 | 536.95 | 8897.4 | 68
2011-06-21 | Truck Driver | Labour | hr | 9 | 39.18 | 352.62 | 68
2011-06-21 | Labour | Labour | hr | 9 | 32.2 | 289.8 | 68
2011-06-21 | Labour | Labour | hr | 9 | 39.39 | 354.51 | 68
2011-06-21 |  | Plant Float - Allciv | hr | 7 | 7 | 49 | 68
2011-06-21 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 7 | 42.79 | 299.53 | 68
2011-06-21 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-06-21 | Labour | Labour | hr | 9 | 30 | 270 | 68
2011-06-22 | Labour | Labour | hr | 8.5 | 39.39 | 334.815 | 68
2011-06-22 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-06-25 | Truck Driver | Labour | hr | 8 | 39.18 | 313.44 | 68
2011-06-27 | Truck Driver | Labour | hr | 9 | 39.18 | 352.62 | 68
2011-06-27 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8 | 42.79 | 342.32 | 68
2011-06-28 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 68
2011-06-28 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 68
2011-06-29 | Labour | Labour | hr | 6.5 | 39.39 | 256.035 | 68
2011-06-29 | Water Charges from 7/6/11 to 15/06/11 | Water Meter Interface |  | 1 | 304.5 | 304.5 | 68 | Isaac Regional Council
2011-06-29 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8 | 42.79 | 342.32 | 68
2011-06-29 | Truck Driver | Labour | hr | 10 | 39.18 | 391.8 | 68
2011-06-29 | Sealing Truck | Paveline Truck | hr | 6 | 50 | 300 | 68
2011-06-29 | Labour | Labour | hr | 5.5 | 30 | 165 | 68
2011-06-30 |  | Plant Float - Allciv | hr | 10 | 7 | 70 | 68
2011-06-30 | Sealing Truck | Paveline Truck | hr | 11 | 50 | 550 | 68
2011-06-30 | Labour | Labour | hr | 11.5 | 30 | 345 | 68
2011-06-30 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 68
2011-06-30 | Labour | Labour | hr | 11.5 | 32.2 | 370.3 | 68
2011-06-30 | Truck Driver | Labour | hr | 11 | 39.18 | 430.98 | 68
2011-06-30 | Stand Down SD Roller | Bomag 124DH (Stand Down) | hr | 8 | 10.75 | 86 | 68
2011-07-05 |  | Traffic Lights | day | 1 | 125 | 125 | 68
2011-07-05 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 5.5 | 66.07 | 363.385 | 68
2011-07-05 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-07-05 | Dry Hire - Cat Rentals | Grader 120H | day | 1 | 536.95 | 536.95 | 68
2011-07-05 | Labour | Labour | hr | 8 | 39.39 | 315.12 | 68
2011-07-05 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 68
2011-07-05 | Labour | Labour | hr | 10.5 | 32.2 | 338.1 | 68
2011-07-06 | Labour | Labour | hr | 9.5 | 39.39 | 374.205 | 68
2011-07-06 | Labour | Labour | hr | 10 | 32.2 | 322 | 68
2011-07-06 |  | Traffic Lights | day | 1 | 125 | 125 | 68
2011-07-06 | Dry Hire - Cat Rentals | Grader 120H | day | 1 | 536.95 | 536.95 | 68
2011-07-06 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 68
2011-07-06 | Labour | Labour | hr | 10.5 | 30 | 315 | 68
2011-07-06 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 6.5 | 66.07 | 429.455 | 68
2011-07-06 |  | Plant Float - Allciv | hr | 9 | 7 | 63 | 68
2011-07-06 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9 | 42.79 | 385.11 | 68
2011-07-06 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-07-06 | Stand Down SD Roller | Bomag 124DH (Stand Down) | hr | 7.5 | 10.75 | 80.625 | 68
2011-07-07 | Dry Hire - Cat Rentals | Grader 120H | day | 1 | 536.95 | 9665.2 | 68
2011-07-07 | Labour | Labour | hr | 4 | 32.2 | 128.8 | 68
2011-07-07 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 68
2011-07-07 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-07-07 | Labour | Labour | hr | 4 | 30 | 120 | 68
2011-07-07 |  | Plant Float - Allciv | hr | 9 | 7 | 63 | 68
2011-07-07 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9 | 42.79 | 385.11 | 68
2011-07-07 | Stand Down SD Roller | Bomag 124DH (Stand Down) | hr | 3 | 10.75 | 32.25 | 68
2011-07-07 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 3 | 66.07 | 198.21 | 68
2011-07-07 | UD Spreader Truck - No Driver | UD Spreader | hr | 3 | 21.61 | 64.83 | 68
2011-07-07 |  | Traffic Lights | day | 1 | 125 | 125 | 68
2011-07-07 | Labour | Labour | hr | 4 | 39.39 | 157.56 | 68
2011-07-08 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 68
2011-07-08 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9 | 42.79 | 385.11 | 68
2011-07-09 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9 | 42.79 | 385.11 | 68
2011-07-09 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 68
2011-07-10 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9 | 42.79 | 385.11 | 68
2011-07-10 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 68
2011-07-11 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9 | 42.79 | 385.11 | 68
2011-07-11 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 68
2011-07-12 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 68
2011-07-12 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 7.5 | 42.79 | 320.925 | 68
2011-07-14 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-07-19 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-07-19 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 68
2011-07-19 | Labour | Labour | hr | 5 | 30 | 150 | 68
2011-07-19 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7 | 66.07 | 462.49 | 68
2011-07-19 | Stand Down SD Roller | Bomag 124DH (Stand Down) | hr | 6.5 | 10.75 | 69.875 | 68
2011-07-19 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-07-19 | UD Spreader Truck - No Driver | UD Spreader | hr | 6 | 21.61 | 129.66 | 68
2011-07-19 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 68
2011-07-20 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7 | 66.07 | 462.49 | 68
2011-07-20 | Labour | Labour | hr | 5.5 | 30 | 165 | 68
2011-07-20 | UD Spreader Truck - No Driver | UD Spreader | hr | 6 | 21.61 | 129.66 | 68
2011-07-20 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 68
2011-07-20 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-07-20 | Truck Driver | Labour | hr | 5.5 | 39.18 | 215.49 | 68
2011-07-20 | Labour | Labour | hr | 5.5 | 32.2 | 177.1 | 68
2011-07-20 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 6.5 | 26.46 | 171.99 | 68
2011-07-21 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7 | 66.07 | 462.49 | 68
2011-07-21 | Truck Driver | Labour | hr | 5.5 | 39.18 | 215.49 | 68
2011-07-21 | Labour | Labour | hr | 5.5 | 30 | 165 | 68
2011-07-21 | UD Spreader Truck - No Driver | UD Spreader | hr | 6 | 21.61 | 129.66 | 68
2011-07-21 | Truck Driver | Labour | hr | 4 | 39.18 | 156.72 | 68
2011-07-21 | Labour | Labour | hr | 5.5 | 32.2 | 177.1 | 68
2011-07-21 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-07-21 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 68
2011-07-22 | Truck Driver | Labour | hr | 5.5 | 39.18 | 215.49 | 68
2011-07-22 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7 | 66.07 | 462.49 | 68
2011-07-22 | Labour | Labour | hr | 5.5 | 30 | 165 | 68
2011-07-22 | Labour | Labour | hr | 4 | 32.2 | 128.8 | 68
2011-07-22 | Labour | Labour | hr | 5.5 | 32.2 | 177.1 | 68
2011-07-22 | Truck Driver | Labour | hr | 4 | 39.18 | 156.72 | 68
2011-07-22 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 68
2011-07-22 | UD Spreader Truck - No Driver | UD Spreader | hr | 6 | 21.61 | 129.66 | 68
2011-07-23 | Truck Driver | Labour | hr | 5.5 | 39.18 | 215.49 | 68
2011-07-23 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-07-23 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 68
2011-07-23 | Labour | Labour | hr | 5.5 | 30 | 165 | 68
2011-07-23 | UD Spreader Truck - No Driver | UD Spreader | hr | 6 | 21.61 | 129.66 | 68
2011-07-23 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7 | 66.07 | 462.49 | 68
2011-07-23 | Labour | Labour | hr | 5.5 | 32.2 | 177.1 | 68
2011-07-23 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 68
2011-07-24 | Labour | Labour | hr | 4.5 | 32.2 | 144.9 | 68
2011-07-24 | Truck Driver | Labour | hr | 4.5 | 39.18 | 176.31 | 68
2011-07-24 | Labour | Labour | hr | 4.5 | 32.2 | 144.9 | 68
2011-07-24 | Labour | Labour | hr | 4.5 | 39.39 | 177.255 | 68
2011-07-24 | Truck Driver | Labour | hr | 4.5 | 39.18 | 176.31 | 68
2011-07-24 | UD Spreader Truck - No Driver | UD Spreader | hr | 6 | 21.61 | 129.66 | 68
2011-07-24 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7 | 66.07 | 462.49 | 68
2011-07-24 | Labour | Labour | hr | 4.5 | 30 | 135 | 68
2011-07-25 | UD Spreader Truck - No Driver | UD Spreader | hr | 6 | 21.61 | 129.66 | 68
2011-07-25 | Labour | Labour | hr | 4.5 | 30 | 135 | 68
2011-07-25 | Labour | Labour | hr | 5.5 | 32.2 | 177.1 | 68
2011-07-25 | Labour | Labour | hr | 5.5 | 32.2 | 177.1 | 68
2011-07-25 | Labour | Labour | hr | 5.5 | 39.39 | 216.645 | 68
2011-07-25 | Truck Driver | Labour | hr | 5.5 | 39.18 | 215.49 | 68
2011-07-25 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7 | 66.07 | 462.49 | 68
2011-07-26 | Labour | Labour | hr | 4 | 30 | 120 | 68
2011-07-26 | Labour | Labour | hr | 6 | 39.39 | 236.34 | 68
2011-07-26 | Labour | Labour | hr | 6 | 32.2 | 193.2 | 68
2011-07-26 | Labour | Labour | hr | 6 | 32.2 | 193.2 | 68
2011-07-26 | Truck Driver | Labour | hr | 5.5 | 39.18 | 215.49 | 68
2011-07-26 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7 | 66.07 | 462.49 | 68
2011-07-26 | UD Spreader Truck - No Driver | UD Spreader | hr | 6 | 21.61 | 129.66 | 68
2011-08-09 | Tipper 3T - Kennards Hire Inv 12956963 | Tipper 3T |  | 1 | 1940 | 1940 | 68 | Kennards Hire
2011-08-19 | Labour | Labour | hr | 4 | 32.2 | 128.8 | 68
2011-08-19 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 68
2011-08-19 | Labour | Labour | hr | 9.5 | 32.2 | 305.9 | 68
2011-08-19 | UD Spreader Truck - No Driver | UD Spreader | hr | 9.5 | 21.61 | 205.295 | 68
2011-08-19 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 68
2011-08-19 |  | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 68
2011-08-19 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 68
2011-08-20 | Labour | Labour | hr | 10 | 32.2 | 322 | 68
2011-08-20 |  | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 68
2011-08-20 | UD Spreader Truck - No Driver | UD Spreader | hr | 9.5 | 21.61 | 205.295 | 68
2011-08-20 | Truck Driver | Labour | hr | 10 | 39.18 | 391.8 | 68
2011-08-20 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 9.5 | 66.07 | 627.665 | 68
2011-08-20 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 68
2011-08-20 | Labour | Labour | hr | 5.5 | 32.2 | 177.1 | 68
2011-08-21 | UD Spreader Truck - No Driver | UD Spreader | hr | 9.5 | 21.61 | 205.295 | 68
2011-08-21 | Labour | Labour | hr | 10.5 | 30 | 315 | 68
2011-08-21 | Labour | Labour | hr | 10.5 | 32.2 | 338.1 | 68
2011-08-21 |  | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 68
2011-08-21 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 68
2011-08-21 | Labour | Labour | hr | 10 | 32.2 | 322 | 68
2011-08-21 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 9.5 | 66.07 | 627.665 | 68
2011-08-21 | Truck Driver | Labour | hr | 10 | 39.18 | 391.8 | 68
2011-08-22 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-08-22 | Truck Driver | Labour | hr | 11.5 | 39.18 | 450.57 | 68
2011-08-22 | UD Spreader Truck - No Driver | UD Spreader | hr | 9.5 | 21.61 | 205.295 | 68
2011-08-22 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 9.5 | 66.07 | 627.665 | 68
2011-08-22 | Tipper 3T - Kennards Hire Inv - 12986562 | Tipper 3T |  | 1 | 1940 | 1940 | 68 | Kennards Hire
2011-08-22 | Labour | Labour | hr | 5 | 30 | 150 | 68
2011-08-22 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 5 | 26.46 | 132.3 | 68
2011-08-22 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-08-22 |  | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 68
2011-08-22 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 11.5 | 42.79 | 492.085 | 68
2011-08-23 | UD Spreader Truck - No Driver | UD Spreader | hr | 9.5 | 21.61 | 205.295 | 68
2011-08-23 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 9.5 | 66.07 | 627.665 | 68
2011-08-23 | Labour | Labour | hr | 5 | 30 | 150 | 68
2011-08-23 | SD Roller - Dry Inv - 6000028675 | SD Roller |  | 1 | 5892.48 | 5892.48 | 68 | Hastings
2011-08-23 | Plate Compactor - Dry Hire Inv -7767555 | Plate Compactor |  | 1 | 67 | 67 | 68 | Tutt Bryant Hire
2011-08-23 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-08-23 | Truck Driver | Labour | hr | 11.5 | 39.18 | 450.57 | 68
2011-08-23 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-08-23 |  | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 68
2011-08-23 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 11.5 | 42.79 | 492.085 | 68
2011-08-23 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 5 | 26.46 | 132.3 | 68
2011-08-24 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 9.5 | 66.07 | 627.665 | 68
2011-08-24 | UD Spreader Truck - No Driver | UD Spreader | hr | 9.5 | 21.61 | 205.295 | 68
2011-08-24 | Labour | Labour | hr | 5 | 30 | 150 | 68
2011-08-24 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-08-24 | Truck Driver | Labour | hr | 10 | 39.18 | 391.8 | 68
2011-08-24 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-08-24 |  | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 68
2011-08-24 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 11.5 | 42.79 | 492.085 | 68
2011-08-24 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 5 | 26.46 | 132.3 | 68
2011-08-25 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 68
2011-08-25 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 68
2011-08-25 | Labour | Labour | hr | 4 | 30 | 120 | 68
2011-08-25 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-08-25 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 68
2011-08-25 | Labour | Labour | hr | 4 | 32.2 | 128.8 | 68
2011-08-29 | Stabilising In House iNV 70224 | Stabilising |  | 1 | 1039 | 1039 | 68 | Isaac Regioal Council
2011-08-29 | Grader - Wet Hire Inv - 6000028834 | Grader |  | 1 | 5369.55 | 5369.55 | 68 | Hastings Deering
2011-08-30 | Labour | Labour | hr | 5.5 | 32.2 | 177.1 | 68
2011-08-30 | Labour | Labour | hr | 5.5 | 32.2 | 177.1 | 68
2011-08-31 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 68
2011-08-31 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 68
2011-08-31 | UD Spreader Truck - No Driver | UD Spreader | hr | 8 | 21.61 | 172.88 | 68
2011-08-31 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 8 | 66.07 | 528.56 | 68
2011-08-31 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 68
2011-08-31 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 68
2011-08-31 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-08-31 | Stand Down SD Roller | Bomag 124DH (Stand Down) | hr | 7.5 | 10.75 | 80.625 | 68
2011-08-31 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 68
2011-08-31 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-09-01 | Labour | Labour | hr | 4.5 | 39.39 | 177.255 | 68
2011-09-01 | Truck Driver | Labour | hr | 4 | 39.18 | 156.72 | 68
2011-09-01 | Labour | Labour | hr | 4.5 | 32.2 | 144.9 | 68
2011-09-01 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 68
2011-09-01 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-09-01 | UD Spreader Truck - No Driver | UD Spreader | hr | 8 | 21.61 | 172.88 | 68
2011-09-01 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 8 | 66.07 | 528.56 | 68
2011-09-01 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 68
2011-09-01 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 7.5 | 26.46 | 198.45 | 68
2011-09-02 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7.5 | 66.07 | 495.525 | 68
2011-09-02 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-02 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 8.5 | 26.46 | 224.91 | 68
2011-09-02 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8.5 | 42.79 | 363.715 | 68
2011-09-02 | Labour / Standown | Labour | hr | 6 | 45 | 270 | 68
2011-09-02 | Tipper 3T - Kennards Hire | Tipper 3T | day | 8.5 | 213.4 | 1813.9 | 68
2011-09-02 | UD Spreader Truck - No Driver | UD Spreader | hr | 4 | 21.61 | 86.44 | 68
2011-09-02 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-02 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 68
2011-09-02 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-02 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-02 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-03 |  | Plant Float - Allciv | hr | 8.5 | 7 | 59.5 | 68
2011-09-03 | Truck Driver | Labour | hr | 4 | 39.18 | 156.72 | 68
2011-09-03 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8.5 | 42.79 | 363.715 | 68
2011-09-05 | Tipper 3T - Kennards Hire Inv-13022993 | Tipper 3T |  | 1 | 1940 | 1940 | 68 | Kennards Hire
2011-09-07 |  | Plant Float - Allciv | hr | 8.5 | 7 | 59.5 | 68
2011-09-07 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 6 | 66.07 | 396.42 | 68
2011-09-07 | Stabilising In House Inv - 7769049 Whacker Packer. | Stabilising |  | 1 | 82.5 | 82.5 | 68 | Tutt Bryant Hire
2011-09-07 | UD Spreader Truck - No Driver | UD Spreader | hr | 2 | 21.61 | 43.22 | 68
2011-09-07 | Truck Driver | Labour | hr | 4.5 | 39.18 | 176.31 | 68
2011-09-07 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-09-07 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-09-07 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8.5 | 42.79 | 363.715 | 68
2011-09-07 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 8.5 | 26.46 | 224.91 | 68
2011-09-07 | Tipper 3T - Kennards Hire | Tipper 3T | day | 0.5 | 213.4 | 106.7 | 68
2011-09-08 | Truck Driver | Labour | hr | 10.5 | 39.18 | 411.39 | 68
2011-09-08 | Labour | Labour | hr | 7 | 32.2 | 225.4 | 68
2011-09-08 |  | Plant Float - Allciv | hr | 8.5 | 7 | 59.5 | 68
2011-09-08 | Labour | Labour | hr | 7 | 32.2 | 225.4 | 68
2011-09-08 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8.5 | 42.79 | 363.715 | 68
2011-09-08 | Tipper 3T - Kennards Hire | Tipper 3T | day | 0.5 | 213.4 | 106.7 | 68
2011-09-08 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 3 | 26.46 | 79.38 | 68
2011-09-08 | UD Spreader Truck - No Driver | UD Spreader | hr | 2 | 21.61 | 43.22 | 68
2011-09-08 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 6 | 66.07 | 396.42 | 68
2011-09-14 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-14 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-14 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-09-14 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-14 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-09-14 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 68
2011-09-14 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-09-14 | Spreader Truck - 30T | Spreader Truck - 30T | day | 1 | 1250 | 1250 | 68
2011-09-14 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 68
2011-09-14 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8.5 | 42.79 | 363.715 | 68
2011-09-14 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7.5 | 66.07 | 495.525 | 68
2011-09-14 |  | Plant Float - Allciv | hr | 8.5 | 7 | 59.5 | 68
2011-09-15 | Labour | Labour | hr | 9.5 | 32.2 | 305.9 | 68
2011-09-15 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 68
2011-09-15 | Labour | Labour | hr | 9.5 | 39.39 | 374.205 | 68
2011-09-15 | Labour | Labour | hr | 9.5 | 32.2 | 305.9 | 68
2011-09-15 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 68
2011-09-15 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 68
2011-09-15 | Spreader Truck - 30T | Spreader Truck - 30T | day | 1 | 1250 | 1250 | 68
2011-09-15 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-09-15 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7.5 | 66.07 | 495.525 | 68
2011-09-15 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8.5 | 42.79 | 363.715 | 68
2011-09-15 |  | Plant Float - Allciv | hr | 8.5 | 7 | 59.5 | 68
2011-09-16 |  | Plant Float - Allciv | hr | 8.5 | 7 | 59.5 | 68
2011-09-16 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8.5 | 42.79 | 363.715 | 68
2011-09-16 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7.5 | 66.07 | 495.525 | 68
2011-09-16 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-09-16 | Spreader Truck - 30T | Spreader Truck - 30T | day | 1 | 1250 | 1250 | 68
2011-09-16 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-16 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 68
2011-09-16 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-09-16 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 68
2011-09-16 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-16 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-09-17 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-09-17 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8.5 | 42.79 | 363.715 | 68
2011-09-19 | Tipper (Wet Hire) 2 Ton Inv- 13059076 | Tipper |  | 1 | 1466.11 | 1466.11 | 68 | Kennards Hire
2011-09-19 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-09-19 | Vehicle Cover Plus Over 25 yrs Inv - 13059076 | Insurances |  | 1 | 297.15 | 297.15 | 68 | Kennards Hire
2011-09-21 |  | Plant Float - Allciv | hr | 4 | 7 | 28 | 68
2011-09-21 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 68
2011-09-21 | Bobcat - Wet Hire From ( 20/09/2011 m to 21/09/2011 ) Inv - 7769830 | Bobcat |  | 1 | 275 | 275 | 68
2011-09-21 | Truck Driver | Labour | hr | 4 | 39.18 | 156.72 | 68
2011-09-22 | SD Roller - Dry ( 21/08/2011 to 20/09/2011 ) Inv - 6000029921 | SD Roller |  | 1 | 5892.48 | 5892.48 | 68 | Hastings Deering
2011-09-26 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 5 | 66.07 | 330.35 | 68
2011-09-26 | UD Spreader Truck - No Driver | UD Spreader | hr | 5 | 21.61 | 108.05 | 68
2011-09-26 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-09-26 | Labour | Labour | hr | 6.5 | 35.35 | 229.775 | 68
2011-09-26 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 68
2011-09-26 | Labour | Labour | hr | 6 | 35.35 | 212.1 | 68
2011-09-26 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 68
2011-09-26 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 68
2011-09-26 | Truck Driver | Labour | hr | 6 | 39.18 | 235.08 | 68
2011-09-26 |  | Plant Float - Allciv | hr | 4 | 7 | 28 | 68
2011-09-26 | Labour | Labour | hr | 6 | 35.35 | 212.1 | 68
2011-09-27 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 68
2011-09-27 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-27 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-27 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-27 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-27 | UD Spreader Truck - No Driver | UD Spreader | hr | 5 | 21.61 | 108.05 | 68
2011-09-27 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 10 | 66.07 | 660.7 | 68
2011-09-27 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-09-27 | 10 mm sealing aggregate Inv - 2698 | N25 |  | 9.08 | 33.5 | 304.18 | 68 | Crushing Insudtries Aust
2011-09-27 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-09-27 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 68
2011-09-27 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 68
2011-09-27 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-28 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-09-28 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-09-28 | Grader - Wet Hire from ( 28/09/2011 to 27/10/2011 ) Inv - 6000030076 | Grader |  | 1 | 10739.1 | 10739.1 | 68 | Hastings Deering
2011-09-28 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-28 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-28 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 68
2011-09-28 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-28 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 68
2011-09-28 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-28 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 10 | 66.07 | 660.7 | 68
2011-09-28 | UD Spreader Truck - No Driver | UD Spreader | hr | 5 | 21.61 | 108.05 | 68
2011-09-28 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 68
2011-09-29 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 10 | 66.07 | 660.7 | 68
2011-09-29 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-29 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-09-29 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 68
2011-09-29 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 68
2011-09-29 | UD Spreader Truck - No Driver | UD Spreader | hr | 5 | 21.61 | 108.05 | 68
2011-09-29 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-29 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-29 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 68
2011-09-29 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-29 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-09-30 | UD Spreader Truck - No Driver | UD Spreader | hr | 5 | 21.61 | 108.05 | 68
2011-09-30 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-30 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 10 | 66.07 | 660.7 | 68
2011-09-30 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 68
2011-09-30 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 68
2011-09-30 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-30 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 68
2011-09-30 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-09-30 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-09-30 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-09-30 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-01 |  | Traffic Lights | day | 1 | 125 | 125 | 68
2011-10-01 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-01 | UD Spreader Truck - No Driver | UD Spreader | hr | 5 | 21.61 | 108.05 | 68
2011-10-01 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-10-01 | Multi Roller Hire | Multi Roller | day | 0.5 | 365 | 182.5 | 68
2011-10-01 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 68
2011-10-01 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 9 | 66.07 | 594.63 | 68
2011-10-01 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-01 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-01 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-10-01 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 68
2011-10-01 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-01 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 68
2011-10-02 |  | Traffic Lights | day | 1 | 125 | 125 | 68
2011-10-02 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 68
2011-10-02 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-02 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-02 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 68
2011-10-02 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-10-02 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-02 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-02 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 9 | 66.07 | 594.63 | 68
2011-10-02 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-10-02 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 68
2011-10-02 | Multi Roller Hire | Multi Roller | day | 0.5 | 365 | 182.5 | 68
2011-10-02 | UD Spreader Truck - No Driver | UD Spreader | hr | 5 | 21.61 | 108.05 | 68
2011-10-03 | UD Spreader Truck - No Driver | UD Spreader | hr | 5 | 21.61 | 108.05 | 68
2011-10-03 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 9 | 66.07 | 594.63 | 68
2011-10-03 |  | Traffic Lights | day | 1 | 125 | 125 | 68
2011-10-03 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-03 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-03 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-10-03 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 68
2011-10-03 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 68
2011-10-03 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 68
2011-10-03 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-03 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-03 | Multi Roller Hire | Multi Roller | day | 0.5 | 365 | 182.5 | 68
2011-10-03 | Tipper 3T - Kennards Hire | Tipper 3T | day | 1 | 213.4 | 213.4 | 68
2011-10-04 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-04 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 68
2011-10-11 | 10 mm sealing aggregate Inv 2860 | 10 mm Aggregate |  | 9.93 | 33.5 | 332.655 | 68 | Crushing Insudtries Aust
2011-10-12 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 9 | 26.46 | 238.14 | 68
2011-10-12 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-12 | UD Spreader Truck - No Driver | UD Spreader | hr | 5 | 21.61 | 108.05 | 68
2011-10-12 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 68
2011-10-12 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-12 | Tipper 3T - Kennards Hire | Tipper 3T | day | 4 | 213.4 | 853.6 | 68
2011-10-12 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-10-12 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-12 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-12 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-12 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-12 |  | Traffic Lights | day | 0.5 | 125 | 62.5 | 68
2011-10-13 | Tractor and Stabiliser/Profiler | Tractor Mixer | day | 1 | 1500 | 1500 | 68
2011-10-13 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-10-13 | Tipper 3T - Kennards Hire | Tipper 3T | day | 4 | 213.4 | 853.6 | 68
2011-10-13 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-13 | UD Spreader Truck - No Driver | UD Spreader | hr | 5 | 21.61 | 108.05 | 68
2011-10-13 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-13 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-13 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-13 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-13 | Truck Driver | Labour | hr | 6 | 39.18 | 235.08 | 68
2011-10-13 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-13 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 9 | 26.46 | 238.14 | 68
2011-10-14 | Truck Driver | Labour | hr | 6 | 39.18 | 235.08 | 68
2011-10-14 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-14 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 9 | 26.46 | 238.14 | 68
2011-10-14 | UD Spreader Truck - No Driver | UD Spreader | hr | 5 | 21.61 | 108.05 | 68
2011-10-14 | Tractor and Stabiliser/Profiler | Tractor Mixer | day | 1 | 1500 | 1500 | 68
2011-10-14 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-14 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-14 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-14 | Labour | Labour | hr | 5 | 32.2 | 161 | 68
2011-10-14 | Tipper 3T - Kennards Hire | Tipper 3T | day | 4 | 213.4 | 853.6 | 68
2011-10-14 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-14 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-15 | Tractor and Stabiliser/Profiler | Tractor Mixer | day | 1 | 1500 | 1500 | 68
2011-10-15 | UD Spreader Truck - No Driver | UD Spreader | hr | 5 | 21.61 | 108.05 | 68
2011-10-15 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 9 | 66.07 | 594.63 | 68
2011-10-15 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 9 | 26.46 | 238.14 | 68
2011-10-15 | Truck Driver | Labour | hr | 6 | 39.18 | 235.08 | 68
2011-10-15 | Labour | Labour | hr | 4.5 | 35.35 | 159.075 | 68
2011-10-15 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-15 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-15 | Labour | Labour | hr | 4.5 | 32.2 | 144.9 | 68
2011-10-15 |  | Traffic Lights | day | 1 | 125 | 125 | 68
2011-10-15 | Tipper 3T - Kennards Hire | Tipper 3T | day | 4 | 213.4 | 853.6 | 68
2011-10-15 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-15 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-10-15 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 68
2011-10-16 | Tipper 3T - Kennards Hire | Tipper 3T | day | 4 | 213.4 | 853.6 | 68
2011-10-17 | Stabilising In House | Stabilising |  | 1 | 7500 | 7500 | 68 | BCLA PTL LTD
2011-10-31 | Vib Multi Tyres Roller Inv - 7773436 | SD Roller |  | 1 | 7315 | 7315 | 68 | Tutt Bryant Hire
| Subtotal for 068 |  |  |  |  | 223781.7
Cost Code 191
2011-05-26 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 191
2011-05-26 | Truck Driver | Labour | hr | 10.5 | 39.18 | 411.39 | 191
2011-05-26 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-05-26 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 191
2011-05-27 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 191
2011-05-27 | Truck Driver | Labour | hr | 4 | 39.18 | 156.72 | 191
2011-05-27 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-05-27 | Truck Driver | Labour | hr | 5.5 | 39.18 | 215.49 | 191
2011-05-27 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 191
2011-05-28 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 191
2011-05-28 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 191
2011-05-28 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-05-29 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 191
2011-05-29 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-05-29 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 191
2011-05-29 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 191
2011-05-30 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 191
2011-05-30 | Truck Driver | Labour | hr | 5.5 | 39.18 | 215.49 | 191
2011-05-30 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-05-30 | Truck Driver | Labour | hr | 5.5 | 39.18 | 215.49 | 191
2011-05-31 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-06-19 | Labour | Labour | hr | 4 | 39.39 | 157.56 | 191
2011-06-29 | Work Place Health & Safety Officer | WHSO | week | 11.5 | 45 | 517.5 | 191
2011-06-30 | Work Place Health & Safety Officer | WHSO | week | 9.5 | 45 | 427.5 | 191
2011-06-30 | Labour | Labour | hr | 10.5 | 39.39 | 413.595 | 191
2011-07-01 | Work Place Health & Safety Officer | WHSO | week | 3 | 45 | 135 | 191
2011-07-02 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 4 | 66.07 | 264.28 | 191
2011-07-02 | Labour | Labour | hr | 3.5 | 39.39 | 137.865 | 191
2011-07-13 | Labour Hire | Shannon Excavations (Labo | hr | 5 | 40 | 200 | 191
2011-07-13 | Traffic Control | WHSO |  | 7 | 45 | 315 | 191 | WHSO
2011-07-13 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-07-13 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4.5 | 42.79 | 192.555 | 191
2011-07-13 |  | Traffic Lights | day | 0.5 | 125 | 62.5 | 191
2011-07-13 | Truck Driver | Labour | hr | 4.5 | 39.18 | 176.31 | 191
2011-07-13 | Tipper Hire | Michael J Biles Tipper | hr | 6.5 | 95 | 617.5 | 191
2011-07-14 | Truck Driver | Labour | hr | 10 | 39.18 | 391.8 | 191
2011-07-14 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4.5 | 42.79 | 192.555 | 191
2011-07-14 | Tipper Hire | Michael J Biles Tipper | hr | 6.5 | 95 | 617.5 | 191
2011-07-14 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-07-14 | Labour Hire | Shannon Excavations (Labo | hr | 10 | 40 | 400 | 191
2011-07-14 | Traffic Control | WHSO |  | 9 | 45 | 405 | 191 | WHSO
2011-07-15 | Tipper Hire | Michael J Biles Tipper | hr | 3.5 | 95 | 332.5 | 191
2011-07-15 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-07-15 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 191
2011-07-15 | Traffic Control | WHSO |  | 8 | 45 | 360 | 191 | WHSO
2011-07-15 | Truck Driver | Labour | hr | 3 | 39.18 | 117.54 | 191
2011-07-15 | Labour Hire | Shannon Excavations (Labo | hr | 3.5 | 40 | 140 | 191
2011-07-18 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-07-18 | Tipper Hire | Michael J Biles Tipper | hr | 6 | 95 | 570 | 191
2011-07-18 | Labour Hire | Shannon Excavations (Labo | hr | 6 | 40 | 240 | 191
2011-07-18 |  | Plant Float - Allciv | hr | 4.5 | 7 | 31.5 | 191
2011-07-19 | Labour Hire | Shannon Excavations (Labo | hr | 9 | 40 | 360 | 191
2011-07-19 | Tipper Hire | Michael J Biles Tipper | hr | 9 | 95 | 855 | 191
2011-07-19 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 191
2011-07-19 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-07-19 |  | Plant Float - Allciv | hr | 4 | 7 | 28 | 191
2011-07-20 | Labour Hire | Shannon Excavations (Labo | hr | 9.5 | 40 | 380 | 191
2011-07-20 | Tipper Hire | Michael J Biles Tipper | hr | 10 | 95 | 950 | 191
2011-07-20 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-07-20 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 191
2011-07-20 |  | Plant Float - Allciv | hr | 4 | 7 | 28 | 191
2011-07-21 |  | Plant Float - Allciv | hr | 4 | 7 | 28 | 191
2011-07-21 | Labour Hire | Shannon Excavations (Labo | hr | 9.5 | 40 | 380 | 191
2011-07-21 | Tipper Hire | Michael J Biles Tipper | hr | 10 | 95 | 950 | 191
2011-07-22 | Labour Hire | Shannon Excavations (Labo | hr | 8.5 | 40 | 340 | 191
2011-07-22 | Tipper Hire | Michael J Biles Tipper | hr | 8.5 | 95 | 807.5 | 191
2011-07-22 |  | Plant Float - Allciv | hr | 4 | 7 | 28 | 191
2011-07-23 |  | Plant Float - Allciv | hr | 4 | 7 | 28 | 191
2011-07-23 | Tipper Hire | Michael J Biles Tipper | hr | 9 | 95 | 855 | 191
2011-07-23 | Labour Hire | Shannon Excavations (Labo | hr | 9 | 40 | 360 | 191
2011-07-24 | Labour Hire | Shannon Excavations (Labo | hr | 8.5 | 40 | 340 | 191
2011-07-24 | Tipper Hire | Michael J Biles Tipper | hr | 8.5 | 95 | 807.5 | 191
2011-07-24 |  | Plant Float - Allciv | hr | 4 | 7 | 28 | 191
2011-07-25 | Truck Driver | Labour | hr | 6 | 39.18 | 235.08 | 191
2011-07-25 |  | Plant Float - Allciv | hr | 4 | 7 | 28 | 191
2011-07-25 | Labour Hire | Shannon Excavations (Labo | hr | 9.5 | 40 | 380 | 191
2011-07-25 | Tipper Hire | Michael J Biles Tipper | hr | 9.5 | 95 | 902.5 | 191
2011-07-26 | Truck Driver | Labour | hr | 6 | 39.18 | 235.08 | 191
2011-07-26 |  | Plant Float - Allciv | hr | 4 | 7 | 28 | 191
2011-07-26 | Labour Hire | Shannon Excavations (Labo | hr | 5.5 | 40 | 220 | 191
2011-07-26 | Tipper Hire | Michael J Biles Tipper | hr | 5.5 | 95 | 522.5 | 191
2011-07-26 | Truck Driver | Labour | hr | 1 | 39.18 | 39.18 | 191
2011-07-27 |  | Plant Float - Allciv | hr | 4 | 7 | 28 | 191
2011-07-27 | Truck Driver | Labour | hr | 4 | 39.18 | 156.72 | 191
2011-08-15 | Truck Driver | Labour | hr | 10 | 39.18 | 391.8 | 191
2011-08-16 | Truck Driver | Labour | hr | 8.5 | 39.18 | 333.03 | 191
2011-08-17 | Labour | Labour | hr | 4.5 | 32.2 | 144.9 | 191
2011-08-17 | truck and trailer hire | Michael Biles ( dog) | hr | 4.5 | 130 | 585 | 191
2011-08-17 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 191
2011-08-17 | Labour Hire | Shannon Excavations (Labo | hr | 5 | 40 | 200 | 191
2011-08-17 | Truck Driver | Labour | hr | 7 | 39.18 | 274.26 | 191
2011-08-18 | Labour | Labour | hr | 9.5 | 32.2 | 305.9 | 191
2011-08-18 | truck and trailer hire | Michael Biles ( dog) | hr | 7.5 | 130 | 975 | 191
2011-08-18 | Labour | Labour | hr | 9.5 | 39.39 | 374.205 | 191
2011-08-18 | Truck Driver | Labour | hr | 11 | 39.18 | 430.98 | 191
2011-08-18 | Labour Hire | Shannon Excavations (Labo | hr | 9.5 | 40 | 380 | 191
2011-08-18 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 191
2011-08-19 | Truck Driver | Labour | hr | 10.5 | 39.18 | 411.39 | 191
2011-08-19 | truck and trailer hire | Michael Biles ( dog) | hr | 6.5 | 130 | 845 | 191
2011-08-19 | Labour | Labour | hr | 9.5 | 39.39 | 374.205 | 191
2011-08-19 | Sealing Truck | Paveline Truck | hr | 3 | 50 | 150 | 191
2011-08-19 | Dry Hire Cat Rentals 6000028530 | Excavator 12T |  | 1 | 8470 | 8470 | 191 | Hastings
2011-08-19 | Labour Hire | Shannon Excavations (Labo | hr | 10 | 40 | 400 | 191
2011-08-19 | Labour Hire | Labour | hr | 2 | 45 | 90 | 191
2011-08-20 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-08-20 | truck and trailer hire | Michael Biles ( dog) | hr | 7 | 130 | 910 | 191
2011-08-20 | Sealing Truck | Paveline Truck | hr | 3 | 50 | 150 | 191
2011-08-20 | Labour Hire | Shannon Excavations (Labo | hr | 10 | 40 | 400 | 191
2011-08-20 | Labour | Labour | hr | 9.5 | 39.39 | 374.205 | 191
2011-08-20 | Labour Hire | Labour | hr | 1 | 45 | 45 | 191
2011-08-20 | Truck Driver | Labour | hr | 10.5 | 39.18 | 411.39 | 191
2011-08-21 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-08-21 | Truck Driver | Labour | hr | 10.5 | 39.18 | 411.39 | 191
2011-08-21 | Labour | Labour | hr | 9.5 | 39.39 | 374.205 | 191
2011-08-21 | Labour Hire | Shannon Excavations (Labo | hr | 10.5 | 40 | 420 | 191
2011-08-21 | truck and trailer hire | Michael Biles ( dog) | hr | 9 | 130 | 1170 | 191
2011-08-22 | Tipper Hire | Michael J Biles Tipper | hr | 5 | 95 | 475 | 191
2011-08-22 | truck and trailer hire | Michael Biles ( dog) | hr | 4.5 | 130 | 585 | 191
2011-08-22 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-08-22 | Labour | Labour | hr | 10 | 39.39 | 393.9 | 191
2011-08-22 | Labour Hire | Shannon Excavations (Labo | hr | 11 | 40 | 440 | 191
2011-08-22 | Truck Driver | Labour | hr | 11 | 39.18 | 430.98 | 191
2011-08-23 | Truck Driver | Labour | hr | 8.5 | 39.18 | 333.03 | 191
2011-08-23 | Labour | Labour | hr | 10 | 39.39 | 393.9 | 191
2011-08-23 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-08-23 | Labour Hire | Labour | hr | 2 | 45 | 90 | 191
2011-08-23 | Labour Hire | Shannon Excavations (Labo | hr | 9 | 40 | 360 | 191
2011-08-23 | Tipper Hire | Michael J Biles Tipper | hr | 9.5 | 95 | 902.5 | 191
2011-08-24 | Labour | Labour | hr | 10 | 39.39 | 393.9 | 191
2011-08-24 | Labour Hire | Labour | hr | 1 | 45 | 45 | 191
2011-08-24 | Truck Driver | Labour | hr | 11.5 | 39.18 | 450.57 | 191
2011-08-24 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-08-24 | Labour Hire | Shannon Excavations (Labo | hr | 11 | 40 | 440 | 191
2011-08-24 | Tipper Hire | Michael J Biles Tipper | hr | 9 | 95 | 855 | 191
2011-08-25 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 191
2011-08-25 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 191
2011-08-25 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-08-25 |  | Shannon Excavations (Labo | hr | 4.5 | 40 | 180 | 191
2011-08-25 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 191
2011-08-25 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 191
2011-08-25 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 191
2011-08-25 | Tipper Hire | Michael J Biles Tipper | hr | 5 | 95 | 475 | 191
2011-08-30 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 191
2011-08-30 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-08-30 | Truck Driver | Labour | hr | 6 | 39.18 | 235.08 | 191
2011-08-30 | Tipper Hire | Michael J Biles Tipper | hr | 5.5 | 95 | 522.5 | 191
2011-08-30 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 191
2011-08-30 | Labour Hire | Shannon Excavations (Labo | hr | 5 | 40 | 200 | 191
2011-08-31 | Tipper Hire | Hurst Backhoe Hire | hr | 9.5 | 85 | 807.5 | 191
2011-08-31 | Tipper Hire | Michael J Biles Tipper | hr | 9.5 | 95 | 902.5 | 191
2011-08-31 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-08-31 |  | Shannon Excavations (Labo | hr | 9.5 | 40 | 380 | 191
2011-09-01 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-09-01 | truck and trailer hire | Michael Biles ( dog) | hr | 9.5 | 130 | 1235 | 191
2011-09-01 | Labour Hire | Shannon Excavations (Labo | hr | 9.5 | 40 | 380 | 191
2011-09-01 | Truck Driver | Labour | hr | 5.5 | 39.18 | 215.49 | 191
2011-09-01 | Tipper Hire | Hurst Backhoe Hire | hr | 9.5 | 120 | 1140 | 191
2011-09-01 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 191
2011-09-01 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 191
2011-09-02 | Dry Hire Cat Rentals | Excavator 12T | day | 1 | 385 | 385 | 191
2011-09-03 | Truck Driver | Labour | hr | 5.5 | 39.18 | 215.49 | 191
2011-09-09 | Truck Driver | Labour | hr | 8.5 | 39.18 | 333.03 | 191
2011-09-09 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8.5 | 42.79 | 363.715 | 191
2011-09-10 | Truck Driver | Labour | hr | 4 | 39.18 | 156.72 | 191
2011-09-10 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 191
2011-09-20 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 191
2011-09-20 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 191
2011-09-20 | Labour | Labour | hr | 8 | 35.35 | 282.8 | 191
2011-09-20 | Labour | Labour | hr | 4.5 | 35.35 | 159.075 | 191
2011-09-29 | Sealing Truck | Paveline Truck | hr | 5 | 50 | 250 | 191
2011-10-04 |  | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 191
2011-10-04 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 191
2011-10-04 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 191
2011-10-04 |  | Traffic Lights | day | 1 | 125 | 125 | 191
2011-10-04 | Labour | Labour | hr | 9.5 | 32.2 | 305.9 | 191
2011-10-04 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 9 | 66.07 | 594.63 | 191
2011-10-05 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 9 | 66.07 | 594.63 | 191
2011-10-05 |  | Traffic Lights | day | 1 | 125 | 125 | 191
2011-10-05 |  | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 191
2011-10-05 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 191
2011-10-05 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 191
2011-10-05 | Labour | Labour | hr | 9.5 | 32.2 | 305.9 | 191
2011-10-05 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 191
2011-10-05 | truck and trailer hire | Michael Biles ( dog) | hr | 10.5 | 130 | 1365 | 191
2011-10-06 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 191
2011-10-06 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 191
2011-10-06 | Labour | Labour | hr | 4.5 | 35.35 | 159.075 | 191
2011-10-06 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 191
2011-10-06 |  | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 191
2011-10-11 |  | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 191
2011-10-11 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 191
2011-10-11 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 191
2011-10-11 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 191
2011-10-11 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 191
2011-10-11 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 191
2011-10-11 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 191
2011-10-11 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 191
2011-10-11 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 191
2011-10-11 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 191
2011-10-12 |  | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 191
2011-10-12 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 191
2011-10-13 |  | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 191
2011-10-13 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 191
2011-10-14 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 191
2011-10-14 |  | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 191
2011-10-14 | 14 Tonne Excavator ( P&H Gourlay ) | Excavator Hyundi | hr | 8 | 80 | 640 | 191
2011-10-15 |  | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 191
2011-10-15 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 191
2011-10-16 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 191
2011-10-16 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 191
2011-10-16 | Labour | Labour | hr | 8.5 | 35.35 | 300.475 | 191
2011-10-16 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 191
2011-10-16 |  | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 191
2011-10-16 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 191
2011-10-16 | Labour | Labour | hr | 8.5 | 32.2 | 273.7 | 191
2011-10-16 | Sealing Truck | Paveline Truck | hr | 9 | 50 | 450 | 191
2011-10-16 | Truck Driver | Labour | hr | 10 | 39.18 | 391.8 | 191
2011-10-16 | Multi Roller Hire | Multi Roller | day | 9 | 365 | 3285 | 191
2011-10-16 | Labour | Labour | hr | 8.5 | 35.35 | 300.475 | 191
2011-10-17 | ( 21 T Tag Trailor ) | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 191
2011-10-17 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 191
2011-10-17 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 191
2011-10-17 | Truck Driver | Labour | hr | 10.5 | 39.18 | 411.39 | 191
2011-10-17 | Labour | Labour | hr | 8.5 | 32.2 | 273.7 | 191
2011-10-17 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 191
2011-10-17 | Labour | Labour | hr | 8.5 | 35.35 | 300.475 | 191
2011-10-18 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 191
2011-10-18 | 14 Tonne Excavator ( P&H Gourlay ) | Excavator Hyundi | hr | 8 | 80 | 640 | 191
2011-10-18 | ( 21 T Tag Trailor ) | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 191
2011-10-18 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 191
2011-10-18 | Truck Driver | Labour | hr | 11 | 39.18 | 430.98 | 191
2011-10-18 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 191
2011-10-18 | Labour | Labour | hr | 10.5 | 35.35 | 371.175 | 191
2011-10-18 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 191
2011-10-20 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 191
2011-10-20 | Labour | Labour | hr | 3 | 35.35 | 106.05 | 191
2011-10-20 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 191
2011-10-20 | ( 21 T Tag Trailor ) | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 191
2011-10-20 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 191
2011-10-20 | Truck Driver | Labour | hr | 9 | 39.18 | 352.62 | 191
2011-11-01 | SD Roller - Dry Inv - 6000031453 | SD Roller |  | 1 | 1418.76 | 1418.76 | 191 | Hastings Deering
2012-09-17 | Allciv - Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 191
2012-09-17 | Allciv Plant - Excavator | Labour | hr | 5.5 | 48 | 264 | 191
2012-09-17 | Labour | Labour | hr | 8 | 35.35 | 282.8 | 191
2012-09-17 | Allciv - Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 191
2012-09-18 | Allciv Plant - Excavator | Labour | hr | 5.5 | 48 | 264 | 191
2012-09-18 | Labour | Labour | hr | 3 | 35.35 | 106.05 | 191
2012-09-18 | Allciv - Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 191
2012-09-20 | Allciv - Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 191
2012-09-20 | Allciv - Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 191
2012-09-27 | Allciv - Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 191
2012-09-27 | Allciv - Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 191
2012-09-27 | Allciv - Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 191
| Subtotal for 191 |  |  |  |  | 94517.63
Cost Code 902
2011-05-23 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-05-24 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-05-24 | Project Supervisor | Project Supervisor | hr | 9.5 | 57.7 | 548.15 | 902
2011-05-25 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-05-25 | Project Supervisor | Project Supervisor | hr | 10.5 | 57.7 | 605.85 | 902
2011-05-26 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-05-26 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-05-27 | Project Supervisor | Project Supervisor | hr | 9.5 | 57.7 | 548.15 | 902
2011-05-27 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-05-28 | Project Supervisor | Project Supervisor | hr | 9.5 | 57.7 | 548.15 | 902
2011-05-28 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-05-29 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-05-29 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-05-30 | Project Supervisor | Project Supervisor | week | 10 | 57.7 | 577 | 902
2011-05-30 | Construction Manager | Construction Manager |  | 1 | 850 | 850 | 902
2011-05-31 | Project Supervisor | Project Supervisor | week | 10.5 | 57.7 | 605.85 | 902
2011-05-31 | Construction Manager | Construction Manager |  | 1 | 850 | 850 | 902
2011-06-01 | Project Supervisor | Project Supervisor | week | 9 | 57.7 | 519.3 | 902
2011-06-01 | Construction Manager | Construction Manager |  | 1 | 850 | 850 | 902
2011-06-14 | Construction Manager | Construction Manager |  | 1 | 850 | 850 | 902
2011-06-14 | Project Supervisor | Project Supervisor | week | 12 | 57.7 | 692.4 | 902
2011-06-16 | Construction Manager | Construction Manager |  | 1 | 850 | 850 | 902
2011-06-16 | Project Supervisor | Project Supervisor | week | 10 | 57.7 | 577 | 902
2011-06-17 | Project Supervisor | Project Supervisor | week | 11 | 57.7 | 634.7 | 902
2011-06-17 | Construction Manager | Construction Manager |  | 1 | 850 | 850 | 902
2011-06-18 | Project Supervisor | Project Supervisor | week | 10 | 57.7 | 577 | 902
2011-06-19 | Project Supervisor | Project Supervisor | week | 4 | 57.7 | 230.8 | 902
2011-06-20 | Project Supervisor | Project Supervisor | week | 9 | 57.7 | 519.3 | 902
2011-06-21 | Project Supervisor | Project Supervisor | week | 9 | 57.7 | 519.3 | 902
2011-06-22 | Project Supervisor | Project Supervisor | week | 13.5 | 57.7 | 778.95 | 902
2011-06-27 | Project Supervisor | Project Supervisor | week | 7 | 57.7 | 403.9 | 902
2011-06-29 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-06-29 | Project Supervisor | Project Supervisor | week | 11.5 | 57.7 | 663.55 | 902
2011-06-30 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-06-30 | Project Supervisor | Project Supervisor | week | 11.5 | 57.7 | 663.55 | 902
2011-07-01 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-07-01 | Project Supervisor | Project Supervisor | week | 11.5 | 57.7 | 663.55 | 902
2011-07-02 | Project Supervisor | Project Supervisor | week | 10 | 57.7 | 577 | 902
2011-07-03 | Project Supervisor | Project Supervisor | week | 10.5 | 57.7 | 605.85 | 902
2011-07-04 | Project Supervisor | Project Supervisor | week | 10.5 | 57.7 | 605.85 | 902
2011-07-05 | Project Supervisor | Project Supervisor | week | 10.5 | 57.7 | 605.85 | 902
2011-07-06 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-07-06 | 29/6, 30/6 & 1/7 Traffic Control at Dysart | WHSO |  | 25 | 45 | 1125 | 902 | WHSO
2011-07-06 | Project Supervisor | Project Supervisor | week | 10 | 57.7 | 577 | 902
2011-07-07 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-07-07 | Project Supervisor | Project Supervisor | week | 10 | 57.7 | 577 | 902
2011-07-12 | Project Supervisor | Project Supervisor | week | 11.5 | 57.7 | 663.55 | 902
2011-07-12 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-07-13 | Project Supervisor | Project Supervisor | week | 11.5 | 57.7 | 663.55 | 902
2011-07-13 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-07-14 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-07-14 | Project Supervisor | Project Supervisor | week | 10.5 | 57.7 | 605.85 | 902
2011-07-15 | Project Supervisor | Project Supervisor | week | 10 | 57.7 | 577 | 902
2011-07-15 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-07-18 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-07-18 | Project Supervisor | Project Supervisor | week | 10 | 57.7 | 577 | 902
2011-07-19 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-07-19 | Project Supervisor | Project Supervisor | week | 10 | 57.7 | 577 | 902
2011-07-20 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-07-20 | Project Supervisor | Project Supervisor | week | 10.5 | 57.7 | 605.85 | 902
2011-07-21 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-07-21 | Project Supervisor | Project Supervisor | week | 10.5 | 57.7 | 605.85 | 902
2011-07-22 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-07-22 | Project Supervisor | Project Supervisor | week | 9.5 | 57.7 | 548.15 | 902
2011-07-23 | Project Supervisor | Project Supervisor | week | 9.5 | 57.7 | 548.15 | 902
2011-07-24 | Project Supervisor | Project Supervisor | week | 9.5 | 57.7 | 548.15 | 902
2011-07-25 | Project Supervisor | Project Supervisor | week | 9.5 | 57.7 | 548.15 | 902
2011-07-26 | Project Supervisor | Project Supervisor | week | 10 | 57.7 | 577 | 902
2011-07-27 | Project Supervisor | Project Supervisor | week | 10.5 | 57.7 | 605.85 | 902
2011-07-27 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-08-17 | Project Supervisor | Project Supervisor | hr | 9 | 57.7 | 519.3 | 902
2011-08-17 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-08-18 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-08-18 | Project Supervisor | Project Supervisor | hr | 11 | 57.7 | 634.7 | 902
2011-08-19 | Project Supervisor | Project Supervisor | hr | 9.5 | 57.7 | 548.15 | 902
2011-08-19 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-08-20 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-08-20 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-08-21 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-08-22 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-08-23 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-08-24 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-08-25 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-08-30 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-08-31 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-08-31 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-09-01 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-09-01 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-09-02 | Project Supervisor | Project Supervisor | hr | 11 | 57.7 | 634.7 | 902
2011-09-02 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-09-03 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-09-03 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-09-07 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-09-07 | Project Supervisor | Project Supervisor | hr | 11 | 57.7 | 634.7 | 902
2011-09-08 | Project Supervisor | Project Supervisor | hr | 11.5 | 57.7 | 663.55 | 902
2011-09-13 | Project Supervisor | Project Supervisor | hr | 11 | 57.7 | 634.7 | 902
2011-09-13 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-09-14 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-09-14 | Project Supervisor | Project Supervisor | hr | 11 | 57.7 | 634.7 | 902
2011-09-15 | Project Supervisor | Project Supervisor | hr | 9.5 | 57.7 | 548.15 | 902
2011-09-15 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-09-16 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-09-17 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-09-19 | Project Supervisor | Project Supervisor | hr | 9.5 | 57.7 | 548.15 | 902
2011-09-20 | Project Supervisor | Project Supervisor | hr | 13.5 | 57.7 | 778.95 | 902
2011-09-26 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-09-26 | Project Supervisor | Project Supervisor | hr | 11 | 57.7 | 634.7 | 902
2011-09-27 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-09-27 | Project Supervisor | Project Supervisor | hr | 11 | 57.7 | 634.7 | 902
2011-09-28 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-09-28 | Project Supervisor | Project Supervisor | hr | 11 | 57.7 | 634.7 | 902
2011-09-29 | Project Supervisor | Project Supervisor | hr | 11 | 57.7 | 634.7 | 902
2011-09-29 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-09-30 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-10-01 | Project Supervisor | Project Supervisor | hr | 9.5 | 57.7 | 548.15 | 902
2011-10-02 | Project Supervisor | Project Supervisor | hr | 9.5 | 57.7 | 548.15 | 902
2011-10-03 | Project Supervisor | Project Supervisor | hr | 9.5 | 57.7 | 548.15 | 902
2011-10-04 | Project Supervisor | Project Supervisor | hr | 9.5 | 57.7 | 548.15 | 902
2011-10-05 | Project Supervisor | Project Supervisor | hr | 9.5 | 57.7 | 548.15 | 902
2011-10-06 | Project Supervisor | Project Supervisor | hr | 9.5 | 57.7 | 548.15 | 902
2011-10-11 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-10-11 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-10-12 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-10-12 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-10-13 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-10-13 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-10-14 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-10-14 | Construction Manager | Construction Manager | day | 1 | 850 | 850 | 902
2011-10-15 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-10-16 | Project Supervisor | Project Supervisor | hr | 10 | 57.7 | 577 | 902
2011-10-17 | Project Supervisor | Project Supervisor | hr | 9 | 57.7 | 519.3 | 902
2011-10-18 | Project Supervisor | Project Supervisor | hr | 10.5 | 57.7 | 605.85 | 902
2011-10-18 | Work Place Health & Safety Officer | WHSO | week | 4 | 45 | 180 | 902
2011-10-20 | Project Supervisor | Project Supervisor | hr | 8.5 | 57.7 | 490.45 | 902
2012-09-17 | Allciv Project - Supervisor | Supervisor | day | 1 | 580 | 580 | 902
2012-09-17 | Supervisors - Dual Cab Ute. | Dual Cab Ute | hr | 9 | 11.67 | 105.03 | 902
2012-09-18 | Supervisors - Dual Cab Ute. | Dual Cab Ute | hr | 11 | 11.67 | 128.37 | 902
2012-09-18 | Allciv Project - Supervisor | Supervisor | day | 1 | 580 | 580 | 902
2012-09-19 | Allciv Project - Supervisor | Supervisor | day | 1 | 580 | 580 | 902
2012-09-19 | Supervisors - Dual Cab Ute. | Dual Cab Ute | hr | 11 | 11.67 | 128.37 | 902
2012-09-20 | Allciv Project - Supervisor | Supervisor | day | 1 | 580 | 580 | 902
2012-09-20 | Supervisors - Dual Cab Ute. | Dual Cab Ute | hr | 11 | 11.67 | 128.37 | 902
2012-09-26 | Supervisors - Dual Cab Ute. | Dual Cab Ute | hr | 1 | 11.67 | 11.67 | 902
2012-09-27 | Supervisors - Dual Cab Ute. | Dual Cab Ute | hr | 10.5 | 11.67 | 122.535 | 902
| Subtotal for 902 |  |  |  |  | 93792.495
Cost Code 905
2011-05-24 | Ratchet, Padlock etc | Small Tools |  | 1 | 150.18 | 150.18 | 905 | John Crooks Hardware
2011-05-25 | Globe | Small Tools |  | 1 | 8.45 | 8.45 | 905 | Dysart Engineering
2011-05-25 | Globes | Small Tools |  | 1 | 35.18 | 35.18 | 905 | Dysart Engineering
2011-05-26 | Fuel Filter | Small Tools |  | 1 | 13.08 | 13.08 | 905 | Dysart Engineering
2011-05-26 | EDT Treatment | Small Tools |  | 1 | 28.82 | 28.82 | 905 | Dysart Engineering
2011-05-27 | Electronic Fuel Filter | Small Tools |  | 1 | 123.64 | 123.64 | 905 | Middlemount Engineering
2011-06-14 | Inv 10157725 - Spray & Mark Camlocks etc | Small Tools |  | 1 | 180.53 | 180.53 | 905 | Middlemount Rural
2011-06-28 | Tools for Paveline Truck | Small Tools |  | 1 | 286.97 | 286.97 | 905 | Bunnings
2011-08-14 | Inv- 8467/23183 | Small Tools |  | 1 | 180 | 180 | 905 | Bunnings
2011-08-17 | Inv- 8467/23286 | Small Tools |  | 1 | 9.63 | 9.63 | 905 | Bunnings
2011-08-20 | Inv-8467/23365 | Small Tools |  | 1 | 4124 | 4124 | 905 | Bunnings
2011-09-01 | Inv - 10163037 Spray & Mark White | Small Tools |  | 1 | 8.09 | 8.09 | 905 | CRT
2011-09-22 | Washer Flat, Bolt and Nut cupid Inv - 8467/24101 | Small Tools |  | 1 | 110.88 | 110.88 | 905 | Bunnings
2011-10-07 | Degreaser 20 ltrs Inv - 1051946 | Small Tools |  | 1 | 314 | 314 | 905 | Dysart Engineering
2011-10-09 | Kerosene Household Diggers Inv - 8467/24484 | Small Tools |  | 1 | 124.3 | 124.3 | 905 | Bunnings
| Subtotal for 905 |  |  |  |  | 5697.75
Cost Code 907
2011-06-16 | Float Container from Middlemount to Dysart | Float |  | 1 | 585 | 585 | 907 | Dysart Engineering
2011-06-22 |  | Plant Float - Allciv | hr | 13 | 7 | 91 | 907
2011-06-22 | Labour | Labour | hr | 13.5 | 30 | 405 | 907
2011-06-22 | Labour | Labour | hr | 13.5 | 32.2 | 434.7 | 907
2011-06-22 | Truck Driver | Labour | hr | 13.5 | 39.18 | 528.93 | 907
2011-06-22 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 13 | 42.79 | 556.27 | 907
2011-06-25 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 907
2011-06-25 | Labour | Labour | hr | 4 | 39.39 | 157.56 | 907
2011-06-27 | Labour | Labour | hr | 8 | 30 | 240 | 907
2011-06-27 | Labour | Labour | hr | 7 | 32.2 | 225.4 | 907
2011-06-29 | UD Spreader Truck - No Driver | UD Spreader | hr | 7 | 21.61 | 151.27 | 907
2011-06-29 | Labour | Labour | hr | 5 | 30 | 150 | 907
2011-06-29 | Repairs to Skid Steer | Repairs & Maint |  | 1 | 2334.54 | 2334.54 | 907 | Dysart Engineering
2011-06-29 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 907
2011-06-29 | Labour | Labour | hr | 5 | 32.2 | 161 | 907
2011-06-29 | Repairs to Bomag Roller | Repairs & Maint |  | 1 | 249.55 | 249.55 | 907 | Dysart Engineering
2011-06-30 | Repairs to Paveline Truck | Repairs & Maint |  | 1 | 353.45 | 353.45 | 907 | Dysart Engineering
2011-07-07 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 907
2011-07-07 | Labour | Labour | hr | 5 | 32.2 | 161 | 907
2011-07-07 | Labour | Labour | hr | 5 | 30 | 150 | 907
2011-07-12 | Labour | Labour | hr | 11 | 30 | 330 | 907
2011-07-12 | Labour | Labour | hr | 11 | 32.2 | 354.2 | 907
2011-07-12 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 907
2011-07-12 | Labour | Labour | hr | 12 | 32.2 | 386.4 | 907
2011-07-13 | Labour Hire | Labour | hr | 4 | 45 | 180 | 907
2011-07-13 | Work Place Health & Safety Officer | WHSO | week | 4 | 45 | 180 | 907
2011-07-13 | Labour | Labour | hr | 9.5 | 32.2 | 305.9 | 907
2011-07-13 | Labour Hire | Shannon Excavations (Labo | hr | 5 | 40 | 200 | 907
2011-07-13 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 907
2011-07-15 | Labour | Labour | hr | 7 | 39.39 | 275.73 | 907
2011-07-15 | Labour | Labour | hr | 8 | 32.2 | 257.6 | 907
2011-07-15 | Labour | Labour | hr | 7 | 32.2 | 225.4 | 907
2011-07-15 | Truck Driver | Labour | hr | 7 | 39.18 | 274.26 | 907
2011-07-15 | Labour Hire | Shannon Excavations (Labo | hr | 5 | 40 | 200 | 907
2011-07-15 | Labour Hire | Labour | hr | 5 | 45 | 225 | 907
2011-07-15 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8 | 42.79 | 342.32 | 907
2011-07-15 | Labour | Labour | hr | 7 | 30 | 210 | 907
2011-07-18 | Labour | Labour | hr | 7 | 32.2 | 225.4 | 907
2011-07-18 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 907
2011-07-18 | Labour Hire | Labour | hr | 5.5 | 45 | 247.5 | 907
2011-07-18 | Labour | Labour | hr | 5 | 32.2 | 161 | 907
2011-07-18 | Labour Hire | Shannon Excavations (Labo | hr | 5 | 40 | 200 | 907
2011-07-18 | Labour | Labour | hr | 5 | 30 | 150 | 907
2011-07-18 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 907
2011-07-26 | Labour Hire | Labour | hr | 5 | 45 | 225 | 907
2011-07-26 | Labour Hire | Shannon Excavations (Labo | hr | 5 | 40 | 200 | 907
2011-07-27 | Labour | Labour | hr | 5 | 30 | 150 | 907
2011-07-27 | Labour | Labour | hr | 5 | 32.2 | 161 | 907
2011-07-27 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 907
2011-07-27 | Labour | Labour | hr | 5 | 32.2 | 161 | 907
2011-07-27 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 907
2011-07-28 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9 | 42.79 | 385.11 | 907
2011-07-28 | Truck Driver | Labour | hr | 9 | 39.18 | 352.62 | 907
2011-07-31 | Damage Waiver Fees - Inv 7766335 (Traffic Lights) | Insurances |  | 1 | 132 | 132 | 907 | Tutt Bryant Hire
2011-08-16 | Load and Transport Grader Inv - 1049254 | Float |  | 1 | 536.25 | 536.25 | 907 | Dysart Engineering
2011-08-16 | Load and Transport Inv - 1049257 | Float |  | 1 | 536.25 | 536.25 | 907 | Dysart Engineering
2011-08-17 | Truck Driver | Labour | hr | 9 | 39.18 | 352.62 | 907
2011-08-17 | Labour Hire | Labour | hr | 6 | 45 | 270 | 907
2011-08-17 | Labour | Labour | hr | 9 | 32.2 | 289.8 | 907
2011-08-17 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 907
2011-08-17 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 907
2011-08-17 | Labour Hire | Shannon Excavations (Labo | hr | 5 | 40 | 200 | 907
2011-08-17 | Labour | Labour | hr | 5 | 32.2 | 161 | 907
2011-08-18 |  | Plant Float - Allciv | hr | 12.5 | 7 | 87.5 | 907
2011-08-18 | Labour | Labour | hr | 10.5 | 30 | 315 | 907
2011-08-18 | Labour Hire | Labour | hr | 1 | 45 | 45 | 907
2011-08-18 | Truck Driver | Labour | hr | 12.5 | 39.18 | 489.75 | 907
2011-08-18 | Labour | Labour | hr | 11 | 32.2 | 354.2 | 907
2011-08-18 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 12.5 | 42.79 | 534.875 | 907
2011-08-19 | Labour | Labour | hr | 10.5 | 30 | 315 | 907
2011-08-25 | Labour | Labour | hr | 5 | 30 | 150 | 907
2011-08-25 | Labour Hire | Labour | hr | 5 | 45 | 225 | 907
2011-08-25 | Labour Hire | Shannon Excavations (Labo | hr | 5 | 40 | 200 | 907
2011-08-25 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 907
2011-08-25 | Labour | Labour | hr | 5 | 32.2 | 161 | 907
2011-08-25 | Truck Driver | Labour | hr | 5.5 | 39.18 | 215.49 | 907
2011-08-25 | Labour | Labour | hr | 5 | 32.2 | 161 | 907
2011-08-30 | Labour | Labour | hr | 5 | 32.2 | 161 | 907
2011-08-30 |  | Shannon Excavations (Labo | hr | 5 | 40 | 200 | 907
2011-08-30 | Labour Hire | Labour | hr | 5 | 45 | 225 | 907
2011-08-30 | Tipper Hire | Hurst Backhoe Hire | hr | 6 | 40 | 240 | 907
2011-08-30 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 907
2011-08-30 | Labour | Labour | hr | 5 | 39.39 | 196.95 | 907
2011-08-30 | Labour | Labour | hr | 6 | 32.2 | 193.2 | 907
2011-09-02 | Tipper Hire | Hurst Backhoe Hire | hr | 6 | 40 | 240 | 907
2011-09-07 | Grader - Wet Hire Inv - 1050454 | Grader |  | 1 | 780 | 780 | 907 | Dysart Engineering
2011-09-08 | Labour | Labour | hr | 5.5 | 32.2 | 177.1 | 907
2011-09-08 | Labour | Labour | hr | 4.5 | 32.2 | 144.9 | 907
2011-09-13 | Labour | Labour | hr | 11 | 32.2 | 354.2 | 907
2011-09-13 | Truck Driver | Labour | hr | 10 | 39.18 | 391.8 | 907
2011-09-13 | Labour | Labour | hr | 11 | 32.2 | 354.2 | 907
2011-09-13 | Labour | Labour | hr | 10.5 | 39.39 | 413.595 | 907
2011-09-13 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 907
2011-09-13 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 907
2011-09-20 | Labour | Labour | hr | 5 | 32.2 | 161 | 907
2011-09-20 | Labour | Labour | hr | 5 | 32.2 | 161 | 907
2011-09-20 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-09-20 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-09-20 | Truck Driver | Labour | hr | 9.5 | 39.18 | 372.21 | 907
2011-09-20 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-09-26 | Labour | Labour | hr | 6 | 35.35 | 212.1 | 907
2011-09-26 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-09-26 | Labour | Labour | hr | 5 | 32.2 | 161 | 907
2011-09-26 | Truck Driver | Labour | hr | 3 | 39.18 | 117.54 | 907
2011-09-26 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-09-26 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-10-04 | Labour Hire | Labour | hr | 5 | 45 | 225 | 907
2011-10-04 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-10-04 | Labour | Labour | hr | 6 | 35.35 | 212.1 | 907
2011-10-04 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 907
2011-10-06 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-10-06 | Labour Hire | Labour | hr | 5 | 45 | 225 | 907
2011-10-06 | Labour | Labour | hr | 5 | 32.2 | 161 | 907
2011-10-10 | Jumper Leads Inv - 8467/24536 | Small Tools |  | 1 | 24.8 | 24.8 | 907 | Bunnings
2011-10-11 | Labour | Labour | hr | 6 | 35.35 | 212.1 | 907
2011-10-11 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-10-11 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-10-11 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-10-11 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-10-11 | Truck Driver | Labour | hr | 5 | 39.18 | 195.9 | 907
2011-10-11 | Labour | Labour | hr | 5 | 32.2 | 161 | 907
2011-10-11 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-10-16 | 14 Tonne excavator Inv - 00036926 | Excavator - 15T |  | 1 | 2580 | 2580 | 907 | CPL
2011-10-16 | Tractor and Stabiliser/Profiler Inv - 00036927 | Tractor Mixer |  | 1 | 1300 | 1300 | 907 | CPL
2011-10-17 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-10-17 | Labour | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-10-18 | Labour | Labour | hr | 5 | 32.2 | 161 | 907
2011-10-20 | Labour | Labour | hr | 6 | 35.35 | 212.1 | 907
2011-10-20 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-10-20 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 907
2012-09-17 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 7 | 42.79 | 299.53 | 907
2012-09-17 | Allciv - Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-09-17 | Allciv Plant - Excavator | Labour | hr | 4 | 48 | 192 | 907
2012-09-17 | Labour | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-09-17 | Allciv - Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-09-18 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 7 | 42.79 | 299.53 | 907
2012-09-18 | Allciv Plant - Excavator | Labour | hr | 4 | 48 | 192 | 907
2012-09-19 | Allciv - Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-09-19 | Allciv - Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-09-19 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 907
2012-09-19 | Labour | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-09-20 | Allciv - Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 907
2012-09-27 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8 | 42.79 | 342.32 | 907
| Subtotal for 907 |  |  |  |  | 39398.615
Cost Code 911
2011-05-24 | Accommodation - Inv 24.05.11 | Accommodation |  | 2 | 81.81 | 163.62 | 911 | The Whitsunday Hotel
2011-05-27 | 2 x Weeks Rent Garnham Road | Accommodation |  | 2 | 1450 | 2900 | 911 | Mackay Rentals
2011-05-31 | Accommodation & 3 meals Rate - Inv 1031026 | Accommodation |  | 43 | 90.75 | 3902.25 | 911 | The Mac
2011-05-31 | Accommodation & 3 meals Rate - Inv 1031141 | Accommodation |  | 16 | 115 | 1840 | 911 | The Mac
2011-05-31 | Accommodation & 3 meals Rate - Inv 1031027 | Accommodation |  | 3 | 90.75 | 272.25 | 911 | The Mac
2011-06-02 | 2 Weeks Rent 4 McMullen St Dysart | Accommodation |  | 2 | 1500 | 3000 | 911 | Mackay Rentals
2011-06-14 | Labour | Labour | hr | 5 | 30 | 150 | 911
2011-06-14 | Accommodation - 7 Garnham Road Dysart 2 weeks rent | Accommodation |  | 2 | 1450 | 2900 | 911 | Mackay Rentals
2011-06-14 | Labour | Labour | hr | 5 | 32.2 | 161 | 911
2011-06-15 | Accommodation & 3 meals Rate | Accommodation |  | 1 | 428 | 428 | 911 | The Mac
2011-06-15 | Accommodation & 3 meals Rate | Accommodation |  | 1 | 90.75 | 90.75 | 911 | The Mac
2011-06-20 | 2 x Weeks Rent 4 McMullen Court Dysart | Accommodation |  | 1 | 3000 | 3000 | 911 | Mackay Rentals
2011-06-30 | Accommodation & 3 meals Rate | Accommodation |  | 1 | 1633.42 | 1633.42 | 911 | The Mac
2011-06-30 | Accommodation & 3 meals Rate | Accommodation |  | 1 | 1666 | 1666 | 911 | The Mac
2011-07-01 | 2 x Rent - 7 Garnham Rd Dysart | Accommodation |  | 1 | 2900 | 2900 | 911 | Mackay Rentals
2011-07-04 | 2 x Weeks Rent 4 McMullen Crt Dysart | Accommodation |  | 1 | 3000 | 3000 | 911 | Mackay Rentals
2011-07-15 | Accommodation - Inv 1032765 | Accommodation |  | 1 | 93.6 | 93.6 | 911 | The Mac
2011-07-15 | 2 x Weeks rent 7 Garnham Rd Dysart | Accommodation |  | 1 | 2900 | 2900 | 911 | Mackay Rentals
2011-07-15 | Accommodation Inv 1032905 | Accommodation |  | 1 | 2070 | 2070 | 911 | The Mac
2011-07-15 | Accommodation Inv 1032655 | Accommodation |  | 1 | 748.8 | 748.8 | 911 | The Mac
2011-07-15 | 2 x Weeks Rent 4 McMullen Street Dysart | Accommodation |  | 1 | 3000 | 3000 | 911 | Mackay Rentals
2011-07-22 | Electricity Charges - 7 Garnham Dr Dysart | Accommodation |  | 1 | 219.03 | 219.03 | 911 | Ergon Energy
2011-07-25 | 2 x weeks rent 4 McMullen Crt Dysart | Accommodation |  | 1 | 3000 | 3000 | 911 | Mackay Rentals
2011-07-25 | 2 x Weeks Rent 7 garnham Rd Dysart | Accommodation |  | 1 | 2900 | 2900 | 911 | Mackay Rentals
2011-07-28 | Electricity charges 4 McMullen St Dysart | Accommodation |  | 1 | 185.1 | 185.1 | 911 | Ergon Energy
2011-07-31 | Accommodation & Meals - Inv 1033585 | Accommodation |  | 1 | 2527.2 | 2527.2 | 911 | The Mac
2011-07-31 | Accommodation & Meals | Accommodation |  | 1 | 2828 | 2828 | 911 | The Mac
2011-08-31 | Accommodation ( 16/08/2011 TO 31/08/2011 ) | Accommodation |  | 1 | 2490.98 | 2490.98 | 911 | The Mac
2011-09-08 | Accommodation & 3 meals Rate (01/08/2011 to 14/08/2011 ) | Accommodation |  | 1 | 398 | 398 | 911 | The Mac
2011-09-08 | Accommodation & 3 meals Ratem (01/08/2011 to 15/08/2011 inv 1034269 | Accommodation |  | 1 | 93.6 | 93.6 | 911 | The Mac
2011-09-08 | Accommodatio and meals (26/08/2011 TO 30/08/2011 ) | Accommodation |  | 1 | 2562 | 2562 | 911 | The Mac
2011-09-08 | Accommodation & 3 meals Rate (16/08/2011 to 31/08/2011 ) | Accommodation |  | 1 | 842.4 | 842.4 | 911 | The Mac
2011-09-08 | Accommodation & 3 meals Rate ( 01/08/2011 to 15/08/2011 ) | Accommodation |  | 1 | 237.24 | 237.24 | 911 | The Mac
2011-09-15 | Accommodation & 3 meals Rate Inv - 1035653 From 01/09/2011 to 15/09/2011 | Accommodation |  | 1 | 655.2 | 655.2 | 911 | The Mac
2011-09-15 | Accommodation & 3 meals Rate Inv - 1035477 From 2/09/2011 to 13/09/2011 | Accommodation |  | 1 | 1682 | 1682 | 911 | The Mac
2011-09-30 | Accommodation & 3 meals Rate From the (16/09/2011 to 30/09/2011) Inv - 1036287 | Accommodation |  | 1 | 2959.09 | 2959.09 | 911 | The Mac
2011-10-10 | Ergon Energy Acc No 17482038 | Power |  | 1 | 53.36 | 53.36 | 911 | Ergon Energy
2011-10-11 | Ergon Energy Acc No 16889789 | Power |  | 1 | 393.54 | 393.54 | 911 | Ergon Energy
2011-10-15 | Accommodation & 3 meals Rate between the (6/10/2011 to 12/10/2011 ) Inv - 1037161 | Accommodation |  | 1 | 3431.82 | 3431.82 | 911 | The Mac
2011-10-17 | Acc No - 16889762 | Power |  | 1 | 279.54 | 279.54 | 911 | Ergon Energy
2011-10-31 | Accommodation & 3 meals Rate From the 16/10/2011 to the 31/10/2011 Inv - 1038095 | Accommodation |  | 1 | 2809.1 | 2809.1 | 911 | The Mac
| Subtotal for 911 |  |  |  |  | 67366.89
Cost Code CSA
2011-05-25 | Cement Powder - 2 Tonne Bag | Cement - 2 Tonne Bag |  | 34 | 395 | 13430 | CSA | Cement Australia
2011-05-30 | Bulk GP / GB Cement | Cement | tonne | 1 | 395 | 395 | CSA
2011-06-07 | Cement Powder - 2 Tonne Bag | Cement - 2 Tonne Bag |  | 34 | 395 | 13430 | CSA | Cement Australia
2011-06-22 | Cement Powder - 2 Tonne Bag | Cement - 2 Tonne Bag |  | 34 | 410 | 13940 | CSA | Cement Australia
2011-07-05 | Cement Powder - 2 Tonne Bag - Inv 94378799 | Cement - 2 Tonne Bag |  | 34 | 395 | 13430 | CSA | Cement Australia
2011-07-27 | Bulk GP / GB Cement - Inv 94378799 | Cement |  | 34 | 395 | 13430 | CSA | Cement Australia
2011-09-02 | Bulk GP / GB Cement Inv- 94454644 | Cement |  | 34 | 395 | 13430 | CSA | Cement Australia
2011-09-20 | Bulk GP / GB Cement Docket No 82894313 Inv - 94474917 | Cement |  | 36 | 395 | 14220 | CSA | Cement Australia
2011-10-04 | Bulk GP / GB Cement Doc - 82899746 Inv - 94477860 | Cement |  | 34 | 395 | 13430 | CSA | Cement Australia
| Subtotal for CSA |  |  |  |  | 109135
Cost Code QM2.3
2011-06-14 | Inv 2043 | 2.3 Roadbase |  | 12.1 | 21.5 | 260.15 | QM2.3 | Crushing Insudtries Aust
2011-06-16 | Inv 2075 | 2.3 Roadbase |  | 23.97 | 21.5 | 515.355 | QM2.3 | Crushing Insudtries Aust
2011-06-17 | Inv 2092 | 2.3 Roadbase |  | 11.99 | 21.5 | 257.785 | QM2.3 | Crushing Insudtries Aust
2011-07-06 | 2.3 Roadbase - Inv 2239 | 2.3 Roadbase |  | 24.56 | 21.5 | 528.04 | QM2.3 | Crushing Insudtries Aust
2011-07-12 | 2.3 Road Base - Inv 2298 | 2.3 Roadbase |  | 12.52 | 21.5 | 269.18 | QM2.3 | Crushing Insudtries Aust
2011-07-13 | 2.3 Road base - Inv 2267 | 2.3 Roadbase |  | 12.05 | 21.5 | 259.075 | QM2.3 | Crushing Insudtries Aust
2011-07-19 | 2.3 Roadbase - Inv 2316 | 2.3 Roadbase |  | 5.95 | 21.5 | 127.925 | QM2.3 | Crushing Insudtries Aust
2011-07-23 | 2.3 Roadbase Inv 2341 | 2.3 Roadbase |  | 32.64 | 21.5 | 701.76 | QM2.3 | Crushing Insudtries Aust
2011-07-26 | Inv 2388 | 2.3 Roadbase |  | 11.37 | 21.5 | 244.455 | QM2.3 | Crushing Insudtries Aust
2011-08-31 | Inv-2613 | 2.3 Roadbase |  | 10.99 | 21.5 | 236.285 | QM2.3 | Crushing Insudtries Aust
2011-10-16 | 10 mm sealing aggregate 2.3 Road Base Dock - 29893 | 10 mm Aggregate |  | 11.85 | 37 | 438.45 | QM2.3 | CIA Rankins Quarry
| Subtotal for QM2.3 |  |  |  |  | 3838.46
Cost Code QMR
2011-09-26 | Inv - 30624 | 10 mm Aggregate |  | 8.47 | 37 | 313.39 | QMR | Crushing Insudtries Aust
2011-09-26 | Inv - 30624 | 10 mm Aggregate |  | 8.47 | 195 | 1651.65 | QMR | Cement Australia
2011-09-28 | 10 mm sealing aggregate Inv 30677 | 10 mm Aggregate |  | 19.13 | 37 | 707.81 | QMR | CIA Rankins Quarry
2011-09-28 | Bedding Sand Docket No 30677 | Rock Breaker |  | 19.3 | 28 | 540.4 | QMR | CIA Rankins Quarry
2011-09-29 | 7 mm Aggr Doc - 30716 | 10 mm Aggregate |  | 25.32 | 37 | 936.84 | QMR | CIA Rankins Quarry
2011-09-29 | Doc - 30716 | 10 mm Aggregate |  | 25.32 | 37 | 936.84 | QMR | CIA Rankins Quarry
2011-09-30 | 10 mm sealing aggregate 7 mm Doc - 30720 | 10 mm Aggregate |  | 18.59 | 37 | 687.83 | QMR | CIA Rankins Quarry
2011-09-30 | 10 mm sealing aggregate Doc - 30720 | 10 mm Aggregate |  | 18.59 | 37 | 687.83 | QMR | CIA Rankins Quarry
2011-10-01 | 10 mm sealing aggregate 7 mm Agg Doc - 30723 | 10 mm Aggregate |  | 8.96 | 37 | 331.52 | QMR | CIA Rankins Quarry
2011-10-01 | 10 mm sealing aggregate Doc 30723 | 10 mm Aggregate |  | 8.96 | 37 | 331.52 | QMR | CIA Rankins Quarry
2011-10-02 | 10 mm sealing aggregate 7 mm Agg Doc- 30725 | 10 mm Aggregate |  | 19.52 | 37 | 722.24 | QMR | CIA Rankins Quarry
2011-10-02 | 10 mm sealing aggregate Doc - 30725 | 10 mm Aggregate |  | 19.52 | 37 | 722.24 | QMR | CIA Rankins Quarry
2011-10-03 | 10 mm sealing aggregate Doc 30748 | 10 mm Aggregate |  | 10.45 | 37 | 386.65 | QMR | CIA Rankins Quarry
2011-10-04 | 10 mm sealing aggregate 7 mm Agg Doc - 30748 | 10 mm Aggregate |  | 10.45 | 37 | 386.65 | QMR
2011-10-05 | 10 mm sealing aggregate Doc 29780 | 10 mm Aggregate |  | 51.29 | 37 | 1897.73 | QMR | CIA Rankins Quarry
2011-10-06 | 10 mm sealing aggregate 7 mm Dock - 29784 | 10 mm Aggregate |  | 51.5 | 37 | 1905.5 | QMR | CIA Rankins Quarry
2011-10-06 | 10 mm sealing aggregate Dock - 29784 | 10 mm Aggregate |  | 51.5 | 37 | 1905.5 | QMR | CIA Rankins Quarry
2011-10-06 | 10 mm sealing aggregate 7 mm agg Doc- 29780 | 10 mm Aggregate |  | 51.29 | 37 | 1897.73 | QMR | CIA Rankins Quarry
2011-10-11 | 10 mm sealing aggregate 7 mm Agg Doct - 29824 | 10 mm Aggregate |  | 9.33 | 37 | 345.21 | QMR | CIA Rankins Quarry
2011-10-13 | 7 mm ( Dock - 29865 ) | 10 mm Aggregate |  | 8.4 | 195 | 1638 | QMR | CIA Rankins Quarry
2011-10-13 | 10mm ( Dock - 29865) | 10 mm Aggregate |  | 8.34 | 195 | 1626.3 | QMR | CIA Rankins Quarry
2011-10-15 | 10 mm ( Dock - 29888 ) | 10 mm Aggregate |  | 11.05 | 195 | 2154.75 | QMR | CIA Rankins Quarry
2011-10-15 | 7 mm ( Dock - 29888 ) | 10 mm Aggregate |  | 11.05 | 195 | 2154.75 | QMR | CIA Rankins Quarry
2011-10-16 | 10 mm sealing aggregate Dock - 29894 | 10 mm Aggregate |  | 15.81 | 37 | 584.97 | QMR | CIA Rankins Quarry
2011-10-16 | 7mm sealing aggregate Dock - 29894 | 10 mm Aggregate |  | 15.81 | 37 | 584.97 | QMR | CIA Rankins Quarry
| Subtotal for QMR |  |  |  |  | 26038.82
| Grand Total |  |  |  |  | 814588.615