## Estimate
[9 empty] | 3194691.6815 |  |  | 418984.586 | 518531.055 | 861068.8567 | 1396107.1838 | 3194691.6815
WBS | Line No | Resource Name | Unit | Type | No | Prodn | Quantity | Rate | Cost | Usage | Duration | Labour | Material | Plant | Subcontract | Total | Portfolio WBS
1000 | Line No 1 Item No | ANZAC STREET
| Line No 3 Item No | QUALITY SYSTEM
5 | Line No 5 Item No QP1 | Quality System Documents & Records (for entire Package A) | Lump |  |  |  | 1 |  | 39000 |  | 0 | 39000 | 0 | 0 | 0 | 39000
Tasks ongoing throughout project
5.1 | 1 | Project Engineer | week | L | 1 | 1 | 6 | 3250 | 19500 | 6 | 6 | 19500 | 0 | 0 | 0 | 19500 | 901
| 2 | Technical Officer | week | L | 1 | 1 | 6 | 3250 | 19500 | 6 | 6 | 19500 | 0 | 0 | 0 | 19500 | 901
| Line No 6 Item No CQC | QUALITY CONTROL REQUIREMENTS
6 | Line No 7 Item No QCP1 | Quality Verification & Control | Lump |  |  |  | 1 |  | 6460 |  | 0 | 3250 | 0 | 0 | 3210 | 6460
Tasks ongoing throughout project
| 1 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 | 1 | 1 | 3250 | 0 | 0 | 0 | 3250 | 901
6.1 | 2 | Field Density Tests (QTY) |  |  |  |  | 12
6.2 | 3 | Concrete Cylinders (QTY) |  |  |  |  | 6
| 4 | Field Density | each | S | 1 | 1 | 12 | 45 | 540 | 12 | 12 | 0 | 0 | 0 | 540 | 540 | 13
| 5 | Gravel Properties Testing | each | S | 1 | 1 | 3 | 390 | 1170 | 3 | 3 | 0 | 0 | 0 | 1170 | 1170 | 13
| 6 | Concrete Cylinders | each | S | 1 | 1 | 6 | 150 | 900 | 6 | 6 | 0 | 0 | 0 | 900 | 900 | 13
6.3 | 7 | Survey | Item | S | 1 | 1 | 600 | 1 | 600 |  | 600 | 0 | 0 | 0 | 600 | 600 | 11
| Line No 9 Item No | GENERAL REQUIREMENTS
7 | Line No 11 Item No C101(b) | Site Establishment & Disestablishment | Lump |  |  |  | 1 |  | 22050 |  | 6 | 9650 | 0 | 12400 | 0 | 22050
Float of Machinery - in order: Grader; SD Roller; MW Roller; Water Cart; Truck & Dogs; Bobcat; Excavator & Site Office. Allow to purchase a generator & Project supervisor for 1 week.
| 1 | Float | LS | P | 600 | 1 | 1 | 1 | 600 |  |  | 0 | 0 | 600 | 0 | 600 | 907
| 2 | Float | LS | P | 900 | 1 | 1 | 1 | 900 |  |  | 0 | 0 | 900 | 0 | 900 | 907
| 3 | Float | LS | P | 900 | 1 | 1 | 1 | 900 |  |  | 0 | 0 | 900 | 0 | 900 | 907
| 4 | Float | LS | P | 300 | 1 | 1 | 1 | 300 |  |  | 0 | 0 | 300 | 0 | 300 | 907
| 5 | Float | LS | P | 300 | 1 | 1 | 1 | 300 |  |  | 0 | 0 | 300 | 0 | 300 | 907
| 6 | Float | LS | P | 600 | 1 | 1 | 1 | 600 |  |  | 0 | 0 | 600 | 0 | 600 | 907
| 7 | Float | LS | P | 600 | 1 | 1 | 1 | 600 |  |  | 0 | 0 | 600 | 0 | 600 | 907
| 8 | Float | LS | P | 1200 | 1 | 1 | 1 | 1200 |  |  | 0 | 0 | 1200 | 0 | 1200 | 907
| 9 | Generator | Item | P | 1 | 1 | 1 | 7000 | 7000 | 1 | 1 | 0 | 0 | 7000 | 0 | 7000 | 907
| 10 | Project Supervisor | week | L | 1 | 1 | 1 | 3350 | 3350 | 1 | 1 | 3350 | 0 | 0 | 0 | 3350 | 902
| 11 | Labour | hr | L | 3 | 1 | 50 | 42 | 6300 | 150 | 50 | 6300 | 0 | 0 | 0 | 6300 | 907
| Line No 13 Item No | ROAD & EARTHWORKS
| Line No 14 Item No C201 | CONTROL OF TRAFFIC
8 | Line No 15 Item No C201(a) | Control of Traffic | Lump |  |  |  | 1 |  | 11646.24 |  | 10 | 0 | 0 | 0 | 11646.24 | 11646.24
8.1 | 1 | Duration (Weeks) |  |  |  |  | 2
| 2 | Traffic Control Crew | hr | S | 6 | 0.10526 | 2 | 102.16 | 11646.24 | 60 | 10 | 0 | 0 | 0 | 11646.24 | 11646.24 | 141
| Line No 16 Item No C201(b) | Provision of Temporary Roadways, Side-tracks and Detours (Provisional) | Lump |  |  |  | 1
| Line No 17 Item No C213 | EARTHWORKS
9 | Line No 18 Item No C213(b) | General Earthworks Cut | m3 |  |  |  | 60 |  | 2268 |  | 1 | 168 | 0 | 2100 | 0 | 2268
9.1 | 1 | Excavator - 25T | hr | P | 1 | 15 | 60 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 53
9.2 | 2 | Truck & Dog | hr | P | 2 | 15 | 60 | 145 | 1160 | 8 | 4 | 0 | 0 | 1160 | 0 | 1160 | 53
| 3 | Water Cart - Hire | hr | P | 1 | 15 | 60 | 100 | 400 | 4 | 4 | 0 | 0 | 400 | 0 | 400 | 53
9.3 | 4 | Labour | hr | L | 1 | 15 | 60 | 42 | 168 | 4 | 4 | 168 | 0 | 0 | 0 | 168 | 53
10 | Line No 19 Item No C213(d) | Replace unsuitable material below sub grade with select material complete (Provisional) | m3 |  |  |  | 10 |  | 655.3333 |  | 1 | 112 | 0 | 543.3333 | 0 | 655.3333
10.1 | 1 | Excavator - 25T | hr | P | 1 | 15 | 10 | 135 | 90 | 0.66667 | 0.66667 | 0 | 0 | 90 | 0 | 90 | 57
10.2 | 2 | Truck & Dog | hr | P | 2 | 15 | 10 | 145 | 193.3333 | 1.3333 | 0.66667 | 0 | 0 | 193.3333 | 0 | 193.3333 | 57
| 3 | Water Cart - Hire | hr | P | 1 | 15 | 10 | 100 | 66.6667 | 0.66667 | 0.66667 | 0 | 0 | 66.6667 | 0 | 66.6667 | 57
| 4 | Labour | hr | L | 1 | 15 | 10 | 42 | 28 | 0.66667 | 0.66667 | 28 | 0 | 0 | 0 | 28 | 57
| 5 | Fill
10.3 | 6 | Excavator - 25T | hr | P | 1 | 15 | 10 | 135 | 90 | 0.66667 | 0.66667 | 0 | 0 | 90 | 0 | 90 | 57
| 7 | SD Roller - Wet (No Op) | hr | P | 1 | 15 | 10 | 55 | 36.6667 | 0.66667 | 0.66667 | 0 | 0 | 36.6667 | 0 | 36.6667 | 57
| 8 | Water Cart - Hire | hr | P | 1 | 15 | 10 | 100 | 66.6667 | 0.66667 | 0.66667 | 0 | 0 | 66.6667 | 0 | 66.6667 | 57
10.4 | 9 | Labour | hr | L | 3 | 15 | 10 | 42 | 84 | 2 | 0.66667 | 84 | 0 | 0 | 0 | 84 | 57
| Line No 21 Item No | STORMWATER DRAINAGE
| Line No 22 Item No C221 | PIPE DRAINAGE (SUPPLY & INSTALL)
| Line No 23 Item No C221(a) | STEEL REINFORCED CONCRETE
| Line No 25 Item No C222 | PRECAST BOX CULVERTS (SUPPLY & INSTALL)
11 | Line No 26 Item No C222(a) | In-Situ reinforced concrete Base Slab for culverts complete | m3 |  |  |  | 4 |  | 2604.1778 |  | 2 | 0 | 1304.1778 | 0 | 1300 | 2604.1778
| 1 | 1200 x 600 (12m)
| 2 | Area = QTY/.2 |  |  |  |  | 20
| 3 | Sand | tonne | M | 1 | 1 | 2 | 24 | 48 |  |  | 0 | 48 | 0 | 0 | 48 | QMS
| 4 | RL1218 | m² | M | 1 | 1 | 24 | 18 | 432 |  |  | 0 | 432 | 0 | 0 | 432 | RSM
| 5 | Bar Chairs | each | M | 1 | 1 | 22.2222 | 0.8 | 17.7778 |  |  | 0 | 17.7778 | 0 | 0 | 17.7778 | RSM
| 6 | N32 | m³ | M | 1 | 1 | 4.2 | 192 | 806.4 |  |  | 0 | 806.4 | 0 | 0 | 806.4 | C32
| 7 | RCBC Slab Subbie | m² | S | 1 | 1 | 20 | 65 | 1300 | 20 | 20 | 0 | 0 | 0 | 1300 | 1300 | 72
12 | Line No 27 Item No C222(b) | 1200 x 600 | m |  |  |  | 12 |  | 7902.5 |  | 2 | 1260 | 4975 | 1667.5 | 0 | 7902.5
| 1 | (10) Box Units to Stand - 1.2m long each |  |  |  |  | 10
| 2 | (15) Hand Placed Backfill - 1.25 cum / m |  |  |  |  | 15
| 3 | RCBC - 1200 x 600 | m | M | 1 | 1 | 12 | 400 | 4800 |  |  | 0 | 4800 | 0 | 0 | 4800 | SWC
| 4 | Excavator - 25T | hr | P | 1 | 2 | 10 | 135 | 675 | 5 | 5 | 0 | 0 | 675 | 0 | 675 | 181
12.1 | 5 | Labour | hr | L | 3 | 2 | 10 | 42 | 630 | 15 | 5 | 630 | 0 | 0 | 0 | 630 | 181
| 6 | Denso Tape | m | M | 1 | 1 | 35 | 5 | 175 |  |  | 0 | 175 | 0 | 0 | 175 | 181
12.2 | 7 | Bobcat | hr | P | 1 | 3 | 15 | 95 | 475 | 5 | 5 | 0 | 0 | 475 | 0 | 475 | 181
12.3 | 8 | Labour | hr | L | 3 | 3 | 15 | 42 | 630 | 15 | 5 | 630 | 0 | 0 | 0 | 630 | 181
| 9 | Plate Compactor | hr | P | 1 | 3 | 15 | 3.5 | 17.5 | 5 | 5 | 0 | 0 | 17.5 | 0 | 17.5 | 181
| 10 | Water Cart - Hire | hr | P | 1 | 3 | 15 | 100 | 500 | 5 | 5 | 0 | 0 | 500 | 0 | 500 | 181
| Line No 28 Item No C223 | DRAINAGE STRUCTURES
13 | Line No 29 Item No C223(a) | Cast in situ Concrete Headwalls & Wingwalls & Aprons complete | m3 |  |  |  | 3 |  | 2733.6 |  | 2 | 0 | 633.6 | 0 | 2100 | 2733.6
| 1 | N32 | m³ | M | 1 | 1 | 3.3 | 192 | 633.6 |  |  | 0 | 633.6 | 0 | 0 | 633.6 | C32
| 2 | Concrete Sub-contract | m² | S | 1 | 1 | 3 | 700 | 2100 | 3 | 3 | 0 | 0 | 0 | 2100 | 2100 | 181
| Line No 30 Item No C224 | OPEN DRAINS, INCLUDING KERB & CHANNEL
14 | Line No 31 Item No C224(b) | Excavation - Inlet, Outlet & Diversion Channels | m3 |  |  |  | 60 |  | 2268 |  | 1 | 168 | 0 | 2100 | 0 | 2268
14.1 | 1 | Excavator - 25T | hr | P | 1 | 15 | 60 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 53
14.2 | 2 | Truck & Dog | hr | P | 2 | 15 | 60 | 145 | 1160 | 8 | 4 | 0 | 0 | 1160 | 0 | 1160 | 53
| 3 | Water Cart - Hire | hr | P | 1 | 15 | 60 | 100 | 400 | 4 | 4 | 0 | 0 | 400 | 0 | 400 | 53
| 4 | Labour | hr | L | 1 | 15 | 60 | 42 | 168 | 4 | 4 | 168 | 0 | 0 | 0 | 168 | 53
| Line No 33 Item No | PAVEMENTS
| Line No 34 Item No C241 | STABILIZATION
15 | Line No 35 Item No | Full service, supply agent and mix complete (Provisional if ordered) | m2 |  |  |  | 170 |  | 5918.8258 |  | 1 | 1511.9111 | 918 | 3488.9148 | 0 | 5918.8258
| 1 | Stabilising
15.1 | 1 | CAT297 Stabiliser | hr | P | 1 | 18.89 | 170 | 66.07 | 594.595 | 8.9995 | 8.9995 | 0 | 0 | 594.595 | 0 | 594.595 | 68
| 2 | Grader | hr | P | 1 | 18.89 | 170 | 145 | 1304.9232 | 8.9995 | 8.9995 | 0 | 0 | 1304.9232 | 0 | 1304.9232 | 68
| 3 | Water Cart - Hire | hr | P | 1 | 18.89 | 170 | 100 | 899.9471 | 8.9995 | 8.9995 | 0 | 0 | 899.9471 | 0 | 899.9471 | 68
| 4 | SD Roller - Wet (No Op) | hr | P | 1 | 18.89 | 170 | 55 | 494.9709 | 8.9995 | 8.9995 | 0 | 0 | 494.9709 | 0 | 494.9709 | 68
| 5 | UD Spreader | hr | P | 1 | 18.89 | 170 | 21.61 | 194.4786 | 8.9995 | 8.9995 | 0 | 0 | 194.4786 | 0 | 194.4786 | 68
15.2 | 6 | Labour | hr | L | 4 | 18.89 | 170 | 42 | 1511.9111 | 35.9979 | 8.9995 | 1511.9111 | 0 | 0 | 0 | 1511.9111 | 68
15.3 | 2 | Cement | tonne | M | 0.012 | 1 | 2.04 | 450 | 918 |  |  | 0 | 918 | 0 | 0 | 918 | CSA
| Line No 36 Item No C242 | FLEXIBLE PAVEMENTS
16 | Line No 37 Item No | Place only Type 2.1 (cement modified) | m3 |  |  |  | 20 |  | 3798.8716 |  | 1 | 796.3744 | 0 | 3002.4971 | 0 | 3798.8716
16.1 | 1 | Tonnes Gravel = QTY*density |  |  | 2.4 |  | 48
16.2 | 2 | Truck & Dog | hr | P | 3 | 37 | 48 | 145 | 564.3243 | 3.8919 | 1.2973 | 0 | 0 | 564.3243 | 0 | 564.3243 | 62
| 3 | Placement
16.25 | 4 | Grader | hr | P | 1 | 11.11 | 48 | 145 | 626.4626 | 4.3204 | 4.3204 | 0 | 0 | 626.4626 | 0 | 626.4626 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 11.11 | 48 | 100 | 432.0432 | 4.3204 | 4.3204 | 0 | 0 | 432.0432 | 0 | 432.0432 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 11.11 | 48 | 55 | 237.6238 | 4.3204 | 4.3204 | 0 | 0 | 237.6238 | 0 | 237.6238 | 62
| 7 | Labour | hr | L | 3 | 11.11 | 48 | 42 | 544.3744 | 12.9613 | 4.3204 | 544.3744 | 0 | 0 | 0 | 544.3744 | 62
| 8 | Backhoe | hr | P | 1 | 11.11 | 48 | 100 | 432.0432 | 4.3204 | 4.3204 | 0 | 0 | 432.0432 | 0 | 432.0432 | 62
| 9 | Final Trim
16.3 | 10 | Grader | hr | P | 1 | 100 | 200 | 145 | 290 | 2 | 2 | 0 | 0 | 290 | 0 | 290 | 63
| 11 | Water Cart - Hire | hr | P | 1 | 100 | 200 | 100 | 200 | 2 | 2 | 0 | 0 | 200 | 0 | 200 | 63
| 12 | MW Roller | hr | P | 1 | 50 | 200 | 55 | 220 | 4 | 4 | 0 | 0 | 220 | 0 | 220 | 63
16.4 | 13 | Labour | hr | L | 3 | 100 | 200 | 42 | 252 | 6 | 2 | 252 | 0 | 0 | 0 | 252 | 63
17 | Line No 38 Item No | Place only Type 2.3 (cement modified) | m3 |  |  |  | 20 |  | 2836.8716 |  | 1 | 544.3744 | 0 | 2292.4971 | 0 | 2836.8716
17.1 | 1 | Tonnes Gravel = QTY*density |  |  | 2.4 |  | 48
17.2 | 2 | Truck & Dog | hr | P | 3 | 37 | 48 | 145 | 564.3243 | 3.8919 | 1.2973 | 0 | 0 | 564.3243 | 0 | 564.3243 | 62
| 3 | Placement
17.3 | 4 | Grader | hr | P | 1 | 11.11 | 48 | 145 | 626.4626 | 4.3204 | 4.3204 | 0 | 0 | 626.4626 | 0 | 626.4626 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 11.11 | 48 | 100 | 432.0432 | 4.3204 | 4.3204 | 0 | 0 | 432.0432 | 0 | 432.0432 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 11.11 | 48 | 55 | 237.6238 | 4.3204 | 4.3204 | 0 | 0 | 237.6238 | 0 | 237.6238 | 62
17.4 | 7 | Labour | hr | L | 3 | 11.11 | 48 | 42 | 544.3744 | 12.9613 | 4.3204 | 544.3744 | 0 | 0 | 0 | 544.3744 | 62
| 8 | Backhoe | hr | P | 1 | 11.11 | 48 | 100 | 432.0432 | 4.3204 | 4.3204 | 0 | 0 | 432.0432 | 0 | 432.0432 | 62
| Line No 39 Item No C244 | SPRAYED BITUMINOUS SURFACING
| Line No 40 Item No C244(a) | Supply & Spray Primer, supply & spread aggregates, Primerbinder (including preparation of surface) complete
18 | Line No 41 Item No C244(a) | (vii) AMC5 | m2 |  |  |  | 200 |  | 10878 |  | 1 | 0 | 0 | 0 | 10878 | 10878
18.1 | 1 | Seal Visit One | m² | S | 1.05 | 1 | 210 | 51.8 | 10878 |  | 210 | 0 | 0 | 0 | 10878 | 10878 | 64
19 | Line No 42 Item No C244(b) | Supply & Spray Binder - Bitumen (includes PMB's, Adhesion Agent where required and Preparation of Surface) supply & spread aggregates complete | m2 |  |  |  | 200 |  | 10878 |  | 1 | 0 | 0 | 0 | 10878 | 10878
19.1 | 1 | Seal Visit One | m² | S | 1.05 | 1 | 210 | 51.8 | 10878 |  | 210 | 0 | 0 | 0 | 10878 | 10878 | 64
| Line No 44 Item No | ROAD FURNISHINGS
| Line No 45 Item No C263 | GUIDE POSTS
20 | Line No 46 Item No C263(a) | Guide Posts complete supply and install | each |  |  |  | 4 |  | 140 |  | 1 | 0 | 140 | 0 | 0 | 140
| 1 | Guide Post | each | M | 1 | 1 | 4 | 35 | 140 |  |  | 0 | 140 | 0 | 0 | 140 | 67
| Line No 48 Item No | MISCELLANEOUS
| Line No 49 Item No C273 | LANDSCAPE
| Line No 50 Item No C273(a) | Vegetation of Slopes 1 in 3 or Flatter
21 | Line No 51 Item No C273(a) | (i) Grass Seeding | m2 |  |  |  | 100 |  | 269.5 |  |  | 0 | 0 | 0 | 269.5 | 269.5
21.1 | 1 | Grass Seeding | m² | S | 1.1 | 1 | 110 | 2.45 | 269.5 |  | 110 | 0 | 0 | 0 | 269.5 | 269.5 | 121
| Line No 53 Item No | SPECIFIED WORKS | [9 empty] | Contributing
22 | Line No 54 Item No | Special Item - As Constructed Survey and Plans | Lump |  |  |  | 1 |  | 800 |  | 1 | 0 | 0 | 0 | 800 | 800
| 1 | Survey | Item | S | 1 | 1 | 800 | 1 | 800 |  | 6.4 | 0 | 0 | 0 | 800 | 800 | 12
2000 | Line No 58 Item No | DOBBINS LANE
| Line No 60 Item No | QUALITY SYSTEM
| Line No 61 Item No CQC | QUALITY CONTROL REQUIREMENTS
23 | Line No 62 Item No QCP1 | Quality Verification & Control | Lump |  |  |  | 1 |  | 11795 |  |  | 3250 | 0 | 0 | 8545 | 11795
Tasks ongoing throughout project
| 1 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 | 1 | 1 | 3250 | 0 | 0 | 0 | 3250 | 901
23.1 | 2 | (15) Field Density Tests |  |  |  |  | 15
23.2 | 3 | (6) Concrete Cylinder Sets |  |  |  |  | 6
| 4 | Field Density | each | S | 1 | 1 | 15 | 45 | 675 | 15 | 15 | 0 | 0 | 0 | 675 | 675 | 13
| 5 | Gravel Properties Testing | each | S | 1 | 1 | 3 | 390 | 1170 | 3 | 3 | 0 | 0 | 0 | 1170 | 1170 | 13
| 6 | Concrete Cylinders | each | S | 1 | 1 | 6 | 150 | 900 | 6 | 6 | 0 | 0 | 0 | 900 | 900 | 13
23.4 | 7 | Survey | Item | S | 1 | 1 | 5800 | 1 | 5800 |  | 46.4 | 0 | 0 | 0 | 5800 | 5800 | 11
| Line No 64 Item No | GENERAL REQUIREMENTS
| Line No 65 Item No C101 | GENERAL
| Line No 66 Item No C101(b) | Site Establishment & Disestablishment | Lump |  |  |  | 1 |  |  |  |  | Contributing
| Line No 68 Item No | ROAD & EARTHWORKS
| Line No 69 Item No C201 | CONTROL OF TRAFFIC
25 | Line No 70 Item No C201(a) | Control of Traffic | Lump |  |  |  | 1 |  | 34938.72 |  | 30 | 0 | 0 | 0 | 34938.72 | 34938.72
| 1 | (6) No. Weeks TC Required |  |  | 6 |  | 6
| 2 | Traffic Control Crew | hr | S | 6 | 0.10526 | 6 | 102.16 | 34938.72 | 180 | 30 | 0 | 0 | 0 | 34938.72 | 34938.72 | 141
| Line No 71 Item No C211 | CONTROL OF EROSION & SEDIMENTATION
26 | Line No 72 Item No C211(a) | Temporary Erosion & Sedimentation Control (includes supply and installation of all components) | Lump |  |  |  | 1 |  | 11050 |  | 6 | 6300 | 0 | 4750 | 0 | 11050
26.1 | 1 | Labour | hr | L | 3 | 1 | 50 | 42 | 6300 | 150 | 50 | 6300 | 0 | 0 | 0 | 6300 | 151
| 2 | Bobcat | hr | P | 1 | 1 | 50 | 95 | 4750 | 50 | 50 | 0 | 0 | 4750 | 0 | 4750 | 151
| Line No 73 Item No C213 | EARTHWORKS
27 | Line No 74 Item No C213(b) | General Earthworks Cut | m3 |  |  |  | 998 |  | 20828.5297 |  | 4 | 1954.1919 | 0 | 18874.3378 | 0 | 20828.5297
| 1 | Excavator - 25T | hr | P | 1 | 40 | 998 | 135 | 3368.25 | 24.95 | 24.95 | 0 | 0 | 3368.25 | 0 | 3368.25 | 53
| 2 | Truck & Dog | hr | P | 3 | 40 | 998 | 145 | 10853.25 | 74.85 | 24.95 | 0 | 0 | 10853.25 | 0 | 10853.25 | 53
| 3 | Water Cart - Hire | hr | P | 1 | 40 | 998 | 100 | 2495 | 24.95 | 24.95 | 0 | 0 | 2495 | 0 | 2495 | 53
| 4 | Labour | hr | L | 1 | 40 | 998 | 42 | 1047.9 | 24.95 | 24.95 | 1047.9 | 0 | 0 | 0 | 1047.9 | 53
| 5 | Prepare Sub-grade
27.1 | 6 | Grader | hr | P | 1 | 250 | 1798.1982 | 145 | 1042.955 | 7.1928 | 7.1928 | 0 | 0 | 1042.955 | 0 | 1042.955 | 61
| 7 | Water Cart - Hire | hr | P | 1 | 250 | 1798.1982 | 100 | 719.2793 | 7.1928 | 7.1928 | 0 | 0 | 719.2793 | 0 | 719.2793 | 61
| 8 | SD Roller - Wet (No Op) | hr | P | 1 | 250 | 1798.1982 | 55 | 395.6036 | 7.1928 | 7.1928 | 0 | 0 | 395.6036 | 0 | 395.6036 | 61
27.2 | 9 | Labour | hr | L | 3 | 250 | 1798.1982 | 42 | 906.2919 | 21.5784 | 7.1928 | 906.2919 | 0 | 0 | 0 | 906.2919 | 61
28 | Line No 75 Item No C213(d) | Replace unsuitable material below sub grade with select material complete (PROVISIONAL) | m3 |  |  |  | 10 |  | 655.3333 |  | 1 | 112 | 0 | 543.3333 | 0 | 655.3333
28.1 | 1 | Excavator - 25T | hr | P | 1 | 15 | 10 | 135 | 90 | 0.66667 | 0.66667 | 0 | 0 | 90 | 0 | 90 | 57
| 2 | Truck & Dog | hr | P | 2 | 15 | 10 | 145 | 193.3333 | 1.3333 | 0.66667 | 0 | 0 | 193.3333 | 0 | 193.3333 | 57
| 3 | Water Cart - Hire | hr | P | 1 | 15 | 10 | 100 | 66.6667 | 0.66667 | 0.66667 | 0 | 0 | 66.6667 | 0 | 66.6667 | 57
| 4 | Labour | hr | L | 1 | 15 | 10 | 42 | 28 | 0.66667 | 0.66667 | 28 | 0 | 0 | 0 | 28 | 57
| 5 | Fill
28.2 | 6 | Excavator - 25T | hr | P | 1 | 15 | 10 | 135 | 90 | 0.66667 | 0.66667 | 0 | 0 | 90 | 0 | 90 | 57
| 7 | SD Roller - Wet (No Op) | hr | P | 1 | 15 | 10 | 55 | 36.6667 | 0.66667 | 0.66667 | 0 | 0 | 36.6667 | 0 | 36.6667 | 57
| 8 | Water Cart - Hire | hr | P | 1 | 15 | 10 | 100 | 66.6667 | 0.66667 | 0.66667 | 0 | 0 | 66.6667 | 0 | 66.6667 | 57
28.3 | 9 | Labour | hr | L | 3 | 15 | 10 | 42 | 84 | 2 | 0.66667 | 84 | 0 | 0 | 0 | 84 | 57
| Line No 77 Item No | STORMWATER DRAINAGE
| Line No 78 Item No C220 | STORMWATER DRAINAGE - GENERAL
29 | Line No 79 Item No | Removal / Demolition of Drainage Components complete | Lump |  |  |  | 1 |  | 10066.6667 |  | 2 | 1400 | 0 | 8666.6667 | 0 | 10066.6667
29.1 | 1 | Excavator - 25T | hr | P | 1 | 0.06 | 1 | 135 | 2250 | 16.6667 | 16.6667 | 0 | 0 | 2250 | 0 | 2250 | 41
| 2 | Tipper | hr | P | 3 | 0.06 | 1 | 95 | 4750 | 50 | 16.6667 | 0 | 0 | 4750 | 0 | 4750 | 41
| 3 | Labour | hr | L | 2 | 0.06 | 1 | 42 | 1400 | 33.3333 | 16.6667 | 1400 | 0 | 0 | 0 | 1400 | 41
| 4 | Water Cart - Hire | hr | P | 1 | 0.06 | 1 | 100 | 1666.6667 | 16.6667 | 16.6667 | 0 | 0 | 1666.6667 | 0 | 1666.6667 | 41
30 | Line No 80 Item No | Alteration to Existing Stormwater Structures (New 225 Upvc at Ch 140 | Lump |  |  |  | 1 |  | 1200 |  | 1 | 0 | 0 | 0 | 1200 | 1200
| 1 | Pit Builder - Modify | each | S | 1 | 1 | 1 | 1200 | 1200 |  | 1 | 0 | 0 | 0 | 1200 | 1200 | 85
| Line No 81 Item No C221 | PIPE DRAINAGE (SUPPLY & INSTALL) | [9 empty] | Contributing
31 | Line No 82 Item No C221(a) | 225mm dia uPVC | m |  |  |  | 16 |  | 2313 |  | 1 | 630 | 1008 | 675 | 0 | 2313
31.1 | 1 | Excavator - 25T | hr | P | 1 | 3.2 | 16 | 135 | 675 | 5 | 5 | 0 | 0 | 675 | 0 | 675 | 81
| 2 | 300 RCP | m | M | 1 | 1 | 16 | 55 | 880 |  |  | 0 | 880 | 0 | 0 | 880 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 5.3333 | 24 | 128 |  |  | 0 | 128 | 0 | 0 | 128 | QMS
31.2 | 4 | Labour | hr | L | 3 | 3.2 | 16 | 42 | 630 | 15 | 5 | 630 | 0 | 0 | 0 | 630 | 81
32 | Line No 83 Item No C223(b) | (x) Inter-allotment Drainage Pit | each |  |  |  | 1 |  | 3750 |  | 3 | 0 | 0 | 0 | 3750 | 3750
| 1 | Pit Builder | each | S | 1 | 1 | 1 | 3750 | 3750 |  | 3 | 0 | 0 | 0 | 3750 | 3750 | 85
| Line No 84 Item No C224 | OPEN DRAINS, INCLUDING KERB & CHANNEL
33 | Line No 85 Item No C224(c) | Concrete Lining of Open Drains | m2 |  |  |  | 5 |  | 356.1444 |  | 2 | 2.1 | 182.5444 | 11.5 | 160 | 356.1444
| 1 | Purchase Materials
| 2 | N25 | m³ | M | 1 | 1 | 0.55 | 170 | 93.5 |  |  | 0 | 93.5 | 0 | 0 | 93.5 | C25
| 3 | Sand | tonne | M | 1 | 1 | 0.75 | 24 | 18 |  |  | 0 | 18 | 0 | 0 | 18 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 6 | 9.1 | 54.6 |  |  | 0 | 54.6 | 0 | 0 | 54.6 | RSM
| 5 | Abel Flex | m | M | 1 | 1 | 4 | 3 | 12 |  |  | 0 | 12 | 0 | 0 | 12 | RSM
| 6 | Detailed Excavation:
33.1 | 7 | Excavator - 25T | hr | P | 1 | 10 | 0.5 | 135 | 6.75 | 0.05 | 0.05 | 0 | 0 | 6.75 | 0 | 6.75 | 71
| 8 | Tipper | hr | P | 1 | 10 | 0.5 | 95 | 4.75 | 0.05 | 0.05 | 0 | 0 | 4.75 | 0 | 4.75 | 71
| 9 | Labour | hr | L | 1 | 10 | 0.5 | 42 | 2.1 | 0.05 | 0.05 | 2.1 | 0 | 0 | 0 | 2.1 | 71
| 10 | Form Pour & Finish
| 11 | Bar Chairs | each | M | 1 | 1 | 5.5556 | 0.8 | 4.4444 |  |  | 0 | 4.4444 | 0 | 0 | 4.4444 | RSM
| 12 | Concrete Subbie | m² | S | 1 | 1 | 5 | 32 | 160 |  | 0.2 | 0 | 0 | 0 | 160 | 160 | 71
34 | Line No 86 Item No C224(h) | (i) Concrete Barrier Kerb & Channel B1 complete | m |  |  |  | 198 |  | 10526.2786 |  | 1 | 0 | 4586.2786 | 0 | 5940 | 10526.2786
| 1 | Use Kerb Subbie. Allciv to supply sand & cement for slurry
34.1 | 2 | S32 - Kerb Mix | m³ | M | 8.6 | 1 | 23.0233 | 190 | 4374.4186 |  |  | 0 | 4374.4186 | 0 | 0 | 4374.4186 | CKM
34.2 | 3 | Sand | tonne | M | 75 | 1 | 2.64 | 24 | 63.36 |  |  | 0 | 63.36 | 0 | 0 | 63.36 | QMS
34.3 | 4 | Cement | tonne | M | 8 | 1 | 0.33 | 450 | 148.5 |  |  | 0 | 148.5 | 0 | 0 | 148.5 | CSA
| 5 | Kerb Subbie | m | S | 1 | 1 | 198 | 30 | 5940 |  | 198 | 0 | 0 | 0 | 5940 | 5940 | 71
35 | Line No 87 Item No C224(h) | (iv) Concrete Dish Drain (0.9m wide) complete | m |  |  |  | 51 |  | 6633.57 |  | 1 | 0 | 3318.57 | 0 | 3315 | 6633.57
| 1 | Use Kerb Subbie. Allciv to supply sand & cement for slurry
35.1 | 2 | N32 | m³ | M | 3 | 1 | 17 | 192 | 3264 |  |  | 0 | 3264 | 0 | 0 | 3264 | C32
35.2 | 3 | Sand | tonne | M | 75 | 1 | 0.68 | 24 | 16.32 |  |  | 0 | 16.32 | 0 | 0 | 16.32 | QMS
35.3 | 4 | Cement | tonne | M | 8 | 1 | 0.085 | 450 | 38.25 |  |  | 0 | 38.25 | 0 | 0 | 38.25 | CSA
| 5 | Kerb Subbie - Hand | m | S | 1 | 1 | 51 | 65 | 3315 |  | 51 | 0 | 0 | 0 | 3315 | 3315 | 71
36 | Line No 88 Item No C224(h) | (vi) Concrete Kerb (Type B2) complete | m |  |  |  | 48 |  | 2551.826 |  | 1 | 0 | 1111.826 | 0 | 1440 | 2551.826
| 1 | Use Kerb Subbie. Allciv to supply sand & cement for slurry
36.1 | 2 | S32 - Kerb Mix | m³ | M | 8.6 | 1 | 5.5814 | 190 | 1060.466 |  |  | 0 | 1060.466 | 0 | 0 | 1060.466 | CKM
36.2 | 3 | Sand | tonne | M | 75 | 1 | 0.64 | 24 | 15.36 |  |  | 0 | 15.36 | 0 | 0 | 15.36 | QMS
36.3 | 4 | Cement | tonne | M | 8 | 1 | 0.08 | 450 | 36 |  |  | 0 | 36 | 0 | 0 | 36 | CSA
| 5 | Kerb Subbie | m | S | 1 | 1 | 48 | 30 | 1440 |  | 48 | 0 | 0 | 0 | 1440 | 1440 | 71
| Line No 90 Item No | SUB-SURFACE DRAINAGE
| Line No 91 Item No C232 | PAVEMENT DRAINS
37 | Line No 92 Item No C232(b) | (i) 100mm dia Slotted Corrugated Plastic Pipe | m |  |  |  | 372 |  | 15356.9917 |  | 4 | 4218.9019 | 2255.808 | 7818.3618 | 1063.92 | 15356.9917
| 1 | Excavate & install sub-soil drain at a rate of 100m per day. Use 300 trench and sand to backfill.
| 2 | Sub Soil Drain | m | M | 1 | 1 | 372 | 2.5 | 930 |  |  | 0 | 930 | 0 | 0 | 930 | 87
| 3 | Sub Soil Clean Out - Inst | each | S | 50 | 1 | 7.44 | 143 | 1063.92 |  |  | 0 | 0 | 0 | 1063.92 | 1063.92 | 87
| 4 | Sand | tonne | M | 0.1485 | 1 | 55.242 | 24 | 1325.808 |  |  | 0 | 1325.808 | 0 | 0 | 1325.808 | QMS
37.1 | 5 | Excavator - 25T | hr | P | 1 | 11.11 | 372 | 135 | 4520.252 | 33.4833 | 33.4833 | 0 | 0 | 4520.252 | 0 | 4520.252 | 87
37.2 | 6 | Labour | hr | L | 3 | 11.11 | 372 | 42 | 4218.9019 | 100.45 | 33.4833 | 4218.9019 | 0 | 0 | 0 | 4218.9019 | 87
| 7 | Bobcat | hr | P | 1 | 11.11 | 372 | 95 | 3180.9181 | 33.4833 | 33.4833 | 0 | 0 | 3180.9181 | 0 | 3180.9181 | 87
| 8 | Plate Compactor | hr | P | 1 | 11.11 | 372 | 3.5 | 117.1917 | 33.4833 | 33.4833 | 0 | 0 | 117.1917 | 0 | 117.1917 | 87
38 | Line No 93 Item No C232(c) | Cleanout Structures | each |  |  |  | 5 |  | 715 |  | 4 | 0 | 0 | 0 | 715 | 715
| 1 | Sub Soil Clean Out - Inst | each | S | 1 | 1 | 5 | 143 | 715 |  |  | 0 | 0 | 0 | 715 | 715 | 87
| Line No 95 Item No | PAVEMENTS
| Line No 96 Item No C242 | FLEXIBLE PAVEMENTS
39 | Line No 97 Item No | Place only Type 2.3 | m3 |  |  |  | 236 |  | 13363.0414 |  | 2 | 1605.9046 | 0 | 11757.1368 | 0 | 13363.0414
39.1 | 1 | Tonnes Gravel = QTY* density |  |  | 2.4 |  | 566.4
39.2 | 2 | Truck & Dog | hr | P | 3 | 37 | 566.4 | 145 | 6659.027 | 45.9243 | 15.3081 | 0 | 0 | 6659.027 | 0 | 6659.027 | 62
| 3 | Placement
39.3 | 4 | Grader | hr | P | 1 | 44.44 | 566.4 | 145 | 1848.0648 | 12.7453 | 12.7453 | 0 | 0 | 1848.0648 | 0 | 1848.0648 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 44.44 | 566.4 | 100 | 1274.5275 | 12.7453 | 12.7453 | 0 | 0 | 1274.5275 | 0 | 1274.5275 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 44.44 | 566.4 | 55 | 700.9901 | 12.7453 | 12.7453 | 0 | 0 | 700.9901 | 0 | 700.9901 | 62
| 7 | Labour | hr | L | 3 | 44.44 | 566.4 | 42 | 1605.9046 | 38.2358 | 12.7453 | 1605.9046 | 0 | 0 | 0 | 1605.9046 | 62
| 8 | Backhoe | hr | P | 1 | 44.44 | 566.4 | 100 | 1274.5275 | 12.7453 | 12.7453 | 0 | 0 | 1274.5275 | 0 | 1274.5275 | 62
40 | Line No 98 Item No | Place only Type 2.1 | m3 |  |  |  | 488 |  | 33426.4325 |  | 7 | 4838.5775 | 0 | 28587.8549 | 0 | 33426.4325
40.1 | 1 | Tonnes Gravel = QTY*density |  |  | 2.4 |  | 1171.2
| 2 | Truck & Dog | hr | P | 3 | 37 | 1171.2 | 145 | 13769.5135 | 94.9622 | 31.6541 | 0 | 0 | 13769.5135 | 0 | 13769.5135 | 62
| 3 | Placement
| 4 | Grader | hr | P | 1 | 44.4444 | 1171.2 | 145 | 3821.0438 | 26.352 | 26.352 | 0 | 0 | 3821.0438 | 0 | 3821.0438 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 44.4444 | 1171.2 | 100 | 2635.2026 | 26.352 | 26.352 | 0 | 0 | 2635.2026 | 0 | 2635.2026 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 44.4444 | 1171.2 | 55 | 1449.3614 | 26.352 | 26.352 | 0 | 0 | 1449.3614 | 0 | 1449.3614 | 62
| 7 | Labour | hr | L | 3 | 44.4444 | 1171.2 | 42 | 3320.3553 | 79.0561 | 26.352 | 3320.3553 | 0 | 0 | 0 | 3320.3553 | 62
| 8 | Backhoe | hr | P | 1 | 44.4444 | 1171.2 | 100 | 2635.2026 | 26.352 | 26.352 | 0 | 0 | 2635.2026 | 0 | 2635.2026 | 62
| 9 | Final Trim
40.2 | 10 | Grader | hr | P | 1 | 150 | 1807.4074 | 145 | 1747.1605 | 12.0494 | 12.0494 | 0 | 0 | 1747.1605 | 0 | 1747.1605 | 63
| 11 | Water Cart - Hire | hr | P | 1 | 150 | 1807.4074 | 100 | 1204.9383 | 12.0494 | 12.0494 | 0 | 0 | 1204.9383 | 0 | 1204.9383 | 63
| 12 | MW Roller | hr | P | 1 | 75 | 1807.4074 | 55 | 1325.4321 | 24.0988 | 24.0988 | 0 | 0 | 1325.4321 | 0 | 1325.4321 | 63
| 13 | Labour | hr | L | 3 | 150 | 1807.4074 | 42 | 1518.2222 | 36.1481 | 12.0494 | 1518.2222 | 0 | 0 | 0 | 1518.2222 | 63
41 | Line No 99 Item No | Special Item - Geogrid layer | m2 |  |  |  | 1953 |  | 11638.8864 |  | 1 | 474.8874 | 10805.949 | 358.05 | 0 | 11638.8864
41.1 | 1 | TX160 - Geogrid | m² | M | 1.1 | 1 | 2148.3 | 5.03 | 10805.949 |  |  | 0 | 10805.949 | 0 | 0 | 10805.949 | 222
41.2 | 2 | Labour | hr | L | 3 | 570 | 2148.3 | 42 | 474.8874 | 11.3068 | 3.7689 | 474.8874 | 0 | 0 | 0 | 474.8874 | 222
| 3 | Bobcat | hr | P | 1 | 570 | 2148.3 | 95 | 358.05 | 3.7689 | 3.7689 | 0 | 0 | 358.05 | 0 | 358.05 | 222
42 | Line No 100 Item No | Special Item - Geotextile layer | m2 |  |  |  | 1953 |  | 3088.6524 |  | 1 | 474.8874 | 2255.715 | 358.05 | 0 | 3088.6524
42.1 | 1 | A24 | m² | M | 1.1 | 1 | 2148.3 | 1.05 | 2255.715 |  |  | 0 | 2255.715 | 0 | 0 | 2255.715 | 222
| 2 | Labour | hr | L | 3 | 570 | 2148.3 | 42 | 474.8874 | 11.3068 | 3.7689 | 474.8874 | 0 | 0 | 0 | 474.8874 | 222
| 3 | Bobcat | hr | P | 1 | 570 | 2148.3 | 95 | 358.05 | 3.7689 | 3.7689 | 0 | 0 | 358.05 | 0 | 358.05 | 222
43 | Line No 101 Item No C244(a) | (vii) AMC5 | m2 |  |  |  | 1812 |  | 15430.086 |  | 1 | 0 | 0 | 0 | 15430.086 | 15430.086
43.1 | 1 | Seal Visit Two | m² | S | 1.05 | 1 | 1902.6 | 8.11 | 15430.086 |  | 1 | 0 | 0 | 0 | 15430.086 | 15430.086 | 64
| Line No 102 Item No C245(c) | Dense Graded Asphalt in Wearing Course
44 | Line No 103 Item No C245(c) | (ii) 14mm Nominal Size | tonne |  |  |  | 173 |  | 50317.05 |  | 1 | 0 | 0 | 0 | 50317.05 | 50317.05
44.1 | 1 | DG14 - Dobbins Lane | tonne | S | 1.05 | 1 | 181.65 | 277 | 50317.05 |  | 1 | 0 | 0 | 0 | 50317.05 | 50317.05 | 65
| Line No 105 Item No | MISCELLANEOUS
| Line No 106 Item No C271 | MINOR CONCRETE WORKS
45 | Line No 107 Item No C271(c) | (i) 100mm thick concrete footpath | m2 |  |  |  | 53 |  | 3775.1311 |  | 3 | 22.26 | 1934.9711 | 121.9 | 1696 | 3775.1311
| 1 | Purchase Materials
| 2 | N25 | m³ | M | 1 | 1 | 5.83 | 170 | 991.1 |  |  | 0 | 991.1 | 0 | 0 | 991.1 | C25
| 3 | Sand | tonne | M | 1 | 1 | 7.95 | 24 | 190.8 |  |  | 0 | 190.8 | 0 | 0 | 190.8 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 63.6 | 9.1 | 578.76 |  |  | 0 | 578.76 | 0 | 0 | 578.76 | RSM
| 5 | Abel Flex | m | M | 1 | 1 | 42.4 | 3 | 127.2 |  |  | 0 | 127.2 | 0 | 0 | 127.2 | RSM
| 6 | Detailed Excavation:
45.1 | 7 | Excavator - 25T | hr | P | 1 | 10 | 5.3 | 135 | 71.55 | 0.53 | 0.53 | 0 | 0 | 71.55 | 0 | 71.55 | 73
| 8 | Tipper | hr | P | 1 | 10 | 5.3 | 95 | 50.35 | 0.53 | 0.53 | 0 | 0 | 50.35 | 0 | 50.35 | 73
| 9 | Labour | hr | L | 1 | 10 | 5.3 | 42 | 22.26 | 0.53 | 0.53 | 22.26 | 0 | 0 | 0 | 22.26 | 73
| 10 | Form Pour & Finish
| 11 | Bar Chairs | each | M | 1 | 1 | 58.8889 | 0.8 | 47.1111 |  |  | 0 | 47.1111 | 0 | 0 | 47.1111 | RSM
| 12 | Concrete Subbie | m² | S | 1 | 1 | 53 | 32 | 1696 |  | 2.12 | 0 | 0 | 0 | 1696 | 1696 | 73
46 | Line No 108 Item No C271(c) | (ii) Concrete Kerb Ramp | each |  |  |  | 2 |  | 1570 |  | 1 | 0 | 170 | 0 | 1400 | 1570
| 1 | N25 | m³ | M | 1 | 1 | 1 | 170 | 170 |  |  | 0 | 170 | 0 | 0 | 170 | C25
| 2 | Pram Ramps | each | S | 1 | 1 | 2 | 700 | 1400 |  | 1 | 0 | 0 | 0 | 1400 | 1400 | 73
47 | Line No 109 Item No C271(c) | (v) Industrial Invert Crossing | each |  |  |  | 1 |  | 1534.57 |  | 2 | 7.56 | 909.61 | 41.4 | 576 | 1534.57
| 1 | Purchase Materials
18 sqm per invert; 175mm thick, 10% concrete waste
| 2 | N25 | m³ | M | 1 | 1 | 3.465 | 170 | 589.05 |  |  | 0 | 589.05 | 0 | 0 | 589.05 | C25
| 3 | Sand | tonne | M | 1 | 1 | 2.7 | 24 | 64.8 |  |  | 0 | 64.8 | 0 | 0 | 64.8 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 21.6 | 9.1 | 196.56 |  |  | 0 | 196.56 | 0 | 0 | 196.56 | RSM
| 5 | Abel Flex | m | M | 1 | 1 | 14.4 | 3 | 43.2 |  |  | 0 | 43.2 | 0 | 0 | 43.2 | RSM
| 6 | Detailed Excavation:
47.1 | 7 | Excavator - 25T | hr | P | 1 | 10 | 1.8 | 135 | 24.3 | 0.18 | 0.18 | 0 | 0 | 24.3 | 0 | 24.3 | 73
| 8 | Tipper | hr | P | 1 | 10 | 1.8 | 95 | 17.1 | 0.18 | 0.18 | 0 | 0 | 17.1 | 0 | 17.1 | 73
| 9 | Labour | hr | L | 1 | 10 | 1.8 | 42 | 7.56 | 0.18 | 0.18 | 7.56 | 0 | 0 | 0 | 7.56 | 73
| 10 | Form Pour & Finish
| 11 | Bar Chairs | each | M | 1 | 1 | 20 | 0.8 | 16 |  |  | 0 | 16 | 0 | 0 | 16 | RSM
| 12 | Concrete Subbie | m² | S | 1 | 1 | 18 | 32 | 576 |  | 0.72 | 0 | 0 | 0 | 576 | 576 | 73
| Line No 110 Item No C273 | LANDSCAPE
48 | Line No 111 Item No C273(a) | (ii) Turfing | m2 |  |  |  | 150 |  | 1338.75 |  | 1 | 0 | 0 | 0 | 1338.75 | 1338.75
48.1 | 1 | Turf Subbie | m² | S | 1.05 | 1 | 157.5 | 8.5 | 1338.75 |  | 0.01575 | 0 | 0 | 0 | 1338.75 | 1338.75 | 121
49 | Line No 112 Item No | Supply and place Imported Topsoil | m3 |  |  |  | 15 |  | 972.5 |  | 1 | 210 | 525 | 237.5 | 0 | 972.5
| 1 | Topsoil | m³ | M | 1 | 1 | 15 | 35 | 525 |  |  | 0 | 525 | 0 | 0 | 525 | 33
49.1 | 2 | Bobcat | hr | P | 1 | 6 | 15 | 95 | 237.5 | 2.5 | 2.5 | 0 | 0 | 237.5 | 0 | 237.5 | 33
| 3 | Labour | hr | L | 2 | 6 | 15 | 42 | 210 | 5 | 2.5 | 210 | 0 | 0 | 0 | 210 | 33
| Line No 114 Item No | SPECIFIED WORKS
50 | Line No 115 Item No | Special Item - As Constructed Survey and Plans | Lump |  |  |  | 1 |  | 4500 |  | 4 | 0 | 0 | 0 | 4500 | 4500
| 1 | Survey | Item | S | 1 | 1 | 4500 | 1 | 4500 |  | 36 | 0 | 0 | 0 | 4500 | 4500 | 12
300 | Line No 119 Item No | CULTURAL CENTRE CAR PARK
| Line No 121 Item No | QUALITY SYSTEM
| Line No 122 Item No CQC | QUALITY CONTROL REQUIREMENTS
51 | Line No 123 Item No QCP1 | Quality Verification & Control | Lump |  |  |  | 1 |  | 8360 |  | 0 | 3250 | 0 | 0 | 5110 | 8360
Tasks ongoing throughout project
| 1 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 | 1 | 1 | 3250 | 0 | 0 | 0 | 3250 | 901
51.1 | 2 | (12) Field Density Tests |  |  |  |  | 12
51.2 | 3 | (6) Concrete Cylinder Sets |  |  |  |  | 6
| 4 | Field Density | each | S | 1 | 1 | 12 | 45 | 540 |  |  | 0 | 0 | 0 | 540 | 540 | 13
| 5 | Gravel Properties Testing | each | S | 1 | 1 | 3 | 390 | 1170 |  |  | 0 | 0 | 0 | 1170 | 1170 | 13
| 6 | Concrete Cylinders | each | S | 1 | 1 | 6 | 150 | 900 |  |  | 0 | 0 | 0 | 900 | 900 | 13
51.3 | 7 | Survey | Item | S | 1 | 1 | 2500 | 1 | 2500 |  | 20 | 0 | 0 | 0 | 2500 | 2500 | 11
| Line No 125 Item No | GENERAL REQUIREMENTS
52 | Line No 126 Item No C201(a) | Control of Traffic | Lump |  |  |  | 1 |  | 11646.24 |  | 10 | 0 | 0 | 0 | 11646.24 | 11646.24
52.1 | 1 | (2) No. Weeks TC Required |  |  | 2 |  | 2
| 2 | Traffic Control Crew | hr | S | 6 | 1 | 114 | 102.16 | 11646.24 |  | 10 | 0 | 0 | 0 | 11646.24 | 11646.24 | 141
| Line No 128 Item No | ROAD & EARTHWORKS
| Line No 129 Item No C213 | EARTHWORKS
53 | Line No 130 Item No C213(b) | General Earthworks Cut | m3 |  |  |  | 869 |  | 19053.614 |  | 4 | 1972.9246 | 0 | 17080.6895 | 0 | 19053.614
53.1 | 1 | Excavator - 25T | hr | P | 1 | 40 | 869 | 135 | 2932.875 | 21.725 | 21.725 | 0 | 0 | 2932.875 | 0 | 2932.875 | 53
53.2 | 2 | Truck & Dog | hr | P | 3 | 40 | 869 | 145 | 9450.375 | 65.175 | 21.725 | 0 | 0 | 9450.375 | 0 | 9450.375 | 53
| 3 | Water Cart - Hire | hr | P | 1 | 40 | 869 | 100 | 2172.5 | 21.725 | 21.725 | 0 | 0 | 2172.5 | 0 | 2172.5 | 53
| 4 | Labour | hr | L | 1 | 40 | 869 | 42 | 912.45 | 21.725 | 21.725 | 912.45 | 0 | 0 | 0 | 912.45 | 53
| 5 | Prepare Sub-grade
53.3 | 6 | Grader | hr | P | 1 | 250 | 2104.1162 | 145 | 1220.3874 | 8.4165 | 8.4165 | 0 | 0 | 1220.3874 | 0 | 1220.3874 | 61
| 7 | Water Cart - Hire | hr | P | 1 | 250 | 2104.1162 | 100 | 841.6465 | 8.4165 | 8.4165 | 0 | 0 | 841.6465 | 0 | 841.6465 | 61
| 8 | SD Roller - Wet (No Op) | hr | P | 1 | 250 | 2104.1162 | 55 | 462.9056 | 8.4165 | 8.4165 | 0 | 0 | 462.9056 | 0 | 462.9056 | 61
53.4 | 9 | Labour | hr | L | 3 | 250 | 2104.1162 | 42 | 1060.4746 | 25.2494 | 8.4165 | 1060.4746 | 0 | 0 | 0 | 1060.4746 | 61
54 | Line No 131 Item No C213(c) | General Earthworks Fill | m3 |  |  |  | 4 |  | 112.2 |  | 1 | 25.2 | 0 | 87 | 0 | 112.2
54.1 | 1 | Excavator - 25T | hr | P | 1 | 20 | 4 | 135 | 27 | 0.2 | 0.2 | 0 | 0 | 27 | 0 | 27 | 53
| 2 | Grader | hr | P | 1 | 20 | 4 | 145 | 29 | 0.2 | 0.2 | 0 | 0 | 29 | 0 | 29 | 53
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 20 | 4 | 55 | 11 | 0.2 | 0.2 | 0 | 0 | 11 | 0 | 11 | 53
| 4 | Water Cart - Hire | hr | P | 1 | 20 | 4 | 100 | 20 | 0.2 | 0.2 | 0 | 0 | 20 | 0 | 20 | 53
54.2 | 5 | Labour | hr | L | 3 | 20 | 4 | 42 | 25.2 | 0.6 | 0.2 | 25.2 | 0 | 0 | 0 | 25.2 | 53
55 | Line No 132 Item No C213(d) | Replace unsuitable material below sub grade with select material complete (PROVISIONAL) | m3 |  |  |  | 10 |  | 655.3333 |  | 1 | 112 | 0 | 543.3333 | 0 | 655.3333
55.1 | 1 | Excavator - 25T | hr | P | 1 | 15 | 10 | 135 | 90 | 0.66667 | 0.66667 | 0 | 0 | 90 | 0 | 90 | 57
| 2 | Truck & Dog | hr | P | 2 | 15 | 10 | 145 | 193.3333 | 1.3333 | 0.66667 | 0 | 0 | 193.3333 | 0 | 193.3333 | 57
| 3 | Water Cart - Hire | hr | P | 1 | 15 | 10 | 100 | 66.6667 | 0.66667 | 0.66667 | 0 | 0 | 66.6667 | 0 | 66.6667 | 57
| 4 | Labour | hr | L | 1 | 15 | 10 | 42 | 28 | 0.66667 | 0.66667 | 28 | 0 | 0 | 0 | 28 | 57
| 5 | Fill
55.2 | 6 | Excavator - 25T | hr | P | 1 | 15 | 10 | 135 | 90 | 0.66667 | 0.66667 | 0 | 0 | 90 | 0 | 90 | 57
| 7 | SD Roller - Wet (No Op) | hr | P | 1 | 15 | 10 | 55 | 36.6667 | 0.66667 | 0.66667 | 0 | 0 | 36.6667 | 0 | 36.6667 | 57
| 8 | Water Cart - Hire | hr | P | 1 | 15 | 10 | 100 | 66.6667 | 0.66667 | 0.66667 | 0 | 0 | 66.6667 | 0 | 66.6667 | 57
55.3 | 9 | Labour | hr | L | 3 | 15 | 10 | 42 | 84 | 2 | 0.66667 | 84 | 0 | 0 | 0 | 84 | 57
56 | Line No 133 Item No | Alteration to Existing Stormwater Structures (Break new PVC pipt into existing line and andage) | Lump |  |  |  | 1 |  | 1200 |  | 1 | 0 | 0 | 0 | 1200 | 1200
| 1 | Pit Builder - Modify | each | S | 1 | 1 | 1 | 1200 | 1200 |  | 1 | 0 | 0 | 0 | 1200 | 1200 | 85
57 | Line No 134 Item No C221(a) | UPVC pipes (150mm) supply, install, backfill complete | m |  |  |  | 21 |  | 2628 |  | 1 | 630 | 1323 | 675 | 0 | 2628
57.1 | 1 | Excavator - 25T | hr | P | 1 | 4.2 | 21 | 135 | 675 | 5 | 5 | 0 | 0 | 675 | 0 | 675 | 81
| 2 | 300 RCP | m | M | 1 | 1 | 21 | 55 | 1155 |  |  | 0 | 1155 | 0 | 0 | 1155 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 7 | 24 | 168 |  |  | 0 | 168 | 0 | 0 | 168 | QMS
| 4 | Labour | hr | L | 3 | 4.2 | 21 | 42 | 630 | 15 | 5 | 630 | 0 | 0 | 0 | 630 | 81
58 | Line No 135 Item No C221(a) | Connect property drainage pipes | Lump |  |  |  | 1 |  | 3950 |  | 3 | 0 | 2250 | 0 | 1700 | 3950
| 1 | No. properties = 10 |  |  |  |  | 10
| 2 | 150 SN8 Sewer Pipe | m | M | 1 | 1 | 60 | 25 | 1500 |  |  | 0 | 1500 | 0 | 0 | 1500 | SWP
| 3 | Kerb Adaptors | each | M | 1 | 1 | 10 | 75 | 750 |  |  | 0 | 750 | 0 | 0 | 750 | SWP
58.1 | 4 | Plumber | hr | S | 1 | 0.5 | 10 | 85 | 1700 | 20 | 20 | 0 | 0 | 0 | 1700 | 1700 | 81
59 | Line No 136 Item No C223(b) | Construct Complete in place, downpipe extension and overflow grate | each |  |  |  | 1 |  | 2400 |  | 2 | 0 | 0 | 0 | 2400 | 2400
| 1 | Pit Builder - Modify | each | S | 1 | 1 | 2 | 1200 | 2400 | 2 | 2 | 0 | 0 | 0 | 2400 | 2400 | 85
60 | Line No 137 Item No C224(h) | (i) Concrete Barrier Kerb & Channel B1 complete | m |  |  |  | 80 |  | 4253.0419 |  | 1 | 0 | 1853.0419 | 0 | 2400 | 4253.0419
| 1 | Use Kerb Subbie. Allciv to supply sand & cement for slurry
60.1 | 2 | S32 - Kerb Mix | m³ | M | 8.6 | 1 | 9.3023 | 190 | 1767.4419 |  |  | 0 | 1767.4419 | 0 | 0 | 1767.4419 | CKM
60.2 | 3 | Sand | tonne | M | 75 | 1 | 1.0667 | 24 | 25.6 |  |  | 0 | 25.6 | 0 | 0 | 25.6 | QMS
60.3 | 4 | Cement | tonne | M | 8 | 1 | 0.13333 | 450 | 60 |  |  | 0 | 60 | 0 | 0 | 60 | CSA
| 5 | Kerb Subbie | m | S | 1 | 1 | 80 | 30 | 2400 |  | 0.4 | 0 | 0 | 0 | 2400 | 2400 | 71
61 | Line No 138 Item No C224(h) | (iv) Concrete Dish Drain (0.9m wide) complete | m |  |  |  | 12 |  | 1560.84 |  | 1 | 0 | 780.84 | 0 | 780 | 1560.84
| 1 | Use Kerb Subbie. Allciv to supply sand & cement for slurry
61.1 | 2 | N32 | m³ | M | 3 | 1 | 4 | 192 | 768 |  |  | 0 | 768 | 0 | 0 | 768 | C32
61.2 | 3 | Sand | tonne | M | 75 | 1 | 0.16 | 24 | 3.84 |  |  | 0 | 3.84 | 0 | 0 | 3.84 | QMS
61.3 | 4 | Cement | tonne | M | 8 | 1 | 0.02 | 450 | 9 |  |  | 0 | 9 | 0 | 0 | 9 | CSA
| 5 | Kerb Subbie - Hand | m | S | 1 | 1 | 12 | 65 | 780 |  | 0.06 | 0 | 0 | 0 | 780 | 780 | 71
62 | Line No 139 Item No C224(h) | (vi) Concrete Kerb (Type B2) complete | m |  |  |  | 81 |  | 4306.2049 |  | 1 | 0 | 1876.2049 | 0 | 2430 | 4306.2049
| 1 | Use Kerb Subbie. Allciv to supply sand & cement for slurry
62.1 | 2 | S32 - Kerb Mix | m³ | M | 8.6 | 1 | 9.4186 | 190 | 1789.5349 |  |  | 0 | 1789.5349 | 0 | 0 | 1789.5349 | CKM
62.2 | 3 | Sand | tonne | M | 75 | 1 | 1.08 | 24 | 25.92 |  |  | 0 | 25.92 | 0 | 0 | 25.92 | QMS
62.3 | 4 | Cement | tonne | M | 8 | 1 | 0.135 | 450 | 60.75 |  |  | 0 | 60.75 | 0 | 0 | 60.75 | CSA
| 5 | Kerb Subbie | m | S | 1 | 1 | 81 | 30 | 2430 |  | 0.405 | 0 | 0 | 0 | 2430 | 2430 | 71
| Line No 140 Item No C232(b) | Subsoil Drain Pipe
63 | Line No 141 Item No C232(b) | (i) 100mm dia Slotted Corrugated Plastic Pipe | m |  |  |  | 312 |  | 12880.0576 |  | 4 | 3538.4338 | 1891.968 | 6557.3357 | 892.32 | 12880.0576
| 1 | Excavate & install sub-soil drain at a rate of 100m per day. Use 300 trench and sand to backfill.
| 2 | Sub Soil Drain | m | M | 1 | 1 | 312 | 2.5 | 780 |  |  | 0 | 780 | 0 | 0 | 780 | 87
| 3 | Sub Soil Clean Out - Inst | each | S | 1 | 1 | 6.24 | 143 | 892.32 |  |  | 0 | 0 | 0 | 892.32 | 892.32 | 87
| 4 | Sand | tonne | M | 1 | 1 | 46.332 | 24 | 1111.968 |  |  | 0 | 1111.968 | 0 | 0 | 1111.968 | QMS
63.1 | 5 | Excavator - 25T | hr | P | 1 | 11.11 | 312 | 135 | 3791.1791 | 28.0828 | 28.0828 | 0 | 0 | 3791.1791 | 0 | 3791.1791 | 87
| 6 | Labour | hr | L | 3 | 11.11 | 312 | 42 | 3538.4338 | 84.2484 | 28.0828 | 3538.4338 | 0 | 0 | 0 | 3538.4338 | 87
| 7 | Bobcat | hr | P | 1 | 11.11 | 312 | 95 | 2667.8668 | 28.0828 | 28.0828 | 0 | 0 | 2667.8668 | 0 | 2667.8668 | 87
| 8 | Plate Compactor | hr | P | 1 | 11.11 | 312 | 3.5 | 98.2898 | 28.0828 | 28.0828 | 0 | 0 | 98.2898 | 0 | 98.2898 | 87
64 | Line No 142 Item No C232(c) | Cleanout Structures | each |  |  |  | 5 |  | 715 |  | 4 | 0 | 0 | 0 | 715 | 715
| 1 | Sub Soil Clean Out - Inst | each | S | 1 | 1 | 5 | 143 | 715 |  |  | 0 | 0 | 0 | 715 | 715 | 87
| Line No 144 Item No C242 | FLEXIBLE PAVEMENTS
65 | Line No 145 Item No | Place only Type 2.1 | m3 |  |  |  | 314 |  | 24537.3132 |  | 6 | 3906.871 | 0 | 20630.4422 | 0 | 24537.3132
65.1 | 1 | Tonnes Gravel = QTY*density |  |  | 2.4 |  | 753.6
65.2 | 2 | Truck & Dog | hr | P | 3 | 37 | 753.6 | 145 | 8859.8919 | 61.1027 | 20.3676 | 0 | 0 | 8859.8919 | 0 | 8859.8919 | 62
| 3 | Placement
65.3 | 4 | Grader | hr | P | 1 | 44.44 | 753.6 | 145 | 2458.8659 | 16.9577 | 16.9577 | 0 | 0 | 2458.8659 | 0 | 2458.8659 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 44.44 | 753.6 | 100 | 1695.7696 | 16.9577 | 16.9577 | 0 | 0 | 1695.7696 | 0 | 1695.7696 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 44.44 | 753.6 | 55 | 932.6733 | 16.9577 | 16.9577 | 0 | 0 | 932.6733 | 0 | 932.6733 | 62
| 7 | Labour | hr | L | 3 | 44.44 | 753.6 | 42 | 2136.6697 | 50.8731 | 16.9577 | 2136.6697 | 0 | 0 | 0 | 2136.6697 | 62
| 8 | Backhoe | hr | P | 1 | 44.44 | 753.6 | 100 | 1695.7696 | 16.9577 | 16.9577 | 0 | 0 | 1695.7696 | 0 | 1695.7696 | 62
| 9 | Final Trim
65.4 | 10 | Grader | hr | P | 1 | 150 | 2107.3826 | 145 | 2037.1365 | 14.0492 | 14.0492 | 0 | 0 | 2037.1365 | 0 | 2037.1365 | 63
| 11 | Water Cart - Hire | hr | P | 1 | 150 | 2107.3826 | 100 | 1404.9217 | 14.0492 | 14.0492 | 0 | 0 | 1404.9217 | 0 | 1404.9217 | 63
| 12 | MW Roller | hr | P | 1 | 75 | 2107.3826 | 55 | 1545.4139 | 28.0984 | 28.0984 | 0 | 0 | 1545.4139 | 0 | 1545.4139 | 63
| 13 | Labour | hr | L | 3 | 150 | 2107.3826 | 42 | 1770.2013 | 42.1477 | 14.0492 | 1770.2013 | 0 | 0 | 0 | 1770.2013 | 63
66 | Line No 146 Item No | Place only Type 2.3 | m3 |  |  |  | 187 |  | 10588.5116 |  | 2 | 1272.4752 | 0 | 9316.0364 | 0 | 10588.5116
66.1 | 1 | Tonnes Gravel = QTY*density |  |  | 2.4 |  | 448.8
66.2 | 2 | Truck & Dog | hr | P | 3 | 37 | 448.8 | 145 | 5276.4324 | 36.3892 | 12.1297 | 0 | 0 | 5276.4324 | 0 | 5276.4324 | 62
| 3 | Placement
66.3 | 4 | Grader | hr | P | 1 | 44.44 | 448.8 | 145 | 1464.3564 | 10.099 | 10.099 | 0 | 0 | 1464.3564 | 0 | 1464.3564 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 44.44 | 448.8 | 100 | 1009.901 | 10.099 | 10.099 | 0 | 0 | 1009.901 | 0 | 1009.901 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 44.44 | 448.8 | 55 | 555.4455 | 10.099 | 10.099 | 0 | 0 | 555.4455 | 0 | 555.4455 | 62
| 7 | Labour | hr | L | 3 | 44.44 | 448.8 | 42 | 1272.4752 | 30.297 | 10.099 | 1272.4752 | 0 | 0 | 0 | 1272.4752 | 62
| 8 | Backhoe | hr | P | 1 | 44.44 | 448.8 | 100 | 1009.901 | 10.099 | 10.099 | 0 | 0 | 1009.901 | 0 | 1009.901 | 62
67 | Line No 147 Item No | Special Item - Geogrid layer | m2 |  |  |  | 2103 |  | 12532.8101 |  | 1 | 511.3611 | 11635.899 | 385.55 | 0 | 12532.8101
67.1 | 1 | TX160 - Geogrid | m² | M | 1.1 | 1 | 2313.3 | 5.03 | 11635.899 |  |  | 0 | 11635.899 | 0 | 0 | 11635.899 | 222
67.2 | 2 | Labour | hr | L | 3 | 570 | 2313.3 | 42 | 511.3611 | 12.1753 | 4.0584 | 511.3611 | 0 | 0 | 0 | 511.3611 | 222
| 3 | Bobcat | hr | P | 1 | 570 | 2313.3 | 95 | 385.55 | 4.0584 | 4.0584 | 0 | 0 | 385.55 | 0 | 385.55 | 222
68 | Line No 148 Item No | Special Item - Geotextile layer | m2 |  |  |  | 2103 |  | 3325.8761 |  | 1 | 511.3611 | 2428.965 | 385.55 | 0 | 3325.8761
68.1 | 1 | A24 | m² | M | 1.1 | 1 | 2313.3 | 1.05 | 2428.965 |  |  | 0 | 2428.965 | 0 | 0 | 2428.965 | 222
68.2 | 2 | Labour | hr | L | 3 | 570 | 2313.3 | 42 | 511.3611 | 12.1753 | 4.0584 | 511.3611 | 0 | 0 | 0 | 511.3611 | 222
| 3 | Bobcat | hr | P | 1 | 570 | 2313.3 | 95 | 385.55 | 4.0584 | 4.0584 | 0 | 0 | 385.55 | 0 | 385.55 | 222
69 | Line No 149 Item No C244(a) | (vii) AMC5 | m2 |  |  |  | 2103 |  | 16781.94 |  | 1 | 0 | 0 | 0 | 16781.94 | 16781.94
69.1 | 1 | Seal Visit Three | m² | S | 1.05 | 1 | 2208.15 | 7.6 | 16781.94 |  | 0.27602 | 0 | 0 | 0 | 16781.94 | 16781.94 | 64
70 | Line No 150 Item No C245(c) | (ii) 14mm Nominal Size | tonne |  |  |  | 202 |  | 58539.6 |  | 1 | 0 | 0 | 0 | 58539.6 | 58539.6
| 1 | DG14 - CCCP | tonne | S | 1.05 | 1 | 212.1 | 276 | 58539.6 |  | 0.8484 | 0 | 0 | 0 | 58539.6 | 58539.6 | 65
| Line No 152 Item No C261 | PAVEMENT MARKINGS
71 | Line No 153 Item No C261(a) | Pavement Marking Paint - Longitudinal Lines including car parking bays | m |  |  |  | 434 |  | 5000 |  | 1 | 0 | 0 | 0 | 5000 | 5000
| 1 | Line Marking | m² | S | 1 | 1 | 5000 | 1 | 5000 |  |  | 0 | 0 | 0 | 5000 | 5000 | 66
72 | Line No 154 Item No C261(b) | Pavement Marking Paint - Transverse Lines, Symbols, Legends, Arrows, Chevrons, Traffic Islands & Kerbs | Item |  |  |  | 1 |  | 1500 |  | 1 | 0 | 0 | 0 | 1500 | 1500
| 1 | Line Marking | m² | S | 1 | 1 | 1500 | 1 | 1500 |  |  | 0 | 0 | 0 | 1500 | 1500 | 66
73 | Line No 155 Item No C271(c) | (i) 100mm thick concrete footpath | m2 |  |  |  | 180 |  | 12821.2 |  | 5 | 75.6 | 6571.6 | 414 | 5760 | 12821.2
| 1 | Purchase Materials
| 2 | N25 | m³ | M | 1 | 1 | 19.8 | 170 | 3366 |  |  | 0 | 3366 | 0 | 0 | 3366 | C25
| 3 | Sand | tonne | M | 1 | 1 | 27 | 24 | 648 |  |  | 0 | 648 | 0 | 0 | 648 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 216 | 9.1 | 1965.6 |  |  | 0 | 1965.6 | 0 | 0 | 1965.6 | RSM
| 5 | Abel Flex | m | M | 1 | 1 | 144 | 3 | 432 |  |  | 0 | 432 | 0 | 0 | 432 | RSM
| 6 | Detailed Excavation:
73.1 | 7 | Excavator - 25T | hr | P | 1 | 10 | 18 | 135 | 243 | 1.8 | 1.8 | 0 | 0 | 243 | 0 | 243 | 71
| 8 | Tipper | hr | P | 1 | 10 | 18 | 95 | 171 | 1.8 | 1.8 | 0 | 0 | 171 | 0 | 171 | 71
| 9 | Labour | hr | L | 1 | 10 | 18 | 42 | 75.6 | 1.8 | 1.8 | 75.6 | 0 | 0 | 0 | 75.6 | 71
| 10 | Form Pour & Finish
| 11 | Bar Chairs | each | M | 1 | 1 | 200 | 0.8 | 160 |  |  | 0 | 160 | 0 | 0 | 160 | RSM
| 12 | Concrete Subbie | m² | S | 1 | 1 | 180 | 32 | 5760 |  | 3.6 | 0 | 0 | 0 | 5760 | 5760 | 71
74 | Line No 156 Item No C271(c) | (ii) Concrete Kerb Ramp | each |  |  |  | 5 |  | 3925 |  | 3 | 0 | 425 | 0 | 3500 | 3925
| 1 | N25 | m³ | M | 1 | 1 | 2.5 | 170 | 425 |  |  | 0 | 425 | 0 | 0 | 425 | C25
| 2 | Pram Ramps | each | S | 1 | 1 | 5 | 700 | 3500 |  | 2.5 | 0 | 0 | 0 | 3500 | 3500 | 71
75 | Line No 157 Item No C271(c) | (iv) Residential Invert Crossing | each |  |  |  | 1 |  | 620.4533 |  | 2 | 25.2 | 265.2533 | 138 | 192 | 620.4533
| 1 | Purchase Materials: 6 sqm per invert, 125mm thick, 10% wastage, 1 chair / 0.9 sqm
| 2 | N32 | m³ | M | 1 | 1 | 0.825 | 192 | 158.4 |  |  | 0 | 158.4 | 0 | 0 | 158.4 | C32
| 3 | Sand | tonne | M | 1 | 1 | 0.9 | 24 | 21.6 |  |  | 0 | 21.6 | 0 | 0 | 21.6 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 7.2 | 9.1 | 65.52 |  |  | 0 | 65.52 | 0 | 0 | 65.52 | RSM
| 5 | Abel Flex | m | M | 1 | 1 | 4.8 | 3 | 14.4 |  |  | 0 | 14.4 | 0 | 0 | 14.4 | RSM
| 6 | Detailed Excavation:
75.1 | 7 | Excavator - 25T | hr | P | 1 | 1 | 0.6 | 135 | 81 | 0.6 | 0.6 | 0 | 0 | 81 | 0 | 81 | 71
| 8 | Tipper | hr | P | 1 | 1 | 0.6 | 95 | 57 | 0.6 | 0.6 | 0 | 0 | 57 | 0 | 57 | 71
| 9 | Labour | hr | L | 1 | 1 | 0.6 | 42 | 25.2 | 0.6 | 0.6 | 25.2 | 0 | 0 | 0 | 25.2 | 71
| 10 | Form Pour & Finish
| 11 | Bar Chairs | each | M | 1 | 1 | 6.6667 | 0.8 | 5.3333 |  |  | 0 | 5.3333 | 0 | 0 | 5.3333 | RSM
| 12 | Concrete Subbie | m² | S | 1 | 1 | 6 | 32 | 192 |  | 0.24 | 0 | 0 | 0 | 192 | 192 | 71
76 | Line No 158 Item No C271(c) | (v) Industrial Invert Crossing | each |  |  |  | 1 |  | 1534.57 |  | 2 | 7.56 | 909.61 | 41.4 | 576 | 1534.57
| 1 | Purchase Materials: 18 sqm per invert, 175mm thick, 10% wastage, 1 chair / 0.9 sqm
| 2 | N25 | m³ | M | 1 | 1 | 3.465 | 170 | 589.05 |  |  | 0 | 589.05 | 0 | 0 | 589.05 | C25
| 3 | Sand | tonne | M | 1 | 1 | 2.7 | 24 | 64.8 |  |  | 0 | 64.8 | 0 | 0 | 64.8 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 21.6 | 9.1 | 196.56 |  |  | 0 | 196.56 | 0 | 0 | 196.56 | RSM
| 5 | Abel Flex | m | M | 1 | 1 | 14.4 | 3 | 43.2 |  |  | 0 | 43.2 | 0 | 0 | 43.2 | RSM
| 6 | Detailed Excavation:
76.1 | 7 | Excavator - 25T | hr | P | 1 | 10 | 1.8 | 135 | 24.3 | 0.18 | 0.18 | 0 | 0 | 24.3 | 0 | 24.3 | 71
| 8 | Tipper | hr | P | 1 | 10 | 1.8 | 95 | 17.1 | 0.18 | 0.18 | 0 | 0 | 17.1 | 0 | 17.1 | 71
| 9 | Labour | hr | L | 1 | 10 | 1.8 | 42 | 7.56 | 0.18 | 0.18 | 7.56 | 0 | 0 | 0 | 7.56 | 71
| 10 | Form Pour & Finish
| 11 | Bar Chairs | each | M | 1 | 1 | 20 | 0.8 | 16 |  |  | 0 | 16 | 0 | 0 | 16 | RSM
| 12 | Concrete Subbie | m² | S | 1 | 1 | 18 | 32 | 576 |  | 0.72 | 0 | 0 | 0 | 576 | 576 | 71
77 | Line No 159 Item No | Special Item - Supply & Install Tactile Marking | Lump |  |  |  | 1 |  | 5000 |  | 1 | 0 | 0 | 0 | 5000 | 5000
| 1 | TGSI | Item | S | 1 | 1 | 125 | 40 | 5000 |  |  | 0 | 0 | 0 | 5000 | 5000 | 67
| Line No 161 Item No | SPECIFIED WORKS | [9 empty] | Contributing
78 | Line No 162 Item No | Special Item - As Constructed Survey and Plans | Lump |  |  |  | 1 |  | 2500 |  | 3 | 0 | 0 | 0 | 2500 | 2500
| 1 | Survey | Item | S | 1 | 1 | 2500 | 1 | 2500 |  | 20 | 0 | 0 | 0 | 2500 | 2500 | 12
400 | Line No 166 Item No | DOBBINS LANE WATER MAIN | [9 empty] | Contributing
79 | Line No 168 Item No 1. | Excavate and backfil all materials for following diameter water mains, approved backfill under roads, testing of backfill compaction, disposal of surplus materials and restoration of surfaces: | m |  |  |  | 156 |  | 7020 |  | 2 | 0 | 0 | 0 | 7020 | 7020
| 1 | WDC | Item | S | 1 | 1 | 7020 | 1 | 7020 |  | 1.56 | 0 | 0 | 0 | 7020 | 7020 | 103
| Line No 169 Item No 2. | Supply & place materials, following diameter water mains | [9 empty] | Contributing
80 | Line No 170 Item No | 100mm dia. DICL Class PN35 | m |  |  |  | 156 |  | 39000 |  | 2 | 0 | 0 | 0 | 39000 | 39000
| 1 | WDC | Item | S | 1 | 1 | 39000 | 1 | 39000 |  | 1.56 | 0 | 0 | 0 | 39000 | 39000 | 103
| Line No 171 Item No 3. | Supply materials and install hydrants to the following diameter mains complete including hydrant tee/bend, riser, hydrant box, concrete surround and kerb/pavement marking:
81 | Line No 172 Item No | 100mm dia. | No. |  |  |  | 2 |  | 4000 |  | 1 | 0 | 0 | 0 | 4000 | 4000
| 1 | WDC | Item | S | 1 | 1 | 4000 | 1 | 4000 |  | 1 | 0 | 0 | 0 | 4000 | 4000 | 103
| Line No 173 Item No 4. | Supply materials and install sluice valves to the following diameter mains complete including jointing, margin setts, boxes and kerb/pavement marking
81.5 | Line No 174 Item No | 100mm dia. | No. |  |  |  | 3 |  | 6000 |  | 2 | 0 | 0 | 0 | 6000 | 6000
| 1 | WDC | Item | S | 1 | 1 | 6000 | 1 | 6000 |  | 1.5 | 0 | 0 | 0 | 6000 | 6000 | 103
| Line No 175 Item No 5. | Supply materials and install the following internally lined and externally coated DICL fittings including bed, lay, joint, backfill and thrust blocks:
| Line No 176 Item No | Tee:
82 | Line No 177 Item No | 100mm x 100mm. | No. |  |  |  | 1 |  | 220 |  | 1 | 0 | 0 | 0 | 220 | 220
| 1 | WDC | Item | S | 1 | 1 | 220 | 1 | 220 |  | 0.5 | 0 | 0 | 0 | 220 | 220 | 103
| Line No 178 Item No | Bend:
83 | Line No 179 Item No | 100mm x 45 degree. | No. |  |  |  | 6 |  | 960 |  | 3 | 0 | 0 | 0 | 960 | 960
| 1 | WDC | Item | S | 1 | 1 | 960 | 1 | 960 |  | 3 | 0 | 0 | 0 | 960 | 960 | 103
| Line No 180 Item No | Gibault:
84 | Line No 181 Item No | 100mm | No. |  |  |  | 3 |  | 800 |  | 2 | 0 | 0 | 0 | 800 | 800
| 1 | WDC | Item | S | 1 | 1 | 800 | 1 | 800 |  | 1.5 | 0 | 0 | 0 | 800 | 800 | 103
| Line No 182 Item No | Thrust Flange:
85 | Line No 183 Item No | 100mm | No. |  |  |  | 1 |  | 250 |  | 1 | 0 | 0 | 0 | 250 | 250
| 1 | WDC | Item | S | 1 | 1 | 250 | 1 | 250 |  | 0.5 | 0 | 0 | 0 | 250 | 250 | 103
| Line No 184 Item No 6. | Supply materials and install property service connections
86 | Line No 185 Item No | Single connection with road crossing | No. |  |  |  | 4 |  | 8400 |  | 4 | 0 | 0 | 0 | 8400 | 8400
| 1 | WDC | Item | S | 1 | 1 | 8400 | 1 | 8400 |  | 4 | 0 | 0 | 0 | 8400 | 8400 | 103
87 | Line No 186 Item No | Double connection with road crossing | No. |  |  |  | 2 |  | 4320 |  | 2 | 0 | 0 | 0 | 4320 | 4320
| 1 | WDC | Item | S | 1 | 1 | 4320 | 1 | 4320 |  | 2 | 0 | 0 | 0 | 4320 | 4320 | 103
88 | Line No 187 Item No 7. | Sterilisation of mains including supply of chlorine, water for chlorination and bacteriological sampling and testing. | Item |  |  |  | 1 |  | 2000 |  | 3 | 0 | 0 | 0 | 2000 | 2000
| 1 | WDC | Item | S | 1 | 1 | 2000 | 1 | 2000 |  | 3 | 0 | 0 | 0 | 2000 | 2000 | 103
89 | Line No 188 Item No 8. | Locate existing water main and arrange connection of new water main. (Work by WRC). | PC It |  |  |  | 1 |  | 5400 |  | 1 | 0 | 0 | 0 | 5400 | 5400
| 1 | WDC | Item | S | 1 | 1 | 5400 | 1 | 5400 |  | 1 | 0 | 0 | 0 | 5400 | 5400 | 103
90 | Line No 189 Item No 9. | Special Item - As Constructed Survey and Plans | Item |  |  |  | 1 |  | 4000 |  | 4 | 0 | 0 | 0 | 4000 | 4000
| 1 | Survey | Item | S | 1 | 1 | 4000 | 1 | 4000 |  | 32 | 0 | 0 | 0 | 4000 | 4000 | 12
500 | Line No 192 Item No | DODD STREET
| Line No 194 Item No | QUALITY SYSTEM
| Line No 195 Item No CQC | QUALITY CONTROL REQUIREMENTS
91 | Line No 196 Item No QCP1 | Quality Verification & Control | Lump |  |  |  | 1 |  | 13160 |  | 0 | 3250 | 0 | 0 | 9910 | 13160
| 1 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 |  |  | 3250 | 0 | 0 | 0 | 3250 | 901
91.1 | 2 | (12) Field Density Tests |  |  |  |  | 12
91.2 | 3 | (6) Concrete Cylinder Sets |  |  |  |  | 6
| 4 | Field Density | each | S | 1 | 1 | 12 | 45 | 540 |  |  | 0 | 0 | 0 | 540 | 540 | 13
| 5 | Gravel Properties Testing | each | S | 1 | 1 | 3 | 390 | 1170 |  |  | 0 | 0 | 0 | 1170 | 1170 | 13
| 6 | Concrete Cylinders | each | S | 1 | 1 | 6 | 150 | 900 |  |  | 0 | 0 | 0 | 900 | 900 | 13
91.3 | 7 | Survey | Item | S | 7300 | 1 | 7300 | 1 | 7300 |  | 58.4 | 0 | 0 | 0 | 7300 | 7300 | 11
| Line No 198 Item No | GENERAL REQUIREMENTS
| Line No 199 Item No C101 | GENERAL
| Line No 200 Item No C101(b) | Site Establishment & Disestablishment | Lump |  |  |  | 1
| Line No 202 Item No | ROAD & EARTHWORKS
| Line No 203 Item No C201 | CONTROL OF TRAFFIC
92 | Line No 204 Item No C201(a) | Control of Traffic | Lump |  |  |  | 1 |  | 23292.48 |  | 20 | 0 | 0 | 0 | 23292.48 | 23292.48
92.1 | 1 | (4) No. Weeks TC Required |  |  | 4 |  | 4
| 2 | Traffic Control Crew | hr | S | 6 | 1 | 228 | 102.16 | 23292.48 |  | 20 | 0 | 0 | 0 | 23292.48 | 23292.48 | 141
| Line No 205 Item No C211 | CONTROL OF EROSION & SEDIMENTATION
93 | Line No 206 Item No C211(a) | Temporary Erosion & Sedimentation Control (includes supply and installation of all components) | Lump |  |  |  | 1 |  | 11050 |  | 6 | 6300 | 0 | 4750 | 0 | 11050
93.1 | 1 | Labour | hr | L | 3 | 1 | 50 | 42 | 6300 | 150 | 50 | 6300 | 0 | 0 | 0 | 6300 | 151
| 2 | Bobcat | hr | P | 1 | 1 | 50 | 95 | 4750 | 50 | 50 | 0 | 0 | 4750 | 0 | 4750 | 151
| Line No 207 Item No C212 | CLEARING & GRUBBING
94 | Line No 208 Item No | Special Item - Demolition of Structure (concrete slabs, culverts, pipes etc) | Lump |  |  |  | 1 |  | 10066.6667 |  | 2 | 1400 | 0 | 8666.6667 | 0 | 10066.6667
94.1 | 1 | Excavator - 25T | hr | P | 1 | 0.06 | 1 | 135 | 2250 | 16.6667 | 16.6667 | 0 | 0 | 2250 | 0 | 2250 | 41
94.2 | 2 | Tipper | hr | P | 3 | 0.06 | 1 | 95 | 4750 | 50 | 16.6667 | 0 | 0 | 4750 | 0 | 4750 | 41
| 3 | Water Cart - Hire | hr | P | 1 | 0.06 | 1 | 100 | 1666.6667 | 16.6667 | 16.6667 | 0 | 0 | 1666.6667 | 0 | 1666.6667 | 41
| 4 | Labour | hr | L | 2 | 0.06 | 1 | 42 | 1400 | 33.3333 | 16.6667 | 1400 | 0 | 0 | 0 | 1400 | 41
| Line No 210 Item No C213 | EARTHWORKS
95 | Line No 211 Item No C213(b) | General Earthworks Cut | m3 |  |  |  | 1430 |  | 29655.2414 |  | 6 | 2744.1207 | 0 | 26911.1207 | 0 | 29655.2414
95.1 | 1 | Excavator - 25T | hr | P | 1 | 40 | 1430 | 135 | 4826.25 | 35.75 | 35.75 | 0 | 0 | 4826.25 | 0 | 4826.25 | 53
95.2 | 2 | Truck & Dog | hr | P | 3 | 40 | 1430 | 145 | 15551.25 | 107.25 | 35.75 | 0 | 0 | 15551.25 | 0 | 15551.25 | 53
| 3 | Water Cart - Hire | hr | P | 1 | 40 | 1430 | 100 | 3575 | 35.75 | 35.75 | 0 | 0 | 3575 | 0 | 3575 | 53
| 4 | Labour | hr | L | 1 | 40 | 1430 | 42 | 1501.5 | 35.75 | 35.75 | 1501.5 | 0 | 0 | 0 | 1501.5 | 53
| 5 | Prepare Sub-grade
95.3 | 6 | Grader | hr | P | 1 | 250 | 2465.5172 | 145 | 1430 | 9.8621 | 9.8621 | 0 | 0 | 1430 | 0 | 1430 | 61
| 7 | Water Cart - Hire | hr | P | 1 | 250 | 2465.5172 | 100 | 986.2069 | 9.8621 | 9.8621 | 0 | 0 | 986.2069 | 0 | 986.2069 | 61
| 8 | SD Roller - Wet (No Op) | hr | P | 1 | 250 | 2465.5172 | 55 | 542.4138 | 9.8621 | 9.8621 | 0 | 0 | 542.4138 | 0 | 542.4138 | 61
| 9 | Labour | hr | L | 3 | 250 | 2465.5172 | 42 | 1242.6207 | 29.5862 | 9.8621 | 1242.6207 | 0 | 0 | 0 | 1242.6207 | 61
| Line No 213 Item No | STORMWATER DRAINAGE
| Line No 214 Item No C220 | STORMWATER DRAINAGE - GENERAL
96 | Line No 215 Item No | Removal / Demolition of Drainage Components complete | Lump |  |  |  | 1 |  | 5490.9091 |  | 2 | 763.6364 | 0 | 4727.2727 | 0 | 5490.9091
96.1 | 1 | Excavator - 25T | hr | P | 1 | 0.11 | 1 | 135 | 1227.2727 | 9.0909 | 9.0909 | 0 | 0 | 1227.2727 | 0 | 1227.2727 | 41
| 2 | Tipper | hr | P | 3 | 0.11 | 1 | 95 | 2590.9091 | 27.2727 | 9.0909 | 0 | 0 | 2590.9091 | 0 | 2590.9091 | 41
| 3 | Water Cart - Hire | hr | P | 1 | 0.11 | 1 | 100 | 909.0909 | 9.0909 | 9.0909 | 0 | 0 | 909.0909 | 0 | 909.0909 | 41
| 4 | Labour | hr | L | 2 | 0.11 | 1 | 42 | 763.6364 | 18.1818 | 9.0909 | 763.6364 | 0 | 0 | 0 | 763.6364 | 41
97 | Line No 216 Item No | Alteration to Existing Stormwater Structures (Break new RCP's into existing RCBC - 4 Nos) | Lump |  |  |  | 1 |  | 9600 |  | 8 | 0 | 0 | 0 | 9600 | 9600
| 1 | Pit Builder - Modify | each | S | 1 | 1 | 8 | 1200 | 9600 | 8 | 8 | 0 | 0 | 0 | 9600 | 9600 | 85
| Line No 217 Item No C221 | PIPE DRAINAGE (SUPPLY & INSTALL) | [9 empty] | Contributing
98 | Line No 218 Item No C221(a) | 375mm dia Class 2, Flush Joint | m |  |  |  | 7.32 |  | 1893.5897 |  | 1 | 631.726 | 585.0144 | 676.8493 | 0 | 1893.5897
98.1 | 1 | Excavator - 25T | hr | P | 1 | 1.46 | 7.32 | 135 | 676.8493 | 5.0137 | 5.0137 | 0 | 0 | 676.8493 | 0 | 676.8493 | 81
| 2 | 375 RCP FJ CL3 | m | M | 1 | 1 | 7.32 | 71.92 | 526.4544 |  |  | 0 | 526.4544 | 0 | 0 | 526.4544 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 2.44 | 24 | 58.56 |  |  | 0 | 58.56 | 0 | 0 | 58.56 | QMS
| 4 | Labour | hr | L | 3 | 1.46 | 7.32 | 42 | 631.726 | 15.0411 | 5.0137 | 631.726 | 0 | 0 | 0 | 631.726 | 81
99 | Line No 219 Item No C221(a) | 375mm dia Class 3, Flush Joint | m |  |  |  | 17.08 |  | 2668.5073 |  | 1 | 629.2632 | 1365.0336 | 674.2105 | 0 | 2668.5073
99.1 | 1 | Excavator - 25T | hr | P | 1 | 3.42 | 17.08 | 135 | 674.2105 | 4.9942 | 4.9942 | 0 | 0 | 674.2105 | 0 | 674.2105 | 81
| 2 | 375 RCP FJ CL3 | m | M | 1 | 1 | 17.08 | 71.92 | 1228.3936 |  |  | 0 | 1228.3936 | 0 | 0 | 1228.3936 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 5.6933 | 24 | 136.64 |  |  | 0 | 136.64 | 0 | 0 | 136.64 | QMS
| 4 | Labour | hr | L | 3 | 3.42 | 17.08 | 42 | 629.2632 | 14.9825 | 4.9942 | 629.2632 | 0 | 0 | 0 | 629.2632 | 81
100 | Line No 220 Item No C221(a) | Renew Property Drainage connections | Lump |  |  |  | 1 |  | 6320 |  | 4 | 0 | 3600 | 0 | 2720 | 6320
100.1 | 1 | (16) No. of properties |  |  | 16 |  | 16
| 2 | 150 SN8 Sewer Pipe | m | M | 1 | 1 | 96 | 25 | 2400 |  |  | 0 | 2400 | 0 | 0 | 2400 | SWP
| 3 | Kerb Adaptors | each | M | 1 | 1 | 16 | 75 | 1200 |  |  | 0 | 1200 | 0 | 0 | 1200 | SWP
| 4 | Plumber | hr | S | 1 | 0.5 | 16 | 85 | 2720 | 32 | 32 | 0 | 0 | 0 | 2720 | 2720 | 81
| Line No 221 Item No C223 | DRAINAGE STRUCTURES
101 | Line No 222 Item No C223(b) | MCC Type A Gully Pit | each |  |  |  | 4 |  | 14020 |  | 10 | 1360 | 5160 | 0 | 7500 | 14020
101.1 | 1 | Pit Builder | each | S | 1 | 2 | 4 | 3750 | 7500 |  | 8 | 0 | 0 | 0 | 7500 | 7500 | 85
| 2 | MCC Type A Gully Top | each | M | 1 | 1 | 4 | 1290 | 5160 |  |  | 0 | 5160 | 0 | 0 | 5160 | SWPC
| 3 | Concretor - Labour | hr | L | 1 | 1 | 16 | 85 | 1360 | 16 | 16 | 1360 | 0 | 0 | 0 | 1360 | 85
| Line No 223 Item No C224 | OPEN DRAINS, INCLUDING KERB & CHANNEL
102 | Line No 224 Item No C224(h) | (i) Concrete Barrier Kerb & Channel B1 complete | m |  |  |  | 524 |  | 27857.4242 |  | 3 | 0 | 12137.4242 | 0 | 15720 | 27857.4242
| 1 | Use Kerb Subbie. Allciv to supply sand & cement for slurry
102.1 | 2 | S32 - Kerb Mix | m³ | M | 8.6 | 1 | 60.9302 | 190 | 11576.7442 |  |  | 0 | 11576.7442 | 0 | 0 | 11576.7442 | CKM
102.2 | 3 | Sand | tonne | M | 75 | 1 | 6.9867 | 24 | 167.68 |  |  | 0 | 167.68 | 0 | 0 | 167.68 | QMS
102.3 | 4 | Cement | tonne | M | 8 | 1 | 0.87333 | 450 | 393 |  |  | 0 | 393 | 0 | 0 | 393 | CSA
| 5 | Kerb Subbie | m | S | 1 | 1 | 524 | 30 | 15720 |  | 2.62 | 0 | 0 | 0 | 15720 | 15720 | 71
103 | Line No 225 Item No C224(h) | (ii) Concrete Mountable Kerb & Channel M1 complete | m |  |  |  | 42 |  | 2354.94 |  | 1 | 0 | 1094.94 | 0 | 1260 | 2354.94
| 1 | Use Kerb Subbie. Allciv to supply sand & cement for slurry
103.1 | 2 | S32 - Kerb Mix | m³ | M | 7.6 | 1 | 5.5263 | 190 | 1050 |  |  | 0 | 1050 | 0 | 0 | 1050 | CKM
103.2 | 3 | Sand | tonne | M | 75 | 1 | 0.56 | 24 | 13.44 |  |  | 0 | 13.44 | 0 | 0 | 13.44 | QMS
103.3 | 4 | Cement | tonne | M | 8 | 1 | 0.07 | 450 | 31.5 |  |  | 0 | 31.5 | 0 | 0 | 31.5 | CSA
| 5 | Kerb Subbie | m | S | 1 | 1 | 42 | 30 | 1260 |  | 0.21 | 0 | 0 | 0 | 1260 | 1260 | 71
| Line No 227 Item No | SUB-SURFACE DRAINAGE
| Line No 228 Item No C231 | SUBSOIL & FOUNDATION DRAINS
104 | Line No 229 Item No C232(b) | (i) 100mm dia Slotted Corrugated Plastic Pipe | m |  |  |  | 491 |  | 20269.5778 |  | 5 | 5568.4968 | 2977.424 | 10319.3969 | 1404.26 | 20269.5778
| 1 | Excavate & install sub-soil drain at a rate of 100m per day. Use 300 trench and sand to backfill.
| 2 | Sub Soil Drain | m | M | 1 | 1 | 491 | 2.5 | 1227.5 |  |  | 0 | 1227.5 | 0 | 0 | 1227.5 | 87
| 3 | Sub Soil Clean Out - Inst | each | S | 1 | 1 | 9.82 | 143 | 1404.26 |  |  | 0 | 0 | 0 | 1404.26 | 1404.26 | 87
| 4 | Sand | tonne | M | 1 | 1 | 72.9135 | 24 | 1749.924 |  |  | 0 | 1749.924 | 0 | 0 | 1749.924 | QMS
104.1 | 5 | Excavator - 25T | hr | P | 1 | 11.11 | 491 | 135 | 5966.2466 | 44.1944 | 44.1944 | 0 | 0 | 5966.2466 | 0 | 5966.2466 | 87
| 6 | Labour | hr | L | 3 | 11.11 | 491 | 42 | 5568.4968 | 132.5833 | 44.1944 | 5568.4968 | 0 | 0 | 0 | 5568.4968 | 87
| 7 | Bobcat | hr | P | 1 | 11.11 | 491 | 95 | 4198.4698 | 44.1944 | 44.1944 | 0 | 0 | 4198.4698 | 0 | 4198.4698 | 87
| 8 | Plate Compactor | hr | P | 1 | 11.11 | 491 | 3.5 | 154.6805 | 44.1944 | 44.1944 | 0 | 0 | 154.6805 | 0 | 154.6805 | 87
105 | Line No 230 Item No C232(c) | Cleanout Structures | each |  |  |  | 14 |  | 2002 |  | 5 | 0 | 0 | 0 | 2002 | 2002
| 1 | Sub Soil Clean Out - Inst | each | S | 1 | 1 | 14 | 143 | 2002 |  |  | 0 | 0 | 0 | 2002 | 2002 | 87
| Line No 232 Item No | PAVEMENTS
| Line No 233 Item No C242 | FLEXIBLE PAVEMENTS
106 | Line No 234 Item No | Place only Type 2.3 (cement modified) | m3 |  |  |  | 521 |  | 29500.6126 |  | 4 | 3545.2385 | 0 | 25955.3741 | 0 | 29500.6126
106.1 | 1 | Tonnes Gravel = QTY*density |  |  | 2.4 |  | 1250.4
106.2 | 2 | Truck & Dog | hr | P | 3 | 37 | 1250.4 | 145 | 14700.6486 | 101.3838 | 33.7946 | 0 | 0 | 14700.6486 | 0 | 14700.6486 | 62
| 3 | Placement
106.3 | 4 | Grader | hr | P | 1 | 44.44 | 1250.4 | 145 | 4079.838 | 28.1368 | 28.1368 | 0 | 0 | 4079.838 | 0 | 4079.838 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 44.44 | 1250.4 | 100 | 2813.6814 | 28.1368 | 28.1368 | 0 | 0 | 2813.6814 | 0 | 2813.6814 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 44.44 | 1250.4 | 55 | 1547.5248 | 28.1368 | 28.1368 | 0 | 0 | 1547.5248 | 0 | 1547.5248 | 62
| 7 | Labour | hr | L | 3 | 44.44 | 1250.4 | 42 | 3545.2385 | 84.4104 | 28.1368 | 3545.2385 | 0 | 0 | 0 | 3545.2385 | 62
| 8 | Backhoe | hr | P | 1 | 44.44 | 1250.4 | 100 | 2813.6814 | 28.1368 | 28.1368 | 0 | 0 | 2813.6814 | 0 | 2813.6814 | 62
107 | Line No 235 Item No | Place only Type 2.1 | m3 |  |  |  | 345 |  | 27437.0975 |  | 7 | 4417.6148 | 0 | 23019.4827 | 0 | 27437.0975
107.1 | 1 | Tonnes Gravel = QTY*density |  |  | 2.4 |  | 828
107.2 | 2 | Truck & Dog | hr | P | 3 | 37 | 828 | 145 | 9734.5946 | 67.1351 | 22.3784 | 0 | 0 | 9734.5946 | 0 | 9734.5946 | 62
| 3 | Placement
107.3 | 4 | Grader | hr | P | 1 | 44.44 | 828 | 145 | 2701.6202 | 18.6319 | 18.6319 | 0 | 0 | 2701.6202 | 0 | 2701.6202 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 44.44 | 828 | 100 | 1863.1863 | 18.6319 | 18.6319 | 0 | 0 | 1863.1863 | 0 | 1863.1863 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 44.44 | 828 | 55 | 1024.7525 | 18.6319 | 18.6319 | 0 | 0 | 1024.7525 | 0 | 1024.7525 | 62
| 7 | Labour | hr | L | 3 | 44.44 | 828 | 42 | 2347.6148 | 55.8956 | 18.6319 | 2347.6148 | 0 | 0 | 0 | 2347.6148 | 62
| 8 | Backhoe | hr | P | 1 | 44.44 | 828 | 100 | 1863.1863 | 18.6319 | 18.6319 | 0 | 0 | 1863.1863 | 0 | 1863.1863 | 62
| 9 | Final Trim
107.4 | 10 | Grader | hr | P | 1 | 150 | 2464.2857 | 145 | 2382.1429 | 16.4286 | 16.4286 | 0 | 0 | 2382.1429 | 0 | 2382.1429 | 63
| 11 | Water Cart - Hire | hr | P | 1 | 150 | 2464.2857 | 100 | 1642.8571 | 16.4286 | 16.4286 | 0 | 0 | 1642.8571 | 0 | 1642.8571 | 63
| 12 | MW Roller | hr | P | 1 | 75 | 2464.2857 | 55 | 1807.1429 | 32.8571 | 32.8571 | 0 | 0 | 1807.1429 | 0 | 1807.1429 | 63
| 13 | Labour | hr | L | 3 | 150 | 2464.2857 | 42 | 2070 | 49.2857 | 16.4286 | 2070 | 0 | 0 | 0 | 2070 | 63
108 | Line No 236 Item No | Special Item - Geotextile layer | m2 |  |  |  | 2797 |  | 4423.431 |  | 1 | 680.1126 | 3230.535 | 512.7833 | 0 | 4423.431
108.1 | 1 | A24 | m² | M | 1.1 | 1 | 3076.7 | 1.05 | 3230.535 |  |  | 0 | 3230.535 | 0 | 0 | 3230.535 | 222
| 2 | Labour | hr | L | 3 | 570 | 3076.7 | 42 | 680.1126 | 16.1932 | 5.3977 | 680.1126 | 0 | 0 | 0 | 680.1126 | 222
| 3 | Bobcat | hr | P | 1 | 570 | 3076.7 | 95 | 512.7833 | 5.3977 | 5.3977 | 0 | 0 | 512.7833 | 0 | 512.7833 | 222
| Line No 237 Item No C244 | SPRAYED BITUMINOUS SURFACING
| Line No 238 Item No C244(a) | Supply & Spray Primer, supply & spread aggregates, Primerbinder (including preparation of surface) complete
109 | Line No 239 Item No C244(a) | (vii) AMC5 | m2 |  |  |  | 2466 |  | 18617.067 |  | 1 | 0 | 0 | 0 | 18617.067 | 18617.067
109.1 | 1 | Seal Visit Four | m² | S | 1.05 | 1 | 2589.3 | 7.19 | 18617.067 |  | 0.32366 | 0 | 0 | 0 | 18617.067 | 18617.067 | 64
| Line No 240 Item No C245 | ASPHALTIC CONCRETE
| Line No 241 Item No C245(c) | Dense Graded Asphalt in Wearing Course
110 | Line No 242 Item No C245(c) | (ii) 14mm Nominal Size | tonne |  |  |  | 296 |  | 80186.4 |  | 2 | 0 | 0 | 0 | 80186.4 | 80186.4
110.1 | 1 | DG14 - Dodd St | tonne | S | 1.05 | 1 | 310.8 | 258 | 80186.4 |  | 1.2432 | 0 | 0 | 0 | 80186.4 | 80186.4 | 65
| Line No 244 Item No | ROAD FURNISHINGS
| Line No 245 Item No C261 | PAVEMENT MARKINGS
111 | Line No 246 Item No C261(b) | Pavement Marking Paint - Transverse Lines, Symbols, Legends, Arrows, Chevrons, Traffic Islands & Kerbs | Item |  |  |  | 2 |  | 2000 |  | 1 | 0 | 0 | 0 | 2000 | 2000
| 1 | Line Marking | m² | S | 1 | 1 | 2000 | 1 | 2000 |  | 1 | 0 | 0 | 0 | 2000 | 2000 | 66
112 | Line No 247 Item No C262(g) | Remove and reinstate Existing Signs & Support Structures | Item |  |  |  | 2 |  | 472 |  | 1 | 0 | 472 | 0 | 0 | 472
| 1 | Signs Complete | each | M | 1 | 1 | 2 | 140 | 280 |  | 4 | 0 | 280 | 0 | 0 | 280 | RFS
| 2 | N32 | m³ | M | 1 | 1 | 1 | 192 | 192 |  |  | 0 | 192 | 0 | 0 | 192 | C32
| Line No 249 Item No | MISCELLANEOUS
| Line No 250 Item No C271 | MINOR CONCRETE WORKS
| Line No 251 Item No C271(c) | Footpaths, Bike paths, Driveways, Median Toppings & Works of Similar Nature
113 | Line No 252 Item No C271(c) | (iv) Residential Invert Crossing | each |  |  |  | 7 |  | 3363.9733 |  | 4 | 25.2 | 1856.7733 | 138 | 1344 | 3363.9733
| 1 | Purchase Materials
| 2 | N32 | m³ | M | 1 | 1 | 5.775 | 192 | 1108.8 |  |  | 0 | 1108.8 | 0 | 0 | 1108.8 | C32
| 3 | Sand | tonne | M | 1 | 1 | 6.3 | 24 | 151.2 |  |  | 0 | 151.2 | 0 | 0 | 151.2 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 50.4 | 9.1 | 458.64 |  |  | 0 | 458.64 | 0 | 0 | 458.64 | RSM
| 5 | Abel Flex | m | M | 1 | 1 | 33.6 | 3 | 100.8 |  |  | 0 | 100.8 | 0 | 0 | 100.8 | RSM
| 6 | Detailed Excavation:
113.1 | 7 | Excavator - 25T | hr | P | 1 | 7 | 4.2 | 135 | 81 | 0.6 | 0.6 | 0 | 0 | 81 | 0 | 81 | 71
| 8 | Tipper | hr | P | 1 | 7 | 4.2 | 95 | 57 | 0.6 | 0.6 | 0 | 0 | 57 | 0 | 57 | 71
| 9 | Labour | hr | L | 1 | 7 | 4.2 | 42 | 25.2 | 0.6 | 0.6 | 25.2 | 0 | 0 | 0 | 25.2 | 71
| 10 | Form Pour & Finish
| 11 | Bar Chairs | each | M | 1 | 1 | 46.6667 | 0.8 | 37.3333 |  |  | 0 | 37.3333 | 0 | 0 | 37.3333 | RSM
| 12 | Concrete Subbie | m² | S | 1 | 1 | 42 | 32 | 1344 |  | 3.5 | 0 | 0 | 0 | 1344 | 1344 | 71
| Line No 254 Item No | SERVICES
| Line No 255 Item No C320 | WATER RETICULATION
| Line No 256 Item No | Reinstate Existing water main | Lump |  |  |  | 1
| Line No 258 Item No | SPECIFIED WORKS
114 | Line No 259 Item No | Special Item - As Constructed Survey and Plans | Lump |  |  |  | 1 |  | 2500 |  | 20 | 0 | 0 | 0 | 2500 | 2500
| 1 | Survey | Item | S | 1 | 1 | 2500 | 1 | 2500 |  | 20 | 0 | 0 | 0 | 2500 | 2500 | 12
600 | Line No 263 Item No | DOHERTY STREET
| Line No 265 Item No | QUALITY SYSTEM
| Line No 266 Item No CQC | QUALITY CONTROL REQUIREMENTS
115 | Line No 267 Item No QCP1 | Quality Verification & Control | Lump |  |  |  | 1 |  | 9760 |  | 0 | 3250 | 0 | 0 | 6510 | 9760
| 1 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 |  |  | 3250 | 0 | 0 | 0 | 3250 | 901
115.1 | 2 | (12) Field Density Tests |  |  |  |  | 12
115.2 | 3 | (6) Concrete Cylinder Sets |  |  |  |  | 6
| 4 | Field Density | each | S | 1 | 1 | 12 | 45 | 540 |  | 0.096 | 0 | 0 | 0 | 540 | 540 | 13
| 5 | Gravel Properties Testing | each | S | 1 | 1 | 3 | 390 | 1170 |  | 0.024 | 0 | 0 | 0 | 1170 | 1170 | 13
| 6 | Concrete Cylinders | each | S | 1 | 1 | 6 | 150 | 900 |  | 0.048 | 0 | 0 | 0 | 900 | 900 | 13
115.3 | 7 | Survey | Item | S | 3900 | 1 | 3900 | 1 | 3900 |  | 31.2 | 0 | 0 | 0 | 3900 | 3900 | 11
| Line No 269 Item No | GENERAL REQUIREMENTS
| Line No 270 Item No C101 | GENERAL
| Line No 271 Item No C101(b) | Site Establishment & Disestablishment | Lump |  |  |  | 1
| Line No 273 Item No | ROAD & EARTHWORKS
| Line No 274 Item No C201 | CONTROL OF TRAFFIC
116 | Line No 275 Item No C201(a) | Control of Traffic | Lump |  |  |  | 1 |  | 23292.48 |  | 20 | 0 | 0 | 0 | 23292.48 | 23292.48
116.1 | 1 | (4) No. Weeks TC Required - No. = days per week |  |  |  |  | 4
116.2 | 2 | Traffic Control Crew | hr | S | 6 | 1 | 38 | 102.16 | 23292.48 |  | 20 | 0 | 0 | 0 | 23292.48 | 23292.48 | 141
| Line No 276 Item No C213 | EARTHWORKS
117 | Line No 277 Item No C213(b) | General Earthworks Cut | m3 |  |  |  | 652 |  | 13017.3001 |  | 3 | 1102.1451 | 0 | 11915.155 | 0 | 13017.3001
| 1 | Excavator - 25T | hr | P | 1 | 40 | 652 | 135 | 2200.5 | 16.3 | 16.3 | 0 | 0 | 2200.5 | 0 | 2200.5 | 53
| 2 | Truck & Dog | hr | P | 3 | 40 | 652 | 145 | 7090.5 | 48.9 | 16.3 | 0 | 0 | 7090.5 | 0 | 7090.5 | 53
| 3 | Water Cart - Hire | hr | P | 1 | 40 | 652 | 100 | 1630 | 16.3 | 16.3 | 0 | 0 | 1630 | 0 | 1630 | 53
| 4 | Labour | hr | L | 1 | 40 | 652 | 42 | 684.6 | 16.3 | 16.3 | 684.6 | 0 | 0 | 0 | 684.6 | 53
| 5 | Prepare Sub-grade
117.1 | 6 | Grader | hr | P | 1 | 250 | 828.4625 | 145 | 480.5083 | 3.3139 | 3.3139 | 0 | 0 | 480.5083 | 0 | 480.5083 | 61
| 7 | Water Cart - Hire | hr | P | 1 | 250 | 828.4625 | 100 | 331.385 | 3.3139 | 3.3139 | 0 | 0 | 331.385 | 0 | 331.385 | 61
| 8 | SD Roller - Wet (No Op) | hr | P | 1 | 250 | 828.4625 | 55 | 182.2618 | 3.3139 | 3.3139 | 0 | 0 | 182.2618 | 0 | 182.2618 | 61
117.2 | 9 | Labour | hr | L | 3 | 250 | 828.4625 | 42 | 417.5451 | 9.9416 | 3.3139 | 417.5451 | 0 | 0 | 0 | 417.5451 | 61
118 | Line No 278 Item No C213(c) | General Earthworks Fill (Fill behind kerb to boundary) | m3 |  |  |  | 104 |  | 2917.2 |  | 1 | 655.2 | 0 | 2262 | 0 | 2917.2
118.1 | 1 | Excavator - 25T | hr | P | 1 | 20 | 104 | 135 | 702 | 5.2 | 5.2 | 0 | 0 | 702 | 0 | 702 | 33
| 2 | Grader | hr | P | 1 | 20 | 104 | 145 | 754 | 5.2 | 5.2 | 0 | 0 | 754 | 0 | 754 | 33
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 20 | 104 | 55 | 286 | 5.2 | 5.2 | 0 | 0 | 286 | 0 | 286 | 33
| 4 | Water Cart - Hire | hr | P | 1 | 20 | 104 | 100 | 520 | 5.2 | 5.2 | 0 | 0 | 520 | 0 | 520 | 33
118.2 | 5 | Labour | hr | L | 3 | 20 | 104 | 42 | 655.2 | 15.6 | 5.2 | 655.2 | 0 | 0 | 0 | 655.2 | 33
119 | Line No 279 Item No C213(d) | Replace unsuitable material below sub grade with select material complete (PROVISIONAL) | m3 |  |  |  | 65 |  | 4259.6667 |  | 1 | 728 | 0 | 3531.6667 | 0 | 4259.6667
119.1 | 1 | Excavator - 25T | hr | P | 1 | 15 | 65 | 135 | 585 | 4.3333 | 4.3333 | 0 | 0 | 585 | 0 | 585 | 57
119.2 | 2 | Truck & Dog | hr | P | 2 | 15 | 65 | 145 | 1256.6667 | 8.6667 | 4.3333 | 0 | 0 | 1256.6667 | 0 | 1256.6667 | 57
| 3 | Water Cart - Hire | hr | P | 1 | 15 | 65 | 100 | 433.3333 | 4.3333 | 4.3333 | 0 | 0 | 433.3333 | 0 | 433.3333 | 57
| 4 | Labour | hr | L | 1 | 15 | 65 | 42 | 182 | 4.3333 | 4.3333 | 182 | 0 | 0 | 0 | 182 | 57
| 5 | Fill
| 6 | Excavator - 25T | hr | P | 1 | 15 | 65 | 135 | 585 | 4.3333 | 4.3333 | 0 | 0 | 585 | 0 | 585 | 57
| 7 | SD Roller - Wet (No Op) | hr | P | 1 | 15 | 65 | 55 | 238.3333 | 4.3333 | 4.3333 | 0 | 0 | 238.3333 | 0 | 238.3333 | 57
| 8 | Water Cart - Hire | hr | P | 1 | 15 | 65 | 100 | 433.3333 | 4.3333 | 4.3333 | 0 | 0 | 433.3333 | 0 | 433.3333 | 57
119.3 | 9 | Labour | hr | L | 3 | 15 | 65 | 42 | 546 | 13 | 4.3333 | 546 | 0 | 0 | 0 | 546 | 57
| Line No 281 Item No | STORMWATER DRAINAGE
| Line No 282 Item No C220 | STORMWATER DRAINAGE - GENERAL
120 | Line No 283 Item No | Removal / Demolition of Drainage Components complete | Lump |  |  |  | 2 |  | 5490.9091 |  | 2 | 763.6364 | 0 | 4727.2727 | 0 | 5490.9091
120.1 | 1 | Excavator - 25T | hr | P | 1 | 0.22 | 2 | 135 | 1227.2727 | 9.0909 | 9.0909 | 0 | 0 | 1227.2727 | 0 | 1227.2727 | 41
120.2 | 2 | Tipper | hr | P | 3 | 0.22 | 2 | 95 | 2590.9091 | 27.2727 | 9.0909 | 0 | 0 | 2590.9091 | 0 | 2590.9091 | 41
| 3 | Water Cart - Hire | hr | P | 1 | 0.22 | 2 | 100 | 909.0909 | 9.0909 | 9.0909 | 0 | 0 | 909.0909 | 0 | 909.0909 | 41
| 4 | Labour | hr | L | 2 | 0.22 | 2 | 42 | 763.6364 | 18.1818 | 9.0909 | 763.6364 | 0 | 0 | 0 | 763.6364 | 41
121 | Line No 284 Item No | Relocate existing kerb adapter and roofwater connection from property | Item |  |  |  | 2 |  | 790 |  | 1 | 0 | 450 | 0 | 340 | 790
| 1 | (2) No. of properties |  |  |  |  | 2
| 2 | 150 SN8 Sewer Pipe | m | M | 1 | 1 | 12 | 25 | 300 |  |  | 0 | 300 | 0 | 0 | 300 | SWP
| 3 | Kerb Adaptors | each | M | 1 | 1 | 2 | 75 | 150 |  |  | 0 | 150 | 0 | 0 | 150 | SWP
121.1 | 4 | Plumber | hr | S | 1 | 0.5 | 2 | 85 | 340 | 4 | 4 | 0 | 0 | 0 | 340 | 340 | 81
| Line No 285 Item No C221 | PIPE DRAINAGE (SUPPLY & INSTALL)
| Line No 286 Item No C221(a) | STEEL REINFORCED CONCRETE
122 | Line No 287 Item No C221(a) | 375mm dia Class 2, Flush Joint | m |  |  |  | 93 |  | 12899.4519 |  | 3 | 2639.1892 | 7432.56 | 2827.7027 | 0 | 12899.4519
122.1 | 1 | Excavator - 25T | hr | P | 1 | 4.44 | 93 | 135 | 2827.7027 | 20.9459 | 20.9459 | 0 | 0 | 2827.7027 | 0 | 2827.7027 | 81
| 2 | 375 RCP FJ CL3 | m | M | 1 | 1 | 93 | 71.92 | 6688.56 |  |  | 0 | 6688.56 | 0 | 0 | 6688.56 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 31 | 24 | 744 |  |  | 0 | 744 | 0 | 0 | 744 | QMS
122.2 | 4 | Labour | hr | L | 3 | 4.44 | 93 | 42 | 2639.1892 | 62.8378 | 20.9459 | 2639.1892 | 0 | 0 | 0 | 2639.1892 | 81
123 | Line No 288 Item No C221(a) | 450mm dia Class 2, Flush Joint | m |  |  |  | 9.72 |  | 2280.6627 |  | 1 | 631.299 | 972.972 | 676.3918 | 0 | 2280.6627
123.1 | 1 | Excavator - 25T | hr | P | 1 | 1.94 | 9.72 | 135 | 676.3918 | 5.0103 | 5.0103 | 0 | 0 | 676.3918 | 0 | 676.3918 | 81
| 2 | 450 RCP FJ CL2 | m | M | 1 | 1 | 9.72 | 92.1 | 895.212 |  |  | 0 | 895.212 | 0 | 0 | 895.212 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 3.24 | 24 | 77.76 |  |  | 0 | 77.76 | 0 | 0 | 77.76 | QMS
123.2 | 4 | Labour | hr | L | 3 | 1.94 | 9.72 | 42 | 631.299 | 15.0309 | 5.0103 | 631.299 | 0 | 0 | 0 | 631.299 | 81
Line No 289 Item No C221(a)
| Line No 290 Item No C221(a) | FIBRE REINFORCED CEMENT
124 | Line No 291 Item No C221(a) | 450mm dia Class 2, Rubber Ring Joint | m |  |  |  | 30 |  | 5354.3514 |  | 2 | 1135.1351 | 3003 | 1216.2162 | 0 | 5354.3514
124.1 | 1 | Excavator - 25T | hr | P | 1 | 3.33 | 30 | 135 | 1216.2162 | 9.009 | 9.009 | 0 | 0 | 1216.2162 | 0 | 1216.2162 | 81
| 2 | 450 RCP FJ CL2 | m | M | 1 | 1 | 30 | 92.1 | 2763 |  |  | 0 | 2763 | 0 | 0 | 2763 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 10 | 24 | 240 |  |  | 0 | 240 | 0 | 0 | 240 | QMS
124.2 | 4 | Labour | hr | L | 3 | 3.33 | 30 | 42 | 1135.1351 | 27.027 | 9.009 | 1135.1351 | 0 | 0 | 0 | 1135.1351 | 81
| Line No 292 Item No C222 | PRECAST BOX CULVERTS (SUPPLY & INSTALL)
125 | Line No 293 Item No C222(b) | 900 x 450 | m |  |  |  | 12 |  | 7752.5 |  | 2 | 1260 | 4825 | 1667.5 | 0 | 7752.5
| 1 | (10) Box Units to Stand |  |  |  |  | 10
| 2 | (15) Hand Placed Backfill |  |  |  |  | 15
| 3 | RCBC - 1200 x 450 | m | M | 1 | 1 | 12 | 387.5 | 4650 |  |  | 0 | 4650 | 0 | 0 | 4650 | SWC
125.1 | 4 | Excavator - 25T | hr | P | 1 | 2 | 10 | 135 | 675 | 5 | 5 | 0 | 0 | 675 | 0 | 675 | 181
125.2 | 5 | Labour | hr | L | 3 | 2 | 10 | 42 | 630 | 15 | 5 | 630 | 0 | 0 | 0 | 630 | 181
| 6 | Denso Tape | m | M | 1 | 1 | 35 | 5 | 175 |  |  | 0 | 175 | 0 | 0 | 175 | 181
125.3 | 7 | Bobcat | hr | P | 1 | 3 | 15 | 95 | 475 | 5 | 5 | 0 | 0 | 475 | 0 | 475 | 181
125.4 | 8 | Labour | hr | L | 3 | 3 | 15 | 42 | 630 | 15 | 5 | 630 | 0 | 0 | 0 | 630 | 181
| 9 | Plate Compactor | hr | P | 1 | 3 | 15 | 3.5 | 17.5 | 5 | 5 | 0 | 0 | 17.5 | 0 | 17.5 | 181
| 10 | Water Cart - Hire | hr | P | 1 | 3 | 15 | 100 | 500 | 5 | 5 | 0 | 0 | 500 | 0 | 500 | 181
126 | Line No 294 Item No C222(b) | 1200 x 450 | m |  |  |  | 88 |  | 50229.5 |  | 6 | 6552 | 35705 | 7972.5 | 0 | 50229.5
| 1 | (74) Box Units to Stand |  |  |  |  | 74
| 2 | EE formula - =q(45) Hand Placed Backfill |  |  |  |  | 45
| 3 | RCBC - 1200 x 450 | m | M | 1 | 1 | 88.8 | 387.5 | 34410 |  |  | 0 | 34410 | 0 | 0 | 34410 | SWC
126.1 | 4 | Excavator - 25T | hr | P | 1 | 2 | 74 | 135 | 4995 | 37 | 37 | 0 | 0 | 4995 | 0 | 4995 | 181
126.2 | 5 | Labour | hr | L | 3 | 2 | 74 | 42 | 4662 | 111 | 37 | 4662 | 0 | 0 | 0 | 4662 | 181
| 6 | Denso Tape | m | M | 1 | 1 | 259 | 5 | 1295 |  |  | 0 | 1295 | 0 | 0 | 1295 | 181
126.3 | 7 | Bobcat | hr | P | 1 | 3 | 45 | 95 | 1425 | 15 | 15 | 0 | 0 | 1425 | 0 | 1425 | 181
126.4 | 8 | Labour | hr | L | 3 | 3 | 45 | 42 | 1890 | 45 | 15 | 1890 | 0 | 0 | 0 | 1890 | 181
| 9 | Plate Compactor | hr | P | 1 | 3 | 45 | 3.5 | 52.5 | 15 | 15 | 0 | 0 | 52.5 | 0 | 52.5 | 181
| 10 | Water Cart - Hire | hr | P | 1 | 3 | 45 | 100 | 1500 | 15 | 15 | 0 | 0 | 1500 | 0 | 1500 | 181
127 | Line No 295 Item No C222(b) | 1200 x 600 | m |  |  |  | 10 |  | 7274.5 |  | 2 | 1197 | 4477.5 | 1600 | 0 | 7274.5
| 1 | (9) Box Units to Stand |  |  |  |  | 9
| 2 | EE formula - =q(15) Hand Placed Backfill |  |  |  |  | 15
| 3 | RCBC - 1200 x 600 | m | M | 1 | 1 | 10.8 | 400 | 4320 |  |  | 0 | 4320 | 0 | 0 | 4320 | SWC
127.1 | 4 | Excavator - 25T | hr | P | 1 | 2 | 9 | 135 | 607.5 | 4.5 | 4.5 | 0 | 0 | 607.5 | 0 | 607.5 | 181
127.2 | 5 | Labour | hr | L | 3 | 2 | 9 | 42 | 567 | 13.5 | 4.5 | 567 | 0 | 0 | 0 | 567 | 181
| 6 | Denso Tape | m | M | 1 | 1 | 31.5 | 5 | 157.5 |  |  | 0 | 157.5 | 0 | 0 | 157.5 | 181
127.3 | 7 | Bobcat | hr | P | 1 | 3 | 15 | 95 | 475 | 5 | 5 | 0 | 0 | 475 | 0 | 475 | 181
127.4 | 8 | Labour | hr | L | 3 | 3 | 15 | 42 | 630 | 15 | 5 | 630 | 0 | 0 | 0 | 630 | 181
| 9 | Plate Compactor | hr | P | 1 | 3 | 15 | 3.5 | 17.5 | 5 | 5 | 0 | 0 | 17.5 | 0 | 17.5 | 181
| 10 | Water Cart - Hire | hr | P | 1 | 3 | 15 | 100 | 500 | 5 | 5 | 0 | 0 | 500 | 0 | 500 | 181
| Line No 296 Item No C223 | DRAINAGE STRUCTURES
128 | Line No 297 Item No C223(a) | Cast in situ Concrete Headwalls & Wingwalls & Aprons complete | m3 |  |  |  | 0.63 |  | 410.158 |  | 2 | 0 | 205.408 | 0 | 204.75 | 410.158
| 1 | 1200 x 600 (12m)
| 2 | QTY/.2) = Area |  |  |  |  | 3.15
| 3 | Sand | tonne | M | 1 | 1 | 0.315 | 24 | 7.56 |  |  | 0 | 7.56 | 0 | 0 | 7.56 | QMS
| 4 | RL1218 | m² | M | 1 | 1 | 3.78 | 18 | 68.04 |  |  | 0 | 68.04 | 0 | 0 | 68.04 | RSM
| 5 | Bar Chairs | each | M | 1 | 1 | 3.5 | 0.8 | 2.8 |  |  | 0 | 2.8 | 0 | 0 | 2.8 | RSM
| 6 | N32 | m³ | M | 1 | 1 | 0.6615 | 192 | 127.008 |  |  | 0 | 127.008 | 0 | 0 | 127.008 | C32
| 7 | RCBC Slab Subbie | m² | S | 1 | 1 | 3.15 | 65 | 204.75 | 3.15 | 3.15 | 0 | 0 | 0 | 204.75 | 204.75 | 72
| Line No 298 Item No C223(b) | Pits, Dissipators, Channel Basins & Other Supplementary Structures
129 | Line No 299 Item No C223(b) | BRO Pit Gully Pit | each |  |  |  | 5 |  | 27181.3 |  | 10 | 1700 | 6731.3 | 0 | 18750 | 27181.3
| 1 | Pit Builder | each | S | 1 | 1 | 5 | 3750 | 18750 | 5 | 5 | 0 | 0 | 0 | 18750 | 18750 | 85
| 2 | Bro Pit - 1C1T | each | M | 1 | 1 | 5 | 1346.26 | 6731.3 |  |  | 0 | 6731.3 | 0 | 0 | 6731.3 | SWPC
| 3 | Concretor - Labour | hr | L | 1 | 1 | 20 | 85 | 1700 | 20 | 20 | 1700 | 0 | 0 | 0 | 1700 | 85
130 | Line No 300 Item No C223(b) | (v) Concrete Manholes - Cast Insitu | each |  |  |  | 2 |  | 7500 |  | 4 | 0 | 0 | 0 | 7500 | 7500
| 1 | Pit Builder | each | S | 1 | 1 | 2 | 3750 | 7500 | 2 | 2 | 0 | 0 | 0 | 7500 | 7500 | 85
| Line No 301 Item No C224 | OPEN DRAINS, INCLUDING KERB & CHANNEL
| Line No 302 Item No C224(h) | Kerb &/or Channel
131 | Line No 303 Item No C224(h) | (i) Concrete Barrier Kerb & Channel B1 complete | m |  |  |  | 32 |  | 1701.2167 |  | 1 | 0 | 741.2167 | 0 | 960 | 1701.2167
| 1 | Use Kerb Subbie. Allciv to supply sand & cement for slurry
| 2 | S32 - Kerb Mix | m³ | M | 1 | 1 | 3.7209 | 190 | 706.9767 |  |  | 0 | 706.9767 | 0 | 0 | 706.9767 | CKM
| 3 | Sand | tonne | M | 1 | 1 | 0.42667 | 24 | 10.24 |  |  | 0 | 10.24 | 0 | 0 | 10.24 | QMS
| 4 | Cement | tonne | M | 1 | 1 | 0.053333 | 450 | 24 |  |  | 0 | 24 | 0 | 0 | 24 | CSA
| 5 | Kerb Subbie | m | S | 1 | 1 | 32 | 30 | 960 | 32 | 32 | 0 | 0 | 0 | 960 | 960 | 71
132 | Line No 304 Item No C224(h) | (ii) Concrete Mountable Kerb & Channel M1 complete | m |  |  |  | 180 |  | 10092.6 |  | 1 | 0 | 4692.6 | 0 | 5400 | 10092.6
| 1 | Use Kerb Subbie. Allciv to supply sand & cement for slurry
| 2 | S32 - Kerb Mix | m³ | M | 1 | 1 | 23.6842 | 190 | 4500 |  |  | 0 | 4500 | 0 | 0 | 4500 | CKM
| 3 | Sand | tonne | M | 1 | 1 | 2.4 | 24 | 57.6 |  |  | 0 | 57.6 | 0 | 0 | 57.6 | QMS
| 4 | Cement | tonne | M | 1 | 1 | 0.3 | 450 | 135 |  |  | 0 | 135 | 0 | 0 | 135 | CSA
| 5 | Kerb Subbie | m | S | 1 | 1 | 180 | 30 | 5400 | 180 | 180 | 0 | 0 | 0 | 5400 | 5400 | 71
| Line No 306 Item No | SUB-SURFACE DRAINAGE
| Line No 307 Item No C232 | PAVEMENT DRAINS
| Line No 308 Item No C232(b) | Subsoil Drain Pipe
133 | Line No 309 Item No C232(b) | (i) 100mm dia Slotted Corrugated Plastic Pipe | m |  |  |  | 210 |  | 8669.2695 |  | 3 | 2381.6382 | 1273.44 | 4413.5914 | 600.6 | 8669.2695
| 1 | Excavate & install sub-soil drain at a rate of 100m per day. Use 300 trench and sand to backfill.
| 2 | Sub Soil Drain | m | M | 1 | 1 | 210 | 2.5 | 525 |  |  | 0 | 525 | 0 | 0 | 525 | 87
| 3 | Sub Soil Clean Out - Inst | each | S | 1 | 1 | 4.2 | 143 | 600.6 | 4.2 | 4.2 | 0 | 0 | 0 | 600.6 | 600.6 | 87
| 4 | Sand | tonne | M | 1 | 1 | 31.185 | 24 | 748.44 |  |  | 0 | 748.44 | 0 | 0 | 748.44 | QMS
133.1 | 5 | Excavator - 25T | hr | P | 1 | 11.11 | 210 | 135 | 2551.7552 | 18.9019 | 18.9019 | 0 | 0 | 2551.7552 | 0 | 2551.7552 | 87
133.2 | 6 | Labour | hr | L | 3 | 11.11 | 210 | 42 | 2381.6382 | 56.7057 | 18.9019 | 2381.6382 | 0 | 0 | 0 | 2381.6382 | 87
| 7 | Bobcat | hr | P | 1 | 11.11 | 210 | 95 | 1795.6796 | 18.9019 | 18.9019 | 0 | 0 | 1795.6796 | 0 | 1795.6796 | 87
| 8 | Plate Compactor | hr | P | 1 | 11.11 | 210 | 3.5 | 66.1566 | 18.9019 | 18.9019 | 0 | 0 | 66.1566 | 0 | 66.1566 | 87
134 | Line No 310 Item No C232(c) | Cleanout Structures | each |  |  |  | 6 |  | 858 |  | 1 | 0 | 0 | 0 | 858 | 858
| 1 | Sub Soil Clean Out - Inst | each | S | 1 | 1 | 6 | 143 | 858 | 6 | 6 | 0 | 0 | 0 | 858 | 858 | 87
| Line No 312 Item No | PAVEMENTS
| Line No 313 Item No C242 | FLEXIBLE PAVEMENTS
135 | Line No 314 Item No | Place only Type 2.3 | m3 |  |  |  | 148 |  | 8380.2124 |  | 2 | 1007.0927 | 0 | 7373.1197 | 0 | 8380.2124
135.1 | 1 | QTY*density Tonnes Gravel |  |  | 2.4 |  | 355.2
135.2 | 2 | Truck & Dog | hr | P | 3 | 37 | 355.2 | 145 | 4176 | 28.8 | 9.6 | 0 | 0 | 4176 | 0 | 4176 | 62
| 3 | Placement
135.3 | 4 | Grader | hr | P | 1 | 44.44 | 355.2 | 145 | 1158.9559 | 7.9928 | 7.9928 | 0 | 0 | 1158.9559 | 0 | 1158.9559 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 44.44 | 355.2 | 100 | 799.2799 | 7.9928 | 7.9928 | 0 | 0 | 799.2799 | 0 | 799.2799 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 44.44 | 355.2 | 55 | 439.604 | 7.9928 | 7.9928 | 0 | 0 | 439.604 | 0 | 439.604 | 62
135.4 | 7 | Labour | hr | L | 3 | 44.44 | 355.2 | 42 | 1007.0927 | 23.9784 | 7.9928 | 1007.0927 | 0 | 0 | 0 | 1007.0927 | 62
| 8 | Backhoe | hr | P | 1 | 44.44 | 355.2 | 100 | 799.2799 | 7.9928 | 7.9928 | 0 | 0 | 799.2799 | 0 | 799.2799 | 62
136 | Line No 315 Item No | Place only Type 2.1 (828m²) | m3 |  |  |  | 96 |  | 8090.9335 |  | 3 | 1348.7693 | 0 | 6742.1641 | 0 | 8090.9335
136.1 | 1 | QTY*density Tonnes Gravel |  |  | 2.4 |  | 230.4
136.2 | 2 | Truck & Dog | hr | P | 3 | 37 | 230.4 | 145 | 2708.7568 | 18.6811 | 6.227 | 0 | 0 | 2708.7568 | 0 | 2708.7568 | 62
| 3 | Placement
136.3 | 4 | Grader | hr | P | 1 | 44.44 | 230.4 | 145 | 751.7552 | 5.1845 | 5.1845 | 0 | 0 | 751.7552 | 0 | 751.7552 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 44.44 | 230.4 | 100 | 518.4518 | 5.1845 | 5.1845 | 0 | 0 | 518.4518 | 0 | 518.4518 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 44.44 | 230.4 | 55 | 285.1485 | 5.1845 | 5.1845 | 0 | 0 | 285.1485 | 0 | 285.1485 | 62
| 7 | Labour | hr | L | 3 | 44.44 | 230.4 | 42 | 653.2493 | 15.5536 | 5.1845 | 653.2493 | 0 | 0 | 0 | 653.2493 | 62
| 8 | Backhoe | hr | P | 1 | 44.44 | 230.4 | 100 | 518.4518 | 5.1845 | 5.1845 | 0 | 0 | 518.4518 | 0 | 518.4518 | 62
| 9 | Final Trim
136.4 | 10 | Grader | hr | P | 1 | 150 | 828 | 145 | 800.4 | 5.52 | 5.52 | 0 | 0 | 800.4 | 0 | 800.4 | 63
| 11 | Water Cart - Hire | hr | P | 1 | 150 | 828 | 100 | 552 | 5.52 | 5.52 | 0 | 0 | 552 | 0 | 552 | 63
| 12 | MW Roller | hr | P | 1 | 75 | 828 | 55 | 607.2 | 11.04 | 11.04 | 0 | 0 | 607.2 | 0 | 607.2 | 63
136.5 | 13 | Labour | hr | L | 3 | 150 | 828 | 42 | 695.52 | 16.56 | 5.52 | 695.52 | 0 | 0 | 0 | 695.52 | 63
137 | Line No 316 Item No | Special Item - Geotextile layer | m2 |  |  |  | 928 |  | 1467.6239 |  | 1 | 225.6505 | 1071.84 | 170.1333 | 0 | 1467.6239
| 1 | A24 | m² | M | 1 | 1 | 1020.8 | 1.05 | 1071.84 |  |  | 0 | 1071.84 | 0 | 0 | 1071.84 | 222
137.1 | 2 | Labour | hr | L | 3 | 570 | 1020.8 | 42 | 225.6505 | 5.3726 | 1.7909 | 225.6505 | 0 | 0 | 0 | 225.6505 | 222
| 3 | Bobcat | hr | P | 1 | 570 | 1020.8 | 95 | 170.1333 | 1.7909 | 1.7909 | 0 | 0 | 170.1333 | 0 | 170.1333 | 222
| Line No 317 Item No C244 | SPRAYED BITUMINOUS SURFACING
| Line No 318 Item No C244(a) | Supply & Spray Primer, supply & spread aggregates, Primerbinder (including preparation of surface and precoated aggregate) complete
138 | Line No 319 Item No C244(a) | (vii) AMC5 | m2 |  |  |  | 828 |  | 13597.416 |  | 1 | 0 | 0 | 0 | 13597.416 | 13597.416
| 1 | Seal Visit Five | m² | S | 1 | 1 | 869.4 | 15.64 | 13597.416 | 869.4 | 869.4 | 0 | 0 | 0 | 13597.416 | 13597.416 | 64
| Line No 320 Item No C245 | ASPHALTIC CONCRETE
| Line No 321 Item No C245(c) | Dense Graded Asphalt in Wearing Course
139 | Line No 322 Item No C245(c) | (ii) 14mm Nominal Size | tonne |  |  |  | 99.36 |  | 33384.96 |  | 1 | 0 | 0 | 0 | 33384.96 | 33384.96
| 1 | DG14 - Doherty St | tonne | S | 1 | 1 | 104.328 | 320 | 33384.96 | 104.328 | 104.328 | 0 | 0 | 0 | 33384.96 | 33384.96 | 65
| Line No 324 Item No | ROAD FURNISHINGS
| Line No 325 Item No C262 | SIGNPOSTING
140 | Line No 326 Item No C262(g) | Remove and reinstate Existing Signs & Support Structures | Item |  |  |  | 2 |  | 1048 |  | 1 | 0 | 1048 | 0 | 0 | 1048
| 1 | Signs Complete | each | M | 1 | 1 | 2 | 140 | 280 |  | 4 | 0 | 280 | 0 | 0 | 280 | RFS
| 2 | N32 | m³ | M | 1 | 1 | 4 | 192 | 768 |  |  | 0 | 768 | 0 | 0 | 768 | C32
| Line No 327 Item No C265 | BOUNDARY FENCING
| Line No 328 Item No C265(a) | Supply & Erection of Boundary Fencing
141 | Line No 329 Item No C265(a) | Supply & Erection of Boundary Fencing (1200 high chainlink star picket fence) | m |  |  |  | 11 |  | 1375 |  | 1 | 0 | 0 | 0 | 1375 | 1375
| 1 | Fencing Subbie | LS | S | 1 | 1 | 1375 | 1 | 1375 |  | 2750 | 0 | 0 | 0 | 1375 | 1375 | 67
| Line No 331 Item No | MISCELLANEOUS
| Line No 332 Item No C271 | MINOR CONCRETE WORKS
| Line No 333 Item No C271(c) | Footpaths, Bike paths, Driveways, Median Toppings & Works of Similar Nature
142 | Line No 334 Item No C271(c) | (iv) Residential Invert Crossing (? m) | each |  |  |  | 5 |  | 2449.4667 |  | 4 | 25.2 | 1326.2667 | 138 | 960 | 2449.4667
| 1 | Purchase Materials
| 2 | N32 | m³ | M | 1 | 1 | 4.125 | 192 | 792 |  |  | 0 | 792 | 0 | 0 | 792 | C32
| 3 | Sand | tonne | M | 1 | 1 | 4.5 | 24 | 108 |  |  | 0 | 108 | 0 | 0 | 108 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 36 | 9.1 | 327.6 |  |  | 0 | 327.6 | 0 | 0 | 327.6 | RSM
| 5 | Abel Flex | m | M | 1 | 1 | 24 | 3 | 72 |  |  | 0 | 72 | 0 | 0 | 72 | RSM
| 6 | Detailed Excavation:
142.1 | 7 | Excavator - 25T | hr | P | 1 | 5 | 3 | 135 | 81 | 0.6 | 0.6 | 0 | 0 | 81 | 0 | 81 | 71
| 8 | Tipper | hr | P | 1 | 5 | 3 | 95 | 57 | 0.6 | 0.6 | 0 | 0 | 57 | 0 | 57 | 71
| 9 | Labour | hr | L | 1 | 5 | 3 | 42 | 25.2 | 0.6 | 0.6 | 25.2 | 0 | 0 | 0 | 25.2 | 71
| 10 | Form Pour & Finish
| 11 | Bar Chairs | each | M | 1 | 1 | 33.3333 | 0.8 | 26.6667 |  |  | 0 | 26.6667 | 0 | 0 | 26.6667 | RSM
| 12 | Concrete Subbie | m² | S | 1 | 1 | 30 | 32 | 960 | 30 | 30 | 0 | 0 | 0 | 960 | 960 | 71
| Line No 336 Item No | SERVICES
| Line No 337 Item No C320 | WATER RETICULATION
143 | Line No 338 Item No | Service connections | Lump |  |  |  | 1 |  | 7920 |  | 3 | 0 | 0 | 0 | 7920 | 7920
| 1 | WDC | Item | S | 1 | 1 | 7920 | 1 | 7920 |  | 3 | 0 | 0 | 0 | 7920 | 7920 | 103
144 | Line No 339 Item No | Alterations to water main | Lump |  |  |  | 1 |  | 7000 |  | 2 | 0 | 0 | 0 | 7000 | 7000
| 1 | WDC | Item | S | 1 | 1 | 7000 | 1 | 7000 |  | 2 | 0 | 0 | 0 | 7000 | 7000 | 103
145 | Line No 340 Item No | Alterations to valves and hydrant margins | Lump |  |  |  | 1 |  | 1000 |  | 2 | 0 | 0 | 0 | 1000 | 1000
| 1 | WDC | Item | S | 1 | 1 | 1000 | 1 | 1000 |  | 2 | 0 | 0 | 0 | 1000 | 1000 | 103
| Line No 342 Item No | SPECIFIED WORKS
146 | Line No 343 Item No | Special Item - As Constructed Survey and Plans | Lump |  |  |  | 1 |  | 2400 |  | 3 | 0 | 0 | 0 | 2400 | 2400
| 1 | Survey | Item | S | 1 | 1 | 2400 | 1 | 2400 |  | 19.2 | 0 | 0 | 0 | 2400 | 2400 | 12
700 | Line No 347 Item No | FAUST STREET
| Line No 349 Item No | QUALITY SYSTEM
| Line No 350 Item No CQC | QUALITY CONTROL REQUIREMENTS
147 | Line No 351 Item No QCP1 | Quality Verification & Control | Lump |  |  |  | 1 |  | 10470 |  | 0 | 3250 | 0 | 0 | 7220 | 10470
| 1 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 |  |  | 3250 | 0 | 0 | 0 | 3250 | 901
147.1 | 2 | (30) Field Density Tests |  |  |  |  | 30
147.2 | 3 | (6) Concrete Cylinder Sets |  |  |  |  | 6
| 4 | Field Density | each | S | 1 | 1 | 30 | 45 | 1350 |  |  | 0 | 0 | 0 | 1350 | 1350 | 13
| 5 | Gravel Properties Testing | each | S | 1 | 1 | 3 | 390 | 1170 |  |  | 0 | 0 | 0 | 1170 | 1170 | 13
| 6 | Concrete Cylinders | each | S | 1 | 1 | 6 | 150 | 900 |  |  | 0 | 0 | 0 | 900 | 900 | 13
147.3 | 7 | Survey | Item | S | 3800 | 1 | 3800 | 1 | 3800 |  |  | 0 | 0 | 0 | 3800 | 3800 | 11
| Line No 353 Item No | GENERAL REQUIREMENTS
| Line No 354 Item No C101 | GENERAL
| Line No 355 Item No C101(b) | Site Establishment & Disestablishment | Lump |  |  |  | 1
| Line No 357 Item No | ROAD & EARTHWORKS
| Line No 358 Item No C201 | CONTROL OF TRAFFIC
148 | Line No 359 Item No C201(a) | Control of Traffic | Lump |  |  |  | 1 |  | 34938.72 |  | 30 | 0 | 0 | 0 | 34938.72 | 34938.72
| 1 | (6) No. Weeks TC Required; No. = 6 days per week |  |  |  |  | 6
148.1 | 2 | Traffic Control Crew | hr | S | 6 | 1 | 342 | 102.16 | 34938.72 |  | 30 | 0 | 0 | 0 | 34938.72 | 34938.72 | 141
| Line No 360 Item No C211 | CONTROL OF EROSION & SEDIMENTATION
149 | Line No 361 Item No C211(a) | Temporary Erosion & Sedimentation Control (includes supply and installation of all components) | Lump |  |  |  | 1 |  | 11050 |  | 6 | 6300 | 0 | 4750 | 0 | 11050
| 1 | Labour | hr | L | 3 | 1 | 50 | 42 | 6300 | 150 | 50 | 6300 | 0 | 0 | 0 | 6300 | 151
| 2 | Bobcat | hr | P | 1 | 1 | 50 | 95 | 4750 | 50 | 50 | 0 | 0 | 4750 | 0 | 4750 | 151
| Line No 362 Item No C212 | CLEARING & GRUBBING
150 | Line No 363 Item No C212(a) | Clearing and Grubbing (removal of kerb & channel) | Lump |  |  |  | 1 |  | 10066.6667 |  | 2 | 1400 | 0 | 8666.6667 | 0 | 10066.6667
150.1 | 1 | Excavator - 25T | hr | P | 1 | 0.06 | 1 | 135 | 2250 | 16.6667 | 16.6667 | 0 | 0 | 2250 | 0 | 2250 | 41
150.2 | 2 | Tipper | hr | P | 3 | 0.06 | 1 | 95 | 4750 | 50 | 16.6667 | 0 | 0 | 4750 | 0 | 4750 | 41
| 3 | Water Cart - Hire | hr | P | 1 | 0.06 | 1 | 100 | 1666.6667 | 16.6667 | 16.6667 | 0 | 0 | 1666.6667 | 0 | 1666.6667 | 41
| 4 | Labour | hr | L | 2 | 0.06 | 1 | 42 | 1400 | 33.3333 | 16.6667 | 1400 | 0 | 0 | 0 | 1400 | 41
| Line No 364 Item No C213 | EARTHWORKS
151 | Line No 365 Item No C213(b) | General Earthworks Cut | m3 |  |  |  | 543 |  | 13092.3333 |  | 3 | 1583.75 | 0 | 11508.5833 | 0 | 13092.3333
151.1 | 1 | Excavator - 25T | hr | P | 1 | 40 | 543 | 135 | 1832.625 | 13.575 | 13.575 | 0 | 0 | 1832.625 | 0 | 1832.625 | 53
| 2 | Truck & Dog | hr | P | 3 | 40 | 543 | 145 | 5905.125 | 40.725 | 13.575 | 0 | 0 | 5905.125 | 0 | 5905.125 | 53
| 3 | Water Cart - Hire | hr | P | 1 | 40 | 543 | 100 | 1357.5 | 13.575 | 13.575 | 0 | 0 | 1357.5 | 0 | 1357.5 | 53
| 4 | Labour | hr | L | 1 | 40 | 543 | 42 | 570.15 | 13.575 | 13.575 | 570.15 | 0 | 0 | 0 | 570.15 | 53
| 5 | Prepare Sub-grade
151.2 | 6 | Grader | hr | P | 1 | 150 | 1206.6667 | 145 | 1166.4444 | 8.0444 | 8.0444 | 0 | 0 | 1166.4444 | 0 | 1166.4444 | 61
| 7 | Water Cart - Hire | hr | P | 1 | 150 | 1206.6667 | 100 | 804.4444 | 8.0444 | 8.0444 | 0 | 0 | 804.4444 | 0 | 804.4444 | 61
| 8 | SD Roller - Wet (No Op) | hr | P | 1 | 150 | 1206.6667 | 55 | 442.4444 | 8.0444 | 8.0444 | 0 | 0 | 442.4444 | 0 | 442.4444 | 61
| 9 | Labour | hr | L | 3 | 150 | 1206.6667 | 42 | 1013.6 | 24.1333 | 8.0444 | 1013.6 | 0 | 0 | 0 | 1013.6 | 61
152 | Line No 366 Item No C213(d) | Replace unsuitable material below sub grade with select material complete (provisional) | m3 |  |  |  | 20 |  | 1310.6667 |  | 1 | 224 | 0 | 1086.6667 | 0 | 1310.6667
152.1 | 1 | Excavator - 25T | hr | P | 1 | 15 | 20 | 135 | 180 | 1.3333 | 1.3333 | 0 | 0 | 180 | 0 | 180 | 57
| 2 | Truck & Dog | hr | P | 2 | 15 | 20 | 145 | 386.6667 | 2.6667 | 1.3333 | 0 | 0 | 386.6667 | 0 | 386.6667 | 57
| 3 | Water Cart - Hire | hr | P | 1 | 15 | 20 | 100 | 133.3333 | 1.3333 | 1.3333 | 0 | 0 | 133.3333 | 0 | 133.3333 | 57
| 4 | Labour | hr | L | 1 | 15 | 20 | 42 | 56 | 1.3333 | 1.3333 | 56 | 0 | 0 | 0 | 56 | 57
| 5 | Fill
152.2 | 6 | Excavator - 25T | hr | P | 1 | 15 | 20 | 135 | 180 | 1.3333 | 1.3333 | 0 | 0 | 180 | 0 | 180 | 57
| 7 | SD Roller - Wet (No Op) | hr | P | 1 | 15 | 20 | 55 | 73.3333 | 1.3333 | 1.3333 | 0 | 0 | 73.3333 | 0 | 73.3333 | 57
| 8 | Water Cart - Hire | hr | P | 1 | 15 | 20 | 100 | 133.3333 | 1.3333 | 1.3333 | 0 | 0 | 133.3333 | 0 | 133.3333 | 57
| 9 | Labour | hr | L | 3 | 15 | 20 | 42 | 168 | 4 | 1.3333 | 168 | 0 | 0 | 0 | 168 | 57
| Line No 368 Item No | STORMWATER DRAINAGE
| Line No 369 Item No C220 | STORMWATER DRAINAGE - GENERAL
153 | Line No 370 Item No | Removal / Demolition of Drainage Components complete | Lump |  |  |  | 1 |  | 5452.498 |  | 2 | 756.7568 | 0 | 4695.7412 | 0 | 5452.498
153.1 | 1 | Excavator - 25T | hr | P | 1 | 0.11 | 1 | 135 | 1227.2727 | 9.0909 | 9.0909 | 0 | 0 | 1227.2727 | 0 | 1227.2727 | 41
153.2 | 2 | Tipper | hr | P | 3 | 0.111 | 1 | 95 | 2567.5676 | 27.027 | 9.009 | 0 | 0 | 2567.5676 | 0 | 2567.5676 | 41
| 3 | Water Cart - Hire | hr | P | 1 | 0.111 | 1 | 100 | 900.9009 | 9.009 | 9.009 | 0 | 0 | 900.9009 | 0 | 900.9009 | 41
| 4 | Labour | hr | L | 2 | 0.111 | 1 | 42 | 756.7568 | 18.018 | 9.009 | 756.7568 | 0 | 0 | 0 | 756.7568 | 41
| Line No 371 Item No C221 | PIPE DRAINAGE (SUPPLY & INSTALL)
| Line No 372 Item No C221(a) | OTHER
154 | Line No 373 Item No C221(a) | Connect property drainage pipes (No. 21) | Lump |  |  |  | 1 |  | 8295 |  | 5 | 0 | 4725 | 0 | 3570 | 8295
| 1 | (21) No. of properties |  |  |  |  | 21
| 2 | 150 SN8 Sewer Pipe | m | M | 1 | 1 | 126 | 25 | 3150 |  |  | 0 | 3150 | 0 | 0 | 3150 | SWP
| 3 | Kerb Adaptors | each | M | 1 | 1 | 21 | 75 | 1575 |  |  | 0 | 1575 | 0 | 0 | 1575 | SWP
154.1 | 4 | Plumber | hr | S | 1 | 0.5 | 21 | 85 | 3570 | 42 | 42 | 0 | 0 | 0 | 3570 | 3570 | 81
| Line No 374 Item No C222 | PRECAST BOX CULVERTS (SUPPLY & INSTALL)
155 | Line No 375 Item No C222(a) | In-Situ reinforced concrete Base Slab for culverts complete | m3 |  |  |  | 3 |  | 1953.1333 |  | 2 | 0 | 978.1333 | 0 | 975 | 1953.1333
| 1 | 1200 x 600 (12m)
| 2 | QTY/.2 = Area |  |  |  |  | 15
| 3 | Sand | tonne | M | 1 | 1 | 1.5 | 24 | 36 |  |  | 0 | 36 | 0 | 0 | 36 | QMS
| 4 | RL1218 | m² | M | 1 | 1 | 18 | 18 | 324 |  |  | 0 | 324 | 0 | 0 | 324 | RSM
| 5 | Bar Chairs | each | M | 1 | 1 | 16.6667 | 0.8 | 13.3333 |  |  | 0 | 13.3333 | 0 | 0 | 13.3333 | RSM
| 6 | N32 | m³ | M | 1 | 1 | 3.15 | 192 | 604.8 |  |  | 0 | 604.8 | 0 | 0 | 604.8 | C32
| 7 | RCBC Slab Subbie | m² | S | 1 | 1 | 15 | 65 | 975 | 15 | 15 | 0 | 0 | 0 | 975 | 975 | 72
156 | Line No 376 Item No C222(b) | 1200 x 300 | m |  |  |  | 12.4 |  | 8442.852 |  | 2 | 1323 | 5384.852 | 1735 | 0 | 8442.852
| 1 | (11) Box Units to Stand |  |  |  |  | 11
| 2 | (15) Hand Placed Backfill |  |  |  |  | 15
| 3 | RCBC - 1200 x 300 | m | M | 1 | 1 | 13.2 | 393.36 | 5192.352 |  |  | 0 | 5192.352 | 0 | 0 | 5192.352 | SWC
156.1 | 4 | Excavator - 25T | hr | P | 1 | 2 | 11 | 135 | 742.5 | 5.5 | 5.5 | 0 | 0 | 742.5 | 0 | 742.5 | 181
156.2 | 5 | Labour | hr | L | 3 | 2 | 11 | 42 | 693 | 16.5 | 5.5 | 693 | 0 | 0 | 0 | 693 | 181
| 6 | Denso Tape | m | M | 1 | 1 | 38.5 | 5 | 192.5 |  |  | 0 | 192.5 | 0 | 0 | 192.5 | 181
156.3 | 7 | Bobcat | hr | P | 1 | 3 | 15 | 95 | 475 | 5 | 5 | 0 | 0 | 475 | 0 | 475 | 181
156.4 | 8 | Labour | hr | L | 3 | 3 | 15 | 42 | 630 | 15 | 5 | 630 | 0 | 0 | 0 | 630 | 181
| 9 | Plate Compactor | hr | P | 1 | 3 | 15 | 3.5 | 17.5 | 5 | 5 | 0 | 0 | 17.5 | 0 | 17.5 | 181
| 10 | Water Cart - Hire | hr | P | 1 | 3 | 15 | 100 | 500 | 5 | 5 | 0 | 0 | 500 | 0 | 500 | 181
| Line No 377 Item No C223 | DRAINAGE STRUCTURES
| Line No 378 Item No C223(b) | Pits, Dissipators, Channel Basins & Other Supplementary Structures
157 | Line No 379 Item No C223(b) | MCC Type A Gully Pit | each |  |  |  | 4 |  | 14020 |  | 4 | 1360 | 5160 | 0 | 7500 | 14020
| 1 | Pit Builder | each | S | 1 | 2 | 4 | 3750 | 7500 | 2 | 2 | 0 | 0 | 0 | 7500 | 7500 | 85
| 2 | MCC Type A Gully Top | each | M | 1 | 1 | 4 | 1290 | 5160 |  |  | 0 | 5160 | 0 | 0 | 5160 | SWPC
| 3 | Concretor - Labour | hr | L | 1 | 1 | 16 | 85 | 1360 | 16 | 16 | 1360 | 0 | 0 | 0 | 1360 | 85
| Line No 380 Item No C224 | OPEN DRAINS, INCLUDING KERB & CHANNEL
| Line No 381 Item No C224(h) | Kerb &/or Channel
158 | Line No 382 Item No C224(h) | (i) Concrete Barrier Kerb & Channel B1 complete | m |  |  |  | 475 |  | 25252.436 |  | 3 | 0 | 11002.436 | 0 | 14250 | 25252.436
| 1 | Use Kerb Subbie. We will supply sand & cement for slurry
| 2 | S32 - Kerb Mix | m³ | M | 1 | 1 | 55.2326 | 190 | 10494.186 |  |  | 0 | 10494.186 | 0 | 0 | 10494.186 | CKM
| 3 | Sand | tonne | M | 1 | 1 | 6.3333 | 24 | 152 |  |  | 0 | 152 | 0 | 0 | 152 | QMS
| 4 | Cement | tonne | M | 1 | 1 | 0.79167 | 450 | 356.25 |  |  | 0 | 356.25 | 0 | 0 | 356.25 | CSA
| 5 | Kerb Subbie | m | S | 1 | 1 | 475 | 30 | 14250 | 2.375 | 2.375 | 0 | 0 | 0 | 14250 | 14250 | 71
| Line No 384 Item No | SUB-SURFACE DRAINAGE
| Line No 385 Item No C231 | SUBSOIL & FOUNDATION DRAINS
159 | Line No 386 Item No C231(b) | Subsoil Drain Pipe - 100mm dia Slotted Corrugated Plastic Pipe complete (provisional quantity) | m |  |  |  | 475 |  | 19609.062 |  | 6 | 5387.0387 | 2880.4 | 9983.1233 | 1358.5 | 19609.062
| 1 | Excavate & install sub-soil drain at a rate of 100m per day. Use 300 trench and sand to backfill.
| 2 | Sub Soil Drain | m | M | 1 | 1 | 475 | 2.5 | 1187.5 |  |  | 0 | 1187.5 | 0 | 0 | 1187.5 | 87
| 3 | Sub Soil Clean Out - Inst | each | S | 1 | 1 | 9.5 | 143 | 1358.5 | 9.5 | 9.5 | 0 | 0 | 0 | 1358.5 | 1358.5 | 87
| 4 | Sand | tonne | M | 1 | 1 | 70.5375 | 24 | 1692.9 |  |  | 0 | 1692.9 | 0 | 0 | 1692.9 | QMS
159.1 | 5 | Excavator - 25T | hr | P | 1 | 11.11 | 475 | 135 | 5771.8272 | 42.7543 | 42.7543 | 0 | 0 | 5771.8272 | 0 | 5771.8272 | 87
| 6 | Labour | hr | L | 3 | 11.11 | 475 | 42 | 5387.0387 | 128.2628 | 42.7543 | 5387.0387 | 0 | 0 | 0 | 5387.0387 | 87
| 7 | Bobcat | hr | P | 1 | 11.11 | 475 | 95 | 4061.6562 | 42.7543 | 42.7543 | 0 | 0 | 4061.6562 | 0 | 4061.6562 | 87
| 8 | Plate Compactor | hr | P | 1 | 11.11 | 475 | 3.5 | 149.64 | 42.7543 | 42.7543 | 0 | 0 | 149.64 | 0 | 149.64 | 87
| Line No 388 Item No | PAVEMENTS
| Line No 389 Item No C242 | FLEXIBLE PAVEMENTS
160 | Line No 390 Item No | Place only Type 2.3 (includes cart, place, compact & trim) | m3 |  |  |  | 304 |  | 22392.3302 |  | 3 | 3309.2009 | 0 | 19083.1293 | 0 | 22392.3302
160.1 | 1 | QTY*2.4 Tonnes Gravel |  |  | 2.4 |  | 729.6
160.2 | 2 | Truck & Dog | hr | P | 3 | 37 | 729.6 | 145 | 8577.7297 | 59.1568 | 19.7189 | 0 | 0 | 8577.7297 | 0 | 8577.7297 | 62
| 3 | Placement
160.3 | 4 | Grader | hr | P | 1 | 27.78 | 729.6 | 145 | 3808.2073 | 26.2635 | 26.2635 | 0 | 0 | 3808.2073 | 0 | 3808.2073 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 27.78 | 729.6 | 100 | 2626.3499 | 26.2635 | 26.2635 | 0 | 0 | 2626.3499 | 0 | 2626.3499 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 27.78 | 729.6 | 55 | 1444.4924 | 26.2635 | 26.2635 | 0 | 0 | 1444.4924 | 0 | 1444.4924 | 62
| 7 | Labour | hr | L | 3 | 27.78 | 729.6 | 42 | 3309.2009 | 78.7905 | 26.2635 | 3309.2009 | 0 | 0 | 0 | 3309.2009 | 62
| 8 | Backhoe | hr | P | 1 | 27.78 | 729.6 | 100 | 2626.3499 | 26.2635 | 26.2635 | 0 | 0 | 2626.3499 | 0 | 2626.3499 | 62
161 | Line No 391 Item No | Place only Type 2.1 (includes cart, place, compact & trim) | m3 |  |  |  | 181 |  | 17201.6533 |  | 4 | 2983.8808 | 0 | 14217.7725 | 0 | 17201.6533
161.1 | 1 | QTY*2.4 Tonnes Gravel |  |  | 2.4 |  | 434.4
161.2 | 2 | Truck & Dog | hr | P | 3 | 37 | 434.4 | 145 | 5107.1351 | 35.2216 | 11.7405 | 0 | 0 | 5107.1351 | 0 | 5107.1351 | 62
| 3 | Placement
161.3 | 4 | Grader | hr | P | 1 | 27.78 | 434.4 | 145 | 2267.3866 | 15.6371 | 15.6371 | 0 | 0 | 2267.3866 | 0 | 2267.3866 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 27.78 | 434.4 | 100 | 1563.7149 | 15.6371 | 15.6371 | 0 | 0 | 1563.7149 | 0 | 1563.7149 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 27.78 | 434.4 | 55 | 860.0432 | 15.6371 | 15.6371 | 0 | 0 | 860.0432 | 0 | 860.0432 | 62
| 7 | Labour | hr | L | 3 | 27.78 | 434.4 | 42 | 1970.2808 | 46.9114 | 15.6371 | 1970.2808 | 0 | 0 | 0 | 1970.2808 | 62
| 8 | Backhoe | hr | P | 1 | 27.78 | 434.4 | 100 | 1563.7149 | 15.6371 | 15.6371 | 0 | 0 | 1563.7149 | 0 | 1563.7149 | 62
| 9 | Final Trim
161.4 | 10 | Grader | hr | P | 1 | 150 | 1206.6667 | 145 | 1166.4444 | 8.0444 | 8.0444 | 0 | 0 | 1166.4444 | 0 | 1166.4444 | 63
| 11 | Water Cart - Hire | hr | P | 1 | 150 | 1206.6667 | 100 | 804.4444 | 8.0444 | 8.0444 | 0 | 0 | 804.4444 | 0 | 804.4444 | 63
| 12 | MW Roller | hr | P | 1 | 75 | 1206.6667 | 55 | 884.8889 | 16.0889 | 16.0889 | 0 | 0 | 884.8889 | 0 | 884.8889 | 63
| 13 | Labour | hr | L | 3 | 150 | 1206.6667 | 42 | 1013.6 | 24.1333 | 8.0444 | 1013.6 | 0 | 0 | 0 | 1013.6 | 63
162 | Line No 392 Item No | Special Item - Geogrid layer | m2 |  |  |  | 1595 |  | 9505.3885 |  | 1 | 387.8368 | 8825.135 | 292.4167 | 0 | 9505.3885
| 1 | TX160 - Geogrid | m² | M | 1 | 1 | 1754.5 | 5.03 | 8825.135 |  |  | 0 | 8825.135 | 0 | 0 | 8825.135 | 222
162.1 | 2 | Labour | hr | L | 3 | 570 | 1754.5 | 42 | 387.8368 | 9.2342 | 3.0781 | 387.8368 | 0 | 0 | 0 | 387.8368 | 222
| 3 | Bobcat | hr | P | 1 | 570 | 1754.5 | 95 | 292.4167 | 3.0781 | 3.0781 | 0 | 0 | 292.4167 | 0 | 292.4167 | 222
163 | Line No 393 Item No | Special Item - Geotextile layer | m2 |  |  |  | 1595 |  | 2522.4785 |  | 1 | 387.8368 | 1842.225 | 292.4167 | 0 | 2522.4785
| 1 | A24 | m² | M | 1 | 1 | 1754.5 | 1.05 | 1842.225 |  |  | 0 | 1842.225 | 0 | 0 | 1842.225 | 222
163.1 | 2 | Labour | hr | L | 3 | 570 | 1754.5 | 42 | 387.8368 | 9.2342 | 3.0781 | 387.8368 | 0 | 0 | 0 | 387.8368 | 222
| 3 | Bobcat | hr | P | 1 | 570 | 1754.5 | 95 | 292.4167 | 3.0781 | 3.0781 | 0 | 0 | 292.4167 | 0 | 292.4167 | 222
| Line No 394 Item No C244 | SPRAYED BITUMINOUS SURFACING
| Line No 395 Item No C244(a) | Supply & Spray Primer, supply & spread aggregates, Primerbinder (including preparation of surface) complete
164 | Line No 396 Item No C244(a) | (vii) AMC5 | m2 |  |  |  | 1206 |  | 14537.124 |  | 1 | 0 | 0 | 0 | 14537.124 | 14537.124
| 1 | Seal Visit Six | m² | S | 1 | 1 | 1266.3 | 11.48 | 14537.124 |  | 0.603 | 0 | 0 | 0 | 14537.124 | 14537.124 | 64
| Line No 397 Item No C245 | ASPHALTIC CONCRETE
| Line No 398 Item No C245(c) | Dense Graded Asphalt in Wearing Course
165 | Line No 399 Item No C245(c) | (i) 10mm Nominal Size | tonne |  |  |  | 87 |  | 30256.947 |  | 1 | 0 | 0 | 0 | 30256.947 | 30256.947
| 1 | DG14 - Faust St | tonne | S | 1 | 1 | 91.35 | 331.22 | 30256.947 |  | 0.435 | 0 | 0 | 0 | 30256.947 | 30256.947 | 65
| Line No 401 Item No | ROAD FURNISHINGS
| Line No 402 Item No C261 | PAVEMENT MARKINGS
166 | Line No 403 Item No C261(a) | Pavement Marking Paint - Longitudinal Lines including car parking bays | m |  |  |  | 475 |  | 4000 |  | 1 | 0 | 0 | 0 | 4000 | 4000
| 1 | Line Marking | m² | S | 1 | 1 | 4000 | 1 | 4000 |  | 0.2375 | 0 | 0 | 0 | 4000 | 4000 | 66
| Line No 404 Item No C262 | SIGNPOSTING
167 | Line No 405 Item No C262(g) | Remove and reinstate Existing Signs & Support Structures | Item |  |  |  | 1 |  | 2832 |  | 2 | 0 | 2832 | 0 | 0 | 2832
| 1 | Signs Complete | each | M | 1 | 1 | 12 | 140 | 1680 |  | 18 | 0 | 1680 | 0 | 0 | 1680 | RFS
| 2 | N32 | m³ | M | 1 | 1 | 6 | 192 | 1152 |  |  | 0 | 1152 | 0 | 0 | 1152 | C32
| Line No 407 Item No | MISCELLANEOUS
| Line No 408 Item No C271 | MINOR CONCRETE WORKS
| Line No 409 Item No C271(c) | Footpaths, Bike paths, Driveways, Median Toppings & Works of Similar Nature
168 | Line No 410 Item No C271(c) | (iv) Residential Invert Crossing | each |  |  |  | 21 |  | 9765.52 |  | 9 | 25.2 | 5570.32 | 138 | 4032 | 9765.52
| 1 | Purchase Materials
| 2 | N32 | m³ | M | 1 | 1 | 17.325 | 192 | 3326.4 |  |  | 0 | 3326.4 | 0 | 0 | 3326.4 | C32
| 3 | Sand | tonne | M | 1 | 1 | 18.9 | 24 | 453.6 |  |  | 0 | 453.6 | 0 | 0 | 453.6 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 151.2 | 9.1 | 1375.92 |  |  | 0 | 1375.92 | 0 | 0 | 1375.92 | RSM
| 5 | Abel Flex | m | M | 1 | 1 | 100.8 | 3 | 302.4 |  |  | 0 | 302.4 | 0 | 0 | 302.4 | RSM
| 6 | Detailed Excavation:
168.1 | 7 | Excavator - 25T | hr | P | 1 | 21 | 12.6 | 135 | 81 | 0.6 | 0.6 | 0 | 0 | 81 | 0 | 81 | 71
| 8 | Tipper | hr | P | 1 | 21 | 12.6 | 95 | 57 | 0.6 | 0.6 | 0 | 0 | 57 | 0 | 57 | 71
| 9 | Labour | hr | L | 1 | 21 | 12.6 | 42 | 25.2 | 0.6 | 0.6 | 25.2 | 0 | 0 | 0 | 25.2 | 71
| 10 | Form Pour & Finish
| 11 | Bar Chairs | each | M | 1 | 1 | 140 | 0.8 | 112 |  |  | 0 | 112 | 0 | 0 | 112 | RSM
| 12 | Concrete Subbie | m² | S | 1 | 1 | 126 | 32 | 4032 |  | 7 | 0 | 0 | 0 | 4032 | 4032 | 71
| Line No 411 Item No C273 | LANDSCAPE
| Line No 412 Item No C273(a) | Vegetation of Slopes 1 in 3 or Flatter
169 | Line No 413 Item No C273(a) | (i) Grass Seeding | m2 |  |  |  | 500 |  | 1347.5 |  | 1 | 0 | 0 | 0 | 1347.5 | 1347.5
| 1 | Grass Seeding | m² | S | 1 | 1 | 550 | 2.45 | 1347.5 |  | 0.055 | 0 | 0 | 0 | 1347.5 | 1347.5 | 121
170 | Line No 414 Item No C273(a) | (ii) Turfing | m2 |  |  |  | 250 |  | 2231.25 |  | 1 | 0 | 0 | 0 | 2231.25 | 2231.25
| 1 | Turf Subbie | m² | S | 1 | 1 | 262.5 | 8.5 | 2231.25 |  | 0.525 | 0 | 0 | 0 | 2231.25 | 2231.25 | 121
| Line No 415 Item No C273(d) | Landscape Planting
171 | Line No 416 Item No C273(d) | (iii) Individual Planting | each |  |  |  | 4 |  | 3000 |  | 1 | 0 | 0 | 0 | 3000 | 3000
| 1 | Pot Plants | each | S | 1 | 1 | 4 | 750 | 3000 |  | 0.04 | 0 | 0 | 0 | 3000 | 3000 | 121
172 | Line No 417 Item No | Supply and place Imported Topsoil | m3 |  |  |  | 50 |  | 2645 |  | 1 | 420 | 1750 | 475 | 0 | 2645
| 1 | Topsoil | m³ | M | 1 | 1 | 50 | 35 | 1750 |  |  | 0 | 1750 | 0 | 0 | 1750 | 33
172.1 | 2 | Bobcat | hr | P | 1 | 10 | 50 | 95 | 475 | 5 | 5 | 0 | 0 | 475 | 0 | 475 | 33
| 3 | Labour | hr | L | 2 | 10 | 50 | 42 | 420 | 10 | 5 | 420 | 0 | 0 | 0 | 420 | 33
| Line No 419 Item No | SERVICES
| Line No 420 Item No C306 | ROAD OPENINGS & RESTORATION
| Line No 421 Item No C306(a) | Sawcut Existing Pavement / Footpath
173 | Line No 422 Item No C306(a) | Sawcut Bituminous pavement | m |  |  |  | 300 |  | 3000 |  | 2 | 0 | 0 | 0 | 3000 | 3000
| 1 | Sawcut | m | S | 1 | 1 | 300 | 10 | 3000 |  | 2 | 0 | 0 | 0 | 3000 | 3000 | 75
| Line No 423 Item No C320 | WATER RETICULATION
174 | Line No 424 Item No | Service connections | Lump |  |  |  | 1 |  | 29880 |  | 4 | 0 | 0 | 0 | 29880 | 29880
| 1 | WDC | Item | S | 1 | 1 | 29880 | 1 | 29880 |  | 4 | 0 | 0 | 0 | 29880 | 29880 | 103
| Line No 426 Item No | SPECIFIED WORKS
175 | Line No 427 Item No | Special Item - As Constructed Survey and Plans | Lump |  |  |  | 1 |  | 2400 |  | 3 | 0 | 0 | 0 | 2400 | 2400
| 1 | Survey | Item | S | 1 | 1 | 2400 | 1 | 2400 |  | 19.2 | 0 | 0 | 0 | 2400 | 2400 | 12
800 | Line No 431 Item No | JUPP STREET
| Line No 433 Item No | QUALITY SYSTEM
| Line No 434 Item No CQC | QUALITY CONTROL REQUIREMENTS
176 | Line No 435 Item No QCP1 | Quality Verification & Control | Lump |  |  |  | 1 |  | 9860 |  | 0 | 3250 | 0 | 0 | 6610 | 9860
| 1 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 |  |  | 3250 | 0 | 0 | 0 | 3250 | 901
176.1 | 2 | (12) Field Density Tests |  |  |  |  | 12
176.2 | 3 | (6) Concrete Cylinder Sets |  |  |  |  | 6
| 4 | Field Density | each | S | 1 | 1 | 12 | 45 | 540 |  |  | 0 | 0 | 0 | 540 | 540 | 13
| 5 | Gravel Properties Testing | each | S | 1 | 1 | 3 | 390 | 1170 |  |  | 0 | 0 | 0 | 1170 | 1170 | 13
| 6 | Concrete Cylinders | each | S | 1 | 1 | 6 | 150 | 900 |  |  | 0 | 0 | 0 | 900 | 900 | 13
176.3 | 7 | Survey | Item | S | 4000 | 1 | 4000 | 1 | 4000 |  |  | 0 | 0 | 0 | 4000 | 4000 | 11
| Line No 437 Item No | GENERAL REQUIREMENTS
| Line No 438 Item No C101 | GENERAL
| Line No 439 Item No C101(b) | Site Establishment & Disestablishment | Lump |  |  |  | 1
| Line No 441 Item No | ROAD & EARTHWORKS
| Line No 442 Item No C201 | CONTROL OF TRAFFIC
177 | Line No 443 Item No C201(a) | Control of Traffic | Lump |  |  |  | 1 |  | 23292.48 |  | 20 | 0 | 0 | 0 | 23292.48 | 23292.48
| 1 | (4) No. Weeks TC Required; No. = 6 days per week |  |  |  |  | 4
177.1 | 2 | Traffic Control Crew | hr | S | 6 | 1 | 228 | 102.16 | 23292.48 |  | 20 | 0 | 0 | 0 | 23292.48 | 23292.48 | 141
| Line No 444 Item No C201(b) | Provision of Temporary Roadways, Side-tracks and Detours | Lump |  |  |  | 1
| Line No 445 Item No C211 | CONTROL OF EROSION & SEDIMENTATION
178 | Line No 446 Item No C211(a) | Temporary Erosion & Sedimentation Control (includes supply and installation of all components) | Lump |  |  |  | 1 |  | 11050 |  | 6 | 6300 | 0 | 4750 | 0 | 11050
| 1 | Labour | hr | L | 3 | 1 | 50 | 42 | 6300 | 150 | 50 | 6300 | 0 | 0 | 0 | 6300 | 151
| 2 | Bobcat | hr | P | 1 | 1 | 50 | 95 | 4750 | 50 | 50 | 0 | 0 | 4750 | 0 | 4750 | 151
| Line No 447 Item No C212 | CLEARING & GRUBBING
179 | Line No 448 Item No | Special Item - Demolition of Structure (concrete slabs, culverts, pipes etc) | Lump |  |  |  | 1 |  | 10066.6667 |  | 2 | 1400 | 0 | 8666.6667 | 0 | 10066.6667
179.1 | 1 | Excavator - 25T | hr | P | 1 | 0.06 | 1 | 135 | 2250 | 16.6667 | 16.6667 | 0 | 0 | 2250 | 0 | 2250 | 41
179.2 | 2 | Tipper | hr | P | 3 | 0.06 | 1 | 95 | 4750 | 50 | 16.6667 | 0 | 0 | 4750 | 0 | 4750 | 41
| 3 | Water Cart - Hire | hr | P | 1 | 0.06 | 1 | 100 | 1666.6667 | 16.6667 | 16.6667 | 0 | 0 | 1666.6667 | 0 | 1666.6667 | 41
| 4 | Labour | hr | L | 2 | 0.06 | 1 | 42 | 1400 | 33.3333 | 16.6667 | 1400 | 0 | 0 | 0 | 1400 | 41
| Line No 450 Item No C213 | EARTHWORKS
180 | Line No 451 Item No C213(a) | Removal & Stockpiling of Topsoil for reuse (100mm thick nom.) | m3 |  |  |  | 155 |  | 2613.5614 |  | 1 | 195.3195 | 0 | 2418.2418 | 0 | 2613.5614
180.1 | 1 | Excavator - 25T | hr | P | 1 | 33.33 | 155 | 135 | 627.8128 | 4.6505 | 4.6505 | 0 | 0 | 627.8128 | 0 | 627.8128 | 33
180.2 | 2 | Tipper | hr | P | 3 | 33.33 | 155 | 95 | 1325.3825 | 13.9514 | 4.6505 | 0 | 0 | 1325.3825 | 0 | 1325.3825 | 33
| 3 | Water Cart - Hire | hr | P | 1 | 33.33 | 155 | 100 | 465.0465 | 4.6505 | 4.6505 | 0 | 0 | 465.0465 | 0 | 465.0465 | 33
| 4 | Labour | hr | L | 1 | 33.33 | 155 | 42 | 195.3195 | 4.6505 | 4.6505 | 195.3195 | 0 | 0 | 0 | 195.3195 | 33
181 | Line No 452 Item No C213(b) | General Earthworks Cut | m3 |  |  |  | 775 |  | 15596.6371 |  | 3 | 1346.6286 | 0 | 14250.0085 | 0 | 15596.6371
181.1 | 1 | Excavator - 25T | hr | P | 1 | 40 | 775 | 135 | 2615.625 | 19.375 | 19.375 | 0 | 0 | 2615.625 | 0 | 2615.625 | 53
181.2 | 2 | Truck & Dog | hr | P | 3 | 40 | 775 | 145 | 8428.125 | 58.125 | 19.375 | 0 | 0 | 8428.125 | 0 | 8428.125 | 53
| 3 | Water Cart - Hire | hr | P | 1 | 40 | 775 | 100 | 1937.5 | 19.375 | 19.375 | 0 | 0 | 1937.5 | 0 | 1937.5 | 53
| 4 | Labour | hr | L | 1 | 40 | 775 | 42 | 813.75 | 19.375 | 19.375 | 813.75 | 0 | 0 | 0 | 813.75 | 53
| 5 | Prepare Sub-grade
181.3 | 6 | Grader | hr | P | 1 | 250 | 1057.2988 | 145 | 613.2333 | 4.2292 | 4.2292 | 0 | 0 | 613.2333 | 0 | 613.2333 | 61
| 7 | Water Cart - Hire | hr | P | 1 | 250 | 1057.2988 | 100 | 422.9195 | 4.2292 | 4.2292 | 0 | 0 | 422.9195 | 0 | 422.9195 | 61
| 8 | SD Roller - Wet (No Op) | hr | P | 1 | 250 | 1057.2988 | 55 | 232.6057 | 4.2292 | 4.2292 | 0 | 0 | 232.6057 | 0 | 232.6057 | 61
| 9 | Labour | hr | L | 3 | 250 | 1057.2988 | 42 | 532.8786 | 12.6876 | 4.2292 | 532.8786 | 0 | 0 | 0 | 532.8786 | 61
182 | Line No 453 Item No C213(c) | General Earthworks Fill | m3 |  |  |  | 27 |  | 757.35 |  | 1 | 170.1 | 0 | 587.25 | 0 | 757.35
182.1 | 1 | Excavator - 25T | hr | P | 1 | 20 | 27 | 135 | 182.25 | 1.35 | 1.35 | 0 | 0 | 182.25 | 0 | 182.25 | 53
| 2 | Grader | hr | P | 1 | 20 | 27 | 145 | 195.75 | 1.35 | 1.35 | 0 | 0 | 195.75 | 0 | 195.75 | 53
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 20 | 27 | 55 | 74.25 | 1.35 | 1.35 | 0 | 0 | 74.25 | 0 | 74.25 | 53
| 4 | Water Cart - Hire | hr | P | 1 | 20 | 27 | 100 | 135 | 1.35 | 1.35 | 0 | 0 | 135 | 0 | 135 | 53
| 5 | Labour | hr | L | 3 | 20 | 27 | 42 | 170.1 | 4.05 | 1.35 | 170.1 | 0 | 0 | 0 | 170.1 | 53
183 | Line No 454 Item No C213(d) | Replace unsuitable material below sub grade with select material complete (PROVISIONAL) | m3 |  |  |  | 20 |  | 1310.6667 |  | 1 | 224 | 0 | 1086.6667 | 0 | 1310.6667
183.1 | 1 | Excavator - 25T | hr | P | 1 | 15 | 20 | 135 | 180 | 1.3333 | 1.3333 | 0 | 0 | 180 | 0 | 180 | 57
183.2 | 2 | Truck & Dog | hr | P | 2 | 15 | 20 | 145 | 386.6667 | 2.6667 | 1.3333 | 0 | 0 | 386.6667 | 0 | 386.6667 | 57
| 3 | Water Cart - Hire | hr | P | 1 | 15 | 20 | 100 | 133.3333 | 1.3333 | 1.3333 | 0 | 0 | 133.3333 | 0 | 133.3333 | 57
| 4 | Labour | hr | L | 1 | 15 | 20 | 42 | 56 | 1.3333 | 1.3333 | 56 | 0 | 0 | 0 | 56 | 57
| 5 | Fill
183.3 | 6 | Excavator - 25T | hr | P | 1 | 15 | 20 | 135 | 180 | 1.3333 | 1.3333 | 0 | 0 | 180 | 0 | 180 | 57
| 7 | SD Roller - Wet (No Op) | hr | P | 1 | 15 | 20 | 55 | 73.3333 | 1.3333 | 1.3333 | 0 | 0 | 73.3333 | 0 | 73.3333 | 57
| 8 | Water Cart - Hire | hr | P | 1 | 15 | 20 | 100 | 133.3333 | 1.3333 | 1.3333 | 0 | 0 | 133.3333 | 0 | 133.3333 | 57
| 9 | Labour | hr | L | 3 | 15 | 20 | 42 | 168 | 4 | 1.3333 | 168 | 0 | 0 | 0 | 168 | 57
| Line No 456 Item No | STORMWATER DRAINAGE
| Line No 457 Item No C220 | STORMWATER DRAINAGE - GENERAL
184 | Line No 458 Item No | Removal / Demolition of Drainage Components complete | Lump |  |  |  | 1 |  | 5490.9091 |  | 2 | 763.6364 | 0 | 4727.2727 | 0 | 5490.9091
184.1 | 1 | Excavator - 25T | hr | P | 1 | 0.11 | 1 | 135 | 1227.2727 | 9.0909 | 9.0909 | 0 | 0 | 1227.2727 | 0 | 1227.2727 | 41
184.2 | 2 | Tipper | hr | P | 3 | 0.11 | 1 | 95 | 2590.9091 | 27.2727 | 9.0909 | 0 | 0 | 2590.9091 | 0 | 2590.9091 | 41
| 3 | Water Cart - Hire | hr | P | 1 | 0.11 | 1 | 100 | 909.0909 | 9.0909 | 9.0909 | 0 | 0 | 909.0909 | 0 | 909.0909 | 41
| 4 | Labour | hr | L | 2 | 0.11 | 1 | 42 | 763.6364 | 18.1818 | 9.0909 | 763.6364 | 0 | 0 | 0 | 763.6364 | 41
| Line No 459 Item No C221 | PIPE DRAINAGE (SUPPLY & INSTALL)
185 | Line No 460 Item No C221(a) | Connect property drainage pipes ( 7 No.) | Lump |  |  |  | 1 |  | 2765 |  | 2 | 0 | 1575 | 0 | 1190 | 2765
| 1 | EE formula - =q(7) No. of properties |  |  |  |  | 7
| 2 | 150 SN8 Sewer Pipe | m | M | 1 | 1 | 42 | 25 | 1050 |  |  | 0 | 1050 | 0 | 0 | 1050 | SWP
| 3 | Kerb Adaptors | each | M | 1 | 1 | 7 | 75 | 525 |  |  | 0 | 525 | 0 | 0 | 525 | SWP
| 4 | Plumber | hr | S | 1 | 0.5 | 7 | 85 | 1190 | 14 | 14 | 0 | 0 | 0 | 1190 | 1190 | 81
| Line No 461 Item No C222 | PRECAST BOX CULVERTS (SUPPLY & INSTALL)
186 | Line No 462 Item No C222(a) | In-Situ reinforced concrete Base Slab for culverts complete | m3 |  |  |  | 2.6 |  | 1692.7156 |  | 2 | 0 | 847.7156 | 0 | 845 | 1692.7156
| 1 | 1200 x 600 (12m)
| 2 | QTY/.2 = Area |  |  |  |  | 13
| 3 | Sand | tonne | M | 1 | 1 | 1.3 | 24 | 31.2 |  |  | 0 | 31.2 | 0 | 0 | 31.2 | QMS
| 4 | RL1218 | m² | M | 1 | 1 | 15.6 | 18 | 280.8 |  |  | 0 | 280.8 | 0 | 0 | 280.8 | RSM
| 5 | Bar Chairs | each | M | 1 | 1 | 14.4444 | 0.8 | 11.5556 |  |  | 0 | 11.5556 | 0 | 0 | 11.5556 | RSM
| 6 | N32 | m³ | M | 1 | 1 | 2.73 | 192 | 524.16 |  |  | 0 | 524.16 | 0 | 0 | 524.16 | C32
| 7 | RCBC Slab Subbie | m² | S | 1 | 1 | 13 | 65 | 845 |  | 0.26 | 0 | 0 | 0 | 845 | 845 | 72
187 | Line No 463 Item No C222(b) | 750 x 300 | m |  |  |  | 13.2 |  | 8530.5 |  | 2 | 1323 | 5472.5 | 1735 | 0 | 8530.5
| 1 | (11) Box Units to Stand |  |  |  |  | 11
| 2 | EE formula - =q(15) Hand Placed Backfill |  |  |  |  | 15
| 3 | RCBC - 1200 x 600 | m | M | 1 | 1 | 13.2 | 400 | 5280 |  |  | 0 | 5280 | 0 | 0 | 5280 | SWC
187.1 | 4 | Excavator - 25T | hr | P | 1 | 2 | 11 | 135 | 742.5 | 5.5 | 5.5 | 0 | 0 | 742.5 | 0 | 742.5 | 181
187.2 | 5 | Labour | hr | L | 3 | 2 | 11 | 42 | 693 | 16.5 | 5.5 | 693 | 0 | 0 | 0 | 693 | 181
| 6 | Denso Tape | m | M | 1 | 1 | 38.5 | 5 | 192.5 |  |  | 0 | 192.5 | 0 | 0 | 192.5 | 181
187.3 | 7 | Bobcat | hr | P | 1 | 3 | 15 | 95 | 475 | 5 | 5 | 0 | 0 | 475 | 0 | 475 | 181
187.4 | 8 | Labour | hr | L | 3 | 3 | 15 | 42 | 630 | 15 | 5 | 630 | 0 | 0 | 0 | 630 | 181
| 9 | Plate Compactor | hr | P | 1 | 3 | 15 | 3.5 | 17.5 | 5 | 5 | 0 | 0 | 17.5 | 0 | 17.5 | 181
| 10 | Water Cart - Hire | hr | P | 1 | 3 | 15 | 100 | 500 | 5 | 5 | 0 | 0 | 500 | 0 | 500 | 181
| Line No 464 Item No C223 | DRAINAGE STRUCTURES
188 | Line No 465 Item No C223(b) | MCC Type A Gully Pit (including chamber) | each |  |  |  | 1 |  | 3505 |  | 2 | 340 | 1290 | 0 | 1875 | 3505
| 1 | Pit Builder | each | S | 1 | 2 | 1 | 3750 | 1875 |  | 2 | 0 | 0 | 0 | 1875 | 1875 | 85
| 2 | MCC Type A Gully Top | each | M | 1 | 1 | 1 | 1290 | 1290 |  |  | 0 | 1290 | 0 | 0 | 1290 | SWPC
| 3 | Concretor - Labour | hr | L | 1 | 1 | 4 | 85 | 340 | 4 | 4 | 340 | 0 | 0 | 0 | 340 | 85
| Line No 466 Item No C224 | OPEN DRAINS, INCLUDING KERB & CHANNEL
189 | Line No 467 Item No C224(h) | (i) Concrete Barrier Kerb & Channel B1 complete | m |  |  |  | 313 |  | 16640.0263 |  | 2 | 0 | 7250.0263 | 0 | 9390 | 16640.0263
| 1 | Use Kerb Subbie. Allciv to supply sand & cement for slurry
| 2 | S32 - Kerb Mix | m³ | M | 1 | 1 | 36.3953 | 190 | 6915.1163 |  |  | 0 | 6915.1163 | 0 | 0 | 6915.1163 | CKM
| 3 | Sand | tonne | M | 1 | 1 | 4.1733 | 24 | 100.16 |  |  | 0 | 100.16 | 0 | 0 | 100.16 | QMS
| 4 | Cement | tonne | M | 1 | 1 | 0.52167 | 450 | 234.75 |  |  | 0 | 234.75 | 0 | 0 | 234.75 | CSA
| 5 | Kerb Subbie | m | S | 1 | 1 | 313 | 30 | 9390 |  | 1.565 | 0 | 0 | 0 | 9390 | 9390 | 71
190 | Line No 468 Item No C224(h) | (iv) Concrete Dish Drain (600 wide) complete | m |  |  |  | 13 |  | 1690.91 |  | 1 | 0 | 845.91 | 0 | 845 | 1690.91
| 1 | Use Kerb Subbie. Allciv to supply sand & cement for slurry
| 2 | N32 | m³ | M | 1 | 1 | 4.3333 | 192 | 832 |  |  | 0 | 832 | 0 | 0 | 832 | C32
| 3 | Sand | tonne | M | 1 | 1 | 0.17333 | 24 | 4.16 |  |  | 0 | 4.16 | 0 | 0 | 4.16 | QMS
| 4 | Cement | tonne | M | 1 | 1 | 0.021667 | 450 | 9.75 |  |  | 0 | 9.75 | 0 | 0 | 9.75 | CSA
| 5 | Kerb Subbie - Hand | m | S | 1 | 1 | 13 | 65 | 845 |  | 0.065 | 0 | 0 | 0 | 845 | 845 | 71
| Line No 470 Item No | SUB-SURFACE DRAINAGE
| Line No 471 Item No C231 | SUBSOIL & FOUNDATION DRAINS
191 | Line No 472 Item No C231(b) | Subsoil Drain Pipe - 100mm dia Slotted Corrugated Plastic Pipe complete | m |  |  |  | 281 |  | 11600.3083 |  | 4 | 3186.8587 | 1703.984 | 5905.8056 | 803.66 | 11600.3083
| 1 | Excavate & install sub-soil drain at a rate of 100m per day. Use 300 trench and sand to backfill.
| 2 | Sub Soil Drain | m | M | 1 | 1 | 281 | 2.5 | 702.5 |  |  | 0 | 702.5 | 0 | 0 | 702.5 | 87
| 3 | Sub Soil Clean Out - Inst | each | S | 1 | 1 | 5.62 | 143 | 803.66 | 5.62 | 5.62 | 0 | 0 | 0 | 803.66 | 803.66 | 87
| 4 | Sand | tonne | M | 1 | 1 | 41.7285 | 24 | 1001.484 |  |  | 0 | 1001.484 | 0 | 0 | 1001.484 | QMS
191.1 | 5 | Excavator - 25T | hr | P | 1 | 11.11 | 281 | 135 | 3414.4914 | 25.2925 | 25.2925 | 0 | 0 | 3414.4914 | 0 | 3414.4914 | 87
| 6 | Labour | hr | L | 3 | 11.11 | 281 | 42 | 3186.8587 | 75.8776 | 25.2925 | 3186.8587 | 0 | 0 | 0 | 3186.8587 | 87
| 7 | Bobcat | hr | P | 1 | 11.11 | 281 | 95 | 2402.7903 | 25.2925 | 25.2925 | 0 | 0 | 2402.7903 | 0 | 2402.7903 | 87
| 8 | Plate Compactor | hr | P | 1 | 11.11 | 281 | 3.5 | 88.5239 | 25.2925 | 25.2925 | 0 | 0 | 88.5239 | 0 | 88.5239 | 87
192 | Line No 473 Item No | Special Item -Subsoil Drain Pipe - 100mm dia Slotted Corrugated Plastic Pipe encased in no fines concrete complete as shown on drawings | m |  |  |  | 242 |  | 16027.7171 |  | 3 | 2744.5545 | 7504.904 | 5086.1386 | 692.12 | 16027.7171
| 1 | Excavate & install sub-soil drain at a rate of 100m per day. Use 300 trench and sand to backfill.
| 2 | Sub Soil Drain | m | M | 1 | 1 | 242 | 2.5 | 605 |  |  | 0 | 605 | 0 | 0 | 605 | 87
| 3 | Sub Soil Clean Out - Inst | each | S | 1 | 1 | 4.84 | 143 | 692.12 | 4.84 | 4.84 | 0 | 0 | 0 | 692.12 | 692.12 | 87
| 4 | N32 | m³ | M | 1 | 1 | 35.937 | 192 | 6899.904 |  |  | 0 | 6899.904 | 0 | 0 | 6899.904 | C32
192.1 | 5 | Excavator - 25T | hr | P | 1 | 11.11 | 242 | 135 | 2940.5941 | 21.7822 | 21.7822 | 0 | 0 | 2940.5941 | 0 | 2940.5941 | 87
| 6 | Labour | hr | L | 3 | 11.11 | 242 | 42 | 2744.5545 | 65.3465 | 21.7822 | 2744.5545 | 0 | 0 | 0 | 2744.5545 | 87
| 7 | Bobcat | hr | P | 1 | 11.11 | 242 | 95 | 2069.3069 | 21.7822 | 21.7822 | 0 | 0 | 2069.3069 | 0 | 2069.3069 | 87
| 8 | Plate Compactor | hr | P | 1 | 11.11 | 242 | 3.5 | 76.2376 | 21.7822 | 21.7822 | 0 | 0 | 76.2376 | 0 | 76.2376 | 87
193 | Line No 474 Item No C232(c) | Cleanout Structures | each |  |  |  | 13 |  | 1859 |  | 2 | 0 | 0 | 0 | 1859 | 1859
| 1 | Sub Soil Clean Out - Inst | each | S | 1 | 1 | 13 | 143 | 1859 | 13 | 13 | 0 | 0 | 0 | 1859 | 1859 | 87
| Line No 476 Item No | PAVEMENTS
| Line No 477 Item No C242 | FLEXIBLE PAVEMENTS
194 | Line No 478 Item No | Place only Type 2.3 (cement modified) | m3 |  |  |  | 378 |  | 21403.5155 |  | 4 | 2572.1692 | 0 | 18831.3463 | 0 | 21403.5155
194.1 | 1 | QTY*2.4 Tonnes Gravel |  |  | 2.4 |  | 907.2
194.2 | 2 | Truck & Dog | hr | P | 3 | 37 | 907.2 | 145 | 10665.7297 | 73.5568 | 24.5189 | 0 | 0 | 10665.7297 | 0 | 10665.7297 | 62
| 3 | Placement
194.3 | 4 | Grader | hr | P | 1 | 44.44 | 907.2 | 145 | 2960.036 | 20.414 | 20.414 | 0 | 0 | 2960.036 | 0 | 2960.036 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 44.44 | 907.2 | 100 | 2041.4041 | 20.414 | 20.414 | 0 | 0 | 2041.4041 | 0 | 2041.4041 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 44.44 | 907.2 | 55 | 1122.7723 | 20.414 | 20.414 | 0 | 0 | 1122.7723 | 0 | 1122.7723 | 62
| 7 | Labour | hr | L | 3 | 44.44 | 907.2 | 42 | 2572.1692 | 61.2421 | 20.414 | 2572.1692 | 0 | 0 | 0 | 2572.1692 | 62
| 8 | Backhoe | hr | P | 1 | 44.44 | 907.2 | 100 | 2041.4041 | 20.414 | 20.414 | 0 | 0 | 2041.4041 | 0 | 2041.4041 | 62
195 | Line No 479 Item No | Place only Type 2.1 (cement modified) | m3 |  |  |  | 127 |  | 10584.8504 |  | 3 | 1753.1944 | 0 | 8831.656 | 0 | 10584.8504
195.1 | 1 | QTY*2.4 Tonnes Gravel |  |  | 2.4 |  | 304.8
| 2 | Truck & Dog | hr | P | 3 | 37 | 304.8 | 145 | 3583.4595 | 24.7135 | 8.2378 | 0 | 0 | 3583.4595 | 0 | 3583.4595 | 62
| 3 | Placement
195.2 | 4 | Grader | hr | P | 1 | 44.44 | 304.8 | 145 | 994.5095 | 6.8587 | 6.8587 | 0 | 0 | 994.5095 | 0 | 994.5095 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 44.44 | 304.8 | 100 | 685.8686 | 6.8587 | 6.8587 | 0 | 0 | 685.8686 | 0 | 685.8686 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 44.44 | 304.8 | 55 | 377.2277 | 6.8587 | 6.8587 | 0 | 0 | 377.2277 | 0 | 377.2277 | 62
| 7 | Labour | hr | L | 3 | 44.44 | 304.8 | 42 | 864.1944 | 20.5761 | 6.8587 | 864.1944 | 0 | 0 | 0 | 864.1944 | 62
| 8 | Backhoe | hr | P | 1 | 44.44 | 304.8 | 100 | 685.8686 | 6.8587 | 6.8587 | 0 | 0 | 685.8686 | 0 | 685.8686 | 62
| 9 | Final Trim
195.3 | 10 | Grader | hr | P | 1 | 150 | 1058.3333 | 145 | 1023.0556 | 7.0556 | 7.0556 | 0 | 0 | 1023.0556 | 0 | 1023.0556 | 63
| 11 | Water Cart - Hire | hr | P | 1 | 150 | 1058.3333 | 100 | 705.5556 | 7.0556 | 7.0556 | 0 | 0 | 705.5556 | 0 | 705.5556 | 63
| 12 | MW Roller | hr | P | 1 | 75 | 1058.3333 | 55 | 776.1111 | 14.1111 | 14.1111 | 0 | 0 | 776.1111 | 0 | 776.1111 | 63
| 13 | Labour | hr | L | 3 | 150 | 1058.3333 | 42 | 889 | 21.1667 | 7.0556 | 889 | 0 | 0 | 0 | 889 | 63
196 | Line No 480 Item No | Special Item - Geogrid layer (PROVISIONAL) | m2 |  |  |  | 1260 |  | 7508.9589 |  | 1 | 306.3789 | 6971.58 | 231 | 0 | 7508.9589
| 1 | TX160 - Geogrid | m² | M | 1 | 1 | 1386 | 5.03 | 6971.58 |  |  | 0 | 6971.58 | 0 | 0 | 6971.58 | 222
196.1 | 2 | Labour | hr | L | 3 | 570 | 1386 | 42 | 306.3789 | 7.2947 | 2.4316 | 306.3789 | 0 | 0 | 0 | 306.3789 | 222
| 3 | Bobcat | hr | P | 1 | 570 | 1386 | 95 | 231 | 2.4316 | 2.4316 | 0 | 0 | 231 | 0 | 231 | 222
197 | Line No 481 Item No | Special Item -Geotextile layer (PROVISIONAL) | m2 |  |  |  | 1260 |  | 1992.6789 |  | 1 | 306.3789 | 1455.3 | 231 | 0 | 1992.6789
| 1 | A24 | m² | M | 1 | 1 | 1386 | 1.05 | 1455.3 |  |  | 0 | 1455.3 | 0 | 0 | 1455.3 | 222
197.1 | 2 | Labour | hr | L | 3 | 570 | 1386 | 42 | 306.3789 | 7.2947 | 2.4316 | 306.3789 | 0 | 0 | 0 | 306.3789 | 222
| 3 | Bobcat | hr | P | 1 | 570 | 1386 | 95 | 231 | 2.4316 | 2.4316 | 0 | 0 | 231 | 0 | 231 | 222
| Line No 482 Item No C244 | SPRAYED BITUMINOUS SURFACING
| Line No 483 Item No C244(a) | Supply & Spray Primer, supply & spread aggregates, Primerbinder (including preparation of surface) complete
198 | Line No 484 Item No C244(a) | (vi) AMC4 | m2 |  |  |  | 1057 |  | 14172.7845 |  | 1 | 0 | 0 | 0 | 14172.7845 | 14172.7845
| 1 | Seal Visit Seven | m² | S | 1 | 1 | 1109.85 | 12.77 | 14172.7845 |  | 0.55493 | 0 | 0 | 0 | 14172.7845 | 14172.7845 | 64
| Line No 485 Item No C245 | ASPHALTIC CONCRETE
| Line No 486 Item No C245(c) | Dense Graded Asphalt in Wearing Course
199 | Line No 487 Item No C245(c) | (ii) 14mm Nominal Size | tonne |  |  |  | 102 |  | 34057.8 |  | 1 | 0 | 0 | 0 | 34057.8 | 34057.8
| 1 | DG14 - Jupp St | tonne | S | 1 | 1 | 107.1 | 318 | 34057.8 |  | 0.5355 | 0 | 0 | 0 | 34057.8 | 34057.8 | 65
| Line No 489 Item No | MISCELLANEOUS
| Line No 490 Item No C271 | MINOR CONCRETE WORKS
| Line No 491 Item No C271(c) | Footpaths, Bike paths, Driveways, Median Toppings & Works of Similar Nature
200 | Line No 492 Item No C271(c) | (iv) Residential Invert Crossing (3.1m to 4.5m) | each |  |  |  | 11 |  | 5192.9867 |  | 8 | 25.2 | 2917.7867 | 138 | 2112 | 5192.9867
| 1 | Purchase Materials
| 2 | N32 | m³ | M | 1 | 1 | 9.075 | 192 | 1742.4 |  |  | 0 | 1742.4 | 0 | 0 | 1742.4 | C32
| 3 | Sand | tonne | M | 1 | 1 | 9.9 | 24 | 237.6 |  |  | 0 | 237.6 | 0 | 0 | 237.6 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 79.2 | 9.1 | 720.72 |  |  | 0 | 720.72 | 0 | 0 | 720.72 | RSM
| 5 | Abel Flex | m | M | 1 | 1 | 52.8 | 3 | 158.4 |  |  | 0 | 158.4 | 0 | 0 | 158.4 | RSM
| 6 | Detailed Excavation:
200.1 | 7 | Excavator - 25T | hr | P | 1 | 11 | 6.6 | 135 | 81 | 0.6 | 0.6 | 0 | 0 | 81 | 0 | 81 | 71
| 8 | Tipper | hr | P | 1 | 11 | 6.6 | 95 | 57 | 0.6 | 0.6 | 0 | 0 | 57 | 0 | 57 | 71
| 9 | Labour | hr | L | 1 | 11 | 6.6 | 42 | 25.2 | 0.6 | 0.6 | 25.2 | 0 | 0 | 0 | 25.2 | 71
| 10 | Form Pour & Finish
| 11 | Bar Chairs | each | M | 1 | 1 | 73.3333 | 0.8 | 58.6667 |  |  | 0 | 58.6667 | 0 | 0 | 58.6667 | RSM
| 12 | Concrete Subbie | m² | S | 1 | 1 | 66 | 32 | 2112 |  | 5.5 | 0 | 0 | 0 | 2112 | 2112 | 71
201 | Line No 493 Item No C271(c) | (viii) Hand Placed Concrete Paving (Footpath / Bikeway) | m2 |  |  |  | 93 |  | 6624.2867 |  | 4 | 39.06 | 3395.3267 | 213.9 | 2976 | 6624.2867
| 1 | Purchase Materials
| 2 | N25 | m³ | M | 1 | 1 | 10.23 | 170 | 1739.1 |  |  | 0 | 1739.1 | 0 | 0 | 1739.1 | C25
| 3 | Sand | tonne | M | 1 | 1 | 13.95 | 24 | 334.8 |  |  | 0 | 334.8 | 0 | 0 | 334.8 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 111.6 | 9.1 | 1015.56 |  |  | 0 | 1015.56 | 0 | 0 | 1015.56 | RSM
| 5 | Abel Flex | m | M | 1 | 1 | 74.4 | 3 | 223.2 |  |  | 0 | 223.2 | 0 | 0 | 223.2 | RSM
| 6 | Detailed Excavation:
201.1 | 7 | Excavator - 25T | hr | P | 1 | 10 | 9.3 | 135 | 125.55 | 0.93 | 0.93 | 0 | 0 | 125.55 | 0 | 125.55 | 71
| 8 | Tipper | hr | P | 1 | 10 | 9.3 | 95 | 88.35 | 0.93 | 0.93 | 0 | 0 | 88.35 | 0 | 88.35 | 71
| 9 | Labour | hr | L | 1 | 10 | 9.3 | 42 | 39.06 | 0.93 | 0.93 | 39.06 | 0 | 0 | 0 | 39.06 | 71
| 10 | Form Pour & Finish
| 11 | Bar Chairs | each | M | 1 | 1 | 103.3333 | 0.8 | 82.6667 |  |  | 0 | 82.6667 | 0 | 0 | 82.6667 | RSM
| 12 | Concrete Subbie | m² | S | 1 | 1 | 93 | 32 | 2976 |  | 1.86 | 0 | 0 | 0 | 2976 | 2976 | 71
| Line No 494 Item No C273 | LANDSCAPE
| Line No 495 Item No C273(a) | Vegetation of Slopes 1 in 3 or Flatter
202 | Line No 496 Item No C273(a) | (i) Grass Seeding | m2 |  |  |  | 905 |  | 2438.975 |  | 1 | 0 | 0 | 0 | 2438.975 | 2438.975
| 1 | Grass Seeding | m² | S | 1 | 1 | 995.5 | 2.45 | 2438.975 |  | 0.09955 | 0 | 0 | 0 | 2438.975 | 2438.975 | 121
| Line No 498 Item No | SERVICES
| Line No 499 Item No C320 | WATER RETICULATION
203 | Line No 500 Item No | Supply and install mains and reticulation | Lump |  |  |  | 1 |  | 9200 |  | 2 | 0 | 0 | 0 | 9200 | 9200
| 1 | WDC | Item | S | 1 | 1 | 9200 | 1 | 9200 |  | 2 | 0 | 0 | 0 | 9200 | 9200 | 103
| Line No 502 Item No | SPECIFIED WORKS
204 | Line No 503 Item No | Special Item - As Constructed Survey and Plans | Lump |  |  |  | 1 |  | 2400 |  | 3 | 0 | 0 | 0 | 2400 | 2400
| 1 | Survey | Item | S | 1 | 1 | 2400 | 1 | 2400 |  | 19.2 | 0 | 0 | 0 | 2400 | 2400 | 12
900 | Line No 507 Item No | STERRY STREET
| Line No 509 Item No | QUALITY SYSTEM
| Line No 510 Item No CQC | QUALITY CONTROL REQUIREMENTS
205 | Line No 511 Item No QCP1 | Quality Verification & Control | Lump |  |  |  | 1 |  | 10350 |  | 0 | 3250 | 0 | 0 | 7100 | 10350
| 1 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 |  |  | 3250 | 0 | 0 | 0 | 3250 | 901
205.1 | 2 | (24) Field Density Tests |  |  |  |  | 24
205.2 | 3 | (6) Concrete Cylinder Sets |  |  |  |  | 6
| 4 | Field Density | each | S | 1 | 1 | 24 | 45 | 1080 |  |  | 0 | 0 | 0 | 1080 | 1080 | 13
| 5 | Gravel Properties Testing | each | S | 1 | 1 | 3 | 390 | 1170 |  |  | 0 | 0 | 0 | 1170 | 1170 | 13
| 6 | Concrete Cylinders | each | S | 1 | 1 | 6 | 150 | 900 |  |  | 0 | 0 | 0 | 900 | 900 | 13
205.3 | 7 | Survey | Item | S | 3950 | 1 | 3950 | 1 | 3950 |  |  | 0 | 0 | 0 | 3950 | 3950 | 11
| Line No 513 Item No | GENERAL REQUIREMENTS
| Line No 514 Item No C101 | GENERAL
| Line No 515 Item No C101(b) | Site Establishment & Disestablishment | Lump |  |  |  | 1
| Line No 517 Item No | ROAD & EARTHWORKS
| Line No 518 Item No C201 | CONTROL OF TRAFFIC
206 | Line No 519 Item No C201(a) | Control of Traffic | Lump |  |  |  | 1 |  | 29115.6 |  | 25 | 0 | 0 | 0 | 29115.6 | 29115.6
| 1 | (5) No. Weeks TC Required; No. = 6 days per week |  |  |  |  | 5
206.1 | 2 | Traffic Control Crew | hr | S | 6 | 1 | 285 | 102.16 | 29115.6 |  | 25 | 0 | 0 | 0 | 29115.6 | 29115.6 | 141
| Line No 520 Item No C211 | CONTROL OF EROSION & SEDIMENTATION
207 | Line No 521 Item No C211(a) | Temporary Erosion & Sedimentation Control (includes supply and installation of all components) | Lump |  |  |  | 1 |  | 11050 |  | 6 | 6300 | 0 | 4750 | 0 | 11050
| 1 | Labour | hr | L | 3 | 1 | 50 | 42 | 6300 | 150 | 50 | 6300 | 0 | 0 | 0 | 6300 | 151
| 2 | Bobcat | hr | P | 1 | 1 | 50 | 95 | 4750 | 50 | 50 | 0 | 0 | 4750 | 0 | 4750 | 151
| Line No 522 Item No C212 | CLEARING & GRUBBING
208 | Line No 523 Item No | Special Item - Demolition of Structure (concrete slabs, culverts, pipes etc) | Lump |  |  |  | 1 |  | 10066.6667 |  | 2 | 1400 | 0 | 8666.6667 | 0 | 10066.6667
208.1 | 1 | Excavator - 25T | hr | P | 1 | 0.06 | 1 | 135 | 2250 | 16.6667 | 16.6667 | 0 | 0 | 2250 | 0 | 2250 | 41
| 2 | Tipper | hr | P | 3 | 0.06 | 1 | 95 | 4750 | 50 | 16.6667 | 0 | 0 | 4750 | 0 | 4750 | 41
| 3 | Water Cart - Hire | hr | P | 1 | 0.06 | 1 | 100 | 1666.6667 | 16.6667 | 16.6667 | 0 | 0 | 1666.6667 | 0 | 1666.6667 | 41
| 4 | Labour | hr | L | 2 | 0.06 | 1 | 42 | 1400 | 33.3333 | 16.6667 | 1400 | 0 | 0 | 0 | 1400 | 41
| Line No 524 Item No C213 | EARTHWORKS
209 | Line No 525 Item No C213(b) | General Earthworks Cut | m3 |  |  |  | 1700 |  | 34970.2439 |  | 6 | 3178.1707 | 0 | 31792.0732 | 0 | 34970.2439
209.1 | 1 | Excavator - 25T | hr | P | 1 | 40 | 1700 | 135 | 5737.5 | 42.5 | 42.5 | 0 | 0 | 5737.5 | 0 | 5737.5 | 53
209.2 | 2 | Truck & Dog | hr | P | 3 | 40 | 1700 | 145 | 18487.5 | 127.5 | 42.5 | 0 | 0 | 18487.5 | 0 | 18487.5 | 53
| 3 | Water Cart - Hire | hr | P | 1 | 40 | 1700 | 100 | 4250 | 42.5 | 42.5 | 0 | 0 | 4250 | 0 | 4250 | 53
| 4 | Labour | hr | L | 1 | 40 | 1700 | 42 | 1785 | 42.5 | 42.5 | 1785 | 0 | 0 | 0 | 1785 | 53
| 5 | Prepare Sub-grade
209.3 | 6 | Grader | hr | P | 1 | 250 | 2764.2276 | 145 | 1603.252 | 11.0569 | 11.0569 | 0 | 0 | 1603.252 | 0 | 1603.252 | 61
| 7 | Water Cart - Hire | hr | P | 1 | 250 | 2764.2276 | 100 | 1105.6911 | 11.0569 | 11.0569 | 0 | 0 | 1105.6911 | 0 | 1105.6911 | 61
| 8 | SD Roller - Wet (No Op) | hr | P | 1 | 250 | 2764.2276 | 55 | 608.1301 | 11.0569 | 11.0569 | 0 | 0 | 608.1301 | 0 | 608.1301 | 61
| 9 | Labour | hr | L | 3 | 250 | 2764.2276 | 42 | 1393.1707 | 33.1707 | 11.0569 | 1393.1707 | 0 | 0 | 0 | 1393.1707 | 61
| Line No 527 Item No | STORMWATER DRAINAGE
| Line No 528 Item No C220 | STORMWATER DRAINAGE - GENERAL
210 | Line No 529 Item No | Removal / Demolition of Drainage Components complete | Lump |  |  |  | 1 |  | 5490.9091 |  | 2 | 763.6364 | 0 | 4727.2727 | 0 | 5490.9091
210.1 | 1 | Excavator - 25T | hr | P | 1 | 0.11 | 1 | 135 | 1227.2727 | 9.0909 | 9.0909 | 0 | 0 | 1227.2727 | 0 | 1227.2727 | 41
210.2 | 2 | Tipper | hr | P | 3 | 0.11 | 1 | 95 | 2590.9091 | 27.2727 | 9.0909 | 0 | 0 | 2590.9091 | 0 | 2590.9091 | 41
| 3 | Water Cart - Hire | hr | P | 1 | 0.11 | 1 | 100 | 909.0909 | 9.0909 | 9.0909 | 0 | 0 | 909.0909 | 0 | 909.0909 | 41
| 4 | Labour | hr | L | 2 | 0.11 | 1 | 42 | 763.6364 | 18.1818 | 9.0909 | 763.6364 | 0 | 0 | 0 | 763.6364 | 41
211 | Line No 530 Item No | Alteration to Existing Stormwater Structures | Lump |  |  |  | 1 |  | 7860 |  | 6 | 1260 | 3000 | 0 | 3600 | 7860
| 1 | 6 x new grates. 3 x walls dowelled & pinned.
| 2 | Pit Builder - Modify | each | S | 1 | 1 | 3 | 1200 | 3600 |  | 6 | 0 | 0 | 0 | 3600 | 3600 | 85
| 3 | Grate & Frame | each | M | 1 | 1 | 6 | 500 | 3000 |  |  | 0 | 3000 | 0 | 0 | 3000 | SWL
| 4 | Labour | hr | L | 1 | 1 | 30 | 42 | 1260 | 30 | 30 | 1260 | 0 | 0 | 0 | 1260 | 85
| Line No 531 Item No C221 | PIPE DRAINAGE (SUPPLY & INSTALL)
212 | Line No 532 Item No C221(a) | Connect property drainage pipes | Lump |  |  |  | 1 |  | 6715 |  | 4 | 0 | 3825 | 0 | 2890 | 6715
| 1 | (17) No. of properties |  |  |  |  | 17
| 2 | 150 SN8 Sewer Pipe | m | M | 1 | 1 | 102 | 25 | 2550 |  |  | 0 | 2550 | 0 | 0 | 2550 | SWP
| 3 | Kerb Adaptors | each | M | 1 | 1 | 17 | 75 | 1275 |  |  | 0 | 1275 | 0 | 0 | 1275 | SWP
212.1 | 4 | Plumber | hr | S | 1 | 0.5 | 17 | 85 | 2890 | 34 | 34 | 0 | 0 | 0 | 2890 | 2890 | 81
| Line No 533 Item No C222 | PRECAST BOX CULVERTS (SUPPLY & INSTALL)
213 | Line No 534 Item No C222(a) | In-Situ reinforced concrete Base Slab for culverts complete | m3 |  |  |  | 7 |  | 4557.3111 |  | 3 | 0 | 2282.3111 | 0 | 2275 | 4557.3111
| 1 | QTY/.2 = Area |  |  |  |  | 35
| 2 | Sand | tonne | M | 1 | 1 | 3.5 | 24 | 84 |  |  | 0 | 84 | 0 | 0 | 84 | QMS
| 3 | RL1218 | m² | M | 1 | 1 | 42 | 18 | 756 |  |  | 0 | 756 | 0 | 0 | 756 | RSM
| 4 | Bar Chairs | each | M | 1 | 1 | 38.8889 | 0.8 | 31.1111 |  |  | 0 | 31.1111 | 0 | 0 | 31.1111 | RSM
| 5 | N32 | m³ | M | 1 | 1 | 7.35 | 192 | 1411.2 |  |  | 0 | 1411.2 | 0 | 0 | 1411.2 | C32
| 6 | RCBC Slab Subbie | m² | S | 1 | 1 | 35 | 65 | 2275 |  | 0.7 | 0 | 0 | 0 | 2275 | 2275 | 72
214 | Line No 535 Item No C222(b) | 750 x 300 | m |  |  |  | 35 |  | 12883.6467 |  | 3 | 2940 | 6264.48 | 3679.1667 | 0 | 12883.6467
| 1 | (30) Box Units to Stand |  |  |  |  | 30
| 2 | EE formula - =q(25) Hand Placed Backfill |  |  |  |  | 25
| 3 | RCBC - 750 x 450 | m | M | 1 | 1 | 36 | 159.43 | 5739.48 |  |  | 0 | 5739.48 | 0 | 0 | 5739.48 | SWC
214.1 | 4 | Excavator - 25T | hr | P | 1 | 2 | 30 | 135 | 2025 | 15 | 15 | 0 | 0 | 2025 | 0 | 2025 | 181
214.2 | 5 | Labour | hr | L | 3 | 2 | 30 | 42 | 1890 | 45 | 15 | 1890 | 0 | 0 | 0 | 1890 | 181
| 6 | Denso Tape | m | M | 1 | 1 | 105 | 5 | 525 |  |  | 0 | 525 | 0 | 0 | 525 | 181
214.3 | 7 | Bobcat | hr | P | 1 | 3 | 25 | 95 | 791.6667 | 8.3333 | 8.3333 | 0 | 0 | 791.6667 | 0 | 791.6667 | 181
214.4 | 8 | Labour | hr | L | 3 | 3 | 25 | 42 | 1050 | 25 | 8.3333 | 1050 | 0 | 0 | 0 | 1050 | 181
| 9 | Plate Compactor | hr | P | 1 | 3 | 25 | 3.5 | 29.1667 | 8.3333 | 8.3333 | 0 | 0 | 29.1667 | 0 | 29.1667 | 181
| 10 | Water Cart - Hire | hr | P | 1 | 3 | 25 | 100 | 833.3333 | 8.3333 | 8.3333 | 0 | 0 | 833.3333 | 0 | 833.3333 | 181
| Line No 536 Item No C223 | DRAINAGE STRUCTURES
215 | Line No 537 Item No C223(b) | MCC Type A Gully Pit | each |  |  |  | 1 |  | 3505 |  | 2 | 340 | 1290 | 0 | 1875 | 3505
| 1 | Pit Builder | each | S | 1 | 2 | 1 | 3750 | 1875 |  | 0.5 | 0 | 0 | 0 | 1875 | 1875 | 85
| 2 | MCC Type A Gully Top | each | M | 1 | 1 | 1 | 1290 | 1290 |  |  | 0 | 1290 | 0 | 0 | 1290 | SWPC
| 3 | Concretor - Labour | hr | L | 1 | 1 | 4 | 85 | 340 | 4 | 4 | 340 | 0 | 0 | 0 | 340 | 85
| Line No 538 Item No C224 | OPEN DRAINS, INCLUDING KERB & CHANNEL
216 | Line No 539 Item No C224(h) | (i) Concrete Barrier Kerb & Channel B1 complete | m |  |  |  | 140 |  | 7442.8233 |  | 1 | 0 | 3242.8233 | 0 | 4200 | 7442.8233
| 1 | Use Kerb Subbie. Allciv to supply sand & cement for slurry
| 2 | S32 - Kerb Mix | m³ | M | 1 | 1 | 16.2791 | 190 | 3093.0233 |  |  | 0 | 3093.0233 | 0 | 0 | 3093.0233 | CKM
| 3 | Sand | tonne | M | 1 | 1 | 1.8667 | 24 | 44.8 |  |  | 0 | 44.8 | 0 | 0 | 44.8 | QMS
| 4 | Cement | tonne | M | 1 | 1 | 0.23333 | 450 | 105 |  |  | 0 | 105 | 0 | 0 | 105 | CSA
| 5 | Kerb Subbie | m | S | 1 | 1 | 140 | 30 | 4200 |  | 0.7 | 0 | 0 | 0 | 4200 | 4200 | 71
| Line No 541 Item No | SUB-SURFACE DRAINAGE
| Line No 542 Item No C231 | SUBSOIL & FOUNDATION DRAINS
217 | Line No 543 Item No C231(b) | Subsoil Drain Pipe - 100mm dia Slotted Corrugated Plastic Pipe complete (provisional quantity) | m |  |  |  | 420 |  | 17338.539 |  | 6 | 4763.2763 | 2546.88 | 8827.1827 | 1201.2 | 17338.539
| 1 | Excavate & install sub-soil drain at a rate of 100m per day. Use 300 trench and sand to backfill.
| 2 | Sub Soil Drain | m | M | 1 | 1 | 420 | 2.5 | 1050 |  |  | 0 | 1050 | 0 | 0 | 1050 | 87
| 3 | Sub Soil Clean Out - Inst | each | S | 1 | 1 | 8.4 | 143 | 1201.2 | 8.4 | 8.4 | 0 | 0 | 0 | 1201.2 | 1201.2 | 87
| 4 | Sand | tonne | M | 1 | 1 | 62.37 | 24 | 1496.88 |  |  | 0 | 1496.88 | 0 | 0 | 1496.88 | QMS
217.1 | 5 | Excavator - 25T | hr | P | 1 | 11.11 | 420 | 135 | 5103.5104 | 37.8038 | 37.8038 | 0 | 0 | 5103.5104 | 0 | 5103.5104 | 87
| 6 | Labour | hr | L | 3 | 11.11 | 420 | 42 | 4763.2763 | 113.4113 | 37.8038 | 4763.2763 | 0 | 0 | 0 | 4763.2763 | 87
| 7 | Bobcat | hr | P | 1 | 11.11 | 420 | 95 | 3591.3591 | 37.8038 | 37.8038 | 0 | 0 | 3591.3591 | 0 | 3591.3591 | 87
| 8 | Plate Compactor | hr | P | 1 | 11.11 | 420 | 3.5 | 132.3132 | 37.8038 | 37.8038 | 0 | 0 | 132.3132 | 0 | 132.3132 | 87
218 | Line No 544 Item No C232(c) | Cleanout Structures | each |  |  |  | 12 |  | 1716 |  | 2 | 0 | 0 | 0 | 1716 | 1716
| 1 | Sub Soil Clean Out - Inst | each | S | 1 | 1 | 12 | 143 | 1716 | 12 | 12 | 0 | 0 | 0 | 1716 | 1716 | 87
| Line No 546 Item No | PAVEMENTS
| Line No 547 Item No C242 | FLEXIBLE PAVEMENTS
219 | Line No 548 Item No | Place only Type 2.3 | m3 |  |  |  | 415 |  | 23498.5686 |  | 4 | 2823.9424 | 0 | 20674.6262 | 0 | 23498.5686
219.1 | 1 | QTY*2.4 Tonnes Gravel |  |  | 2.4 |  | 996
219.2 | 2 | Truck & Dog | hr | P | 3 | 37 | 996 | 145 | 11709.7297 | 80.7568 | 26.9189 | 0 | 0 | 11709.7297 | 0 | 11709.7297 | 62
| 3 | Placement
219.3 | 4 | Grader | hr | P | 1 | 44.44 | 996 | 145 | 3249.775 | 22.4122 | 22.4122 | 0 | 0 | 3249.775 | 0 | 3249.775 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 44.44 | 996 | 100 | 2241.2241 | 22.4122 | 22.4122 | 0 | 0 | 2241.2241 | 0 | 2241.2241 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 44.44 | 996 | 55 | 1232.6733 | 22.4122 | 22.4122 | 0 | 0 | 1232.6733 | 0 | 1232.6733 | 62
| 7 | Labour | hr | L | 3 | 44.44 | 996 | 42 | 2823.9424 | 67.2367 | 22.4122 | 2823.9424 | 0 | 0 | 0 | 2823.9424 | 62
| 8 | Backhoe | hr | P | 1 | 44.44 | 996 | 100 | 2241.2241 | 22.4122 | 22.4122 | 0 | 0 | 2241.2241 | 0 | 2241.2241 | 62
220 | Line No 549 Item No | Place only Type 2.5 (cement modified) | m3 |  |  |  | 555 |  | 31425.7966 |  | 5 | 3776.5977 | 0 | 27649.1989 | 0 | 31425.7966
220.1 | 1 | QTY*2.4 Tonnes Gravel |  |  | 2.4 |  | 1332
220.2 | 2 | Truck & Dog | hr | P | 3 | 37 | 1332 | 145 | 15660 | 108 | 36 | 0 | 0 | 15660 | 0 | 15660 | 62
| 3 | Placement
220.3 | 4 | Grader | hr | P | 1 | 44.44 | 1332 | 145 | 4346.0846 | 29.973 | 29.973 | 0 | 0 | 4346.0846 | 0 | 4346.0846 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 44.44 | 1332 | 100 | 2997.2997 | 29.973 | 29.973 | 0 | 0 | 2997.2997 | 0 | 2997.2997 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 44.44 | 1332 | 55 | 1648.5149 | 29.973 | 29.973 | 0 | 0 | 1648.5149 | 0 | 1648.5149 | 62
| 7 | Labour | hr | L | 3 | 44.44 | 1332 | 42 | 3776.5977 | 89.919 | 29.973 | 3776.5977 | 0 | 0 | 0 | 3776.5977 | 62
| 8 | Backhoe | hr | P | 1 | 44.44 | 1332 | 100 | 2997.2997 | 29.973 | 29.973 | 0 | 0 | 2997.2997 | 0 | 2997.2997 | 62
221 | Line No 550 Item No | Place only Type 2.1 | m3 |  |  |  | 405 |  | 31590.338 |  | 8 | 5023.8956 | 0 | 26566.4425 | 0 | 31590.338
221.1 | 1 | 2.4*density Tonnes Gravel |  |  | 2.4 |  | 972
221.2 | 2 | Truck & Dog | hr | P | 3 | 37 | 972 | 145 | 11427.5676 | 78.8108 | 26.2703 | 0 | 0 | 11427.5676 | 0 | 11427.5676 | 62
| 3 | Placement
221.3 | 4 | Grader | hr | P | 1 | 44.44 | 972 | 145 | 3171.4671 | 21.8722 | 21.8722 | 0 | 0 | 3171.4671 | 0 | 3171.4671 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 44.44 | 972 | 100 | 2187.2187 | 21.8722 | 21.8722 | 0 | 0 | 2187.2187 | 0 | 2187.2187 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 44.44 | 972 | 55 | 1202.9703 | 21.8722 | 21.8722 | 0 | 0 | 1202.9703 | 0 | 1202.9703 | 62
| 7 | Labour | hr | L | 3 | 44.44 | 972 | 42 | 2755.8956 | 65.6166 | 21.8722 | 2755.8956 | 0 | 0 | 0 | 2755.8956 | 62
| 8 | Backhoe | hr | P | 1 | 44.44 | 972 | 100 | 2187.2187 | 21.8722 | 21.8722 | 0 | 0 | 2187.2187 | 0 | 2187.2187 | 62
| 9 | Final Trim
221.4 | 10 | Grader | hr | P | 1 | 150 | 2700 | 145 | 2610 | 18 | 18 | 0 | 0 | 2610 | 0 | 2610 | 63
| 11 | Water Cart - Hire | hr | P | 1 | 150 | 2700 | 100 | 1800 | 18 | 18 | 0 | 0 | 1800 | 0 | 1800 | 63
| 12 | MW Roller | hr | P | 1 | 75 | 2700 | 55 | 1980 | 36 | 36 | 0 | 0 | 1980 | 0 | 1980 | 63
| 13 | Labour | hr | L | 3 | 150 | 2700 | 42 | 2268 | 54 | 18 | 2268 | 0 | 0 | 0 | 2268 | 63
222 | Line No 551 Item No | Special Item - Geogrid layer | m2 |  |  |  | 2765 |  | 16477.9932 |  | 1 | 672.3316 | 15298.745 | 506.9167 | 0 | 16477.9932
| 1 | TX160 - Geogrid | m² | M | 1 | 1 | 3041.5 | 5.03 | 15298.745 |  |  | 0 | 15298.745 | 0 | 0 | 15298.745 | 222
222.1 | 2 | Labour | hr | L | 3 | 570 | 3041.5 | 42 | 672.3316 | 16.0079 | 5.336 | 672.3316 | 0 | 0 | 0 | 672.3316 | 222
| 3 | Bobcat | hr | P | 1 | 570 | 3041.5 | 95 | 506.9167 | 5.336 | 5.336 | 0 | 0 | 506.9167 | 0 | 506.9167 | 222
223 | Line No 552 Item No | Special Item - Geotextile layer | m2 |  |  |  | 2765 |  | 4372.8232 |  | 1 | 672.3316 | 3193.575 | 506.9167 | 0 | 4372.8232
| 1 | A24 | m² | M | 1 | 1 | 3041.5 | 1.05 | 3193.575 |  |  | 0 | 3193.575 | 0 | 0 | 3193.575 | 222
223.1 | 2 | Labour | hr | L | 3 | 570 | 3041.5 | 42 | 672.3316 | 16.0079 | 5.336 | 672.3316 | 0 | 0 | 0 | 672.3316 | 222
| 3 | Bobcat | hr | P | 1 | 570 | 3041.5 | 95 | 506.9167 | 5.336 | 5.336 | 0 | 0 | 506.9167 | 0 | 506.9167 | 222
| Line No 553 Item No C245 | ASPHALTIC CONCRETE
| Line No 554 Item No C245(c) | Dense Graded Asphalt in Wearing Course
224 | Line No 555 Item No C245(c) | (ii) 14mm Nominal Size | tonne |  |  |  | 310 |  | 100970.1 |  | 3 | 0 | 0 | 0 | 100970.1 | 100970.1
| 1 | Seal Visit Eight | m² | S | 1 | 1 | 3255 | 5.92 | 19269.6 |  | 1 | 0 | 0 | 0 | 19269.6 | 19269.6 | 64
| 2 | DG14 - Sterry St | tonne | S | 1 | 1 | 325.5 | 251 | 81700.5 |  | 2 | 0 | 0 | 0 | 81700.5 | 81700.5 | 65
| Line No 557 Item No | ROAD FURNISHINGS
| Line No 558 Item No C261 | PAVEMENT MARKINGS
225 | Line No 559 Item No C261(a) | Pavement Marking Paint - Longitudinal Lines including car parking bays | m |  |  |  | 405 |  | 5000 |  | 1 | 0 | 0 | 0 | 5000 | 5000
| 1 | Line Marking | m² | S | 1 | 1 | 5000 | 1 | 5000 |  | 0.2025 | 0 | 0 | 0 | 5000 | 5000 | 66
226 | Line No 560 Item No C261(b) | Pavement Marking Paint - Transverse Lines, Symbols, Legends, Arrows, Chevrons, Traffic Islands & Kerbs | Item |  |  |  | 1 |  | 2000 |  | 1 | 0 | 0 | 0 | 2000 | 2000
| 1 | Line Marking | m² | S | 1 | 1 | 2000 | 1 | 2000 |  | 0.4 | 0 | 0 | 0 | 2000 | 2000 | 66
| Line No 561 Item No C262 | SIGNPOSTING
227 | Line No 562 Item No C262(g) | Remove and reinstate Existing Signs & Support Structures | Item |  |  |  | 1 |  | 1652 |  | 2 | 0 | 1652 | 0 | 0 | 1652
| 1 | Signs Complete | each | M | 1 | 1 | 7 | 140 | 980 |  | 14 | 0 | 980 | 0 | 0 | 980 | RFS
| 2 | N32 | m³ | M | 1 | 1 | 3.5 | 192 | 672 |  |  | 0 | 672 | 0 | 0 | 672 | C32
228 | Line No 563 Item No | Supply & Installation of all Signs (complete) | each |  |  |  | 1 |  | 4215 |  | 1 | 420 | 3320 | 475 | 0 | 4215
| 1 | Signs Complete | each | M | 1 | 1 | 10 | 140 | 1400 |  |  | 0 | 1400 | 0 | 0 | 1400 | RFS
| 2 | N32 | m³ | M | 1 | 1 | 10 | 192 | 1920 |  |  | 0 | 1920 | 0 | 0 | 1920 | C32
| 3 | Labour | hr | L | 2 | 2 | 10 | 42 | 420 | 10 | 5 | 420 | 0 | 0 | 0 | 420 | 67
| 4 | Bobcat | hr | P | 1 | 2 | 10 | 95 | 475 | 5 | 5 | 0 | 0 | 475 | 0 | 475 | 67
| Line No 565 Item No | MISCELLANEOUS
| Line No 566 Item No C271 | MINOR CONCRETE WORKS
| Line No 567 Item No C271(c) | Footpaths, Bike paths, Driveways, Median Toppings & Works of Similar Nature
229 | Line No 568 Item No C271(c) | (ii) Concrete Kerb Ramp (1 No) | each |  |  |  | 1 |  | 785 |  | 2 | 0 | 85 | 0 | 700 | 785
| 1 | N25 | m³ | M | 1 | 1 | 0.5 | 170 | 85 |  |  | 0 | 85 | 0 | 0 | 85 | C25
| 2 | Pram Ramps | each | S | 1 | 1 | 1 | 700 | 700 | 1 | 1 | 0 | 0 | 0 | 700 | 700 | 71
230 | Line No 569 Item No C271(c) | (iv) Residential Invert Crossing (10.5 m) | each |  |  |  | 3 |  | 2493.92 |  | 4 | 50.4 | 1591.52 | 276 | 576 | 2493.92
| 1 | Purchase Materials
| 2 | N32 | m³ | M | 1 | 1 | 4.95 | 192 | 950.4 |  |  | 0 | 950.4 | 0 | 0 | 950.4 | C32
| 3 | Sand | tonne | M | 1 | 1 | 5.4 | 24 | 129.6 |  |  | 0 | 129.6 | 0 | 0 | 129.6 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 43.2 | 9.1 | 393.12 |  |  | 0 | 393.12 | 0 | 0 | 393.12 | RSM
| 5 | Abel Flex | m | M | 1 | 1 | 28.8 | 3 | 86.4 |  |  | 0 | 86.4 | 0 | 0 | 86.4 | RSM
| 6 | Detailed Excavation:
230.1 | 7 | Excavator - 25T | hr | P | 1 | 3 | 3.6 | 135 | 162 | 1.2 | 1.2 | 0 | 0 | 162 | 0 | 162 | 71
| 8 | Tipper | hr | P | 1 | 3 | 3.6 | 95 | 114 | 1.2 | 1.2 | 0 | 0 | 114 | 0 | 114 | 71
| 9 | Labour | hr | L | 1 | 3 | 3.6 | 42 | 50.4 | 1.2 | 1.2 | 50.4 | 0 | 0 | 0 | 50.4 | 71
| 10 | Form Pour & Finish
| 11 | Bar Chairs | each | M | 1 | 1 | 40 | 0.8 | 32 |  |  | 0 | 32 | 0 | 0 | 32 | RSM
| 12 | Concrete Subbie | m² | S | 1 | 1 | 18 | 32 | 576 |  | 1.5 | 0 | 0 | 0 | 576 | 576 | 71
231 | Line No 570 Item No C271(c) | (viii) Hand Placed Concrete Paving (Footpath / Bikeway) | m2 |  |  |  | 18 | 71.2289 | 1282.12 |  | 3 | 7.56 | 657.16 | 41.4 | 576 | 1282.12
| 1 | Purchase Materials
| 2 | N25 | m³ | M | 1 | 1 | 1.98 | 170 | 336.6 |  |  | 0 | 336.6 | 0 | 0 | 336.6 | C25
| 3 | Sand | tonne | M | 1 | 1 | 2.7 | 24 | 64.8 |  |  | 0 | 64.8 | 0 | 0 | 64.8 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 21.6 | 9.1 | 196.56 |  |  | 0 | 196.56 | 0 | 0 | 196.56 | RSM
| 5 | Abel Flex | m | M | 1 | 1 | 14.4 | 3 | 43.2 |  |  | 0 | 43.2 | 0 | 0 | 43.2 | RSM
| 6 | Detailed Excavation:
231.1 | 7 | Excavator - 25T | hr | P | 1 | 10 | 1.8 | 135 | 24.3 | 0.18 | 0.18 | 0 | 0 | 24.3 | 0 | 24.3 | 71
| 8 | Tipper | hr | P | 1 | 10 | 1.8 | 95 | 17.1 | 0.18 | 0.18 | 0 | 0 | 17.1 | 0 | 17.1 | 71
| 9 | Labour | hr | L | 1 | 10 | 1.8 | 42 | 7.56 | 0.18 | 0.18 | 7.56 | 0 | 0 | 0 | 7.56 | 71
| 10 | Form Pour & Finish
| 11 | Bar Chairs | each | M | 1 | 1 | 20 | 0.8 | 16 |  |  | 0 | 16 | 0 | 0 | 16 | RSM
| 12 | Concrete Subbie | m² | S | 1 | 1 | 18 | 32 | 576 |  | 0.36 | 0 | 0 | 0 | 576 | 576 | 71
| Line No 571 Item No C273 | LANDSCAPE
| Line No 572 Item No C273(a) | Vegetation of Slopes 1 in 3 or Flatter
232 | Line No 573 Item No C273(a) | (ii) Turfing | m2 |  |  |  | 100 |  | 892.5 |  | 1 | 0 | 0 | 0 | 892.5 | 892.5
| 1 | Turf Subbie | m² | S | 1 | 1 | 105 | 8.5 | 892.5 |  | 0.21 | 0 | 0 | 0 | 892.5 | 892.5 | 121
| Line No 575 Item No | SERVICES
| Line No 576 Item No C320 | WATER RETICULATION
233 | Line No 577 Item No | Supply and install mains and reticulation | Lump |  |  |  | 1 |  | 8000 |  | 2 | 0 | 0 | 0 | 8000 | 8000
| 1 | WDC | Item | S | 1 | 1 | 8000 | 1 | 8000 |  | 2 | 0 | 0 | 0 | 8000 | 8000 | 103
234 | Line No 578 Item No | Service connections | Lump |  |  |  | 1 |  | 10980 |  | 3 | 0 | 0 | 0 | 10980 | 10980
| 1 | WDC | Item | S | 1 | 1 | 10980 | 1 | 10980 |  | 2.745 | 0 | 0 | 0 | 10980 | 10980 | 103
| Line No 580 Item No | SPECIFIED WORKS
235 | Line No 581 Item No | Special Item - As Constructed Survey and Plans | Lump |  |  |  | 1 |  | 2400 |  | 3 | 0 | 0 | 0 | 2400 | 2400
| 1 | Survey | Item | S | 1 | 1 | 2400 | 1 | 2400 |  | 19.2 | 0 | 0 | 0 | 2400 | 2400 | 12
| Line No | Comment | Unit |  | No | Production | Quantity |  |  |  |  | Labour | Material | Plant | Subcontract | Total
9001 | Line No OH 1 Item No | Project Engineering |  |  |  |  | 1 |  | 6500 |  |  | 6500 | 0 | 0 | 0 | 6500
| 1 | Project Engineer | week | L | 1 | 1 | 2 | 3250 | 6500 | 2 | 2 | 6500 | 0 | 0 | 0 | 6500 | 901
9002 | Line No OH 2 Item No | Project Supervision |  |  |  |  | 1 |  | 107200 |  |  | 107200 | 0 | 0 | 0 | 107200
| 1 | Project Supervisor | week | L | 1 | 1 | 32 | 3350 | 107200 | 32 | 32 | 107200 | 0 | 0 | 0 | 107200 | 902
9003 | Line No OH 3 Item No | Insurances & Fees |  |  |  |  | 1 |  | 32500 |  |  | 0 | 0 | 0 | 32500 | 32500
| 1 | CAR | Item | S | 1 | 1 | 20800 | 1 | 20800 |  |  | 0 | 0 | 0 | 20800 | 20800 | 904
| 2 | Retention Costs | Item | S | 1 | 1 | 11700 | 1 | 11700 |  |  | 0 | 0 | 0 | 11700 | 11700 | 904
9004 | Line No OH 4 Item No | Site Vehicle |  |  |  |  | 1 |  | 20000 |  |  | 0 | 0 | 20000 | 0 | 20000
| 1 | Ute - Hire | day | P | 1 | 1 | 20000 | 1 | 20000 |  |  | 0 | 0 | 20000 | 0 | 20000 | 903
9005 | Line No OH 5 Item No | Site Facilities |  |  |  |  | 1 |  | 32500 |  |  | 0 | 0 | 32500 | 0 | 32500
9005.1 | 1 | Crib Facilities | week | P | 26 | 1 | 1 | 1250 | 32500 |  |  | 0 | 0 | 32500 | 0 | 32500 | 903
VARIATIONS
JSV01 | JUPP_PV01 | Jupp Street Geotextile wrapping around no fines concrete | m |  |  |  | 242 |  | 1137.6074 |  | 1 | 174.24 | 831.996 | 131.3714 | 0 | 1137.6074
| 1 | A24 | m² | M | 1 | 1 | 348.48 | 1.05 | 365.904 |  |  | 0 | 365.904 | 0 | 0 | 365.904 | 222
| 2 | S32 - No Fines | m3 | M | 1 | 1 | 2.178 | 214 | 466.092 |  |  | 0 | 466.092 | 0 | 0 | 466.092 | 222
JSV01.1 | 3 | Labour | hr | L | 3 | 175 | 242 | 42 | 174.24 | 4.1486 | 1.3829 | 174.24 | 0 | 0 | 0 | 174.24 | 222
| 4 | Bobcat | hr | P | 1 | 175 | 242 | 95 | 131.3714 | 1.3829 | 1.3829 | 0 | 0 | 131.3714 | 0 | 131.3714 | 222
JSV02 | JUPP_PV02 | Jupp_PV02 - Boundary Pits & Pipes | each |  |  |  | 1 |  | 2325 |  | 2 | 0 | 0 | 0 | 2325 | 2325
| 1 | WDC | Item | S | 1 | 1 | 2325 | 1 | 2325 |  | 2 | 0 | 0 | 0 | 2325 | 2325 | 86
JSV03 | JUPP_PV | Jupp St - Haul & Place Type 2.3 gravel | m³ |  |  |  | 40 |  | 2264.9223 |  | 1 | 272.1872 | 0 | 1992.7351 | 0 | 2264.9223
JSV03.1 | 1 | QTY*2.4 Tonnes Gravel |  |  | 2.4 |  | 96
| 2 | Truck & Dog | hr | P | 3 | 37 | 96 | 145 | 1128.6486 | 7.7838 | 2.5946 | 0 | 0 | 1128.6486 | 0 | 1128.6486 | 62
| 3 | Placement
JSV03.2 | 4 | Grader | hr | P | 1 | 44.44 | 96 | 145 | 313.2313 | 2.1602 | 2.1602 | 0 | 0 | 313.2313 | 0 | 313.2313 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 44.44 | 96 | 100 | 216.0216 | 2.1602 | 2.1602 | 0 | 0 | 216.0216 | 0 | 216.0216 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 44.44 | 96 | 55 | 118.8119 | 2.1602 | 2.1602 | 0 | 0 | 118.8119 | 0 | 118.8119 | 62
| 7 | Labour | hr | L | 3 | 44.44 | 96 | 42 | 272.1872 | 6.4806 | 2.1602 | 272.1872 | 0 | 0 | 0 | 272.1872 | 62
| 8 | Backhoe | hr | P | 1 | 44.44 | 96 | 100 | 216.0216 | 2.1602 | 2.1602 | 0 | 0 | 216.0216 | 0 | 216.0216 | 62
JSV04 | JUPP_PV03 | Jupp St_PV03 - Replace AC watermain crossing at Jupp and Anzac Rd | item |  |  |  | 1 |  | 23859.3462 |  | 6 | 3016.2222 | 671.724 | 1567.5 | 18603.9 | 23859.3462
| 1 | Installation of water main Jupp and anzac two crossing
| 2 | WDC | Item | S | 1 | 1 | 18603.9 | 1 | 18603.9 |  | 4 | 0 | 0 | 0 | 18603.9 | 18603.9 | 103
| 3 | Project Supervisor | hr | L | 1 | 1 | 0.31111 | 3350 | 1042.2222 |  | 7.7778e-05 | 1042.2222 | 0 | 0 | 0 | 1042.2222 | 902
| 4 | Traffic Controller | hr | L | 1 | 1 | 47 | 42 | 1974 |  | 5.2222 | 1974 | 0 | 0 | 0 | 1974 | 141
| 5 | Tipper | hr | P | 1 | 1 | 16.5 | 95 | 1567.5 |  | 1.8333 | 0 | 0 | 1567.5 | 0 | 1567.5 | 103
| 6 | CBR45 | tonne | M | 1 | 1 | 11.88 | 28.3 | 336.204 |  |  | 0 | 336.204 | 0 | 0 | 336.204 | 62
| 7 | Sand | tonne | M | 1 | 1 | 13.98 | 24 | 335.52 |  |  | 0 | 335.52 | 0 | 0 | 335.52 | QMS
JSV05 | JUPP_PV04 | Jupp_PV04 - Extend Kerb & Channel On Anzac Road | item |  |  |  | 1 |  | 691.1193 |  | 1 | 0 | 301.1193 | 0 | 390 | 691.1193
| 1 | Install kerbing on Anzac Rd type B1 | m
| 2 | Use Kerb Subbie. Allciv to supply sand & cement for slurry
| 3 | S32 - Kerb Mix | m³ | M | 1 | 1 | 1.5116 | 190 | 287.2093 |  |  | 0 | 287.2093 | 0 | 0 | 287.2093 | CKM
| 4 | Sand | tonne | M | 1 | 1 | 0.17333 | 24 | 4.16 |  |  | 0 | 4.16 | 0 | 0 | 4.16 | QMS
| 5 | Cement | tonne | M | 1 | 1 | 0.021667 | 450 | 9.75 |  |  | 0 | 9.75 | 0 | 0 | 9.75 | CSA
| 6 | Kerb Subbie | m | S | 1 | 1 | 13 | 30 | 390 |  | 0.065 | 0 | 0 | 0 | 390 | 390 | 71
JSV06 | JUPP_PV05 | Jupp_PV05 - Extend Kerb & Channel on Phaff Street | item |  |  |  | 1 |  | 1086.1193 |  | 1 | 0 | 526.1193 | 0 | 560 | 1086.1193
| 1 | Kerbing type B1 Phaff st | m
| 2 | Use Kerb Subbie. Allciv to supply sand & cement for slurry
| 3 | S32 - Kerb Mix | m³ | M | 1 | 1 | 1.5116 | 190 | 287.2093 |  |  | 0 | 287.2093 | 0 | 0 | 287.2093 | CKM
| 4 | Sand | tonne | M | 1 | 1 | 0.17333 | 24 | 4.16 |  |  | 0 | 4.16 | 0 | 0 | 4.16 | QMS
| 5 | Cement | tonne | M | 1 | 1 | 0.021667 | 450 | 9.75 |  |  | 0 | 9.75 | 0 | 0 | 9.75 | CSA
| 6 | Kerb Subbie | m | S | 1 | 1 | 13 | 30 | 390 |  | 0.065 | 0 | 0 | 0 | 390 | 390 | 71
| 7 | Property Connection and kerb adaptor Phaff Street | each
| 8 | No. properties = 1 |  |  |  |  | 1
| 9 | 150 SN8 Sewer Pipe | m | M | 1 | 1 | 6 | 25 | 150 |  |  | 0 | 150 | 0 | 0 | 150 | SWP
| 10 | Kerb Adaptors | each | M | 1 | 1 | 1 | 75 | 75 |  |  | 0 | 75 | 0 | 0 | 75 | SWP
JSV06.1 | 11 | Plumber | hr | S | 1 | 0.5 | 1 | 85 | 170 | 2 | 2 | 0 | 0 | 0 | 170 | 170 | 81
DSV01 | DODD_PV01 | Dodd St - Geogrid layer | m² |  |  |  | 2797 |  | 16668.697 |  | 1 | 680.1126 | 15475.801 | 512.7833 | 0 | 16668.697
DSV01.1 | 1 | TX160 - Geogrid | m² | M | 1.1 | 1 | 3076.7 | 5.03 | 15475.801 |  |  | 0 | 15475.801 | 0 | 0 | 15475.801 | 222
DSV01.2 | 2 | Labour | hr | L | 3 | 570 | 3076.7 | 42 | 680.1126 | 16.1932 | 5.3977 | 680.1126 | 0 | 0 | 0 | 680.1126 | 222
| 3 | Bobcat | hr | P | 1 | 570 | 3076.7 | 95 | 512.7833 | 5.3977 | 5.3977 | 0 | 0 | 512.7833 | 0 | 512.7833 | 222
DSV02 | DODD_PV02 | Dodd Street-PV02 Supply and Install Entry pits, RCBC and Concrete Nib Wall and Nib | item |  |  |  | 1 |  | 12004.176 |  | 8 | 962.1818 | 7031.176 | 1470.8182 | 2540 | 12004.176
| 1 | Supply and install 1200x300 RCBC | m |  |  |  | 9.6
| 2 | (11) Box Units to Stand |  |  |  |  | 8
| 3 | (15) Hand Placed Backfill |  |  |  |  | 10.9091
| 4 | RCBC - 1200 x 300 | m | M | 1 | 1 | 9.6 | 393.36 | 3776.256 |  |  | 0 | 3776.256 | 0 | 0 | 3776.256 | SWC
DSV02.1 | 5 | Excavator - 25T | hr | P | 1 | 2 | 8 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 181
DSV02.2 | 6 | Labour | hr | L | 3 | 2 | 8 | 42 | 504 | 12 | 4 | 504 | 0 | 0 | 0 | 504 | 181
| 7 | Denso Tape | m | M | 1 | 1 | 28 | 5 | 140 |  |  | 0 | 140 | 0 | 0 | 140 | 181
DSV02.3 | 8 | Bobcat | hr | P | 1 | 3 | 10.9091 | 95 | 345.4545 | 3.6364 | 3.6364 | 0 | 0 | 345.4545 | 0 | 345.4545 | 181
DSV02.4 | 9 | Labour | hr | L | 3 | 3 | 10.9091 | 42 | 458.1818 | 10.9091 | 3.6364 | 458.1818 | 0 | 0 | 0 | 458.1818 | 181
| 10 | Plate Compactor | hr | P | 1 | 3 | 10.9091 | 3.5 | 12.7273 | 3.6364 | 3.6364 | 0 | 0 | 12.7273 | 0 | 12.7273 | 181
| 11 | Water Cart - Hire | hr | P | 1 | 3 | 10.9091 | 100 | 363.6364 | 3.6364 | 3.6364 | 0 | 0 | 363.6364 | 0 | 363.6364 | 181
DSV02.5 | 12 | Install concrete Nib Wall and Nib | m³ |  |  |  | 2
| 13 | N32 | m² | M | 1 | 1 | 2.2 | 192 | 422.4 |  |  | 0 | 422.4 | 0 | 0 | 422.4 | C32
| 14 | Concrete Sub-contract | hr | S | 1 | 1 | 2.2 | 700 | 1540 | 2.2 | 2.2 | 0 | 0 | 0 | 1540 | 1540 | 181
| 15 | Bobcat | hr | P | 1 | 1 | 2.2 | 95 | 209 | 2.2 | 2.2 | 0 | 0 | 209 | 0 | 209 | 181
DSV02.6 | 16 | Supply and Install 2 MCC Type A Kerb entry pits | each |  |  |  | 2
| 17 | Bro Pit - 1C1T | Item | M | 1 | 1 | 2 | 1346.26 | 2692.52 |  |  | 0 | 2692.52 | 0 | 0 | 2692.52 | SWPC
| 18 | WDC | Item | S | 1 | 1 | 1000 | 1 | 1000 |  | 4 | 0 | 0 | 0 | 1000 | 1000 | 86
DSV03 | DODD_PV03 | Dodd Street water main replacement Install new 100mm Dia DICL Watermains 3 locations | item |  |  |  | 1 |  | 42341 |  | 9 | 925 | 0 | 0 | 41416 | 42341
DSV03.1 | 1 | Water Main Dodd St /Anzac Road at CH 315 | item |  |  |  | 1
| 2 | WDC | Item | S | 1 | 1 | 14705 | 1 | 14705 |  | 4 | 0 | 0 | 0 | 14705 | 14705 | 103
DSV03.2 |  | Replace AC Watermain Crossing at Dodd and Phaff Street | each |  |  |  | 1
| 1 | WDC | Item | S | 1 | 1 | 26711 | 1 | 26711 |  | 4 | 0 | 0 | 0 | 26711 | 26711 | 103
|  | Survey water main | item |  |  |  | 1
| 1 | Surveyor | Item | L | 1 | 1 | 5 | 185 | 925 |  | 1 | 925 | 0 | 0 | 0 | 925 | 11
DSV04 | DODD_PV04 | Dodd Street_ PV04 - Extend Deep Lift AC at Culvert Crossing Anzac Drive | tonne |  |  |  | 3.29 |  | 891.261 |  | 1 | 0 | 0 | 0 | 891.261 | 891.261
| 1 | DG14 - Dodd St | tonne | S | 1 | 1 | 3.4545 | 258 | 891.261 |  | 0.017273 | 0 | 0 | 0 | 891.261 | 891.261 | 65
DSV05 | DODD_PV05 | Dodd Street_PV05 - New Bropit and RCBC arrangement | item |  |  |  | 1 |  | 5434.44 |  | 4 | 0 | 1709.44 | 0 | 3725 | 5434.44
| 1 | Bro Pit - 1C2T | Item | M | 1 | 1 | 1 | 1709.44 | 1709.44 |  |  | 0 | 1709.44 | 0 | 0 | 1709.44 | SWPC
| 2 | WDC | Item | S | 1 | 1 | 3725 | 1 | 3725 |  | 4 | 0 | 0 | 0 | 3725 | 3725 | 86
DSV06 | DODD_PV06 | Install new Type A MCC side entry pit, 13m of 450 RCP break in to existing drainage line and install a flush point. | item |  |  |  | 1 |  | 6552.74 |  | 3 | 1092 | 3010.74 | 1170 | 1280 | 6552.74
| 1 | Bro Pit - 1C2T | Item | M | 1 | 1 | 1 | 1709.44 | 1709.44 |  |  | 0 | 1709.44 | 0 | 0 | 1709.44 | SWPC
| 2 | WDC | Item | S | 1 | 1 | 1280 | 1 | 1280 |  | 2 | 0 | 0 | 0 | 1280 | 1280 | 86
| 3 | Install 13m 450 FJ RCP |  |  |  |  | 13
DSV06.1 | 4 | Excavator - 25T | hr | P | 1 | 1.5 | 13 | 135 | 1170 | 8.6667 | 8.6667 | 0 | 0 | 1170 | 0 | 1170 | 81
| 5 | 450 RCP FJ CL2 | m | M | 1 | 1 | 13 | 92.1 | 1197.3 |  |  | 0 | 1197.3 | 0 | 0 | 1197.3 | SWP
| 6 | Sand | tonne | M | 1 | 1 | 4.3333 | 24 | 104 |  |  | 0 | 104 | 0 | 0 | 104 | QMS
DSV06.2 | 4 | Labour | hr | L | 3 | 1.5 | 13 | 42 | 1092 | 26 | 8.6667 | 1092 | 0 | 0 | 0 | 1092 | 81
DSV07 | DODD_P0V7 | Installation Pram Ramps Dodd street | item |  |  |  | 1 |  | 15632.4433 |  | 4 | 7974.2186 | 4208.7057 | 270.959 | 3178.56 | 15632.4433
| 1 | Project Supervisor | Item | L | 1 | 1 | 2 | 3350 | 6700 |  |  | 6700 | 0 | 0 | 0 | 6700 | 902
| 1 | TGSI | Item | S | 1 | 1 | 20 | 40 | 800 |  | 2 | 0 | 0 | 0 | 800 | 800 | 67
| 1 | Pram Ramps | Item | M | 1 | 1 | 2 | 700 | 1400 |  |  | 0 | 1400 | 0 | 0 | 1400 | 73
DSV07.1 | 1 | Hand placed concrete paving |  |  |  |  | 6.72
| 1 | Purchase Materials
| 2 | N25 | m³ | M | 1 | 1 | 0.7392 | 170 | 125.664 |  |  | 0 | 125.664 | 0 | 0 | 125.664 | C25
| 3 | Sand | tonne | M | 1 | 1 | 1.008 | 24 | 24.192 |  |  | 0 | 24.192 | 0 | 0 | 24.192 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 8.064 | 9.1 | 73.3824 |  |  | 0 | 73.3824 | 0 | 0 | 73.3824 | RSM
| 5 | Abel Flex | m | M | 1 | 1 | 5.376 | 3 | 16.128 |  |  | 0 | 16.128 | 0 | 0 | 16.128 | RSM
| 6 | Detailed Excavation:
DSV07.2 | 7 | Excavator - 25T | hr | P | 1 | 10 | 0.672 | 135 | 9.072 | 0.0672 | 0.0672 | 0 | 0 | 9.072 | 0 | 9.072 | 73
| 8 | Tipper | hr | P | 1 | 10 | 0.672 | 95 | 6.384 | 0.0672 | 0.0672 | 0 | 0 | 6.384 | 0 | 6.384 | 73
| 9 | Labour | hr | L | 1 | 10 | 0.672 | 42 | 2.8224 | 0.0672 | 0.0672 | 2.8224 | 0 | 0 | 0 | 2.8224 | 73
| 10 | Form Pour & Finish
| 11 | Bar Chairs | each | M | 1 | 1 | 7.4667 | 0.8 | 5.9733 |  |  | 0 | 5.9733 | 0 | 0 | 5.9733 | RSM
| 12 | Concrete Subbie | m² | S | 1 | 1 | 6.72 | 32 | 215.04 |  | 0.2688 | 0 | 0 | 0 | 215.04 | 215.04 | 73
DSV07.3 | 1 | Demolition of Existing Pram Ramp |  |  |  |  | 2
| 1 | Backhoe | Item | P | 1 | 2 | 2 | 100 | 100 |  | 1 | 0 | 0 | 100 | 0 | 100 | 41
| 1 | Tipper | Item | M | 1 | 2 | 2 | 95 | 95 |  | 1 | 0 | 95 | 0 | 0 | 95 | 41
| 1 | Labour | Item | L | 2 | 1 | 2 | 42 | 168 |  | 2 | 168 | 0 | 0 | 0 | 168 | 41
DSV07.4 | 1 | Reinstate footpath - 2.1m x 24.1m | m2 |  |  |  | 50.61
| 1 | Purchase Materials
| 2 | N25 | m³ | M | 1 | 1 | 5.5671 | 170 | 946.407 |  |  | 0 | 946.407 | 0 | 0 | 946.407 | C25
| 3 | Sand | tonne | M | 1 | 1 | 7.5915 | 24 | 182.196 |  |  | 0 | 182.196 | 0 | 0 | 182.196 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 60.732 | 9.1 | 552.6612 |  |  | 0 | 552.6612 | 0 | 0 | 552.6612 | RSM
| 5 | Abel Flex | m | M | 1 | 1 | 40.488 | 3 | 121.464 |  |  | 0 | 121.464 | 0 | 0 | 121.464 | RSM
| 6 | Detailed Excavation:
DSV07.5 | 7 | Excavator - 25T | hr | P | 1 | 10 | 5.061 | 135 | 68.3235 | 0.5061 | 0.5061 | 0 | 0 | 68.3235 | 0 | 68.3235 | 73
| 8 | Tipper | hr | P | 1 | 10 | 5.061 | 95 | 48.0795 | 0.5061 | 0.5061 | 0 | 0 | 48.0795 | 0 | 48.0795 | 73
| 9 | Labour | hr | L | 1 | 10 | 5.061 | 42 | 21.2562 | 0.5061 | 0.5061 | 21.2562 | 0 | 0 | 0 | 21.2562 | 73
| 10 | Form Pour & Finish
| 11 | Bar Chairs | each | M | 1 | 1 | 56.2333 | 0.8 | 44.9867 |  |  | 0 | 44.9867 | 0 | 0 | 44.9867 | RSM
| 12 | Concrete Subbie | m² | S | 1 | 1 | 50.61 | 32 | 1619.52 |  | 1.0122 | 0 | 0 | 0 | 1619.52 | 1619.52 | 73
DSV07.6 | 1 | Hand placed kerb - 17m | m |  |  |  | 17
| 1 | Purchase Materials
| 2 | N25 | m³ | M | 1 | 1 | 1.87 | 170 | 317.9 |  |  | 0 | 317.9 | 0 | 0 | 317.9 | C25
| 3 | Sand | tonne | M | 1 | 1 | 2.55 | 24 | 61.2 |  |  | 0 | 61.2 | 0 | 0 | 61.2 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 20.4 | 9.1 | 185.64 |  |  | 0 | 185.64 | 0 | 0 | 185.64 | RSM
| 5 | Abel Flex | m | M | 1 | 1 | 13.6 | 3 | 40.8 |  |  | 0 | 40.8 | 0 | 0 | 40.8 | RSM
| 6 | Detailed Excavation:
DSV07.7 | 7 | Excavator - 25T | hr | P | 1 | 10 | 1.7 | 135 | 22.95 | 0.17 | 0.17 | 0 | 0 | 22.95 | 0 | 22.95 | 71
| 8 | Tipper | hr | P | 1 | 10 | 1.7 | 95 | 16.15 | 0.17 | 0.17 | 0 | 0 | 16.15 | 0 | 16.15 | 71
| 9 | Labour | hr | L | 1 | 10 | 1.7 | 42 | 7.14 | 0.17 | 0.17 | 7.14 | 0 | 0 | 0 | 7.14 | 41
| 10 | Form Pour & Finish
| 11 | Bar Chairs | each | M | 1 | 1 | 18.8889 | 0.8 | 15.1111 |  |  | 0 | 15.1111 | 0 | 0 | 15.1111 | RSM
| 12 | Concrete Subbie | m² | S | 1 | 1 | 17 | 32 | 544 |  | 0.68 | 0 | 0 | 0 | 544 | 544 | 41
| 2 | Project Engineer | Item | L | 2 | 1 | 0.1 | 3250 | 650 |  | 0.1 | 650 | 0 | 0 | 0 | 650 | 901
| 3 | Project Manager | Item | L | 2 | 1 | 0.05 | 4250 | 425 |  | 0.05 | 425 | 0 | 0 | 0 | 425 | 901
DSV08 | DODD_PV08 | Dodd Street - Water main Protection Lurline Street - works completed formal vairation to be provided Refer to email 2 May sent | m³ |  |  |  | 11.6 |  | 2169.2 |  | 1 | 0 | 2169.2 | 0 | 0 | 2169.2
| 1 | N25 | m³ | M | 1 | 1 | 12.76 | 170 | 2169.2 |  | 0.42533 | 0 | 2169.2 | 0 | 0 | 2169.2 | C25
DSV09 | DODD_PV09 | Vairation to design levels mismatch to road surface - 44m Lurline Street to match levels to existing road surface. | hr |  |  |  | 1 |  | 325 |  | 0 | 325 | 0 | 0 | 0 | 325
| 1 | Project Engineer | Item | L | 2 | 1 | 0.05 | 3250 | 325 |  | 0.05 | 325 | 0 | 0 | 0 | 325 | 901
CCC01 | CCC_PV01 | CCC_PV01 - Remove and Replace New kerbiing and traffic Islands | item |  |  |  | 1 |  | 2308.0209 |  | 3 | 84 | 974.0209 | 50 | 1200 | 2308.0209
CCC01.1 | 1 | CCC_PV01 - Cultrual Centre Carpark - Install Traffic Islands | m |  |  |  | 40
Use Kerb Subbie. Allciv to supply sand & cement for slurry
CCC01.2 | 2 | S32 - Kerb Mix | m³ | M | 8.6 | 1 | 4.6512 | 190 | 883.7209 |  |  | 0 | 883.7209 | 0 | 0 | 883.7209 | CKM
CCC01.3 | 3 | Sand | tonne | M | 75 | 1 | 0.53333 | 24 | 12.8 |  |  | 0 | 12.8 | 0 | 0 | 12.8 | QMS
CCC01.4 | 4 | Cement | tonne | M | 8 | 1 | 0.066667 | 450 | 30 |  |  | 0 | 30 | 0 | 0 | 30 | 71
| 5 | Kerb Subbie | m | S | 1 | 1 | 40 | 30 | 1200 |  | 0.2 | 0 | 0 | 0 | 1200 | 1200 | 71
CCC01.5 | 6 | Cutrual Carpark Centre - Demolition of kerb invert and islands |  |  |  |  | 1
| 7 | Backhoe | Item | P | 1 | 2 | 1 | 100 | 50 |  | 0.5 | 0 | 0 | 50 | 0 | 50 | 41
| 8 | Tipper | Item | M | 1 | 2 | 1 | 95 | 47.5 |  | 0.5 | 0 | 47.5 | 0 | 0 | 47.5 | 41
| 9 | Labour | Item | L | 2 | 1 | 1 | 42 | 84 |  | 1 | 84 | 0 | 0 | 0 | 84 | 41
CCC02 | CCC_PV02 | CCC_PV02 - Cultrual Centre Carpark - Install 600m dish Drain | m |  |  |  | 44 |  | 5723.08 |  | 2 | 0 | 2863.08 | 0 | 2860 | 5723.08
| 1 | Use Kerb Subbie. Allciv to supply sand & cement for slurry
CCC02.1 | 2 | N32 | m³ | M | 3 | 1 | 14.6667 | 192 | 2816 |  |  | 0 | 2816 | 0 | 0 | 2816 | CKM
CCC02.2 | 3 | Sand | tonne | M | 75 | 1 | 0.58667 | 24 | 14.08 |  |  | 0 | 14.08 | 0 | 0 | 14.08 | QMS
CCC02.3 | 4 | Cement | tonne | M | 8 | 1 | 0.073333 | 450 | 33 |  |  | 0 | 33 | 0 | 0 | 33 | 71
| 5 | Kerb Subbie - Hand | m | S | 1 | 1 | 44 | 65 | 2860 |  | 0.88 | 0 | 0 | 0 | 2860 | 2860 | 71
CCC03 | CCC_PV03 | CCC_PV03 Cultrual Centre Carpark Insitu Stabilising Carpark - 400m2 | m² |  |  |  | 400 | 13.7166 | 5486.63 |  | 2 | 1134 | 1188 | 3164.63 | 0 | 5486.63
| 1 | Purchase Materials
| 2 | Cement | Item | M | 1 | 2 | 5.28 | 450 | 1188 |  |  | 0 | 1188 | 0 | 0 | 1188 | CSA
| 3 | StabIlising:
| 4 | CAT297 Stabiliser | Item | P | 1 | 44.4444 | 400 | 66.07 | 594.63 |  | 1 | 0 | 0 | 594.63 | 0 | 594.63 | 68
| 5 | Water Cart - Hire | Item | P | 1 | 44.4444 | 400 | 100 | 900 |  | 1 | 0 | 0 | 900 | 0 | 900 | 68
| 6 | PF Roller | Item | P | 1 | 400 | 400 | 365 | 365 |  | 1 | 0 | 0 | 365 | 0 | 365 | 68
| 7 | Grader | Item | P | 1 | 44.4444 | 400 | 145 | 1305 |  | 1 | 0 | 0 | 1305 | 0 | 1305 | 68
| 8 | Labour | Item | L | 3 | 44.4444 | 400 | 42 | 1134 |  | 1 | 1134 | 0 | 0 | 0 | 1134 | 68
CCC04 | CCC_PV04 | Unsuitable Subgrade replacement Iron Stone Rock Mattress | Item |  |  |  | 1 |  | 45538.5999 |  | 6 | 7535.5874 | 3803.25 | 34199.7625 | 0 | 45538.5999
CCC04.1 |  | Win, load and Import iron stone gravel | m³ |  |  |  | 539.9
CCC04.2 | 1 | Excavator - 25T | hr | P | 1 | 40 | 539.9 | 135 | 1822.1625 | 13.4975 | 13.4975 | 0 | 0 | 1822.1625 | 0 | 1822.1625 | 57
CCC04.3 | 2 | Truck & Dog | hr | P | 4 | 40 | 539.9 | 145 | 7828.55 | 53.99 | 13.4975 | 0 | 0 | 7828.55 | 0 | 7828.55 | 57
| 3 | Water Cart - Hire | hr | P | 1 | 40 | 539.9 | 100 | 1349.75 | 13.4975 | 13.4975 | 0 | 0 | 1349.75 | 0 | 1349.75 | 57
| 4 | Labour | hr | L | 1 | 40 | 539.9 | 42 | 566.895 | 13.4975 | 13.4975 | 566.895 | 0 | 0 | 0 | 566.895 | 57
|  | Excavate and remove unsitable subgrade to depth 300mm | m³ |  |  |  | 539.9
CCC04.4 | 5 | Excavator - 25T | hr | P | 1 | 15 | 539.9 | 135 | 4859.1 | 35.9933 | 35.9933 | 0 | 0 | 4859.1 | 0 | 4859.1 | 57
CCC04.5 | 6 | Truck & Dog | hr | P | 2 | 15 | 539.9 | 145 | 10438.0667 | 71.9867 | 35.9933 | 0 | 0 | 10438.0667 | 0 | 10438.0667 | 57
| 7 | Water Cart - Hire | hr | P | 1 | 15 | 539.9 | 100 | 3599.3333 | 35.9933 | 35.9933 | 0 | 0 | 3599.3333 | 0 | 3599.3333 | 57
| 8 | Labour | hr | L | 1 | 15 | 539.9 | 42 | 1511.72 | 35.9933 | 35.9933 | 1511.72 | 0 | 0 | 0 | 1511.72 | 57
|  | Supply and install A34 geofabric additional layer provided in redesign | m² |  |  |  | 1383
| 9 | A34 | m² | M | 1 | 1 | 1521.3 | 2.5 | 3803.25 |  |  | 0 | 3803.25 | 0 | 0 | 3803.25 | 222
CCC04.6 | 10 | Labour | hr | L | 3 | 570 | 1521.3 | 42 | 336.2874 | 8.0068 | 2.6689 | 336.2874 | 0 | 0 | 0 | 336.2874 | 222
| 11 | Bobcat | hr | P | 1 | 570 | 1521.3 | 95 | 253.55 | 2.6689 | 2.6689 | 0 | 0 | 253.55 | 0 | 253.55 | 222
|  | Replace unsuitable meterial below subgrade with select material 300mm depth | m³ |  |  |  | 539.9
CCC04.7 | 12 | Grader | hr | P | 1 | 40 | 539.9 | 145 | 1957.1375 | 13.4975 | 13.4975 | 0 | 0 | 1957.1375 | 0 | 1957.1375 | 57
| 13 | SD Roller - Wet (No Op) | hr | P | 1 | 40 | 539.9 | 55 | 742.3625 | 13.4975 | 13.4975 | 0 | 0 | 742.3625 | 0 | 742.3625 | 57
| 14 | Water Cart - Hire | hr | P | 1 | 40 | 539.9 | 100 | 1349.75 | 13.4975 | 13.4975 | 0 | 0 | 1349.75 | 0 | 1349.75 | 57
| 15 | Labour | hr | L | 3 | 40 | 539.9 | 42 | 1700.685 | 40.4925 | 13.4975 | 1700.685 | 0 | 0 | 0 | 1700.685 | 57
| 16 | Project Supervisor | Item | L | 2 | 1 | 0.35 | 3350 | 2345 |  | 0.35 | 2345 | 0 | 0 | 0 | 2345 | 901
| 17 | Project Engineer | Item | L | 2 | 1 | 0.1 | 3250 | 650 |  | 0.1 | 650 | 0 | 0 | 0 | 650 | 902
| 18 | Project Manager | Item | L | 2 | 1 | 0.05 | 4250 | 425 |  | 0.05 | 425 | 0 | 0 | 0 | 425 | 901
SS01 | STERRY_PV01 | Sterry_PV01 Sterry Street - Chapman Street Works | item |  |  |  | 1 |  | 21720.4724 |  | 7 | 358.6 | 16139.0381 | 184 | 5038.8343 | 21720.4724
SS01.1 |  | Kerb and Channel B1 | m |  |  |  | 66.4
| 1 | Use Kerb Subbie. Allciv to supply sand & cement for slurry | [8 empty] | 1
| 2 | S32 - Kerb Mix | m³ | M | 1 | 1 | 7.7209 | 190 | 1466.9767 |  |  | 0 | 1466.9767 | 0 | 0 | 1466.9767 | CKM
| 3 | Sand | tonne | M | 1 | 1 | 0.88533 | 24 | 21.248 |  |  | 0 | 21.248 | 0 | 0 | 21.248 | QMS
| 4 | Cement | tonne | M | 1 | 1 | 0.11067 | 450 | 49.8 |  |  | 0 | 49.8 | 0 | 0 | 49.8 | CSA
| 5 | Kerb Subbie | m | S | 1 | 1 | 66.4 | 30 | 1992 |  | 0.332 | 0 | 0 | 0 | 1992 | 1992 | 71
SS01.2 |  | Concrete Trench Works | m³ |  |  |  | 70 |  |  |  | 1
| 1 | N25 | m³ | M | 1 | 1 | 77 | 170 | 13090 |  | 0.77 | 0 | 13090 | 0 | 0 | 13090 | C25
SS01.3 |  | Asphalt Works to Chaptman Street | tonne |  |  |  | 81 |  |  |  | 0
| 2 | DG14 - Sterry St | tonne | S | 1 | 1 | 2.1 | 251 | 527.1 |  | 1 | 0 | 0 | 0 | 527.1 | 527.1 | 65
SS01.4 |  | Property Connection and Kerb Adaptor Chaptman street | each |  |  |  | 2 |  |  |  | 1
| 1 | No. of properties |  |  |  |  | 2
| 2 | 150 SN8 Sewer Pipe | m | M | 1 | 1 | 12 | 25 | 300 |  |  | 0 | 300 | 0 | 0 | 300 | SWP
| 3 | Kerb Adaptors | each | M | 1 | 1 | 2 | 75 | 150 |  |  | 0 | 150 | 0 | 0 | 150 | SWP
SS01.5 | 4 | Plumber | hr | S | 1 | 0.5 | 2 | 85 | 340 | 0.44444 | 0.44444 | 0 | 0 | 0 | 340 | 340 | 81
SS01.6 |  | Install driveways chapman street | item |  |  |  | 2 |  |  |  | 3
| 1 | Purchase Materials
| 2 | N32 | m³ | M | 1 | 1 | 3.3 | 192 | 633.6 |  |  | 0 | 633.6 | 0 | 0 | 633.6 | C32
| 3 | Sand | tonne | M | 1 | 1 | 3.6 | 24 | 86.4 |  |  | 0 | 86.4 | 0 | 0 | 86.4 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 28.8 | 9.1 | 262.08 |  |  | 0 | 262.08 | 0 | 0 | 262.08 | RSM
| 5 | Abel Flex | m | M | 1 | 1 | 19.2 | 3 | 57.6 |  |  | 0 | 57.6 | 0 | 0 | 57.6 | 73
| 6 | Detailed Excavation:
SS01.7 | 7 | Excavator - 25T | hr | P | 1 | 3 | 2.4 | 135 | 108 | 0.8 | 0.8 | 0 | 0 | 108 | 0 | 108 | 73
| 8 | Tipper | hr | P | 1 | 3 | 2.4 | 95 | 76 | 0.8 | 0.8 | 0 | 0 | 76 | 0 | 76 | 73
| 9 | Labour | hr | L | 1 | 3 | 2.4 | 42 | 33.6 | 0.8 | 0.8 | 33.6 | 0 | 0 | 0 | 33.6 | 73
| 10 | Form Pour & Finish
| 11 | Bar Chairs | each | M | 1 | 1 | 26.6667 | 0.8 | 21.3333 |  |  | 0 | 21.3333 | 0 | 0 | 21.3333 | RSM
| 12 | Concrete Subbie | m² | S | 1 | 1 | 12 | 32 | 384 |  | 1 | 0 | 0 | 0 | 384 | 384 | 73
|  | Profiling existing road edge to match in to grade existing and kerb Chapman Street | hr |  |  |  | 2 |  |  |  | 0
| 3 | Project Engineer | Item | L | 2 | 1 | 0.05 | 3250 | 325 |  | 0.05 | 325 | 0 | 0 | 0 | 325 | 901
SS01.8 |  | Line marking - Remark pavement marks - bus parking area | m |  |  |  | 80 |  |  |  | 0
| 1 | Line Marking | m² | S | 1 | 1 | 987.6543 | 1 | 987.6543 |  | 0.04 | 0 | 0 | 0 | 987.6543 | 987.6543 | 66
SS01.9 |  | Primer Seal | m² |  |  |  | 130 |  |  |  | 1
| 1 | Seal Visit Eight | m² | S | 1 | 1 | 136.5 | 5.92 | 808.08 |  | 1 | 0 | 0 | 0 | 808.08 | 808.08 | 64
SS02 | STERRY_ PV02 | Area1 and Area 2 Sterry Street - Rock mattress, 2 layers of Geogrid and, geofabric | item |  |  |  | 1 |  | 191104.0703 |  |  | 11722.9312 | 106206.5958 | 63674.5433 | 9500 | 191104.0703
SS02.1 |  | PV02 - Directed on the 27 April 2012 to excavate and remove one layer tensar grid. Ch 50 - Ch 60 LHS | item |  |  |  | 1
| 7 | Backhoe | Item | P | 1 | 1 | 1 | 100 | 100 |  | 0.11111 | 0 | 0 | 100 | 0 | 100 | 61
| 8 | Water Cart - Hire | Item | P | 1 | 1 | 1 | 100 | 100 |  | 0.11111 | 0 | 0 | 100 | 0 | 100 | 61
| 9 | Grader | Item | P | 1 | 1 | 1 | 145 | 145 |  | 0.11111 | 0 | 0 | 145 | 0 | 145 | 61
| 10 | SD Roller | Item | P | 1 | 1 | 0.25 | 365 | 91.25 |  | 0.027778 | 0 | 0 | 91.25 | 0 | 91.25 | 61
| 11 | Labour | Item | L | 5 | 1 | 1 | 42 | 210 |  | 0.11111 | 210 | 0 | 0 | 0 | 210 | 61
| 12 | Project Supervisor | Item | L | 1 | 1 | 0.025 | 3350 | 83.75 |  | 0.0027778 | 83.75 | 0 | 0 | 0 | 83.75 | 902
SS02.2 |  | PV02 -Direction 4 May 2012 remove top two grids mix amd compact . | item |  |  |  | 1
| 7 | Backhoe | Item | P | 1 | 1 | 1 | 100 | 100 |  | 0.11111 | 0 | 0 | 100 | 0 | 100 | 61
| 8 | Water Cart - Hire | Item | P | 1 | 1 | 1 | 100 | 100 |  | 0.11111 | 0 | 0 | 100 | 0 | 100 | 61
| 11 | Labour | Item | L | 3 | 1 | 1 | 42 | 126 |  | 0.11111 | 126 | 0 | 0 | 0 | 126 | 61
| 12 | Project Supervisor | Item | L | 1 | 1 | 0.025 | 3350 | 83.75 |  | 0.0027778 | 83.75 | 0 | 0 | 0 | 83.75 | 902
SS02.3 |  | Supervisor | hr |  |  |  | 14
| 12 | Project Supervisor | Item | L | 1 | 1 | 0.35 | 3350 | 1172.5 |  | 0.038889 | 1172.5 | 0 | 0 | 0 | 1172.5 | 902
SS02.4 |  | Traffic Control - maintenance of signs 1 hr/ day @ 50/hr based on 23 days | hr |  |  |  | 23
| 11 | Traffic Controller | Item | L | 1 | 1 | 23 | 42 | 966 |  | 2.5556 | 966 | 0 | 0 | 0 | 966 | 141
SS02.A1 |  | Sterry Street - Area 1 Remove & Replace | [8 empty] | 12
SS02.5 |  | Area 1 Remove cement modify base - subgrade failure | m³ |  |  |  | 155 |  |  |  | 2
SS02.6 | 5 | Excavator - 25T | hr | P | 1 | 15 | 155 | 135 | 1395 | 10.3333 | 10.3333 | 0 | 0 | 1395 | 0 | 1395 | 57
SS02.7 | 6 | Truck & Dog | hr | P | 2 | 15 | 155 | 145 | 2996.6667 | 20.6667 | 10.3333 | 0 | 0 | 2996.6667 | 0 | 2996.6667 | 57
| 7 | Water Cart - Hire | hr | P | 1 | 15 | 155 | 100 | 1033.3333 | 10.3333 | 10.3333 | 0 | 0 | 1033.3333 | 0 | 1033.3333 | 57
| 8 | Labour | hr | L | 1 | 15 | 155 | 42 | 434 | 10.3333 | 10.3333 | 434 | 0 | 0 | 0 | 434 | 57
SS02.8 |  | Area 1 Excavate unsuitable material 200mm below subgrade | m³ |  |  |  | 470 |  |  |  | 4
SS02.9 | 5 | Excavator - 25T | hr | P | 1 | 15 | 470 | 135 | 4230 | 31.3333 | 31.3333 | 0 | 0 | 4230 | 0 | 4230 | 57
SS02.10 | 6 | Truck & Dog | hr | P | 2 | 15 | 470 | 145 | 9086.6667 | 62.6667 | 31.3333 | 0 | 0 | 9086.6667 | 0 | 9086.6667 | 57
| 7 | Water Cart - Hire | hr | P | 1 | 15 | 470 | 100 | 3133.3333 | 31.3333 | 31.3333 | 0 | 0 | 3133.3333 | 0 | 3133.3333 | 57
| 8 | Labour | hr | L | 1 | 15 | 470 | 42 | 1316 | 31.3333 | 31.3333 | 1316 | 0 | 0 | 0 | 1316 | 57
SS02.11 |  | Area 1 Replace unsuitable material with select material complete 400mm depth | m³ |  |  |  | 940 |  |  |  | 3
SS02.12 | 12 | Grader | hr | P | 1 | 40 | 940 | 145 | 3407.5 | 23.5 | 23.5 | 0 | 0 | 3407.5 | 0 | 3407.5 | 57
| 13 | SD Roller - Wet (No Op) | hr | P | 1 | 40 | 940 | 55 | 1292.5 | 23.5 | 23.5 | 0 | 0 | 1292.5 | 0 | 1292.5 | 57
| 14 | Water Cart - Hire | hr | P | 1 | 40 | 940 | 100 | 2350 | 23.5 | 23.5 | 0 | 0 | 2350 | 0 | 2350 | 57
| 15 | Labour | hr | L | 3 | 40 | 940 | 42 | 2961 | 70.5 | 23.5 | 2961 | 0 | 0 | 0 | 2961 | 57
SS02.13 |  | Area 1 Supply and install 2 Layer Geogrid tensar TX160 Top layers only | m² |  |  |  | 5372.6 |  |  |  | 2
SS02.14 | 1 | TX160 - Geogrid | m² | M | 1.1 | 1 | 5909.86 | 5.03 | 29726.5958 |  |  | 0 | 29726.5958 | 0 | 0 | 29726.5958 | 222
SS02.15 | 2 | Labour | hr | L | 3 | 570 | 5909.86 | 42 | 1306.3901 | 31.1045 | 10.3682 | 1306.3901 | 0 | 0 | 0 | 1306.3901 | 222
| 3 | Bobcat | hr | P | 1 | 570 | 5909.86 | 95 | 984.9767 | 10.3682 | 10.3682 | 0 | 0 | 984.9767 | 0 | 984.9767 | 222
SS02.16 |  | Area 1 Supply and install Geofabric Top and side of mattress only | m² |  |  |  | 3054 |  |  |  | 1
SS02.17 | 1 | A34 | m² | M | 1.1 | 1 | 3359.4 | 2.5 | 8398.5 |  |  | 0 | 8398.5 | 0 | 0 | 8398.5 | 222
SS02.18 | 2 | Labour | hr | L | 3 | 570 | 3359.4 | 42 | 742.6042 | 17.6811 | 5.8937 | 742.6042 | 0 | 0 | 0 | 742.6042 | 222
| 3 | Bobcat | hr | P | 1 | 570 | 3359.4 | 95 | 559.9 | 5.8937 | 5.8937 | 0 | 0 | 559.9 | 0 | 559.9 | 222
SS02.19 |  | Area1 Supply Gabion Rock BQC | tonne |  |  |  | 816.58
| 11 | Drainage Agg | tonne | M | 1 | 1 | 816.58 | 37.5 | 30621.75 |  |  | 0 | 30621.75 | 0 | 0 | 30621.75 | QMR
SS02.20 |  | Area 1 Cartage Gabion Rock BQC | hr |  |  |  | 111
| 3 | Truck & Dog | hr | P | 1 | 1 | 111 | 145 | 16095 | 111 | 111 | 0 | 0 | 16095 | 0 | 16095 | 221
SS02.21 |  | Area 1 Project Manager | hr |  |  |  | 4
| 12 | Project Manager | Item | L | 1 | 1 | 0.1 | 4250 | 425 |  | 0.011111 | 425 | 0 | 0 | 0 | 425 | 901
SS02.22 |  | Area 1 Project Engineer | hr |  |  |  | 8
| 12 | Project Engineer | Item | L | 1 | 1 | 0.2 | 3250 | 650 |  | 0.022222 | 650 | 0 | 0 | 0 | 650 | 901
SS02.A2 |  | Sterry Street - Area 2 Remove & Replace | [8 empty] | 3
SS02.23 |  | Area 2 Excavate Unsuitable Material 200mm below subgrade | m³ |  |  |  | 83 |  |  |  | 1
SS02.24 | 5 | Excavator - 25T | hr | P | 1 | 15 | 83 | 135 | 747 | 5.5333 | 5.5333 | 0 | 0 | 747 | 0 | 747 | 57
SS02.25 | 6 | Truck & Dog | hr | P | 2 | 15 | 83 | 145 | 1604.6667 | 11.0667 | 5.5333 | 0 | 0 | 1604.6667 | 0 | 1604.6667 | 57
| 7 | Water Cart - Hire | hr | P | 1 | 15 | 83 | 100 | 553.3333 | 5.5333 | 5.5333 | 0 | 0 | 553.3333 | 0 | 553.3333 | 57
| 8 | Labour | hr | L | 1 | 15 | 83 | 42 | 232.4 | 5.5333 | 5.5333 | 232.4 | 0 | 0 | 0 | 232.4 | 57
SS02.26 |  | Area 2 Replace unsuitable material with select material complete 400mm depth | m³ |  |  |  | 116 |  |  |  | 1
SS02.27 | 12 | Grader | hr | P | 1 | 40 | 116 | 145 | 420.5 | 2.9 | 2.9 | 0 | 0 | 420.5 | 0 | 420.5 | 57
| 13 | SD Roller - Wet (No Op) | hr | P | 1 | 40 | 116 | 55 | 159.5 | 2.9 | 2.9 | 0 | 0 | 159.5 | 0 | 159.5 | 57
| 14 | Water Cart - Hire | hr | P | 1 | 40 | 116 | 100 | 290 | 2.9 | 2.9 | 0 | 0 | 290 | 0 | 290 | 57
| 15 | Labour | hr | L | 3 | 40 | 116 | 42 | 365.4 | 8.7 | 2.9 | 365.4 | 0 | 0 | 0 | 365.4 | 57
SS02.28 |  | Area 2 Supply and install Geofabric Top and side of Mattress only | m² |  |  |  | 455 |  |  |  | 1
SS02.29 | 1 | A34 | m² | M | 1.1 | 1 | 500.5 | 2.5 | 1251.25 |  |  | 0 | 1251.25 | 0 | 0 | 1251.25 | 222
SS02.30 | 2 | Labour | hr | L | 3 | 570 | 500.5 | 42 | 110.6368 | 2.6342 | 0.87807 | 110.6368 | 0 | 0 | 0 | 110.6368 | 222
| 3 | Bobcat | hr | P | 1 | 570 | 500.5 | 95 | 83.4167 | 0.87807 | 0.87807 | 0 | 0 | 83.4167 | 0 | 83.4167 | 222
SS02.31 |  | Area 2 Supply Gabion Rock Wall & Sons | tonne |  |  |  | 267.46
| 11 | Drainage Agg | tonne | M | 1 | 1 | 267.46 | 37.5 | 10029.75 |  |  | 0 | 10029.75 | 0 | 0 | 10029.75 | QMR
SS02.32 |  | Area 2 Cartage Rock Wall &Sons | hr |  |  |  | 35
| 3 | Truck & Dog | hr | P | 1 | 1 | 35 | 145 | 5075 | 35 | 35 | 0 | 0 | 5075 | 0 | 5075 | 221
SS02.33 |  | Area 1 - Supply Rock Wall and Sons | tonne |  |  |  | 698.1
| 11 | Drainage Agg | tonne | M | 1 | 1 | 698.1 | 37.5 | 26178.75 |  |  | 0 | 26178.75 | 0 | 0 | 26178.75 | QMR
SS02.34 |  | Area 1 Additional water service connections (5) | item |  |  |  | 5 |  |  |  | 3
| 2 | WDC | Item | S | 1 | 1 | 9500 | 1 | 9500 |  | 2.5 | 0 | 0 | 0 | 9500 | 9500 | 103
SS02.35 |  | Area 2 Project Manager | hr |  |  |  | 2
| 12 | Project Manager | Item | L | 1 | 1 | 0.05 | 4250 | 212.5 |  | 0.0055556 | 212.5 | 0 | 0 | 0 | 212.5 | 901
SS02.36 |  | Area 2 Project Engineer | hr |  |  |  | 4
| 12 | Project Engineer | Item | L | 1 | 1 | 0.1 | 3250 | 325 |  | 0.011111 | 325 | 0 | 0 | 0 | 325 | 901
SS02.37 |  | Area1 - Cartage Rock Wall & Son | hr |  |  |  | 52
| 3 | Truck & Dog | hr | P | 1 | 1 | 52 | 145 | 7540 | 52 | 52 | 0 | 0 | 7540 | 0 | 7540 | 221
SS04 | STERRY_PV04 | Cement stabilisation - Sterry Street 250mm depth | m² |  |  |  | 2765 |  | 40195.5239 |  | 6 | 6271.02 | 16424.1 | 17500.4039 | 0 | 40195.5239
| 1 | Purchase Materials
SS04.1 | 2 | Cement | Item | M | 1 | 0.012 | 36.498 | 450 | 16424.1 |  |  | 0 | 16424.1 | 0 | 0 | 16424.1 | CSA
| 3 | StabIlising:
SS04.2 | 4 | CAT297 Stabiliser | Item | P | 1 | 55.5556 | 2765 | 66.07 | 3288.3039 |  | 5.53 | 0 | 0 | 3288.3039 | 0 | 3288.3039 | 68
| 5 | Water Cart - Hire | Item | P | 1 | 55.5556 | 2765 | 100 | 4977 |  | 5.53 | 0 | 0 | 4977 | 0 | 4977 | 68
| 6 | PF Roller | Item | P | 1 | 500 | 2765 | 365 | 2018.45 |  | 5.53 | 0 | 0 | 2018.45 | 0 | 2018.45 | 68
| 7 | Grader | Item | P | 1 | 55.5556 | 2765 | 145 | 7216.65 |  | 5.53 | 0 | 0 | 7216.65 | 0 | 7216.65 | 68
| 8 | Labour | Item | L | 3 | 55.5556 | 2765 | 42 | 6271.02 |  | 5.53 | 6271.02 | 0 | 0 | 0 | 6271.02 | 68
SS03 | STERRY_ PV03 | Vairation direction - Removal and Replacement of 150mm Sewer Main Sterry street | item |  |  |  | 1 |  | 9500 |  | 1 | 0 | 0 | 0 | 9500 | 9500
| 2 | WDC | Item | S | 1 | 1 | 9500 | 1 | 9500 |  | 0.5 | 0 | 0 | 0 | 9500 | 9500 | 103
SS05 | STERRY_PV05 | 7 mm Primer Seal Sterry Street | m² |  |  |  | 2765 |  | 17187.24 |  | 1 | 0 | 0 | 0 | 17187.24 | 17187.24
| 1 | Seal Visit Eight | m² | S | 1 | 1 | 2903.25 | 5.92 | 17187.24 |  | 1 | 0 | 0 | 0 | 17187.24 | 17187.24 | 64
SS06 | STERRY_PV06 | Additional Chapman Street works - Kerbing and Miscellaneous concrete works Chapman | m³ |  |  |  | 5 |  | 4460 |  | 1 | 0 | 960 | 0 | 3500 | 4460
| 1 | N32 | m³ | M | 1 | 1 | 5 | 192 | 960 |  |  | 0 | 960 | 0 | 0 | 960 | C32
| 2 | Concrete Sub-contract | m³ | S | 1 | 1 | 5 | 700 | 3500 |  | 1 | 0 | 0 | 0 | 3500 | 3500 | 71
SS07 | STERRY_PV07 | Construct standard driveway access - Proserpine Secondary School | each |  |  |  | 1 |  | 465.0248 |  | 3 | 1.2 | 265.2533 | 6.5714 | 192 | 465.0248
| 1 | Purchase Materials
| 2 | N32 | m³ | M | 1 | 1 | 0.825 | 192 | 158.4 |  |  | 0 | 158.4 | 0 | 0 | 158.4 | C32
| 3 | Sand | tonne | M | 1 | 1 | 0.9 | 24 | 21.6 |  |  | 0 | 21.6 | 0 | 0 | 21.6 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 7.2 | 9.1 | 65.52 |  |  | 0 | 65.52 | 0 | 0 | 65.52 | RSM
| 5 | Abel Flex | m | M | 1 | 1 | 4.8 | 3 | 14.4 |  |  | 0 | 14.4 | 0 | 0 | 14.4 | RSM
| 6 | Detailed Excavation:
SS07.1 | 7 | Excavator - 25T | hr | P | 1 | 21 | 0.6 | 135 | 3.8571 | 0.028571 | 0.028571 | 0 | 0 | 3.8571 | 0 | 3.8571 | 73
| 8 | Tipper | hr | P | 1 | 21 | 0.6 | 95 | 2.7143 | 0.028571 | 0.028571 | 0 | 0 | 2.7143 | 0 | 2.7143 | 73
| 9 | Labour | hr | L | 1 | 21 | 0.6 | 42 | 1.2 | 0.028571 | 0.028571 | 1.2 | 0 | 0 | 0 | 1.2 | 73
| 10 | Form Pour & Finish
| 11 | Bar Chairs | each | M | 1 | 1 | 6.6667 | 0.8 | 5.3333 |  |  | 0 | 5.3333 | 0 | 0 | 5.3333 | RSM
| 12 | Concrete Subbie | m² | S | 1 | 1 | 6 | 32 | 192 |  | 0.33333 | 0 | 0 | 0 | 192 | 192 | 73
SS08 | STERRY_03 | Various Concrete works and fencing and gate alterations - day labour rates + materials | item |  |  |  | 1 |  | 2676 |  | 1 | 0 | 576 | 0 | 2100 | 2676
| 1 | N32 | m³ | M | 1 | 1 | 3 | 192 | 576 |  |  | 0 | 576 | 0 | 0 | 576 | C32
| 2 | Concrete Sub-contract | m³ | S | 1 | 1 | 3 | 700 | 2100 |  | 1 | 0 | 0 | 0 | 2100 | 2100 | 73
DL01 | DOBB_PV01 | Construct three residential property access Dobbins Lane | each |  |  |  | 3 |  | 2493.92 |  | 4 | 50.4 | 1591.52 | 276 | 576 | 2493.92
| 1 | Purchase Materials
| 2 | N32 | m³ | M | 1 | 1 | 4.95 | 192 | 950.4 |  |  | 0 | 950.4 | 0 | 0 | 950.4 | C32
| 3 | Sand | tonne | M | 1 | 1 | 5.4 | 24 | 129.6 |  |  | 0 | 129.6 | 0 | 0 | 129.6 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 43.2 | 9.1 | 393.12 |  |  | 0 | 393.12 | 0 | 0 | 393.12 | RSM
| 5 | Abel Flex | m | M | 1 | 1 | 28.8 | 3 | 86.4 |  |  | 0 | 86.4 | 0 | 0 | 86.4 | RSM
| 6 | Detailed Excavation:
DL01.1 | 7 | Excavator - 25T | hr | P | 1 | 3 | 3.6 | 135 | 162 | 0.13333 | 0.13333 | 0 | 0 | 162 | 0 | 162 | 73
| 8 | Tipper | hr | P | 1 | 3 | 3.6 | 95 | 114 | 0.13333 | 0.13333 | 0 | 0 | 114 | 0 | 114 | 73
| 9 | Labour | hr | L | 1 | 3 | 3.6 | 42 | 50.4 | 0.13333 | 0.13333 | 50.4 | 0 | 0 | 0 | 50.4 | 73
| 10 | Form Pour & Finish
| 11 | Bar Chairs | each | M | 1 | 1 | 40 | 0.8 | 32 |  |  | 0 | 32 | 0 | 0 | 32 | RSM
| 12 | Concrete Subbie | m² | S | 1 | 1 | 18 | 32 | 576 |  | 1.5 | 0 | 0 | 0 | 576 | 576 | 73
DL02 | DOBB_PV02 | Variation Direction to place an additional layer of Geogrid dobbins lane Ch 190 to Ch 230 - 7.5m wide | m² |  |  |  | 300 |  | 1787.8474 |  | 0 | 72.9474 | 1659.9 | 55 | 0 | 1787.8474
DL02.1 | 1 | TX160 - Geogrid | m² | M | 1.1 | 1 | 330 | 5.03 | 1659.9 |  |  | 0 | 1659.9 | 0 | 0 | 1659.9 | 222
DL02.2 | 2 | Labour | hr | L | 3 | 570 | 330 | 42 | 72.9474 | 1.7368 | 0.57895 | 72.9474 | 0 | 0 | 0 | 72.9474 | 222
| 3 | Bobcat | hr | P | 1 | 570 | 330 | 95 | 55 | 0.57895 | 0.57895 | 0 | 0 | 55 | 0 | 55 | 222
DL03 | DOBB_PVO3 A | Remove & Replace Subgrade - Excavate unsutiable material, Blended cement into gravel, import place and compact. | item |  |  |  | 1 |  | 39008.6124 |  | 8 | 6055.756 | 9901.98 | 23050.8764 | 0 | 39008.6124
DL03.1 |  | Excavate Unsuitable Material below subgrade | m³ |  |  |  | 500 |  |  |  | 2
DL03.2 | 5 | Excavator - 25T | hr | P | 1 | 30 | 500 | 135 | 2250 | 1.8519 | 1.8519 | 0 | 0 | 2250 | 0 | 2250 | 57
DL03.3 | 6 | Truck & Dog | hr | P | 2 | 30 | 500 | 145 | 4833.3333 | 3.7037 | 1.8519 | 0 | 0 | 4833.3333 | 0 | 4833.3333 | 57
| 7 | Water Cart - Hire | hr | P | 1 | 30 | 500 | 100 | 1666.6667 | 1.8519 | 1.8519 | 0 | 0 | 1666.6667 | 0 | 1666.6667 | 57
| 8 | Labour | hr | L | 1 | 30 | 500 | 42 | 700 | 1.8519 | 1.8519 | 700 | 0 | 0 | 0 | 700 | 57
|  | Replace unsuitable material with select material | m³ |  |  |  | 500 |  |  |  | 2
DL03.4 | 12 | Grader | hr | P | 1 | 40 | 500 | 145 | 1812.5 | 1.3889 | 1.3889 | 0 | 0 | 1812.5 | 0 | 1812.5 | 57
| 13 | SD Roller - Wet (No Op) | hr | P | 1 | 40 | 500 | 55 | 687.5 | 1.3889 | 1.3889 | 0 | 0 | 687.5 | 0 | 687.5 | 57
| 14 | Water Cart - Hire | hr | P | 1 | 40 | 500 | 100 | 1250 | 1.3889 | 1.3889 | 0 | 0 | 1250 | 0 | 1250 | 57
| 15 | Labour | hr | L | 3 | 40 | 500 | 42 | 1575 | 4.1667 | 1.3889 | 1575 | 0 | 0 | 0 | 1575 | 57
|  | Stabilise Reploaced Gravel | m³ |  |  |  | 1667 |  |  |  | 4
| 1 | Purchase Materials
DL03.5 | 2 | Cement | Item | M | 1 | 0.012 | 22.0044 | 450 | 9901.98 |  |  | 0 | 9901.98 | 0 | 0 | 9901.98 | CSA
| 3 | StabIlising:
DL03.6 | 4 | CAT297 Stabiliser | Item | P | 1 | 55.5556 | 1667 | 66.07 | 1982.4964 |  | 3.334 | 0 | 0 | 1982.4964 | 0 | 1982.4964 | 68
| 5 | Water Cart - Hire | Item | P | 1 | 55.5556 | 1667 | 100 | 3000.6 |  | 3.334 | 0 | 0 | 3000.6 | 0 | 3000.6 | 68
| 6 | PF Roller | Item | P | 1 | 500 | 1667 | 365 | 1216.91 |  | 3.334 | 0 | 0 | 1216.91 | 0 | 1216.91 | 68
| 7 | Grader | Item | P | 1 | 55.5556 | 1667 | 145 | 4350.87 |  | 3.334 | 0 | 0 | 4350.87 | 0 | 4350.87 | 68
| 8 | Labour | Item | L | 3 | 55.5556 | 1667 | 42 | 3780.756 |  | 3.334 | 3780.756 | 0 | 0 | 0 | 3780.756 | 68
DS01 | DOH_PV01 | Variation to water main Doherty street extra over the BOQ | item |  |  |  | 1 |  | 36365 |  | 1 | 0 | 0 | 0 | 36365 | 36365
| 2 | WDC | Item | S | 1 | 1 | 36365 | 1 | 36365 |  | 0.5 | 0 | 0 | 0 | 36365 | 36365 | 103
DS03 | DOH_PV03 | Replacement of AC sewer main ch 37 | item |  |  |  | 1 |  | 5000 |  | 1 | 0 | 0 | 0 | 5000 | 5000
| 2 | WDC | Item | S | 1 | 1 | 5000 | 1 | 5000 |  | 0.5 | 0 | 0 | 0 | 5000 | 5000 | 103
DS02 | DOH_PV02 | Pavement Design | item |  |  |  | 1 |  | 22972.4283 |  | 3 | 2257.5383 | 1804.85 | 18910.04 | 0 | 22972.4283
DS02.1 |  | Excavation of Subgrade | m³ |  |  |  | 443.2
DS02.2 | 5 | Excavator - 25T | hr | P | 1 | 30 | 443.2 | 135 | 1994.4 | 1.6415 | 1.6415 | 0 | 0 | 1994.4 | 0 | 1994.4 | 57
DS02.3 | 6 | Truck & Dog | hr | P | 2 | 30 | 443.2 | 145 | 4284.2667 | 3.283 | 1.6415 | 0 | 0 | 4284.2667 | 0 | 4284.2667 | 57
| 7 | Water Cart - Hire | hr | P | 1 | 30 | 443.2 | 100 | 1477.3333 | 1.6415 | 1.6415 | 0 | 0 | 1477.3333 | 0 | 1477.3333 | 57
| 8 | Labour | hr | L | 1 | 30 | 443.2 | 42 | 620.48 | 1.6415 | 1.6415 | 620.48 | 0 | 0 | 0 | 620.48 | 57
DS02.4 |  | Win, load and import Iron stone | m³ |  |  |  | 378
DS02.5 | 1 | Excavator - 25T | hr | P | 1 | 40 | 378 | 135 | 1275.75 | 1.05 | 1.05 | 0 | 0 | 1275.75 | 0 | 1275.75 | 57
DS02.6 | 2 | Truck & Dog | hr | P | 4 | 40 | 378 | 145 | 5481 | 4.2 | 1.05 | 0 | 0 | 5481 | 0 | 5481 | 57
| 3 | Water Cart - Hire | hr | P | 1 | 40 | 378 | 100 | 945 | 1.05 | 1.05 | 0 | 0 | 945 | 0 | 945 | 57
| 4 | Labour | hr | L | 1 | 40 | 378 | 42 | 396.9 | 1.05 | 1.05 | 396.9 | 0 | 0 | 0 | 396.9 | 57
|  | Replace Unsuitable with select material | m³ |  |  |  | 378
DS02.7 | 12 | Grader | hr | P | 1 | 40 | 378 | 145 | 1370.25 | 1.05 | 1.05 | 0 | 0 | 1370.25 | 0 | 1370.25 | 57
| 13 | SD Roller - Wet (No Op) | hr | P | 1 | 40 | 378 | 55 | 519.75 | 1.05 | 1.05 | 0 | 0 | 519.75 | 0 | 519.75 | 57
| 14 | Water Cart - Hire | hr | P | 1 | 40 | 378 | 100 | 945 | 1.05 | 1.05 | 0 | 0 | 945 | 0 | 945 | 57
| 15 | Labour | hr | L | 3 | 40 | 378 | 42 | 1190.7 | 3.15 | 1.05 | 1190.7 | 0 | 0 | 0 | 1190.7 | 57
|  | Rock Mattress - 23m x4m x 0.4m excavation 23x4x0.7 | tonne |  |  |  | 47
| 11 | Gabion Rock | tonne | M | 1 | 1 | 47 | 26.5 | 1245.5 |  |  | 0 | 1245.5 | 0 | 0 | 1245.5 | QMR
DS02.8 |  | Cartage Rock - foxdale | hr |  |  |  | 4
| 3 | Truck & Dog | hr | P | 1 | 1 | 4 | 145 | 580 | 4 | 4 | 0 | 0 | 580 | 0 | 580 | 221
DS02.9 |  | Supply and lay geofabric | m² |  |  |  | 203.4
DS02.10 | 1 | A34 | m² | M | 1.1 | 1 | 223.74 | 2.5 | 559.35 |  |  | 0 | 559.35 | 0 | 0 | 559.35 | 222
DS02.11 | 2 | Labour | hr | L | 3 | 570 | 223.74 | 42 | 49.4583 | 1.1776 | 0.39253 | 49.4583 | 0 | 0 | 0 | 49.4583 | 222
| 3 | Bobcat | hr | P | 1 | 570 | 223.74 | 95 | 37.29 | 0.39253 | 0.39253 | 0 | 0 | 37.29 | 0 | 37.29 | 222
DS06 | DOH_PV06 | Concrete Driveway 3 Doherty Street | item |  |  |  | 1 |  | 831.3067 |  | 3 | 16.8 | 530.5067 | 92 | 192 | 831.3067
| 1 | Purchase Materials
| 2 | N32 | m³ | M | 1 | 1 | 1.65 | 192 | 316.8 |  |  | 0 | 316.8 | 0 | 0 | 316.8 | C32
| 3 | Sand | tonne | M | 1 | 1 | 1.8 | 24 | 43.2 |  |  | 0 | 43.2 | 0 | 0 | 43.2 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 14.4 | 9.1 | 131.04 |  |  | 0 | 131.04 | 0 | 0 | 131.04 | RSM
| 5 | Abel Flex | m | M | 1 | 1 | 9.6 | 3 | 28.8 |  |  | 0 | 28.8 | 0 | 0 | 28.8 | RSM
| 6 | Detailed Excavation:
DS06.1 | 7 | Excavator - 25T | hr | P | 1 | 3 | 1.2 | 135 | 54 | 0.4 | 0.4 | 0 | 0 | 54 | 0 | 54 | 73
| 8 | Tipper | hr | P | 1 | 3 | 1.2 | 95 | 38 | 0.4 | 0.4 | 0 | 0 | 38 | 0 | 38 | 73
| 9 | Labour | hr | L | 1 | 3 | 1.2 | 42 | 16.8 | 0.4 | 0.4 | 16.8 | 0 | 0 | 0 | 16.8 | 73
| 10 | Form Pour & Finish
| 11 | Bar Chairs | each | M | 1 | 1 | 13.3333 | 0.8 | 10.6667 |  |  | 0 | 10.6667 | 0 | 0 | 10.6667 | RSM
| 12 | Concrete Subbie | m² | S | 1 | 1 | 6 | 32 | 192 |  | 0.5 | 0 | 0 | 0 | 192 | 192 | 73
DS04 | DOH_PV04 | Construct Field Inlet Gully Pit Doherty Street | item |  |  |  | 1 |  | 9050 |  | 1 | 0 | 0 | 0 | 9050 | 9050
| 2 | WDC | Item | S | 1 | 1 | 9050 | 1 | 9050 |  | 0.5 | 0 | 0 | 0 | 9050 | 9050 | 86
DS05 | DOH_PV05 | Kerb extension end of Doherty Street | item |  |  |  | 1 |  | 446 |  | 1 | 0 | 96 | 0 | 350 | 446
| 1 | N32 | m³ | M | 1 | 1 | 0.5 | 192 | 96 |  |  | 0 | 96 | 0 | 0 | 96 | C32
| 2 | Concrete Sub-contract | m³ | S | 1 | 1 | 0.5 | 700 | 350 |  | 1 | 0 | 0 | 0 | 350 | 350 | 71
DS07 | DOH_PVO6 | Doherty Street - Hydromulch 1000m2 | m2 |  |  |  | 1 |  | 2960 |  | 1 | 0 | 0 | 0 | 2960 | 2960
| 2 | Grass Seeding | m2 | S | 1 | 1 | 1000 | 2.45 | 2450 |  | 1 | 0 | 0 | 0 | 2450 | 2450 | 121
| 3 | Turf Subbie | m3 | S | 1 | 1 | 60 | 8.5 | 510 |  | 1 | 0 | 0 | 0 | 510 | 510 | 121
FSXX | FAUST_PV01 | Faust Street drw FSC 04 extra over the BOQ | item |  |  |  | 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
FS00 | FAUST_PV00 | Remove and Replace Unsuitable Subgrade Faust Street | item |  |  |  | 1 |  | 14650.5826 |  | 3 | 1567.4393 | 1499.23 | 11583.9133 | 0 | 14650.5826
FS00.1 |  | Excavation of Subgrade | m³ |  |  |  | 295.4
FS00.2 | 5 | Excavator - 25T | hr | P | 1 | 30 | 295.4 | 135 | 1329.3 | 1.0941 | 1.0941 | 0 | 0 | 1329.3 | 0 | 1329.3 | 57
FS00.3 | 6 | Truck & Dog | hr | P | 2 | 30 | 295.4 | 145 | 2855.5333 | 2.1881 | 1.0941 | 0 | 0 | 2855.5333 | 0 | 2855.5333 | 57
| 7 | Water Cart - Hire | hr | P | 1 | 30 | 295.4 | 100 | 984.6667 | 1.0941 | 1.0941 | 0 | 0 | 984.6667 | 0 | 984.6667 | 57
| 8 | Labour | hr | L | 1 | 30 | 295.4 | 42 | 413.56 | 1.0941 | 1.0941 | 413.56 | 0 | 0 | 0 | 413.56 | 57
FS00.4 |  | Win,load and Import Iron Stone | m³ |  |  |  | 183.6
FS00.5 | 1 | Excavator - 25T | hr | P | 1 | 40 | 183.6 | 135 | 619.65 | 0.51 | 0.51 | 0 | 0 | 619.65 | 0 | 619.65 | 57
FS00.6 | 2 | Truck & Dog | hr | P | 4 | 40 | 183.6 | 145 | 2662.2 | 2.04 | 0.51 | 0 | 0 | 2662.2 | 0 | 2662.2 | 57
| 3 | Water Cart - Hire | hr | P | 1 | 40 | 183.6 | 100 | 459 | 0.51 | 0.51 | 0 | 0 | 459 | 0 | 459 | 57
| 4 | Labour | hr | L | 1 | 40 | 183.6 | 42 | 192.78 | 0.51 | 0.51 | 192.78 | 0 | 0 | 0 | 192.78 | 57
FS00.7 |  | Supply Gabion Rock - Foxdale | tonne |  |  |  | 43.52
| 11 | Gabion Rock | tonne | M | 1 | 1 | 43.52 | 26.5 | 1153.28 |  |  | 0 | 1153.28 | 0 | 0 | 1153.28 | QMR
FS00.8 |  | Supply of geofabric - rockmattress | m² |  |  |  | 125.8
FS00.9 | 1 | A34 | m² | M | 1.1 | 1 | 138.38 | 2.5 | 345.95 |  |  | 0 | 345.95 | 0 | 0 | 345.95 | 222
FS00.10 | 2 | Labour | hr | L | 3 | 570 | 138.38 | 42 | 30.5893 | 0.080924 | 0.026975 | 30.5893 | 0 | 0 | 0 | 30.5893 | 222
| 3 | Bobcat | hr | P | 1 | 570 | 138.38 | 95 | 23.0633 | 0.026975 | 0.026975 | 0 | 0 | 23.0633 | 0 | 23.0633 | 222
FS00.11 |  | Cartage Rock - Foxdale | hr |  |  |  | 3
| 3 | Truck & Dog | hr | P | 1 | 1 | 3 | 145 | 435 | 3 | 3 | 0 | 0 | 435 | 0 | 435 | 221
FS00.12 |  | Replace Unsuitable with select material | m³ |  |  |  | 295.4
FS00.13 | 12 | Grader | hr | P | 1 | 40 | 295.4 | 145 | 1070.825 | 0.82056 | 0.82056 | 0 | 0 | 1070.825 | 0 | 1070.825 | 57
| 13 | SD Roller - Wet (No Op) | hr | P | 1 | 40 | 295.4 | 55 | 406.175 | 0.82056 | 0.82056 | 0 | 0 | 406.175 | 0 | 406.175 | 57
| 14 | Water Cart - Hire | hr | P | 1 | 40 | 295.4 | 100 | 738.5 | 0.82056 | 0.82056 | 0 | 0 | 738.5 | 0 | 738.5 | 57
| 15 | Labour | hr | L | 3 | 40 | 295.4 | 42 | 930.51 | 2.4617 | 0.82056 | 930.51 | 0 | 0 | 0 | 930.51 | 57
FS04 | FAUST_PV04 | Additional Testing Requirements | item |  |  |  | 1 |  | 6310 |  | 0 | 3250 | 0 | 0 | 3060 | 6310
| 2 | Field Density | each | S | 1 | 1 | 24 | 45 | 1080 |  | 1 | 0 | 0 | 0 | 1080 | 1080 | 13
| 3 | Gravel Properties Testing | each | S | 1 | 1 | 3 | 390 | 1170 |  | 1 | 0 | 0 | 0 | 1170 | 1170 | 13
| 4 | Lab Compaction | each | S | 1 | 1 | 3 | 120 | 360 |  | 1 | 0 | 0 | 0 | 360 | 360 | 13
| 5 | Concrete Cylinders | each | S | 1 | 1 | 3 | 150 | 450 |  | 1 | 0 | 0 | 0 | 450 | 450 | 13
| 6 | Project Engineer | each | L | 1 | 1 | 1 | 3250 | 3250 |  | 1 | 3250 | 0 | 0 | 0 | 3250 | 901
FS05 | FAST_PV03 | Blend Iron stone with 1% cement to stockpile | m3 |  |  |  | 45 |  | 739.125 |  | 1 | 47.25 | 0 | 691.875 | 0 | 739.125
FS05.1 | 1 | Excavator - 25T | hr | P | 1 | 40 | 45 | 135 | 151.875 | 0.125 | 0.125 | 0 | 0 | 151.875 | 0 | 151.875 | 57
FS05.2 | 2 | Tipper | hr | P | 4 | 40 | 45 | 95 | 427.5 | 0.5 | 0.125 | 0 | 0 | 427.5 | 0 | 427.5 | 57
| 3 | Water Cart - Hire | hr | P | 1 | 40 | 45 | 100 | 112.5 | 0.125 | 0.125 | 0 | 0 | 112.5 | 0 | 112.5 | 57
| 4 | Labour | hr | L | 1 | 40 | 45 | 42 | 47.25 | 0.125 | 0.125 | 47.25 | 0 | 0 | 0 | 47.25 | 57
FS01 | Faust_Pv01 | Excavation of unsuitable subgrade | m3 |  |  |  | 161 |  | 4757.55 |  | 2 | 732.55 | 0 | 4025 | 0 | 4757.55
|  | Excavate Unsuitable subgrade | m³ |  |  |  | 161
FS01.1 | 5 | Excavator - 25T | hr | P | 1 | 30 | 161 | 135 | 724.5 | 0.5963 | 0.5963 | 0 | 0 | 724.5 | 0 | 724.5 | 57
FS01.2 | 6 | Truck & Dog | hr | P | 2 | 30 | 161 | 145 | 1556.3333 | 1.1926 | 0.5963 | 0 | 0 | 1556.3333 | 0 | 1556.3333 | 57
| 7 | Water Cart - Hire | hr | P | 1 | 30 | 161 | 100 | 536.6667 | 0.5963 | 0.5963 | 0 | 0 | 536.6667 | 0 | 536.6667 | 57
| 8 | Labour | hr | L | 1 | 30 | 161 | 42 | 225.4 | 0.5963 | 0.5963 | 225.4 | 0 | 0 | 0 | 225.4 | 57
|  | Replace Unsuitable with select Material | m³ |  |  |  | 161
FS01.3 | 12 | Grader | hr | P | 1 | 40 | 161 | 145 | 583.625 | 0.44722 | 0.44722 | 0 | 0 | 583.625 | 0 | 583.625 | 57
| 13 | SD Roller - Wet (No Op) | hr | P | 1 | 40 | 161 | 55 | 221.375 | 0.44722 | 0.44722 | 0 | 0 | 221.375 | 0 | 221.375 | 57
| 14 | Water Cart - Hire | hr | P | 1 | 40 | 161 | 100 | 402.5 | 0.44722 | 0.44722 | 0 | 0 | 402.5 | 0 | 402.5 | 57
| 15 | Labour | hr | L | 3 | 40 | 161 | 42 | 507.15 | 1.3417 | 0.44722 | 507.15 | 0 | 0 | 0 | 507.15 | 57
FS01A | Faust_PVO1A | Additional Asphalt for Variation Faust _PV01 | tonne |  |  |  | 15.45 |  | 5117.349 |  | 0 | 0 | 0 | 0 | 5117.349 | 5117.349
| 5 | DG14 - Faust St | tonne | S | 1 | 1 | 15.45 | 331.22 | 5117.349 |  | 1 | 0 | 0 | 0 | 5117.349 | 5117.349 | 65
FS10 | Faust_V10 | Faust Street - Service Crossing | item |  |  |  | 1 |  | 8000 |  | 1 | 0 | 0 | 0 | 8000 | 8000
| 2 | WDC | Item | S | 1 | 1 | 8000 | 1 | 8000 |  | 0.5 | 0 | 0 | 0 | 8000 | 8000 | 103
W01 | Waste_ PV01 | Waste Disposal | item |  |  |  | 124.6 |  | 3115 |  | 0 | 0 | 0 | 0 | 3115 | 3115
| 2 | Tip Fees | Item | S | 1 | 1 | 124.6 | 25 | 3115 |  | 62.3 | 0 | 0 | 0 | 3115 | 3115 | 32

## Resources
| Resource | Description | Type | Unit | Curr | Base Rate
LABOUR RESOURCES | Concretor | Concretor | L | hr | AUD | 50
| Concretor - Labour |  | L | hr | AUD | 85
| Engineer / CQR |  | L | hr | AUD | 135
| Foreman - Hourly |  | L | hr | AUD | 125
| Labour | Labour | L | hr | AUD | 42
| Labour - RATE ONLY |  | L | hr | AUD | 58
| Operator | Plant Operator | L |  | AUD | 48
| PM |  | L | hr | AUD | 145
| Pipe Layer | Pipe Layer | L | hr | AUD | 65
| Pipelayer |  | L | hr | AUD | 75
| Project Engineer | Project Engineer - Weekly Rate | L | week | AUD | 3250
| Project Manager | Weekly Rate - Project Manager | L | week | AUD | 4250
| Project Supervisor | Project Supervisor | L | week | AUD | 3350
| Surveyor | Survey Team | L | hr | AUD | 185
| Technical Officer |  | L | week | AUD | 3250
| Traffic Controller | Traffic Controller with Vehicle | L | hr | AUD | 42
| WHSO | Work Place Health & Safety Officer | L | week | AUD | 3200
MATERIAL RESOURCES | 100 Bend - 11.25 deg |  | M | each | AUD | 58
| 100 Bend - 22.5 deg |  | M | each | AUD | 58
| 100 Bend - 45 deg |  | M | each | AUD | 58
| 100 End Cap |  | M | each | AUD | 39
| 100 Gasket Set |  | M | each | AUD | 18.5
| 100 LD uPVC Electrical |  | M | m | AUD | 4.32
| 100 SV So-So |  | M | each | AUD | 248
| 100 x 100 Tee |  | M | each | AUD | 108.88
| 1050 Manhole per metre | 1050 pre-cast man hole rings (sewer / storm water) | M | m | AUD | 434.16
| 1050 Reducer Slab | 1050 Reducer Slab for 1050 Manhole | M | each | AUD | 218.86
| 1200 RCP FJ CL2 |  | M | m | AUD | 429.14
| 125 LD uPVC Electrical |  | M | m | AUD | 5.34
| 150 Bend - 11.25 deg |  | M | each | AUD | 89
| 150 Bend - 22.5 deg |  | M | each | AUD | 89
| 150 Bend - 45 deg |  | M | each | AUD | 89
| 150 Bend - 90 deg |  | M | each | AUD | 122
| 150 End Cap |  | M | each | AUD | 51
| 150 Gasket Set |  | M | m | AUD | 34
| 150 SN8 Sewer Pipe |  | M | m | AUD | 25
| 150 SV So-So |  | M | each | AUD | 420
| 150 Vari-Gib |  | M | each | AUD | 112
| 150 Water Meter - Helix |  | M | each | AUD | 1449.3
| 150 x 100 Tee |  | M | each | AUD | 257.32
| 150 x 150 Tee |  | M | each | AUD | 318.8
| 20mm Drainage Agg |  | M | ton | AUD | 33.5
| 300 RCP |  | M | m | AUD | 55
| 300 RCP FJ CL3 |  | M | m | AUD | 48.72
| 375 RCP |  | M | m | AUD | 68.6
| 375 RCP FJ CL3 |  | M | m | AUD | 71.92
| 375 Sloping Headwall |  | M | each | AUD | 400
| 40 HD uPVC Electrical |  | M | m | AUD | 1.98
| 40mm Drainage Agg |  | M | ton | AUD | 27.5
| 450 RCP FJ CL2 |  | M | m | AUD | 92.1
| 450 RCP FJ CL4 |  | M | m | AUD | 115.06
| 50 HD uPVC Electrical |  | M | m | AUD | 3
| 50 uPVC Communications |  | M | m | AUD | 2.32
| 525 RCP FJ CL2 |  | M | m | AUD | 105.79
| 63 HD VX Electrical |  | M | m | AUD | 3.85
| 675 RCP FJ CL3 |  | M | m | AUD | 203.21
| 750 HW |  | M | each | AUD | 725
| 750 RCP |  | M | m | AUD | 175
| 80 uPVC Communications |  | M | m | AUD | 4.62
| 900 RCP FJ CL2 |  | M | m | AUD | 259.81
| A24 | A24 - Bidum | M | m² | AUD | 1.05
| A34 |  | M | m² | AUD | 2.5
| A64 | A64 Bidum | M | m² | AUD | 2.49
| Abel Flex |  | M | m | AUD | 3
| Bar Chairs |  | M | each | AUD | 0.8
| Bollard - Plain |  | M | each | AUD | 250
| Bolts |  | M | each | AUD | 7.5
| Bro Pit - 1C1T | Bro Pit 1 Chamber, 1 Trough | M | each | AUD | 1346.26
| Bro Pit - 1C2T | Bro Pit - 1 Chamber, 2 Trough | M | each | AUD | 1709.44
| CBR15 | CBR15 Road Base | M | tonne | AUD | 27.8
| CBR45 | CBR45 Road Base | M | tonne | AUD | 28.3
| CBR80 | CBR80 Road Base - Delivered | M | tonne | AUD | 28.8
| Cast Iron Lid & Surround | Cast Iron Lid (Class D) & Surround for Man Holes | M | each | AUD | 419.97
| Cement | Bulk GP / GB Cement | M | tonne | AUD | 450
| Cement - 2 Tonne Bag | Cement Powder - 2 Tonne Bag | M | tonne | AUD | 240
| Cement - GP Bulk |  | M | tonne | AUD | 293
| Cold Mix AC |  | M | tonne | AUD | 180
| Crusher Dust - Delivered |  | M | tonne | AUD | 21.8
| DN100 uPVC PN18 |  | M | m | AUD | 13.67
| DN100 uPVC SN10 |  | M | m | AUD | 4.35
| DN100 uPVC SN8 |  | M | m | AUD | 9.09
| DN150 uPVC PN16 |  | M | m | AUD | 19.17
| DN150 uPVC PN18 |  | M | m | AUD | 26.67
| DN150 uPVC SN8 |  | M | m | AUD | 9.09
| DN25 PE100 PN12.5 | 50m Roll | M | Item | AUD | 30
| DN32 PE100 PN12.5 | 50m Roll | M | m | AUD | 50
| DN40 PE100 ON12.5 | 50m Roll | M | Item | AUD | 71.74
| DN50 PE100 PN12.5 | 50m Roll | M | Item | AUD | 120.5
| DN63 PE100 PN12.5 | 50m roll | M | Item | AUD | 184.29
| DN63 PE80B SDR11 (Gas) | 110m Roll | M | Item | AUD | 518.45
| DN90 PE100 PN12.5 | 90 PE - 100m roll | M | Item | AUD | 633.14
| Daneley Joints |  | M | each | AUD | 65
| Delineation |  | M | Item | AUD | 12000
| Denso Tape | Denso Tape | M | m | AUD | 5
| Dowels |  | M | each | AUD | 8
| Drainage Agg | Drainage Aggregate | M | tonne | AUD | 37.5
| Draw Rope - Conduits |  | M | m | AUD | 0.11
| Electrical Pit - Precast |  | M | each | AUD | 1800
| Ferrule & Bonnet - 25mm |  | M | each | AUD | 73.97
| Ferrule & Bonnet - 40mm |  | M | each | AUD | 164.31
| Ferrule & Bonnet - 50mm |  | M | each | AUD | 220.46
| Fire Booster Assembly |  | M | each | AUD | 3640.84
| Fire Booster Cabinet |  | M | each | AUD | 1597.57
| Form Boards |  | M | m | AUD | 5
| Form Ply |  | M | m² | AUD | 10
| GCL |  | M | m² | AUD | 7.2
| Gabion Rock | Gabion Rock (150 - 300) | M | tonne | AUD | 26.5
| Gates |  | M | each | AUD | 900
| General Fill | General Fill | M | tonne | AUD | 19
| General Fill (CBR15) | CBR 15 General Fill | M | tonne | AUD | 18
| Grate & Frame |  | M | each | AUD | 500
| Guide Post |  | M | each | AUD | 35
| HW - 1200 x 450 RCBC |  | M | each | AUD | 2342.34
| HW - 2400 x 900 RCBC |  | M | each | AUD | 5347.16
| HW - 3/1200 x 300 RCBC |  | M | each | AUD | 2484.3
| HW - 300 |  | M | each | AUD | 320
| HW - 375 | Head Wall 375 RCP | M | each | AUD | 360
| HW - 375 Sloping |  | M | each | AUD | 625
| HW - 450 |  | M | each | AUD | 313.5
| HW - 450 Sloping |  | M | each | AUD | 645
| HW - 600 x 375 RCBC |  | M | each | AUD | 804.44
| HW - 675 |  | M | each | AUD | 396.31
| HW - 750 x 450 RCBC |  | M | each | AUD | 946.4
| HW 1200 x 600 RCBC |  | M | each | AUD | 2342.34
| Hard Cover - Electrical |  | M | m | AUD | 2.7
| Hazard Board |  | M | each | AUD | 750
| Hose Cock |  | M | each | AUD | 75
| Hydrant Riser |  | M | each | AUD | 230
| Hydrant Riser - 100 Dual |  | M | each | AUD | 614.3
| Hydrant Riser 150 Dual |  | M | each | AUD | 1046.6
| Kerb Adaptors |  | M | each | AUD | 75
| MCC Type A Gully Top |  | M | each | AUD | 1290
| MDPE Junctions |  | M | each | AUD | 391.4
| Marker Post |  | M | each | AUD | 35
| N20 | N20 Concrete | M |  | AUD | 180
| N25 | N25 Concrete | M | m³ | AUD | 170
| N32 | N32 Concrete | M | m³ | AUD | 192
| S32 - No Fines | No Fines Concrete | M | m³ | AUD | 214
| PN10 : 200 DiaPE100 | DN200 - PE100 MDPE Pipe | M | m | AUD | 22.9
| Pickets | Star Pickets | M | each | AUD | 6
| Pre-cast Kerb Unit |  | M | each | AUD | 1484
| Pugmill |  | M | tonne | AUD | 2.5
| RCBC - 1200 x 300 |  | M | m | AUD | 393.36
| RCBC - 1200 x 375 |  | M | each | AUD | 417.6
| RCBC - 1200 x 450 |  | M | m | AUD | 387.5
| RCBC - 1200 x 600 |  | M | m | AUD | 400
| RCBC - 2400 x 900 |  | M | m | AUD | 1176.34
| RCBC - 3600 x 900 | RCBC Crown Unit - 3600 x 900 | M | each | AUD | 1755.6
| RCBC - 600 x 300 |  | M | each | AUD | 273.13
| RCBC - 750 x 450 |  | M | m | AUD | 159.43
| RCBC - 900 x 300 |  | M | each | AUD | 313.2
| RCBC 600 x 375 |  | M | m | AUD | 152.82
| RL1218 |  | M | m² | AUD | 18
| Rag Bolt |  | M | each | AUD | 425
| Rag Bolt - Small |  | M | each | AUD | 300
| Reinforcing Steel |  | M | tonne | AUD | 2200
| S32 - Exposed Aggregate |  | M | m³ | AUD | 260
| S32 - Kerb Mix | S32 - Kerb Mix | M | m³ | AUD | 190
| SL72 | SL72 - Reinforcing Mesh | M | m² | AUD | 9.1
| SL82 | SL82 Reinforcing Mesh | M | m² | AUD | 12.3
| Sand | Bedding Sand | M | tonne | AUD | 24
| Sand Bags |  | M | each | AUD | 1
| Signs - General | General signs & delineation for traffic control. | M | Item | AUD | 3500
| Signs Complete |  | M | each | AUD | 140
| Silt Fence | Silt Fence | M | m | AUD | 2
| Single Check Detector |  | M | each | AUD | 3630.96
| Small Signs |  | M | each | AUD | 350
| Small Tools |  | M | Item | AUD | 1
| Stabilised Sand | Stabilised Sand | M | m³ | AUD | 165
| Sub Soil Drain |  | M | m | AUD | 2.5
| Sub Soil Flush Fittings |  | M | each | AUD | 25
| TX160 - Geogrid |  | M | m² | AUD | 5.03
| Tack Coat |  | M | m² | AUD | 1.5
| Tactiles | MW Roller (Wet No Op)
| Tapping Band - 100 x 25 |  | M | each | AUD | 36.3
| Tapping Band - 100 x 50 |  | M | each | AUD | 57.62
| Tapping Band 100 x 40 |  | M | each | AUD | 57.62
| Topsoil |  | M | m³ | AUD | 35
| Type A Sewer Junction |  | M | each | AUD | 110
| Valve Box & Surround |  | M | each | AUD | 150
| Water Meter Interface |  | M | each | AUD | 378.47
| Wheel Stops | Pre-cast wheel stops | M | each | AUD | 68.83
| DG14 |  | M | tonne | AUD | 299
PLANT RESOURCES | A25 |  | P | hr | AUD | 185
| Back Hoe | Backhoe - Wet Hire | P | hr | AUD | 95
| Backhoe |  | P | hr | AUD | 100
| Bobcat | Bobcat - Wet Hire | P | hr | AUD | 95
| Bobcat - RATE ONLY |  | P | hr | AUD | 115
| Bomag 124DH | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | P | hr | AUD | 26.46
| Bomag 124DH (Stand Down) | Stand Down SD Roller | P | hr | AUD | 10.75
| CAT297 | CAT297C MTL - No Operator | P | hr | AUD | 46.5
| CAT297 Stabiliser | CAT297 Stabiliser - No operator | P | hr | AUD | 66.07
| CAT311 | CAT311D - 12T Excavator (No Operator) | P | hr | AUD | 48
| Container |  | P | week | AUD | 40
| Crane Truck |  | P | day | AUD | 360
| Crib Facilities | Site Office & Tiolet, 1 Pump out during project. | P | week | AUD | 1250
| D6 | D6 Dozer | P | hr | AUD | 185
| Dual Grade Laser |  | P | week | AUD | 277
| Excavator - 15T | 15T Excavator - Wet Hire | P | hr | AUD | 115
| Excavator - 25T | 25T Excavator - Wet Hire | P | hr | AUD | 135
| Excavator - 30T | 30T Excavator - Wet Hire | P | hr | AUD | 135
| Excavator - 8T | 8T Excavator - Wet Hire | P | hr | AUD | 100
| Excavator 25T - RATE ONLY |  | P | hr | AUD | 162.5
| Excavator < 24 RATE ONLY |  | P | hr | AUD | 143.75
| FAE Mixer | FAE Mixer with Tractor | P | day | AUD | 2800
| Float |  | P | LS | AUD | 1
| Ford Utility | Ford Ranger 4WD Utility | P | hr | AUD | 11.67
| Generator |  | P | Item | AUD | 7000
| Grader | Grader - Wet Hire | P | hr | AUD | 145
| Grader - RATE ONLY |  | P | hr | AUD | 168.75
| MW Roller | MW Roller (Wet No Op) | P | hr | AUD | 55
| NH Grader | New Holland Compact Grader - No Operator | P | hr | AUD | 25.78
| PF Roller | Pad Foot Roller - Dry | P | day | AUD | 365
| PF Roller Wet - No OP |  | P | hr | AUD | 58
| Plant Float - Allciv |  | P | hr | AUD | 7
| Plate Compactor | Plate Compactor - Dry Hire | P | hr | AUD | 3.5
| Rock Breaker | Excavator - Wet Hire with Rock Breaker | P | hr | AUD | 85
| SD Roller | SD Roller - Dry | P | day | AUD | 365
| SD Roller - RATE ONLY |  | P | hr | AUD | 95
| SD Roller - Wet (No Op) | SD Roller Wet Hire - No Operator | P | hr | AUD | 55
| Scraper - RATE ONLY |  | P | hr | AUD | 406.25
| Spreader Truck - 30T | Spreader Truck - 30T | P | day | AUD | 1250
| T&D - RATE ONLY |  | P | hr | AUD | 181.25
| Tipper | Tipper (Wet Hire) | P | hr | AUD | 95
| Tipper - Allciv | Tipper - Allciv (No Driver) | P | hr | AUD | 42.79
| Toyota Utility | Toyota Landcruiser 100 Utility | P | hr | AUD | 17
| Trench Roller |  | P | hr | AUD | 15
| Truck & Dog | Truck & Dog - Wet Hire | P | hr | AUD | 145
| Truck - RATE ONLY |  | P | hr | AUD | 106.25
| UD Spreader | UD Spreader Truck - No Driver | P | hr | AUD | 21.61
| UD Spreader - Daily |  | P | day | AUD | 198
| Ute - Hire |  | P | day | AUD | 1
| Variable Message Board | Variable Message Board | P | day | AUD | 100
| WC - Allciv | Water Cart Allciv - No Operator | P | hr | AUD | 42.79
| Water Cart - Hire | Water Cart Hire | P | hr | AUD | 100
| Water Cart - RATE ONLY |  | P | hr | AUD | 118.75
SUBCONTRACT RESOURCES | 10mm Seal | 10mm Spary Seal | S | m² | AUD | 3.19
| 14mm Primerseal | 14mm Primerseal | S | m² | AUD | 4.61
| 7mm Primer Seal | 7mm Primer Seal | S | m² | AUD | 4
| AMC0 Prime |  | S | m² | AUD | 1.5
| Accommodation | Accommodation & 3 meals Rate | S | day | AUD | 125
| CAR | CAR Insurance | S | Item | AUD | 1
| CBR Test |  | S | each | AUD | 400
| CCTV |  | S | Item | AUD | 1
| Concrete Cylinders | Cylinders - Set of Three | S | each | AUD | 150
| Concrete Hole Cutting |  | S | each | AUD | 350
| Concrete Sub-contract | CUM Rate | S | m² | AUD | 700
| Concrete Subbie | Slab on Ground | S | m² | AUD | 32
| Conduit Subbie |  | S | LS | AUD | 1
| Council Fee |  | S | Item | AUD | 1
| DG14 - CCCP |  | S | tonne | AUD | 276
| DG14 - Dobbins Lane |  | S | tonne | AUD | 277
| DG14 - Dodd St |  | S | tonne | AUD | 258
| DG14 - Doherty St |  | S | tonne | AUD | 320
| DG14 - Faust St |  | S | tonne | AUD | 331.22
| DG14 - Jupp St |  | S | tonne | AUD | 318
| DG14 - Sterry St |  | S | tonne | AUD | 251
| Fencing Subbie |  | S | LS | AUD | 1
| Field Density |  | S | each | AUD | 45
| Final Seal |  | S | m² | AUD | 2.91
| Geotech Level One |  | S | hr | AUD | 120
| Grass Seeding |  | S | m² | AUD | 2.45
| Gravel Properties Testing |  | S | each | AUD | 390
| Grinder |  | S | day | AUD | 8500
| HDPE Liner |  | S | Item | AUD | 26553
| Kerb Subbie |  | S | m | AUD | 30
| Kerb Subbie (two) |  | S | m | AUD | 30
| Kerb Subbie - Hand |  | S | m | AUD | 65
| Lab Compaction |  | S | each | AUD | 120
| Manhole Builder (1-2m) |  | S | LS | AUD | 1
| Manhole Builder (2-3m) |  | S | each | AUD | 5500
| PE Welder |  | S | each | AUD | 50
| PL | PL Insurance | S | Item | AUD | 6250
| Pavement Subbie |  | S | Item | AUD | 1
| Pavement Test |  | S | each | AUD | 180
| Pit Builder | Contract Rate per pit | S | each | AUD | 3750
| Pit Builder - Modify | Modify Manholes | S | each | AUD | 1200
| Plumber |  | S | hr | AUD | 85
| Pot Holes R Us |  | S | tonne | AUD | 600
| Pot Plants |  | S | each | AUD | 750
| Power |  | S | Item | AUD | 5000
| Pram Ramps |  | S | each | AUD | 700
| Profiling Subbie |  | S | Item | AUD | 2100
| RCBC Slab Subbie |  | S | m² | AUD | 65
| Retention Costs |  | S | Item | AUD | 1
| SAMI Seal |  | S | m² | AUD | 7.81
| Safety Rails |  | S | m | AUD | 195
| Sand Replacements | Field Density via Sand Replacement Method | S | each | AUD | 145
| Sawcut |  | S | m | AUD | 10
| Seal Visit Eight | Sterry St | S | m² | AUD | 5.92
| Seal Visit Five | Doherty St | S | m² | AUD | 15.64
| Seal Visit Four | Dodd St | S | m² | AUD | 7.19
| Seal Visit One | ANZAC Ave | S | m² | AUD | 51.8
| Seal Visit Seven | Jupp St | S | m² | AUD | 12.77
| Seal Visit Six | Faust St | S | m² | AUD | 11.48
| Seal Visit Three | Cultural Centre Carpark | S | m² | AUD | 7.6
| Seal Visit Two | Dobbins Lane | S | m² | AUD | 8.11
| Security Fence | Security Fence - Three Strand Barb & Crank | S | m | AUD | 66
| Service Locator |  | S | hr | AUD | 135
| Sewer Subbie |  | S | LS | AUD | 1
| Soil Tests |  | S | Item | AUD | 1650
| Steel Fixing |  | S | tonne | AUD | 2200
| Stone Pitching |  | S | m² | AUD | 75
| Sub Soil Clean Out - Inst |  | S | each | AUD | 143
| Survey |  | S | Item | AUD | 1
| Survey - Boundary Pegs |  | S | each | AUD | 45
| TGSI | Tactile Ground Surface Indicators | S | Item | AUD | 40
| Temporary Fencing |  | S | m | AUD | 8
| Tip Fees | Tip fees per ton of waste | S | tonne | AUD | 25
| Traffic Control Crew | 2 x TC's + Ute, Signs & Comms | S | hr | AUD | 102.16
| Traffic Ute |  | S | hr | AUD | 25
| Turf Subbie |  | S | m² | AUD | 8.5
| WDC | Whitsunday Drainage Contractors | S | Item | AUD | 1
| WHS | WHS Insurance / Levy | S | Item | AUD | 1
| Water Subbie |  | S | LS | AUD | 1
| DG10 |  | S | tonne | AUD | 275.7
| Line Marking |  | S | m² | AUD | 1

## Model Inputs
WBS | Description | TYPE | INPUT | UOM
5 | Quality System Documents & Records (for entire Package A) | Q | 1 | Lump
5.1 | Project Engineer | P | 6 | week
6 | Quality Verification & Control | Q | 1 | Lump
6.1 | Field Density Tests (QTY) | P | 12 | each
6.2 | Concrete Cylinders (QTY) | P | 6 | each
6.3 | Survey | P | 600 | Item
7 | Site Establishment & Disestablishment | Q | 1 | Lump
8 | Control of Traffic | Q | 1 | Lump
8.1 | Duration (Weeks) | P | 2 | week
9 | General Earthworks Cut | Q | 60 | m3
9.1 | Excavator - 25T | P | 15 | hr
9.2 | Truck & Dog | P | 2 | hr
9.3 | Labour | P | 1 | hr
10 | Replace unsuitable material below sub grade with select material complete (Provisional) | Q | 10 | m3
10.1 | Excavator - 25T | P | 15 | hr
10.2 | Truck & Dog | P | 2 | hr
10.3 | Excavator - 25T | P | 15 | hr
10.4 | Labour | P | 3 | hr
11 | In-Situ reinforced concrete Base Slab for culverts complete | Q | 4 | m3
12 | 1200 x 600 | Q | 12 | m
12.1 | Labour | P | 3 | hr
12.2 | Bobcat | P | 3 | hr
12.3 | Labour | P | 3 | hr
13 | Cast in situ Concrete Headwalls & Wingwalls & Aprons complete | Q | 3 | m3
14 | Excavation - Inlet, Outlet & Diversion Channels | Q | 60 | m3
14.1 | Excavator - 25T | P | 15 | hr
14.2 | Truck & Dog | P | 2 | hr
15 | Full service, supply agent and mix complete (Provisional if ordered) | Q | 170 | m2
15.1 | CAT297 Stabiliser | P | 18.89 | hr
15.2 | Labour | P | 4 | hr
15.3 | Cement | P | 0.012 | tonne
16 | Place only Type 2.1 (cement modified) | Q | 20 | m3
16.1 | Tonnes Gravel = QTY*density | P | 2.4 | t/m3
16.2 | Truck & Dog | P | 3 | hr
16.25 | Grader | P | 11.11 | hr
16.3 | Grader | P | 100 | hr
16.4 | Labour | P | 3 | hr
17 | Place only Type 2.3 (cement modified) | Q | 20 | m3
17.1 | Tonnes Gravel = QTY*density | P | 2.4 | t/m3
17.2 | Truck & Dog | P | 3 | hr
17.3 | Grader | P | 11.11 | hr
17.4 | Labour | P | 3 | hr
18 | (vii) AMC5 | Q | 200 | m2
18.1 | Seal Visit One | P | 1.05 | m²
19 | Supply & Spray Binder - Bitumen (includes PMB's, Adhesion Agent where required and Preparation of Surface) supply & spread aggregates complete | Q | 200 | m2
19.1 | Seal Visit One | P | 1.05 | m²
20 | Guide Posts complete supply and install | Q | 4 | each
21 | (i) Grass Seeding | Q | 100 | m2
21.1 | Grass Seeding | P | 1.1 | m²
22 | Special Item - As Constructed Survey and Plans | Q | 1 | Lump
23 | Quality Verification & Control | Q | 1 | Lump
23.1 | (15) Field Density Tests | P | 15 | each
23.2 | (6) Concrete Cylinder Sets | P | 6 | each
23.4 | Survey | P | 5800 | Item
25 | Control of Traffic | Q | 1 | Lump
26 | Temporary Erosion & Sedimentation Control (includes supply and installation of all components) | Q | 1 | Lump
26.1 | Labour | P | 3 | hr
27 | General Earthworks Cut | Q | 998 | m3
27.1 | Grader | P | 250 | hr
27.2 | Labour | P | 3 | hr
28 | Replace unsuitable material below sub grade with select material complete (PROVISIONAL) | Q | 10 | m3
28.1 | Excavator - 25T | P | 15 | hr
28.2 | Excavator - 25T | P | 15 | hr
28.3 | Labour | P | 3 | hr
29 | Removal / Demolition of Drainage Components complete | Q | 1 | Lump
29.1 | Excavator - 25T | P | 0.06 | hr
30 | Alteration to Existing Stormwater Structures (New 225 Upvc at Ch 140 | Q | 1 | Lump
31 | 225mm dia uPVC | Q | 16 | m
31.1 | Excavator - 25T | P | 3.2 | hr
31.2 | Labour | P | 3 | hr
32 | (x) Inter-allotment Drainage Pit | Q | 1 | each
33 | Concrete Lining of Open Drains | Q | 5 | m2
33.1 | Excavator - 25T | P | 10 | hr
34 | (i) Concrete Barrier Kerb & Channel B1 complete | Q | 198 | m
34.1 | S32 - Kerb Mix | P | 8.6 | m³
34.2 | Sand | P | 75 | tonne
34.3 | Cement | P | 8 | tonne
35 | (iv) Concrete Dish Drain (0.9m wide) complete | Q | 51 | m
35.1 | N32 | P | 3 | m³
35.2 | Sand | P | 75 | tonne
35.3 | Cement | P | 8 | tonne
36 | (vi) Concrete Kerb (Type B2) complete | Q | 48 | m
36.1 | S32 - Kerb Mix | P | 8.6 | m³
36.2 | Sand | P | 75 | tonne
36.3 | Cement | P | 8 | tonne
37 | (i) 100mm dia Slotted Corrugated Plastic Pipe | Q | 372 | m
37.1 | Excavator - 25T | P | 11.11 | hr
37.2 | Labour | P | 3 | hr
38 | Cleanout Structures | Q | 5 | each
39 | Place only Type 2.3 | Q | 236 | m3
39.1 | Tonnes Gravel = QTY* density | P | 2.4 | t/m3
39.2 | Truck & Dog | P | 3 | hr
39.3 | Grader | P | 44.44 | hr
40 | Place only Type 2.1 | Q | 488 | m3
40.1 | Tonnes Gravel = QTY*density | P | 2.4 | t/m3
40.2 | Grader | P | 150 | hr
41 | Special Item - Geogrid layer | Q | 1953 | m2
41.1 | TX160 - Geogrid | P | 1.1 | m²
41.2 | Labour | P | 570 | hr
42 | Special Item - Geotextile layer | Q | 1953 | m2
42.1 | A24 | P | 1.1 | m²
43 | (vii) AMC5 | Q | 1812 | m2
43.1 | Seal Visit Two | P | 1.05 | m²
44 | (ii) 14mm Nominal Size | Q | 173 | tonne
44.1 | DG14 - Dobbins Lane | P | 1.05 | tonne
45 | (i) 100mm thick concrete footpath | Q | 53 | m2
45.1 | Excavator - 25T | P | 10 | hr
46 | (ii) Concrete Kerb Ramp | Q | 2 | each
47 | (v) Industrial Invert Crossing | Q | 1 | each
47.1 | Excavator - 25T | P | 10 | hr
48 | (ii) Turfing | Q | 150 | m2
48.1 | Turf Subbie | P | 1.05 | m²
49 | Supply and place Imported Topsoil | Q | 15 | m3
49.1 | Bobcat | P | 6 | hr
50 | Special Item - As Constructed Survey and Plans | Q | 1 | Lump
51 | Quality Verification & Control | Q | 1 | Lump
51.1 | (12) Field Density Tests | P | 12 | each
51.2 | (6) Concrete Cylinder Sets | P | 6 | each
51.3 | Survey | P | 2500 | Item
52 | Control of Traffic | Q | 1 | Lump
52.1 | (2) No. Weeks TC Required | P | 2 | week
53 | General Earthworks Cut | Q | 869 | m3
53.1 | Excavator - 25T | P | 40 | hr
53.2 | Truck & Dog | P | 3 | hr
53.3 | Grader | P | 250 | hr
53.4 | Labour | P | 3 | hr
54 | General Earthworks Fill | Q | 4 | m3
54.1 | Excavator - 25T | P | 20 | hr
54.2 | Labour | P | 3 | hr
55 | Replace unsuitable material below sub grade with select material complete (PROVISIONAL) | Q | 10 | m3
55.1 | Excavator - 25T | P | 15 | hr
55.2 | Excavator - 25T | P | 15 | hr
55.3 | Labour | P | 3 | hr
56 | Alteration to Existing Stormwater Structures (Break new PVC pipt into existing line and andage) | Q | 1 | Lump
57 | UPVC pipes (150mm) supply, install, backfill complete | Q | 21 | m
57.1 | Excavator - 25T | P | 4.2 | hr
58 | Connect property drainage pipes | Q | 1 | Lump
58.1 | Plumber | P | 0.5 | hr
59 | Construct Complete in place, downpipe extension and overflow grate | Q | 1 | each
60 | (i) Concrete Barrier Kerb & Channel B1 complete | Q | 80 | m
60.1 | S32 - Kerb Mix | P | 8.6 | m³
60.2 | Sand | P | 75 | tonne
60.3 | Cement | P | 8 | tonne
61 | (iv) Concrete Dish Drain (0.9m wide) complete | Q | 12 | m
61.1 | N32 | P | 3 | m³
61.2 | Sand | P | 75 | tonne
61.3 | Cement | P | 8 | tonne
62 | (vi) Concrete Kerb (Type B2) complete | Q | 81 | m
62.1 | S32 - Kerb Mix | P | 8.6 | m³
62.2 | Sand | P | 75 | tonne
62.3 | Cement | P | 8 | tonne
63 | (i) 100mm dia Slotted Corrugated Plastic Pipe | Q | 312 | m
63.1 | Excavator - 25T | P | 11.11 | hr
64 | Cleanout Structures | Q | 5 | each
65 | Place only Type 2.1 | Q | 314 | m3
65.1 | Tonnes Gravel = QTY*density | P | 2.4 | t/m3
65.2 | Truck & Dog | P | 3 | hr
65.3 | Grader | P | 44.44 | hr
65.4 | Grader | P | 150 | hr
66 | Place only Type 2.3 | Q | 187 | m3
66.1 | Tonnes Gravel = QTY*density | P | 2.4 | t/m3
66.2 | Truck & Dog | P | 3 | hr
66.3 | Grader | P | 44.44 | hr
67 | Special Item - Geogrid layer | Q | 2103 | m2
67.1 | TX160 - Geogrid | P | 1.1 | m²
67.2 | Labour | P | 570 | hr
68 | Special Item - Geotextile layer | Q | 2103 | m2
68.1 | A24 | P | 1.1 | m²
68.2 | Labour | P | 570 | hr
69 | (vii) AMC5 | Q | 2103 | m2
69.1 | Seal Visit Three | P | 1.05 | m²
70 | (ii) 14mm Nominal Size | Q | 202 | tonne
71 | Pavement Marking Paint - Longitudinal Lines including car parking bays | Q | 434 | m
72 | Pavement Marking Paint - Transverse Lines, Symbols, Legends, Arrows, Chevrons, Traffic Islands & Kerbs | Q | 1 | Item
73 | (i) 100mm thick concrete footpath | Q | 180 | m2
73.1 | Excavator - 25T | P | 10 | hr
74 | (ii) Concrete Kerb Ramp | Q | 5 | each
75 | (iv) Residential Invert Crossing | Q | 1 | each
75.1 | Excavator - 25T | P | 1 | hr
76 | (v) Industrial Invert Crossing | Q | 1 | each
76.1 | Excavator - 25T | P | 10 | hr
77 | Special Item - Supply & Install Tactile Marking | Q | 1 | Lump
78 | Special Item - As Constructed Survey and Plans | Q | 1 | Lump
79 | Excavate and backfil all materials for following diameter water mains, approved backfill under roads, testing of backfill compaction, disposal of surplus materials and restoration of surfaces: | Q | 156 | m
80 | 100mm dia. DICL Class PN35 | Q | 156 | m
81 | 100mm dia. | Q | 2 | No.
81.5 | 100mm dia. | Q | 3 | No.
82 | 100mm x 100mm. | Q | 1 | No.
83 | 100mm x 45 degree. | Q | 6 | No.
84 | 100mm | Q | 3 | No.
85 | 100mm | Q | 1 | No.
86 | Single connection with road crossing | Q | 4 | No.
87 | Double connection with road crossing | Q | 2 | No.
88 | Sterilisation of mains including supply of chlorine, water for chlorination and bacteriological sampling and testing. | Q | 1 | Item
89 | Locate existing water main and arrange connection of new water main. (Work by WRC). | Q | 1 | PC It
90 | Special Item - As Constructed Survey and Plans | Q | 1 | Item
91 | Quality Verification & Control | Q | 1 | Lump
91.1 | (12) Field Density Tests | P | 12 | each
91.2 | (6) Concrete Cylinder Sets | P | 6 | each
91.3 | Survey | P | 7300 | Item
92 | Control of Traffic | Q | 1 | Lump
92.1 | (4) No. Weeks TC Required | P | 4 | week
93 | Temporary Erosion & Sedimentation Control (includes supply and installation of all components) | Q | 1 | Lump
93.1 | Labour | P | 3 | hr
94 | Special Item - Demolition of Structure (concrete slabs, culverts, pipes etc) | Q | 1 | Lump
94.1 | Excavator - 25T | P | 0.06 | hr
94.2 | Tipper | P | 3 | hr
95 | General Earthworks Cut | Q | 1430 | m3
95.1 | Excavator - 25T | P | 40 | hr
95.2 | Truck & Dog | P | 3 | hr
95.3 | Grader | P | 250 | hr
96 | Removal / Demolition of Drainage Components complete | Q | 1 | Lump
96.1 | Excavator - 25T | P | 0.11 | hr
97 | Alteration to Existing Stormwater Structures (Break new RCP's into existing RCBC - 4 Nos) | Q | 1 | Lump
98 | 375mm dia Class 2, Flush Joint | Q | 7.32 | m
98.1 | Excavator - 25T | P | 1.46 | hr
99 | 375mm dia Class 3, Flush Joint | Q | 17.08 | m
99.1 | Excavator - 25T | P | 3.42 | hr
100 | Renew Property Drainage connections | Q | 1 | Lump
100.1 | (16) No. of properties | P | 16 | each
101 | MCC Type A Gully Pit | Q | 4 | each
101.1 | Pit Builder | P | 2 | each
102 | (i) Concrete Barrier Kerb & Channel B1 complete | Q | 524 | m
102.1 | S32 - Kerb Mix | P | 8.6 | m³
102.2 | Sand | P | 75 | tonne
102.3 | Cement | P | 8 | tonne
103 | (ii) Concrete Mountable Kerb & Channel M1 complete | Q | 42 | m
103.1 | S32 - Kerb Mix | P | 7.6 | m³
103.2 | Sand | P | 75 | tonne
103.3 | Cement | P | 8 | tonne
104 | (i) 100mm dia Slotted Corrugated Plastic Pipe | Q | 491 | m
104.1 | Excavator - 25T | P | 11.11 | hr
105 | Cleanout Structures | Q | 14 | each
106 | Place only Type 2.3 (cement modified) | Q | 521 | m3
106.1 | Tonnes Gravel = QTY*density | P | 2.4 | t/m3
106.2 | Truck & Dog | P | 3 | hr
106.3 | Grader | P | 44.44 | hr
107 | Place only Type 2.1 | Q | 345 | m3
107.1 | Tonnes Gravel = QTY*density | P | 2.4 | t/m3
107.2 | Truck & Dog | P | 3 | hr
107.3 | Grader | P | 44.44 | hr
107.4 | Grader | P | 150 | hr
108 | Special Item - Geotextile layer | Q | 2797 | m2
108.1 | A24 | P | 1.1 | m²
109 | (vii) AMC5 | Q | 2466 | m2
109.1 | Seal Visit Four | P | 1.05 | m²
110 | (ii) 14mm Nominal Size | Q | 296 | tonne
110.1 | DG14 - Dodd St | P | 1.05 | tonne
111 | Pavement Marking Paint - Transverse Lines, Symbols, Legends, Arrows, Chevrons, Traffic Islands & Kerbs | Q | 2 | Item
112 | Remove and reinstate Existing Signs & Support Structures | Q | 2 | Item
113 | (iv) Residential Invert Crossing | Q | 7 | each
113.1 | Excavator - 25T | P | 7 | hr
114 | Special Item - As Constructed Survey and Plans | Q | 1 | Lump
115 | Quality Verification & Control | Q | 1 | Lump
115.1 | (12) Field Density Tests | P | 12 | each
115.2 | (6) Concrete Cylinder Sets | P | 6 | each
115.3 | Survey | P | 3900 | Item
116 | Control of Traffic | Q | 1 | Lump
116.1 | (4) No. Weeks TC Required - No. = days per week | P | 4 | week
116.2 | Traffic Control Crew | P | 6 | hr
117 | General Earthworks Cut | Q | 652 | m3
117.1 | Grader | P | 250 | hr
117.2 | Labour | P | 3 | hr
118 | General Earthworks Fill (Fill behind kerb to boundary) | Q | 104 | m3
118.1 | Excavator - 25T | P | 20 | hr
118.2 | Labour | P | 3 | hr
119 | Replace unsuitable material below sub grade with select material complete (PROVISIONAL) | Q | 65 | m3
119.1 | Excavator - 25T | P | 15 | hr
119.2 | Truck & Dog | P | 2 | hr
119.3 | Labour | P | 3 | hr
120 | Removal / Demolition of Drainage Components complete | Q | 2 | Lump
120.1 | Excavator - 25T | P | 0.22 | hr
120.2 | Tipper | P | 3 | hr
121 | Relocate existing kerb adapter and roofwater connection from property | Q | 2 | Item
121.1 | Plumber | P | 0.5 | hr
122 | 375mm dia Class 2, Flush Joint | Q | 93 | m
122.1 | Excavator - 25T | P | 4.44 | hr
122.2 | Labour | P | 3 | hr
123 | 450mm dia Class 2, Flush Joint | Q | 9.72 | m
123.1 | Excavator - 25T | P | 1.94 | hr
123.2 | Labour | P | 3 | hr
124 | 450mm dia Class 2, Rubber Ring Joint | Q | 30 | m
124.1 | Excavator - 25T | P | 3.33 | hr
124.2 | Labour | P | 3 | hr
125 | 900 x 450 | Q | 12 | m
125.1 | Excavator - 25T | P | 2 | hr
125.2 | Labour | P | 3 | hr
125.3 | Bobcat | P | 3 | hr
125.4 | Labour | P | 3 | hr
126 | 1200 x 450 | Q | 88 | m
126.1 | Excavator - 25T | P | 2 | hr
126.2 | Labour | P | 3 | hr
126.3 | Bobcat | P | 3 | hr
126.4 | Labour | P | 3 | hr
127 | 1200 x 600 | Q | 10 | m
127.1 | Excavator - 25T | P | 2 | hr
127.2 | Labour | P | 3 | hr
127.3 | Bobcat | P | 3 | hr
127.4 | Labour | P | 3 | hr
128 | Cast in situ Concrete Headwalls & Wingwalls & Aprons complete | Q | 0.63 | m3
129 | BRO Pit Gully Pit | Q | 5 | each
130 | (v) Concrete Manholes - Cast Insitu | Q | 2 | each
131 | (i) Concrete Barrier Kerb & Channel B1 complete | Q | 32 | m
132 | (ii) Concrete Mountable Kerb & Channel M1 complete | Q | 180 | m
133 | (i) 100mm dia Slotted Corrugated Plastic Pipe | Q | 210 | m
133.1 | Excavator - 25T | P | 11.11 | hr
133.2 | Labour | P | 3 | hr
134 | Cleanout Structures | Q | 6 | each
135 | Place only Type 2.3 | Q | 148 | m3
135.1 | QTY*density Tonnes Gravel | P | 2.4 | t/m3
135.2 | Truck & Dog | P | 3 | hr
135.3 | Grader | P | 44.44 | hr
135.4 | Labour | P | 3 | hr
136 | Place only Type 2.1 (828m²) | Q | 96 | m3
136.1 | QTY*density Tonnes Gravel | P | 2.4 | t/m3
136.2 | Truck & Dog | P | 3 | hr
136.3 | Grader | P | 44.44 | hr
136.4 | Grader | P | 150 | hr
136.5 | Labour | P | 3 | hr
137 | Special Item - Geotextile layer | Q | 928 | m2
137.1 | Labour | P | 570 | hr
138 | (vii) AMC5 | Q | 828 | m2
139 | (ii) 14mm Nominal Size | Q | 99.36 | tonne
140 | Remove and reinstate Existing Signs & Support Structures | Q | 2 | Item
141 | Supply & Erection of Boundary Fencing (1200 high chainlink star picket fence) | Q | 11 | m
142 | (iv) Residential Invert Crossing (? m) | Q | 5 | each
142.1 | Excavator - 25T | P | 5 | hr
143 | Service connections | Q | 1 | Lump
144 | Alterations to water main | Q | 1 | Lump
145 | Alterations to valves and hydrant margins | Q | 1 | Lump
146 | Special Item - As Constructed Survey and Plans | Q | 1 | Lump
147 | Quality Verification & Control | Q | 1 | Lump
147.1 | (30) Field Density Tests | P | 30 | each
147.2 | (6) Concrete Cylinder Sets | P | 6 | each
147.3 | Survey | P | 3800 | Item
148 | Control of Traffic | Q | 1 | Lump
148.1 | Traffic Control Crew | P | 6 | hr
149 | Temporary Erosion & Sedimentation Control (includes supply and installation of all components) | Q | 1 | Lump
150 | Clearing and Grubbing (removal of kerb & channel) | Q | 1 | Lump
150.1 | Excavator - 25T | P | 0.06 | hr
150.2 | Tipper | P | 3 | hr
151 | General Earthworks Cut | Q | 543 | m3
151.1 | Excavator - 25T | P | 40 | hr
151.2 | Grader | P | 150 | hr
152 | Replace unsuitable material below sub grade with select material complete (provisional) | Q | 20 | m3
152.1 | Excavator - 25T | P | 15 | hr
152.2 | Excavator - 25T | P | 15 | hr
153 | Removal / Demolition of Drainage Components complete | Q | 1 | Lump
153.1 | Excavator - 25T | P | 0.11 | hr
153.2 | Tipper | P | 3 | hr
154 | Connect property drainage pipes (No. 21) | Q | 1 | Lump
154.1 | Plumber | P | 0.5 | hr
155 | In-Situ reinforced concrete Base Slab for culverts complete | Q | 3 | m3
156 | 1200 x 300 | Q | 12.4 | m
156.1 | Excavator - 25T | P | 2 | hr
156.2 | Labour | P | 3 | hr
156.3 | Bobcat | P | 3 | hr
156.4 | Labour | P | 3 | hr
157 | MCC Type A Gully Pit | Q | 4 | each
158 | (i) Concrete Barrier Kerb & Channel B1 complete | Q | 475 | m
159 | Subsoil Drain Pipe - 100mm dia Slotted Corrugated Plastic Pipe complete (provisional quantity) | Q | 475 | m
159.1 | Excavator - 25T | P | 11.11 | hr
160 | Place only Type 2.3 (includes cart, place, compact & trim) | Q | 304 | m3
160.1 | QTY*2.4 Tonnes Gravel | P | 2.4 | t/m3
160.2 | Truck & Dog | P | 3 | hr
160.3 | Grader | P | 27.78 | hr
161 | Place only Type 2.1 (includes cart, place, compact & trim) | Q | 181 | m3
161.1 | QTY*2.4 Tonnes Gravel | P | 2.4 | t/m3
161.2 | Truck & Dog | P | 3 | hr
161.3 | Grader | P | 27.78 | hr
161.4 | Grader | P | 150 | hr
162 | Special Item - Geogrid layer | Q | 1595 | m2
162.1 | Labour | P | 570 | hr
163 | Special Item - Geotextile layer | Q | 1595 | m2
163.1 | Labour | P | 570 | hr
164 | (vii) AMC5 | Q | 1206 | m2
165 | (i) 10mm Nominal Size | Q | 87 | tonne
166 | Pavement Marking Paint - Longitudinal Lines including car parking bays | Q | 475 | m
167 | Remove and reinstate Existing Signs & Support Structures | Q | 1 | Item
168 | (iv) Residential Invert Crossing | Q | 21 | each
168.1 | Excavator - 25T | P | 21 | hr
169 | (i) Grass Seeding | Q | 500 | m2
170 | (ii) Turfing | Q | 250 | m2
171 | (iii) Individual Planting | Q | 4 | each
172 | Supply and place Imported Topsoil | Q | 50 | m3
172.1 | Bobcat | P | 10 | hr
173 | Sawcut Bituminous pavement | Q | 300 | m
174 | Service connections | Q | 1 | Lump
175 | Special Item - As Constructed Survey and Plans | Q | 1 | Lump
176 | Quality Verification & Control | Q | 1 | Lump
176.1 | (12) Field Density Tests | P | 12 | each
176.2 | (6) Concrete Cylinder Sets | P | 6 | each
176.3 | Survey | P | 4000 | Item
177 | Control of Traffic | Q | 1 | Lump
177.1 | Traffic Control Crew | P | 6 | hr
178 | Temporary Erosion & Sedimentation Control (includes supply and installation of all components) | Q | 1 | Lump
179 | Special Item - Demolition of Structure (concrete slabs, culverts, pipes etc) | Q | 1 | Lump
179.1 | Excavator - 25T | P | 0.06 | hr
179.2 | Tipper | P | 3 | hr
180 | Removal & Stockpiling of Topsoil for reuse (100mm thick nom.) | Q | 155 | m3
180.1 | Excavator - 25T | P | 33.33 | hr
180.2 | Tipper | P | 3 | hr
181 | General Earthworks Cut | Q | 775 | m3
181.1 | Excavator - 25T | P | 40 | hr
181.2 | Truck & Dog | P | 3 | hr
181.3 | Grader | P | 250 | hr
182 | General Earthworks Fill | Q | 27 | m3
182.1 | Excavator - 25T | P | 20 | hr
183 | Replace unsuitable material below sub grade with select material complete (PROVISIONAL) | Q | 20 | m3
183.1 | Excavator - 25T | P | 15 | hr
183.2 | Truck & Dog | P | 2 | hr
183.3 | Excavator - 25T | P | 15 | hr
184 | Removal / Demolition of Drainage Components complete | Q | 1 | Lump
184.1 | Excavator - 25T | P | 0.11 | hr
184.2 | Tipper | P | 3 | hr
185 | Connect property drainage pipes ( 7 No.) | Q | 1 | Lump
186 | In-Situ reinforced concrete Base Slab for culverts complete | Q | 2.6 | m3
187 | 750 x 300 | Q | 13.2 | m
187.1 | Excavator - 25T | P | 2 | hr
187.2 | Labour | P | 3 | hr
187.3 | Bobcat | P | 3 | hr
187.4 | Labour | P | 3 | hr
188 | MCC Type A Gully Pit (including chamber) | Q | 1 | each
189 | (i) Concrete Barrier Kerb & Channel B1 complete | Q | 313 | m
190 | (iv) Concrete Dish Drain (600 wide) complete | Q | 13 | m
191 | Subsoil Drain Pipe - 100mm dia Slotted Corrugated Plastic Pipe complete | Q | 281 | m
191.1 | Excavator - 25T | P | 11.11 | hr
192 | Special Item -Subsoil Drain Pipe - 100mm dia Slotted Corrugated Plastic Pipe encased in no fines concrete complete as shown on drawings | Q | 242 | m
192.1 | Excavator - 25T | P | 11.11 | hr
193 | Cleanout Structures | Q | 13 | each
194 | Place only Type 2.3 (cement modified) | Q | 378 | m3
194.1 | QTY*2.4 Tonnes Gravel | P | 2.4 | t/m3
194.2 | Truck & Dog | P | 3 | hr
194.3 | Grader | P | 44.44 | hr
195 | Place only Type 2.1 (cement modified) | Q | 127 | m3
195.1 | QTY*2.4 Tonnes Gravel | P | 2.4 | t/m3
195.2 | Grader | P | 44.44 | hr
195.3 | Grader | P | 150 | hr
196 | Special Item - Geogrid layer (PROVISIONAL) | Q | 1260 | m2
196.1 | Labour | P | 570 | hr
197 | Special Item -Geotextile layer (PROVISIONAL) | Q | 1260 | m2
197.1 | Labour | P | 570 | hr
198 | (vi) AMC4 | Q | 1057 | m2
199 | (ii) 14mm Nominal Size | Q | 102 | tonne
200 | (iv) Residential Invert Crossing (3.1m to 4.5m) | Q | 11 | each
200.1 | Excavator - 25T | P | 11 | hr
201 | (viii) Hand Placed Concrete Paving (Footpath / Bikeway) | Q | 93 | m2
201.1 | Excavator - 25T | P | 10 | hr
202 | (i) Grass Seeding | Q | 905 | m2
203 | Supply and install mains and reticulation | Q | 1 | Lump
204 | Special Item - As Constructed Survey and Plans | Q | 1 | Lump
205 | Quality Verification & Control | Q | 1 | Lump
205.1 | (24) Field Density Tests | P | 24 | each
205.2 | (6) Concrete Cylinder Sets | P | 6 | each
205.3 | Survey | P | 3950 | Item
206 | Control of Traffic | Q | 1 | Lump
206.1 | Traffic Control Crew | P | 6 | hr
207 | Temporary Erosion & Sedimentation Control (includes supply and installation of all components) | Q | 1 | Lump
208 | Special Item - Demolition of Structure (concrete slabs, culverts, pipes etc) | Q | 1 | Lump
208.1 | Excavator - 25T | P | 0.06 | hr
209 | General Earthworks Cut | Q | 1700 | m3
209.1 | Excavator - 25T | P | 40 | hr
209.2 | Truck & Dog | P | 3 | hr
209.3 | Grader | P | 250 | hr
210 | Removal / Demolition of Drainage Components complete | Q | 1 | Lump
210.1 | Excavator - 25T | P | 0.11 | hr
210.2 | Tipper | P | 3 | hr
211 | Alteration to Existing Stormwater Structures | Q | 1 | Lump
212 | Connect property drainage pipes | Q | 1 | Lump
212.1 | Plumber | P | 0.5 | hr
213 | In-Situ reinforced concrete Base Slab for culverts complete | Q | 7 | m3
214 | 750 x 300 | Q | 35 | m
214.1 | Excavator - 25T | P | 2 | hr
214.2 | Labour | P | 3 | hr
214.3 | Bobcat | P | 3 | hr
214.4 | Labour | P | 3 | hr
215 | MCC Type A Gully Pit | Q | 1 | each
216 | (i) Concrete Barrier Kerb & Channel B1 complete | Q | 140 | m
217 | Subsoil Drain Pipe - 100mm dia Slotted Corrugated Plastic Pipe complete (provisional quantity) | Q | 420 | m
217.1 | Excavator - 25T | P | 11.11 | hr
218 | Cleanout Structures | Q | 12 | each
219 | Place only Type 2.3 | Q | 415 | m3
219.1 | QTY*2.4 Tonnes Gravel | P | 2.4 | t/m3
219.2 | Truck & Dog | P | 3 | hr
219.3 | Grader | P | 44.44 | hr
220 | Place only Type 2.5 (cement modified) | Q | 555 | m3
220.1 | QTY*2.4 Tonnes Gravel | P | 2.4 | t/m3
220.2 | Truck & Dog | P | 3 | hr
220.3 | Grader | P | 44.44 | hr
221 | Place only Type 2.1 | Q | 405 | m3
221.1 | 2.4*density Tonnes Gravel | P | 2.4 | t/m3
221.2 | Truck & Dog | P | 3 | hr
221.3 | Grader | P | 44.44 | hr
221.4 | Grader | P | 150 | hr
222 | Special Item - Geogrid layer | Q | 2765 | m2
222.1 | Labour | P | 570 | hr
223 | Special Item - Geotextile layer | Q | 2765 | m2
223.1 | Labour | P | 570 | hr
224 | (ii) 14mm Nominal Size | Q | 310 | tonne
225 | Pavement Marking Paint - Longitudinal Lines including car parking bays | Q | 405 | m
226 | Pavement Marking Paint - Transverse Lines, Symbols, Legends, Arrows, Chevrons, Traffic Islands & Kerbs | Q | 1 | Item
227 | Remove and reinstate Existing Signs & Support Structures | Q | 1 | Item
228 | Supply & Installation of all Signs (complete) | Q | 1 | each
229 | (ii) Concrete Kerb Ramp (1 No) | Q | 1 | each
230 | (iv) Residential Invert Crossing (10.5 m) | Q | 3 | each
230.1 | Excavator - 25T | P | 3 | hr
231 | (viii) Hand Placed Concrete Paving (Footpath / Bikeway) | Q | 18 | m2
231.1 | Excavator - 25T | P | 10 | hr
232 | (ii) Turfing | Q | 100 | m2
233 | Supply and install mains and reticulation | Q | 1 | Lump
234 | Service connections | Q | 1 | Lump
235 | Special Item - As Constructed Survey and Plans | Q | 1 | Lump
9001 | Project Engineering | Q | 1 | week
9002 | Project Supervision | Q | 1 | week
9003 | Insurances & Fees | Q | 1 | Item
9004 | Site Vehicle | Q | 1 | each
9005 | Site Facilities | Q | 1 | week
9005.1 | Crib Facilities | P | 26 | week
CCC01 | CCC_PV01 - Remove and Replace New kerbiing and traffic Islands | Q | 1 | item
CCC01.1 | CCC_PV01 - Cultrual Centre Carpark - Install Traffic Islands | Q | 40 | m
CCC01.2 | S32 - Kerb Mix | No. | 8.6 | m³
CCC01.3 | Sand | No. | 75 | tonne
CCC01.4 | Cement | No. | 8 | tonne
CCC01.5 | Cutrual Carpark Centre - Demolition of kerb invert and islands | Q | 1 | 0
CCC02 | CCC_PV02 - Cultrual Centre Carpark - Install 600m dish Drain | Q | 44 | m
CCC02.1 | N32 | No. | 3 | m³
CCC02.2 | Sand | No. | 75 | tonne
CCC02.3 | Cement | No. | 8 | tonne
CCC03 | CCC_PV03 Cultrual Centre Carpark Insitu Stabilising Carpark - 400m2 | Q | 400 | m²
CCC04 | Unsuitable Subgrade replacement Iron Stone Rock Mattress | Q | 1 | Item
CCC04.1 | Win, load and Import iron stone gravel | Q | 539.9 | m³
CCC04.2 | Excavator - 25T | P | 40 | hr
CCC04.3 | Truck & Dog | No. | 4 | hr
CCC04.4 | Excavator - 25T | P | 15 | hr
CCC04.5 | Truck & Dog | No. | 2 | hr
CCC04.6 | Labour | P | 570 | hr
CCC04.7 | Grader | P | 40 | hr
DL01 | Construct three residential property access Dobbins Lane | Q | 3 | each
DL01.1 | Excavator - 25T | P | 3 | hr
DL02 | Variation Direction to place an additional layer of Geogrid dobbins lane Ch 190 to Ch 230 - 7.5m wide | Q | 300 | m²
DL02.1 | TX160 - Geogrid | No. | 1.1 | m²
DL02.2 | Labour | P | 570 | hr
DL03 | Remove & Replace Subgrade - Excavate unsutiable material, Blended cement into gravel, import place and compact. | Q | 1 | item
DL03.1 | Excavate Unsuitable Material below subgrade | Q | 500 | m³
DL03.2 | Excavator - 25T | P | 30 | hr
DL03.3 | Truck & Dog | No. | 2 | hr
DL03.4 | Grader | P | 40 | hr
DL03.5 | Cement | P | 0.012 | Item
DL03.6 | CAT297 Stabiliser | P | 55.5556 | Item
DS01 | Variation to water main Doherty street extra over the BOQ | Q | 1 | item
DS02 | Pavement Design | Q | 1 | item
DS02.1 | Excavation of Subgrade | Q | 443.2 | m³
DS02.10 | A34 | No. | 1.1 | m²
DS02.11 | Labour | P | 570 | hr
DS02.2 | Excavator - 25T | P | 30 | hr
DS02.3 | Truck & Dog | No. | 2 | hr
DS02.4 | Win, load and import Iron stone | Q | 378 | m³
DS02.5 | Excavator - 25T | P | 40 | hr
DS02.6 | Truck & Dog | No. | 4 | hr
DS02.7 | Grader | P | 40 | hr
DS02.8 | Cartage Rock - foxdale | Q | 4 | hr
DS03 | Replacement of AC sewer main ch 37 | Q | 1 | item
DS04 | Construct Field Inlet Gully Pit Doherty Street | Q | 1 | item
DS05 | Kerb extension end of Doherty Street | Q | 1 | item
DS06 | Concrete Driveway 3 Doherty Street | Q | 1 | item
DS06.1 | Excavator - 25T | P | 3 | hr
DS07 | Doherty Street - Hydromulch 1000m2 | Q | 1 | m2
DS02.9 | Supply and lay geofabric | Q | 203.4 | m²
DSV01 | Dodd St - Geogrid layer | Q | 2797 | m²
DSV01.1 | TX160 - Geogrid | No. | 1.1 | m²
DSV01.2 | Labour | P | 570 | hr
DSV02 | Dodd Street-PV02 Supply and Install Entry pits, RCBC and Concrete Nib Wall and Nib | Q | 1 | item
DSV02.1 | Excavator - 25T | P | 2 | hr
DSV02.2 | Labour | No. | 3 | hr
DSV02.3 | Bobcat | P | 3 | hr
DSV02.4 | Labour | No. | 3 | hr
DSV02.5 | Install concrete Nib Wall and Nib | Q | 2 | m³
DSV02.6 | Supply and Install 2 MCC Type A Kerb entry pits | Q | 2 | each
DSV03 | Dodd Street water main replacement Install new 100mm Dia DICL Watermains 3 locations | Q | 1 | item
DSV03.1 | Water Main Dodd St /Anzac Road at CH 315 | Q | 1 | item
DSV03.2 | Replace AC Watermain Crossing at Dodd and Phaff Street | Q | 1 | each
DSV04 | Dodd Street_ PV04 - Extend Deep Lift AC at Culvert Crossing Anzac Drive | Q | 3.29 | tonne
DSV05 | Dodd Street_PV05 - New Bropit and RCBC arrangement | Q | 1 | item
DSV06 | Install new Type A MCC side entry pit, 13m of 450 RCP break in to existing drainage line and install a flush point. | Q | 1 | item
DSV06.1 | Excavator - 25T | P | 1.5 | hr
DSV06.2 | Labour | No. | 3 | hr
DSV07 | Installation Pram Ramps Dodd street | Q | 1 | item
DSV07.1 | Hand placed concrete paving | Q | 6.72 | 0
DSV07.2 | Excavator - 25T | P | 10 | hr
DSV07.3 | Demolition of Existing Pram Ramp | Q | 2 | 0
DSV07.4 | Reinstate footpath - 2.1m x 24.1m | Q | 50.61 | m2
DSV07.5 | Excavator - 25T | P | 10 | hr
DSV07.6 | Hand placed kerb - 17m | Q | 17 | m
DSV07.7 | Excavator - 25T | P | 10 | hr
DSV08 | Dodd Street - Water main Protection Lurline Street - works completed formal vairation to be provided Refer to email 2 May sent | Q | 11.6 | m³
DSV09 | Vairation to design levels mismatch to road surface - 44m Lurline Street to match levels to existing road surface. | Q | 1 | hr
FS00 | Remove and Replace Unsuitable Subgrade Faust Street | Q | 1 | item
FS00.1 | Excavation of Subgrade | Q | 295.4 | m³
FS00.10 | Labour | P | 570 | hr
FS00.11 | Cartage Rock - Foxdale | Q | 3 | hr
FS00.12 | Replace Unsuitable with select material | Q | 295.4 | m³
FS00.13 | Grader | P | 40 | hr
FS00.2 | Excavator - 25T | P | 30 | hr
FS00.3 | Truck & Dog | No. | 2 | hr
FS00.4 | Win,load and Import Iron Stone | Q | 183.6 | m³
FS00.5 | Excavator - 25T | P | 40 | hr
FS00.6 | Truck & Dog | No. | 4 | hr
FS00.7 | Supply Gabion Rock - Foxdale | Q | 43.52 | tonne
FS00.8 | Supply of geofabric - rockmattress | Q | 125.8 | m²
FS00.9 | A34 | No. | 1.1 | m²
FS01 | Excavation of unsuitable subgrade | Q | 161 | m3
FS01.1 | Excavator - 25T | P | 30 | hr
FS01.2 | Truck & Dog | No. | 2 | hr
FS01.3 | Grader | P | 40 | hr
FS01A | Additional Asphalt for Variation Faust _PV01 | Q | 15.45 | tonne
FS04 | Additional Testing Requirements | Q | 1 | item
FS05 | Blend Iron stone with 1% cement to stockpile | Q | 45 | m3
FS05.1 | Excavator - 25T | P | 40 | hr
FS05.2 | Tipper | No. | 4 | hr
FS10 | Faust Street - Service Crossing | Q | 1 | item
FSXX | Faust Street drw FSC 04 extra over the BOQ | Q | 1 | item
JSV01 | Jupp Street Geotextile wrapping around no fines concrete | Q | 242 | m
JSV01.1 | Labour | P | 175 | hr
JSV02 | Jupp_PV02 - Boundary Pits & Pipes | Q | 1 | each
JSV03 | Jupp St - Haul & Place Type 2.3 gravel | Q | 40 | m³
JSV03.1 | QTY*2.4 Tonnes Gravel | No. | 2.4 | 0
JSV03.2 | Grader | P | 44.44 | hr
JSV04 | Jupp St_PV03 - Replace AC watermain crossing at Jupp and Anzac Rd | Q | 1 | item
JSV05 | Jupp_PV04 - Extend Kerb & Channel On Anzac Road | Q | 1 | item
JSV06 | Jupp_PV05 - Extend Kerb & Channel on Phaff Street | Q | 1 | item
JSV06.1 | Plumber | P | 0.5 | hr
SS01 | Sterry_PV01 Sterry Street - Chapman Street Works | Q | 1 | item
SS01.1 | Kerb and Channel B1 | Q | 66.4 | m
SS01.2 | Concrete Trench Works | Q | 70 | m³
SS01.3 | Asphalt Works to Chaptman Street | Q | 81 | tonne
SS01.4 | Property Connection and Kerb Adaptor Chaptman street | Q | 2 | each
SS01.5 | Plumber | P | 0.5 | hr
SS01.6 | Install driveways chapman street | Q | 2 | item
SS01.7 | Excavator - 25T | P | 3 | hr
SS01.8 | Line marking - Remark pavement marks - bus parking area | Q | 80 | m
SS01.9 | Primer Seal | Q | 130 | m²
SS02 | Area1 and Area 2 Sterry Street - Rock mattress, 2 layers of Geogrid and, geofabric | Q | 1 | item
SS02.1 | PV02 - Directed on the 27 April 2012 to excavate and remove one layer tensar grid. Ch 50 - Ch 60 LHS | Q | 1 | item
SS02.10 | Truck & Dog | No. | 2 | hr
SS02.11 | Area 1 Replace unsuitable material with select material complete 400mm depth | Q | 940 | m³
SS02.12 | Grader | P | 40 | hr
SS02.13 | Area 1 Supply and install 2 Layer Geogrid tensar TX160 Top layers only | Q | 5372.6 | m²
SS02.14 | TX160 - Geogrid | No. | 1.1 | m²
SS02.15 | Labour | P | 570 | hr
SS02.16 | Area 1 Supply and install Geofabric Top and side of mattress only | Q | 3054 | m²
SS02.17 | A34 | No. | 1.1 | m²
SS02.18 | Labour | P | 570 | hr
SS02.19 | Area1 Supply Gabion Rock BQC | Q | 816.58 | tonne
SS02.2 | PV02 -Direction 4 May 2012 remove top two grids mix amd compact . | Q | 1 | item
SS02.20 | Area 1 Cartage Gabion Rock BQC | Q | 111 | hr
SS02.21 | Area 1 Project Manager | Q | 4 | hr
SS02.22 | Area 1 Project Engineer | Q | 8 | hr
SS02.23 | Area 2 Excavate Unsuitable Material 200mm below subgrade | Q | 83 | m³
SS02.24 | Excavator - 25T | P | 15 | hr
SS02.25 | Truck & Dog | No. | 2 | hr
SS02.26 | Area 2 Replace unsuitable material with select material complete 400mm depth | Q | 116 | m³
SS02.27 | Grader | P | 40 | hr
SS02.28 | Area 2 Supply and install Geofabric Top and side of Mattress only | Q | 455 | m²
SS02.29 | A34 | No. | 1.1 | m²
SS02.3 | Supervisor | Q | 14 | hr
SS02.30 | Labour | P | 570 | hr
SS02.31 | Area 2 Supply Gabion Rock Wall & Sons | Q | 267.46 | tonne
SS02.32 | Area 2 Cartage Rock Wall &Sons | Q | 35 | hr
SS02.33 | Area 1 - Supply Rock Wall and Sons | Q | 698.1 | tonne
SS02.34 | Area 1 Additional water service connections (5) | Q | 5 | item
SS02.35 | Area 2 Project Manager | Q | 2 | hr
SS02.36 | Area 2 Project Engineer | Q | 4 | hr
SS02.37 | Area1 - Cartage Rock Wall & Son | Q | 52 | hr
SS02.4 | Traffic Control - maintenance of signs 1 hr/ day @ 50/hr based on 23 days | Q | 23 | hr
SS02.5 | Area 1 Remove cement modify base - subgrade failure | Q | 155 | m³
SS02.6 | Excavator - 25T | P | 15 | hr
SS02.7 | Truck & Dog | No. | 2 | hr
SS02.8 | Area 1 Excavate unsuitable material 200mm below subgrade | Q | 470 | m³
SS02.9 | Excavator - 25T | P | 15 | hr
SS03 | Vairation direction - Removal and Replacement of 150mm Sewer Main Sterry street | Q | 1 | item
SS04 | Cement stabilisation - Sterry Street 250mm depth | Q | 2765 | m²
SS04.1 | Cement | P | 0.012 | Item
SS04.2 | CAT297 Stabiliser | P | 55.5556 | Item
SS05 | 7 mm Primer Seal Sterry Street | Q | 2765 | m²
SS06 | Additional Chapman Street works - Kerbing and Miscellaneous concrete works Chapman | Q | 5 | m³
SS07 | Construct standard driveway access - Proserpine Secondary School | Q | 1 | each
SS07.1 | Excavator - 25T | P | 21 | hr
SS08 | Various Concrete works and fencing and gate alterations - day labour rates + materials | Q | 1 | item
W01 | Waste Disposal | Q | 124.6 | item

## Non-Work Days
Non-Working Calendar 2011 - 2015 (Queensland - Australia)
| 2011-01-01 |  | 2012-01-01 |  | 2013-01-01 |  | 2014-01-01 |  | 2015-01-01
| 2011-01-08 | 2011-01-09 | 2012-01-14 | 2012-01-15 | 2013-01-19 | 2013-01-20 | 2014-01-18 | 2014-01-19 | 2015-01-17 | 2015-01-18
| 2011-01-01 | 2011-01-02 |  | 2012-01-01 | 2013-01-05 | 2013-01-06 | 2014-01-04 | 2014-01-05 | 2015-01-03 | 2015-01-04
| 2011-01-08 | 2011-01-09 | 2012-01-07 | 2012-01-08 | 2013-01-12 | 2013-01-13 | 2014-01-11 | 2014-01-12 | 2015-01-10 | 2015-01-11
| 2011-01-15 | 2011-01-16 | 2012-01-14 | 2012-01-15 | 2013-01-19 | 2013-01-20 | 2014-01-18 | 2014-01-19 | 2015-01-17 | 2015-01-18
| 2011-01-22 | 2011-01-23 | 2012-01-21 | 2012-01-22 | 2013-01-26 | 2013-01-27 | 2014-01-25 | 2014-01-26 | 2015-01-24 | 2015-01-25
| 2011-01-29 | 2011-01-30 | 2012-01-28 | 2012-01-29 | 2013-02-02 | 2013-02-03 | 2014-02-01 | 2014-02-02 | 2015-01-31 | 2015-02-01
| 2011-02-05 | 2011-02-06 | 2012-02-04 | 2012-02-05 | 2013-02-09 | 2013-02-10 | 2014-02-08 | 2014-02-09 | 2015-02-07 | 2015-02-08
| 2011-02-12 | 2011-02-13 | 2012-02-11 | 2012-02-12 | 2013-02-16 | 2013-02-17 | 2014-02-15 | 2014-02-16 | 2015-02-14 | 2015-02-15
| 2011-02-19 | 2011-02-20 | 2012-02-18 | 2012-02-19 | 2013-02-23 | 2013-02-24 | 2014-02-22 | 2014-02-23 | 2015-02-21 | 2015-02-22
| 2011-02-26 | 2011-02-27 | 2012-02-25 | 2012-02-26 | 2013-03-02 | 2013-03-03 | 2014-03-01 | 2014-03-02 | 2015-02-28 | 2015-03-01
| 2011-03-05 | 2011-03-06 | 2012-03-03 | 2012-03-04 | 2013-03-09 | 2013-03-10 | 2014-03-08 | 2014-03-09 | 2015-03-07 | 2015-03-08
| 2011-03-12 | 2011-03-13 | 2012-03-10 | 2012-03-11 | 2013-03-16 | 2013-03-17 | 2014-03-15 | 2014-03-16 | 2015-03-14 | 2015-03-15
| 2011-03-19 | 2011-03-20 | 2012-03-17 | 2012-03-18 | 2013-03-23 | 2013-03-24 | 2014-03-22 | 2014-03-23 | 2015-03-21 | 2015-03-22
| 2011-03-26 | 2011-03-27 | 2012-03-24 | 2012-03-25 | 2013-03-30 | 2013-03-31 | 2014-03-29 | 2014-03-30 | 2015-03-28 | 2015-03-29
| 2011-04-02 | 2011-04-03 | 2012-03-31 | 2012-04-01 | 2013-04-06 | 2013-04-07 | 2014-04-05 | 2014-04-06 | 2015-04-04 | 2015-04-05
| 2011-04-09 | 2011-04-10 | 2012-04-07 | 2012-04-08 | 2013-04-13 | 2013-04-14 | 2014-04-12 | 2014-04-13 | 2015-04-11 | 2015-04-12
| 2011-04-16 | 2011-04-17 | 2012-04-14 | 2012-04-15 | 2013-04-20 | 2013-04-21 | 2014-04-19 | 2014-04-20 | 2015-04-18 | 2015-04-19
| 2011-04-23 | 2011-04-24 | 2012-04-21 | 2012-04-22 | 2013-04-27 | 2013-04-28 | 2014-04-26 | 2014-04-27 | 2015-04-25 | 2015-04-26
| 2011-04-30 | 2011-05-01 | 2012-04-28 | 2012-04-29 | 2013-05-04 | 2013-05-05 | 2014-05-03 | 2014-05-04 | 2015-05-02 | 2015-05-03
| 2011-05-07 | 2011-05-08 | 2012-05-05 | 2012-05-06 | 2013-05-11 | 2013-05-12 | 2014-05-10 | 2014-05-11 | 2015-05-09 | 2015-05-10
| 2011-05-14 | 2011-05-15 | 2012-05-12 | 2012-05-13 | 2013-05-18 | 2013-05-19 | 2014-05-17 | 2014-05-18 | 2015-05-16 | 2015-05-17
| 2011-05-21 | 2011-05-22 | 2012-05-19 | 2012-05-20 | 2013-05-25 | 2013-05-26 | 2014-05-24 | 2014-05-25 | 2015-05-23 | 2015-05-24
| 2011-05-28 | 2011-05-29 | 2012-05-26 | 2012-05-27 | 2013-06-01 | 2013-06-02 | 2014-05-31 | 2014-06-01 | 2015-05-30 | 2015-05-31
| 2011-06-04 | 2011-06-05 | 2012-06-02 | 2012-06-03 | 2013-06-08 | 2013-06-09 | 2014-06-07 | 2014-06-08 | 2015-06-06 | 2015-06-07
| 2011-06-11 | 2011-06-12 | 2012-06-09 | 2012-06-10 | 2013-06-15 | 2013-06-16 | 2014-06-14 | 2014-06-15 | 2015-06-13 | 2015-06-14
| 2011-06-18 | 2011-06-19 | 2012-06-16 | 2012-06-17 | 2013-06-22 | 2013-06-23 | 2014-06-21 | 2014-06-22 | 2015-06-20 | 2015-06-21
| 2011-06-25 | 2011-06-26 | 2012-06-23 | 2012-06-24 | 2013-06-29 | 2013-06-30 | 2014-06-28 | 2014-06-29 | 2015-06-27 | 2015-06-28
| 2011-07-02 | 2011-07-03 | 2012-06-30 | 2012-07-01 | 2013-07-06 | 2013-07-07 | 2014-07-05 | 2014-07-06 | 2015-07-04 | 2015-07-05
| 2011-07-09 | 2011-07-10 | 2012-07-07 | 2012-07-08 | 2013-07-13 | 2013-07-14 | 2014-07-12 | 2014-07-13 | 2015-07-11 | 2015-07-12
| 2011-07-16 | 2011-07-17 | 2012-07-14 | 2012-07-15 | 2013-07-20 | 2013-07-21 | 2014-07-19 | 2014-07-20 | 2015-07-18 | 2015-07-19
| 2011-07-23 | 2011-07-24 | 2012-07-21 | 2012-07-22 | 2013-07-27 | 2013-07-28 | 2014-07-26 | 2014-07-27 | 2015-07-25 | 2015-07-26
| 2011-07-30 | 2011-07-31 | 2012-07-28 | 2012-07-29 | 2013-08-03 | 2013-08-04 | 2014-08-02 | 2014-08-03 | 2015-08-01 | 2015-08-02
| 2011-08-06 | 2011-08-07 | 2012-08-04 | 2012-08-05 | 2013-08-10 | 2013-08-11 | 2014-08-09 | 2014-08-10 | 2015-08-08 | 2015-08-09
| 2011-08-13 | 2011-08-14 | 2012-08-11 | 2012-08-12 | 2013-08-17 | 2013-08-18 | 2014-08-16 | 2014-08-17 | 2015-08-15 | 2015-08-16
| 2011-08-20 | 2011-08-21 | 2012-08-18 | 2012-08-19 | 2013-08-24 | 2013-08-25 | 2014-08-23 | 2014-08-24 | 2015-08-22 | 2015-08-23
| 2011-08-27 | 2011-08-28 | 2012-08-25 | 2012-08-26 | 2013-08-31 | 2013-09-01 | 2014-08-30 | 2014-08-31 | 2015-08-29 | 2015-08-30
| 2011-09-03 | 2011-09-04 | 2012-09-01 | 2012-09-02 | 2013-09-07 | 2013-09-08 | 2014-09-06 | 2014-09-07 | 2015-09-05 | 2015-09-06
| 2011-09-10 | 2011-09-11 | 2012-09-08 | 2012-09-09 | 2013-09-14 | 2013-09-15 | 2014-09-13 | 2014-09-14 | 2015-09-12 | 2015-09-13
| 2011-09-17 | 2011-09-18 | 2012-09-15 | 2012-09-16 | 2013-09-21 | 2013-09-22 | 2014-09-20 | 2014-09-21 | 2015-09-19 | 2015-09-20
| 2011-09-24 | 2011-09-25 | 2012-09-22 | 2012-09-23 | 2013-09-28 | 2013-09-29 | 2014-09-27 | 2014-09-28 | 2015-09-26 | 2015-09-27
| 2011-10-01 | 2011-10-02 | 2012-09-29 | 2012-09-30 | 2013-10-05 | 2013-10-06 | 2014-10-04 | 2014-10-05 | 2015-10-03 | 2015-10-04
| 2011-10-08 | 2011-10-09 | 2012-10-06 | 2012-10-07 | 2013-10-12 | 2013-10-13 | 2014-10-11 | 2014-10-12 | 2015-10-10 | 2015-10-11
| 2011-10-15 | 2011-10-16 | 2012-10-13 | 2012-10-14 | 2013-10-19 | 2013-10-20 | 2014-10-18 | 2014-10-19 | 2015-10-17 | 2015-10-18
| 2011-10-22 | 2011-10-23 | 2012-10-20 | 2012-10-21 | 2013-10-26 | 2013-10-27 | 2014-10-25 | 2014-10-26 | 2015-10-24 | 2015-10-25
| 2011-10-29 | 2011-10-30 | 2012-10-27 | 2012-10-28 | 2013-11-02 | 2013-11-03 | 2014-11-01 | 2014-11-02 | 2015-10-31 | 2015-11-01
| 2011-11-05 | 2011-11-06 | 2012-11-03 | 2012-11-04 | 2013-11-09 | 2013-11-10 | 2014-11-08 | 2014-11-09 | 2015-11-07 | 2015-11-08
| 2011-11-12 | 2011-11-13 | 2012-11-10 | 2012-11-11 | 2013-11-16 | 2013-11-17 | 2014-11-15 | 2014-11-16 | 2015-11-14 | 2015-11-15
| 2011-11-19 | 2011-11-20 | 2012-11-17 | 2012-11-18 | 2013-11-23 | 2013-11-24 | 2014-11-22 | 2014-11-23 | 2015-11-21 | 2015-11-22
| 2011-11-26 | 2011-11-27 | 2012-11-24 | 2012-11-25 | 2013-11-30 | 2013-12-01 | 2014-11-29 | 2014-11-30 | 2015-11-28 | 2015-11-29
| 2011-12-03 | 2011-12-04 | 2012-12-01 | 2012-12-02 | 2013-12-07 | 2013-12-08 | 2014-12-06 | 2014-12-07 | 2015-12-05 | 2015-12-06
| 2011-12-10 | 2011-12-11 | 2012-12-08 | 2012-12-09 | 2013-12-14 | 2013-12-15 | 2014-12-13 | 2014-12-14 | 2015-12-12 | 2015-12-13
| 2011-12-17 | 2011-12-18 | 2012-12-15 | 2012-12-16 | 2013-12-21 | 2013-12-22 | 2014-12-20 | 2014-12-21 | 2015-12-19 | 2015-12-20
| 2011-12-24 | 2011-12-25 | 2012-12-22 | 2012-12-23 | 2013-12-28 | 2013-12-29 | 2014-12-27 | 2014-12-28 | 2015-12-26 | 2015-12-27
| 2011-12-31 |  | 2012-12-29 | 2012-12-30
Christmas Day | 2011-12-25 | 2011-12-23 | 2012-12-25 | 2012-01-02 | 2013-12-25 | 2013-01-02 | 2014-12-25 | 2014-01-02 | 2015-12-25 | 2015-01-02
Boxing Day | 2011-12-27 | 2011-12-24 | 2012-12-26 | 2012-01-03 | 2013-12-26 | 2013-01-03 | 2014-12-26 | 2014-01-03 | 2015-12-26 | 2015-01-05
New Years Day | 2011-01-01 | 2011-12-28 | 2012-01-01 | 2012-01-04 | 2013-01-01 | 2013-01-04 | 2014-01-01 | 2014-12-22 | 2015-01-01 | 2015-01-06
Australia Day | 2011-01-26 | 2011-12-29 | Australia Day | 2012-01-05 | 2013-01-28 | 2013-12-23 | 2014-01-27 | 2014-12-23 | 2015-01-26 | 2015-01-07
Good Friday | 2011-04-22 | 2011-12-30 | 2012-04-06 | 2012-01-06 | 2013-03-29 | 2013-12-24 | 2014-04-18 | 2014-12-24 | 2015-04-03 | 2015-01-08
Easter Monday | 2011-04-25 |  | 2012-04-09 | 2012-12-24 | 2013-04-01 | 2013-12-27 | 2014-04-21 | 2014-12-29 | 2015-04-06 | 2015-01-09
ANZAC Day | 2011-04-26 |  | 2012-04-25 | 2012-12-27 | 2013-04-25 | 2013-12-30 | 2014-04-25 | 2014-12-30 | 2015-04-27 | 2015-12-24
Labour Day | 2011-05-02 |  | 2012-05-07 | 2012-12-28 | 2013-06-10 | 2013-12-31 | 2014-10-06 | 2014-12-31 | 2015-10-05 | 2015-12-27
Queen's Birthday | 2011-06-13 |  | 2012-06-11 | 2012-12-31 | 2013-10-07 |  | 2014-06-09 |  | 2015-06-08 | 2015-12-28
2015-12-29
2015-12-30
2015-12-31
|  | Xmas S/D | 2012-12-28: Xmas S/D; 2013-12-31: Xmas S/D; 2014-12-31: Xmas S/D; 2015-12-27: Xmas S/D
Work Hours Per Day |  | 9
Start Date |  | 2011-10-17
Note on C71: Brett Thiele: This allows the durations of each task to be turned into days, Durations in hours are rounded up to the nearest full day based on this number.

## Program Links
WBS | TASK | DURATION | Predecessors | Successors | Budget | %C - Oct 11 | %C - Nov 11 | %C - Dec-11 | %C - Jan 12 | %C Feb 12 | %C Mar 12 | %C Apr 12 | %C May 12 | %C Jun 12 | %C Jul 12 | %C Aug 12 | %C Sep 12 | %C Oct 12 | %C Nov 12
1 | Contract Award | 1 |  | 4,23,51,80,93,118,151,181,211
2 | Practical Completion | 1 | 22,50,79,92,117,150,180,210,4,23,51,80,93,118,151,181,211,242,291FF
1000 | ANZAC STREET | 0 | 2 | 3,23,181,51,5
5 | Quality System Documents & Records (for entire Package A) | 0 | 4 | 6 | 39000 | 4% | 8% | 9% | 14% | 50% | 55% | 60% | 65% | 80% | 90% | 100% | 100% | 100% | 100%
6 | Quality Verification & Control | 0 | 5 | 7 | 6460 | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7 | Site Establishment & Disestablishment | 6 | 6 | 8,11,14 | 22050 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
8 | Control of Traffic | 10 | 7 | 9 | 11646.24 | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9 | General Earthworks Cut | 1 | 8 | 10 | 2268 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | Replace unsuitable material below sub grade with select material complete (Provisional) | 1 | 9 | 15 | 655.3333 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
11 | In-Situ reinforced concrete Base Slab for culverts complete | 2 | 7,14 | 12 | 2604.1778 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
12 | 1200 x 600 | 2 | 11 | 13 | 7902.5 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
13 | Cast in situ Concrete Headwalls & Wingwalls & Aprons complete | 2 | 12 | 22 | 2733.6 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
14 | Excavation - Inlet, Outlet & Diversion Channels | 1 | 7 | 11 | 2268 | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
15 | Full service, supply agent and mix complete (Provisional if ordered) | 1 | 10 | 17 | 5918.8258 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
16 | Place only Type 2.1 (cement modified) | 1 | 17 | 18FS+3 days,20,181 | 3798.8716 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
17 | Place only Type 2.3 (cement modified) | 1 | 15 | 16,23 | 2836.8716 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
18 | (vii) AMC5 | 1 | 16FS+3 days | 19FS+5 days,22 | 10878 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
19 | Supply & Spray Binder - Bitumen (includes PMB's, Adhesion Agent where required and Preparation of Surface) supply & spread aggregates complete | 1 | 18FS+5 days | 22 | 10878 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
20 | Guide Posts complete supply and install | 1 | 16 | 21 | 140 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
21 | (i) Grass Seeding | 0 | 20 | 22 | 269.5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.05% | 11.05% | 11.05% | 100% | 100% | 11.05% | 11.05%
22 | Special Item - As Constructed Survey and Plans | 1 | 13,18,19,21 | 3 | 800 | 0% | 0% | 0% | 0% | 0% | 0% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2000 | DOBBINS LANE | 0 | 2,4,17,80 | 3,24 | 0
23 | Quality Verification & Control | 0 | 23 | 25 | 11795 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 50% | 80% | 100% | 100% | 100% | 100%
25 | Control of Traffic | 30 | 24 | 26SS,44 | 34938.72 | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 40% | 60% | 80% | 100% | 100% | 100% | 100%
26 | Temporary Erosion & Sedimentation Control (includes supply and installation of all components) | 6 | 25SS | 27,29 | 11050 | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 40% | 60% | 80% | 100% | 100% | 100% | 100%
27 | General Earthworks Cut | 4 | 26 | 28,33 | 20828.5297 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20.04% | 100% | 100% | 100% | 100% | 100% | 100%
28 | Replace unsuitable material below sub grade with select material complete (PROVISIONAL) | 1 | 27 | 37,41,250 | 655.3333 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 0% | 0%
29 | Removal / Demolition of Drainage Components complete | 2 | 26 | 30 | 10066.6667 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 90% | 100% | 100% | 100% | 100% | 100%
30 | Alteration to Existing Stormwater Structures (New 225 Upvc at Ch 140 | 1 | 29 | 31 | 1200 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
31 | 225mm dia uPVC | 1 | 30 | 32 | 2313 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
32 | (x) Inter-allotment Drainage Pit | 3 | 31 |  | 3750 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100%
33 | Concrete Lining of Open Drains | 2 | 27 |  | 356.1444 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
34 | (i) Concrete Barrier Kerb & Channel B1 complete | 1 | 36 | 35 | 10526.2786 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90% | 100% | 100% | 100% | 100% | 100%
35 | (iv) Concrete Dish Drain (0.9m wide) complete | 1 | 34 | 40 | 6633.57 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 58.82% | 100% | 100% | 100% | 100%
36 | (vi) Concrete Kerb (Type B2) complete | 1 | 39 | 34 | 2551.826 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
37 | (i) 100mm dia Slotted Corrugated Plastic Pipe | 4 | 28250 | 38FF,39,41 | 15356.9917 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 26.88% | 100% | 100% | 100% | 100% | 100% | 100%
38 | Cleanout Structures | 4 | 37FF |  | 715 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100%
39 | Place only Type 2.3 | 2 | 37,42 | 36 | 13363.0414 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 17.37% | 100% | 100% | 100% | 100% | 100% | 100%
40 | Place only Type 2.1 | 7 | 35 | 43FS+3 days,51 | 33426.4325 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 74.96% | 100% | 100% | 100% | 100%
41 | Special Item - Geogrid layer | 1 | 28,37 | 42FF,249 | 11638.8864 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.985% | 100% | 100% | 100% | 100% | 100% | 100%
42 | Special Item - Geotextile layer | 1 | 41FF | 39 | 3088.6524 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.985% | 100% | 100% | 100% | 100% | 100% | 100%
43 | (vii) AMC5 | 1 | 40FS+3 days | 44FS+14 days,45 | 15430.086 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
44 | (ii) 14mm Nominal Size | 1 | 25,43FS+14 days | 50 | 50317.05 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
45 | (i) 100mm thick concrete footpath | 3 | 43 | 46 | 3775.1311 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
46 | (ii) Concrete Kerb Ramp | 1 | 45 | 47 | 1570 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
47 | (v) Industrial Invert Crossing | 2 | 46 | 49248 | 1534.57 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
48 | (ii) Turfing | 1 | 49 | 50 | 1338.75 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
49 | Supply and place Imported Topsoil | 1 | 47248 | 48 | 972.5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
50 | Special Item - As Constructed Survey and Plans | 4 | 44,48 | 3 | 4500 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 60% | 60% | 100% | 100% | 100%
300 | CULTURAL CENTRE CAR PARK | 0 | 2,4,40 | 3,52 | 0
51 | Quality Verification & Control | 0 | 51 | 53 | 8360 | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 50% | 85% | 95% | 100% | 100% | 100% | 100%
52 | Control of Traffic | 10 | 52 | 54SS | 11646.24 | 0% | 0% | 0% | 0% | 0% | 20% | 20% | 50% | 85% | 95% | 100% | 100% | 100% | 100%
53 | General Earthworks Cut | 4 | 53SS | 55 | 19053.614 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
54 | General Earthworks Fill | 1 | 54 | 56 | 112.2 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
55 | Replace unsuitable material below sub grade with select material complete (PROVISIONAL) | 1 | 55 | 57,64,247 | 655.3333 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 0% | 0%
56 | Alteration to Existing Stormwater Structures (Break new PVC pipt into existing line and andage) | 1 | 56 | 58 | 1200 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
57 | UPVC pipes (150mm) supply, install, backfill complete | 1 | 57 | 59 | 2628 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
58 | Connect property drainage pipes | 3 | 58 | 60 | 3950 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
59 | Construct Complete in place, downpipe extension and overflow grate | 2 | 59 | 63 | 2400 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
60 | (i) Concrete Barrier Kerb & Channel B1 complete | 1 | 63246 | 62 | 4253.0419 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
61 | (iv) Concrete Dish Drain (0.9m wide) complete | 1 | 61 | 66 | 1560.84 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
62 | (vi) Concrete Kerb (Type B2) complete | 1 | 60,67 | 61244 | 4306.2049 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
63 | (i) 100mm dia Slotted Corrugated Plastic Pipe | 4 | 56 | 65FF,68 | 12880.0576 | 0% | 0% | 0% | 0% | 0% | 94.87% | 94.87% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
64 | Cleanout Structures | 4 | 64FF |  | 715 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
65 | Place only Type 2.1 | 6 | 62,67,245 | 70FS+3 days | 24537.3132 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
66 | Place only Type 2.3 | 2 | 69 | 63,66 | 10588.5116 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
67 | Special Item - Geogrid layer | 1 | 64246 | 69FF | 12532.8101 | 0% | 0% | 0% | 0% | 0% | 49.98% | 49.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
68 | Special Item - Geotextile layer | 1 | 68FF | 67 | 3325.8761 | 0% | 0% | 0% | 0% | 0% | 49.98% | 49.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
69 | (vii) AMC5 | 1 | 66FS+3 days | 71FS+14 days,74 | 16781.94 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
70 | (ii) 14mm Nominal Size | 1 | 70FS+14 days | 72FS+7 days | 58539.6 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
71 | Pavement Marking Paint - Longitudinal Lines including car parking bays | 1 | 71FS+7 days | 73 | 5000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
72 | Pavement Marking Paint - Transverse Lines, Symbols, Legends, Arrows, Chevrons, Traffic Islands & Kerbs | 1 | 72 | 79 | 1500 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
73 | (i) 100mm thick concrete footpath | 5 | 70 | 75 | 12821.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
74 | (ii) Concrete Kerb Ramp | 3 | 74 | 76,78FS+3 days | 3925 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
75 | (iv) Residential Invert Crossing | 2 | 75 | 77 | 620.4533 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
76 | (v) Industrial Invert Crossing | 2 | 76 | 79 | 1534.57 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
77 | Special Item - Supply & Install Tactile Marking | 1 | 75FS+3 days | 79 | 5000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
78 | Special Item - As Constructed Survey and Plans | 3 | 73,77,78 | 3 | 2500 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100%
400 | DOBBINS LANE WATER MAIN | 0 | 2 | 23,3,81 | 0
79 | Excavate and backfil all materials for following diameter water mains, approved backfill under roads, testing of backfill compaction, disposal of surplus materials and restoration of surfaces: | 2 | 80 | 82FF | 7020 | 0% | 0% | 0% | 0% | 0% | 0% | 64.1% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
80 | 100mm dia. DICL Class PN35 | 2 | 81FF | 83FF,88 | 39000 | 0% | 0% | 0% | 0% | 0% | 0% | 64.1% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
81 | 100mm dia. | 1 | 82FF | 84FF | 4000 | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
82 | 100mm x 100mm. | 1 | 83FF | 85FF | 220 | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
83 | 100mm x 45 degree. | 3 | 84FF | 86FF | 960 | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
84 | 100mm | 2 | 85FF | 87FF | 800 | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
85 | 100mm | 1 | 86FF |  | 250 | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
86 | Single connection with road crossing | 4 | 82 | 89 | 8400 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
87 | Double connection with road crossing | 2 | 88 | 91,90 | 4320 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
88 | Sterilisation of mains including supply of chlorine, water for chlorination and bacteriological sampling and testing. | 3 | 89 | 91 | 2000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
89 | Locate existing water main and arrange connection of new water main. (Work by WRC). | 1 | 89,90 | 92 | 5400 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
90 | Special Item - As Constructed Survey and Plans | 4 | 91 | 3 | 4000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 90% | 95% | 100% | 100% | 100% | 100%
500 | DODD STREET | 0 | 2181201 | 3,211,118,94 | 0
91 | Quality Verification & Control | 0 | 93 | 95266 | 13160 | 0% | 0% | 0% | 25% | 35% | 75% | 85% | 95% | 100% | 100% | 100% | 100% | 100% | 100%
92 | Control of Traffic | 20 | 94 | 96SS,115SS,117 | 23292.48 | 0% | 0% | 0% | 25% | 35% | 75% | 85% | 95% | 100% | 100% | 100% | 100% | 100% | 100%
93 | Temporary Erosion & Sedimentation Control (includes supply and installation of all components) | 6 | 95SS | 97,98,260 | 11050 | 0% | 0% | 0% | 25% | 35% | 75% | 85% | 95% | 100% | 100% | 100% | 100% | 100% | 100%
94 | Special Item - Demolition of Structure (concrete slabs, culverts, pipes etc) | 2 | 96 | 99 | 10066.6667 | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
95 | General Earthworks Cut | 6 | 96 | 107 | 29655.2414 | 0% | 0% | 0% | 33.08% | 75.03% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
96 | Removal / Demolition of Drainage Components complete | 2 | 97 | 100 | 5490.9091 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
97 | Alteration to Existing Stormwater Structures (Break new RCP's into existing RCBC - 4 Nos) | 8 | 99 | 101 | 9600 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
98 | 375mm dia Class 2, Flush Joint | 1 | 100 | 102 | 1893.5897 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
99 | 375mm dia Class 3, Flush Joint | 1 | 101 | 103 | 2668.5073 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
100 | Renew Property Drainage connections | 4 | 102 | 104 | 6320 | 0% | 0% | 0% | 0% | 0% | 82% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
101 | MCC Type A Gully Pit | 10 | 103 | 106259262 | 14020 | 0% | 0% | 0% | 100% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
102 | (i) Concrete Barrier Kerb & Channel B1 complete | 3 | 106 | 110 | 27857.4242 | 0% | 0% | 0% | 0% | 47.71% | 47.71% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
103 | (ii) Concrete Mountable Kerb & Channel M1 complete | 1 | 104109259263 | 105 | 2354.94 | 0% | 0% | 0% | 0% | 32.31% | 32.31% | 32.31% | 32.31% | 32.31% | 32.31% | 32.31% | 32.31% | 32.31% | 32.31%
104 | (i) 100mm dia Slotted Corrugated Plastic Pipe | 5 | 98 | 108FF,111 | 20269.5778 | 0% | 0% | 0% | 0% | 91.65% | 91.65% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
105 | Cleanout Structures | 5 | 107FF |  | 2002 | 0% | 0% | 0% | 0% | 0% | 85.71% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
106 | Place only Type 2.3 (cement modified) | 4 | 111258 | 106 | 29500.6126 | 0% | 0% | 0% | 32.63% | 42.99% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
107 | Place only Type 2.1 | 7 | 105 | 112FS+3 days,116FF,211,118 | 27437.0975 | 0% | 0% | 0% | 0% | 13.91% | 85.51% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
108 | Special Item - Geotextile layer | 1 | 107260265 | 109258 | 4423.431 | 0% | 0% | 0% | 31.46% | 84.98% | 94.99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
109 | (vii) AMC5 | 1 | 110FS+3 days,116,264 | 113FS+14 days | 18617.067 | 0% | 0% | 0% | 0% | 0% | 81.1% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
110 | (ii) 14mm Nominal Size | 2 | 112FS+14 days | 114FS+7 days,261 | 80186.4 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
111 | Pavement Marking Paint - Transverse Lines, Symbols, Legends, Arrows, Chevrons, Traffic Islands & Kerbs | 1 | 113FS+7 days | 117 | 2000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
112 | Remove and reinstate Existing Signs & Support Structures | 1 | 95SS | 117 | 472 | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
113 | (iv) Residential Invert Crossing | 4 | 110FF | 112264 | 3363.9733 | 0% | 0% | 0% | 0% | 0% | 87.5% | 87.5% | 87.5% | 87.5% | 87.5% | 87.5% | 87.5% | 87.5% | 87.5%
114 | Special Item - As Constructed Survey and Plans | 20 | 95114115261 | 3 | 2500 | 0% | 0% | 0% | 0% | 0% | 0% | 80% | 90% | 95% | 95% | 100% | 100% | 100% | 100%
600 | DOHERTY STREET | 0 | 2,93,110 | 3119 | 0
115 | Quality Verification & Control | 0 | 118 | 120 | 9760 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 50% | 75% | 100% | 100% | 100%
116 | Control of Traffic | 20 | 119 | 121SS,144 | 23292.48 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 50% | 75% | 100% | 100% | 100%
117 | General Earthworks Cut | 3 | 120SS | 124123 | 13017.3001 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100%
118 | General Earthworks Fill (Fill behind kerb to boundary) | 1 | 135 | 257 | 2917.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
119 | Replace unsuitable material below sub grade with select material complete (PROVISIONAL) | 1 | 121 | 148252 | 4259.6667 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
120 | Removal / Demolition of Drainage Components complete | 2 | 121 | 126 | 5490.9091 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
121 | Relocate existing kerb adapter and roofwater connection from property | 1 | 136FF |  | 790 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
122 | 375mm dia Class 2, Flush Joint | 3 | 124252 | 127 | 12899.4519
123 | 450mm dia Class 2, Flush Joint | 1 | 126 | 128 | 2280.6627 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100%
124 | 450mm dia Class 2, Rubber Ring Joint | 2 | 127 | 129 | 5354.3514 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0%
125 | 900 x 450 | 2 | 128 | 130 | 7752.5 | 0% | 0% | 0% | 0% | 14.63% | 14.63% | 14.63% | 14.63% | 14.63% | 21.95% | 29.27% | 100% | 100% | 100%
126 | 1200 x 450 | 6 | 129 | 131 | 50229.5 | 0% | 0% | 0% | 0% | 62.86% | 62.86% | 62.86% | 62.86% | 62.86% | 100% | 100% | 100% | 100% | 100%
127 | 1200 x 600 | 2 | 130 | 132133141137 | 7274.5 | 0% | 0% | 0% | 0% | 62.5% | 62.5% | 62.5% | 62.5% | 62.5% | 93.75% | 125% | 125% | 125% | 125%
128 | Cast in situ Concrete Headwalls & Wingwalls & Aprons complete | 2 | 131 | 150 | 410.158 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
129 | BRO Pit Gully Pit | 10 | 131 | 134 | 27181.3 | 0% | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100%
130 | (v) Concrete Manholes - Cast Insitu | 4 | 133 | 136254 | 7500 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100%
131 | (i) Concrete Barrier Kerb & Channel B1 complete | 1 | 136 | 122140146255 | 1701.2167 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
132 | (ii) Concrete Mountable Kerb & Channel M1 complete | 1 | 134139254 | 125FF,135 | 10092.6 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
133 | (i) 100mm dia Slotted Corrugated Plastic Pipe | 3 | 131 | 138FF,139 | 8669.2695 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
134 | Cleanout Structures | 1 | 137FF |  | 858 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
135 | Place only Type 2.3 | 2 | 137141 | 136 | 8380.2124 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
136 | Place only Type 2.1 (828m²) | 3 | 135,146FF,255 | 142FS+5 days | 8090.9335 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
137 | Special Item - Geotextile layer | 1 | 131 | 139 | 1467.6239 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100%
138 | (vii) AMC5 | 1 | 140FS+5 days,146,256 | 143FS+14 days,145 | 13597.416 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
139 | (ii) 14mm Nominal Size | 1 | 142FS+14 days | 150 | 33384.96 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
140 | Remove and reinstate Existing Signs & Support Structures | 1 | 120 | 150 | 1048 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
141 | Supply & Erection of Boundary Fencing (1200 high chainlink star picket fence) | 1 | 142 | 150 | 1375 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
142 | (iv) Residential Invert Crossing (? m) | 4 | 135255 | 140FF,142,256 | 2449.4667 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
143 | Service connections | 3 | 149253 | 150 | 7920 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80% | 100% | 100% | 100% | 100% | 100%
144 | Alterations to water main | 2 | 123 | 149251 | 7000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80% | 100% | 100% | 100% | 100% | 100%
145 | Alterations to valves and hydrant margins | 2 | 148251 | 147253 | 1000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80% | 100% | 100% | 100% | 100% | 100%
146 | Special Item - As Constructed Survey and Plans | 3 | 132,143,144,145FF,147 | 3 | 2400 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 75% | 100% | 100% | 100%
700 | FAUST STREET | 0 | 2211235 | 3152291 | 0
147 | Quality Verification & Control | 0 | 151 | 153273 | 10470 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100%
148 | Control of Traffic | 30 | 152 | 154SS,172SS,180 | 34938.72 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100%
149 | Temporary Erosion & Sedimentation Control (includes supply and installation of all components) | 6 | 153SS | 155 | 11050 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100%
150 | Clearing and Grubbing (removal of kerb & channel) | 2 | 154 | 156158 | 10066.6667 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100%
151 | General Earthworks Cut | 3 | 155 | 157 | 13092.3333 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100%
152 | Replace unsuitable material below sub grade with select material complete (provisional) | 1 | 156 | 164267271 | 1310.6667 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0%
153 | Removal / Demolition of Drainage Components complete | 2 | 155272 | 160 | 5452.498 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100%
154 | Connect property drainage pipes (No. 21) | 5 | 162 |  | 8295 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100%
155 | In-Situ reinforced concrete Base Slab for culverts complete | 2 | 158 | 161 | 1953.1333 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100%
156 | 1200 x 300 | 2 | 160 | 162 | 8442.852 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 66.13% | 100% | 100% | 100%
157 | MCC Type A Gully Pit | 4 | 161 | 159163 | 14020 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 100% | 100% | 100%
158 | (i) Concrete Barrier Kerb & Channel B1 complete | 3 | 162165 | 166 | 25252.436 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.05% | 100% | 100% | 100%
159 | Subsoil Drain Pipe - 100mm dia Slotted Corrugated Plastic Pipe complete (provisional quantity) | 6 | 157268 | 167 | 19609.062 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 61.68% | 100% | 100% | 100%
160 | Place only Type 2.3 (includes cart, place, compact & trim) | 3 | 167 | 163173179 | 22392.3302 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 62.17% | 100% | 100% | 100%
161 | Place only Type 2.1 (includes cart, place, compact & trim) | 4 | 163,173FF | 169FS+5 days | 17201.6533 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 72.38% | 100% | 100% | 100%
162 | Special Item - Geogrid layer | 1 | 164 | 165,168FF | 9505.3885 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 62.45% | 100% | 100% | 100%
163 | Special Item - Geotextile layer | 1 | 167FF |  | 2522.4785 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 62.45% | 100% | 100% | 100%
164 | (vii) AMC5 | 1 | 166FS+5 days,179 | 170FS+14 days | 14537.124 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
165 | (i) 10mm Nominal Size | 1 | 169FS+14 days | 171FS+5 days,269 | 30256.947 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
166 | Pavement Marking Paint - Longitudinal Lines including car parking bays | 1 | 170FS+5 days | 180 | 4000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
167 | Remove and reinstate Existing Signs & Support Structures | 2 | 153SS | 180 | 2832 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
168 | (iv) Residential Invert Crossing | 9 | 165 | 166FF,177 | 9765.52 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 28.57% | 100% | 100% | 100%
169 | (i) Grass Seeding | 1 | 177 | 175 | 1347.5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
170 | (ii) Turfing | 1 | 174 | 176 | 2231.25 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
171 | (iii) Individual Planting | 1 | 175 | 180 | 3000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
172 | Supply and place Imported Topsoil | 1 | 173 | 174 | 2645 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
173 | Sawcut Bituminous pavement | 2 | 179SS |  | 3000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
174 | Service connections | 4 | 165 | 169,178SS,180,272 | 29880 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 100% | 100% | 100%
175 | Special Item - As Constructed Survey and Plans | 3 | 153171172176179 | 3 | 2400 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 100% | 100% | 100%
800 | JUPP STREET | 0 | 2,4,16 | 93,3,182 | 0
176 | Quality Verification & Control | 0 | 181 | 183 | 9860 | 25% | 50% | 50% | 60% | 75% | 80% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
177 | Control of Traffic | 20 | 182 | 184SS,210 | 23292.48 | 20% | 60% | 60% | 70% | 75% | 80% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
178 | Temporary Erosion & Sedimentation Control (includes supply and installation of all components) | 6 | 183SS | 185186 | 11050 | 20% | 60% | 60% | 70% | 75% | 80% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
179 | Special Item - Demolition of Structure (concrete slabs, culverts, pipes etc) | 2 | 184 | 190 | 10066.6667 | 60% | 60% | 60% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
180 | Removal & Stockpiling of Topsoil for reuse (100mm thick nom.) | 1 | 184 | 187 | 2613.5614 | 0% | 24.52% | 24.52% | 89.03% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
181 | General Earthworks Cut | 3 | 186 | 188 | 15596.6371 | 41.81% | 41.81% | 41.81% | 93.42% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
182 | General Earthworks Fill | 1 | 187 | 189 | 757.35 | 0% | 0% | 0% | 74.07% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
183 | Replace unsuitable material below sub grade with select material complete (PROVISIONAL) | 1 | 188 | 197 | 1310.6667 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
184 | Removal / Demolition of Drainage Components complete | 2 | 185 | 192 | 5490.9091 | 80% | 80% | 80% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
185 | Connect property drainage pipes ( 7 No.) | 2 | 194 | 200275 | 2765 | 0% | 70% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
186 | In-Situ reinforced concrete Base Slab for culverts complete | 2 | 190 | 193 | 1692.7156 | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
187 | 750 x 300 | 2 | 192 | 194209 | 8530.5 | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
188 | MCC Type A Gully Pit (including chamber) | 2 | 193 | 191195 | 3505 | 0% | 0% | 90% | 90% | 90% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
189 | (i) Concrete Barrier Kerb & Channel B1 complete | 2 | 194200209276277 | 196278 | 16640.0263 | 0% | 79.87% | 79.87% | 79.87% | 79.87% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
190 | (iv) Concrete Dish Drain (600 wide) complete | 1 | 195279 | 201 | 1690.91 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
191 | Subsoil Drain Pipe - 100mm dia Slotted Corrugated Plastic Pipe complete | 4 | 189 | 198 | 11600.3083 | 0% | 87.19% | 87.19% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
192 | Special Item -Subsoil Drain Pipe - 100mm dia Slotted Corrugated Plastic Pipe encased in no fines concrete complete as shown on drawings | 3 | 197 | 199FF,202,274 | 16027.7171 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
193 | Cleanout Structures | 2 | 198FF |  | 1859 | 0% | 50% | 50% | 76.92% | 76.92% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
194 | Place only Type 2.3 (cement modified) | 4 | 191202275 | 195206276 | 21403.5155 | 27.51% | 66.14% | 66.14% | 93.65% | 93.65% | 94.97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
195 | Place only Type 2.1 (cement modified) | 3 | 196,206FF | 204FS+5 days,93 | 10584.8504 | 0% | 61.42% | 61.42% | 61.42% | 61.42% | 85.04% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
196 | Special Item - Geogrid layer (PROVISIONAL) | 1 | 198274 | 200,203FF | 7508.9589 | 55.95% | 55.95% | 55.95% | 71.83% | 85% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
197 | Special Item -Geotextile layer (PROVISIONAL) | 1 | 202FF |  | 1992.6789 | 55.95% | 55.95% | 55.95% | 71.83% | 85% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
198 | (vi) AMC4 | 1 | 201FS+5 days | 205FS+14 days | 14172.7845 | 0% | 0% | 69.54% | 69.54% | 69.54% | 69.54% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
199 | (ii) 14mm Nominal Size | 1 | 204FS+14 days | 210 | 34057.8 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
200 | (iv) Residential Invert Crossing (3.1m to 4.5m) | 8 | 200276 | 201FF,207 | 5192.9867 | 0% | 72.73% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
201 | (viii) Hand Placed Concrete Paving (Footpath / Bikeway) | 4 | 206 | 208 | 6624.2867 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
202 | (i) Grass Seeding | 1 | 207 | 210 | 2438.975 | 0% | 0% | 0% | 100% | 10% | 50% | 74.97% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
203 | Supply and install mains and reticulation | 2 | 193 | 195277 | 9200 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
204 | Special Item - As Constructed Survey and Plans | 3 | 183205208 | 3 | 2400 | 0% | 0% | 0% | 0% | 0% | 0% | 80% | 80% | 80% | 95% | 100% | 100% | 100% | 100%
900 | STERRY STREET | 0 | 2,93,110 | 151,3,212 | 0
205 | Quality Verification & Control | 0 | 211 | 213 | 10350 | 0% | 0% | 0% | 0% | 10% | 10% | 80% | 90% | 95% | 100% | 100% | 100% | 100% | 100%
206 | Control of Traffic | 25 | 212 | 214SS,234SS | 29115.6 | 0% | 0% | 0% | 0% | 10% | 10% | 80% | 90% | 95% | 100% | 100% | 100% | 100% | 100%
207 | Temporary Erosion & Sedimentation Control (includes supply and installation of all components) | 6 | 213SS | 215216 | 11050 | 0% | 0% | 0% | 0% | 10% | 10% | 80% | 90% | 95% | 100% | 100% | 100% | 100% | 100%
208 | Special Item - Demolition of Structure (concrete slabs, culverts, pipes etc) | 2 | 214 | 217285 | 10066.6667 | 0% | 0% | 0% | 0% | 0% | 0% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
209 | General Earthworks Cut | 6 | 214 | 224 | 34970.2439 | 0% | 0% | 0% | 0% | 0% | 0% | 0.04706% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
210 | Removal / Demolition of Drainage Components complete | 2 | 215 | 218280283 | 5490.9091 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
211 | Alteration to Existing Stormwater Structures | 6 | 217284286 | 220 | 7860 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
212 | Connect property drainage pipes | 4 | 222 | 242 | 6715 | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
213 | In-Situ reinforced concrete Base Slab for culverts complete | 3 | 218 | 221 | 4557.3111 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
214 | 750 x 300 | 3 | 220 | 222 | 12883.6467 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
215 | MCC Type A Gully Pit | 2 | 221 | 219 | 3505 | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
216 | (i) Concrete Barrier Kerb & Channel B1 complete | 1 | 226241282 | 228236 | 7442.8233 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
217 | Subsoil Drain Pipe - 100mm dia Slotted Corrugated Plastic Pipe complete (provisional quantity) | 6 | 216 | 225FF,227,229 | 17338.539 | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
218 | Cleanout Structures | 2 | 224FF |  | 1716 | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
219 | Place only Type 2.3 | 4 | 227 | 223 | 23498.5686 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
220 | Place only Type 2.5 (cement modified) | 5 | 224229 | 226241240 | 31425.7966 | 0% | 0% | 0% | 0% | 0% | 0% | 32.43% | 32.43% | 32.43% | 32.43% | 32.43% | 32.43% | 32.43% | 32.43%
221 | Place only Type 2.1 | 8 | 223,237FF | 231235287 | 31590.338 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
222 | Special Item - Geogrid layer | 1 | 224 | 227,230FF | 16477.9932 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
223 | Special Item - Geotextile layer | 1 | 229FF |  | 4372.8232 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
224 | (ii) 14mm Nominal Size | 3 | 228,287FS+5 days | 232FS+5 days | 100970.1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
225 | Pavement Marking Paint - Longitudinal Lines including car parking bays | 1 | 231FS+5 days | 233 | 5000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
226 | Pavement Marking Paint - Transverse Lines, Symbols, Legends, Arrows, Chevrons, Traffic Islands & Kerbs | 1 | 232 | 242 | 2000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
227 | Remove and reinstate Existing Signs & Support Structures | 2 | 213SS | 242 | 1652 | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100%
228 | Supply & Installation of all Signs (complete) | 1 | 228 | 242151 | 4215 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
229 | (ii) Concrete Kerb Ramp (1 No) | 2 | 223 | 237 | 785 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
230 | (iv) Residential Invert Crossing (10.5 m) | 4 | 236 | 228FF,238,289 | 2493.92 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
231 | (viii) Hand Placed Concrete Paving (Footpath / Bikeway) | 3 | 237289 | 239 | 1282.12 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
232 | (ii) Turfing | 1 | 238 | 242 | 892.5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
233 | Supply and install mains and reticulation | 2 | 227 | 241 | 8000 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
234 | Service connections | 3 | 227240280288290 | 223282 | 10980 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
235 | Special Item - As Constructed Survey and Plans | 3 | 239233219235234 | 3 | 2400 | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 70% | 70% | 95% | 100% | 100% | 100% | 100%
VARIATIONS
CCC01 | CCC_PV01 - Remove and Replace New kerbiing and traffic Islands | 3 | 63 | 245 | 2308.0209 | 0% | 0% | 0% | 0% | 0% | 49.18% | 49.18% | 49.18% | 49.18% | 100% | 100% | 100% | 100% | 100%
CCC02 | CCC_PV02 - Cultrual Centre Carpark - Install 600m dish Drain | 2 | 244 | 66 | 5723.08 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
CCC03 | CCC_PV03 Cultrual Centre Carpark Insitu Stabilising Carpark - 400m2 | 2 | 247 | 61,68 | 5486.63 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
CCC04 | Unsuitable Subgrade replacement Iron Stone Rock Mattress | 6 | 56 | 246 | 45538.5999 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
DL01 | Construct three residential property access Dobbins Lane | 4 | 47 | 49 | 2493.92 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
DL02 | Variation Direction to place an additional layer of Geogrid dobbins lane Ch 190 to Ch 230 - 7.5m wide | 0 | 41 |  | 1787.8474 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
DL03 | Remove & Replace Subgrade - Excavate unsutiable material, Blended cement into gravel, import place and compact. | 8 | 28 | 37 | 39008.6124 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
DS01 | Variation to water main Doherty street extra over the BOQ | 1 | 148 | 149 | 36365 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
DS02 | Pavement Design | 3 | 123 | 126 | 22972.4283 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
DS03 | Replacement of AC sewer main ch 37 | 1 | 149 | 147 | 5000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
DS04 | Construct Field Inlet Gully Pit Doherty Street | 1 | 134 | 136 | 9050 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
DS05 | Kerb extension end of Doherty Street | 1 | 135 | 140146 | 446 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
DS06 | Concrete Driveway 3 Doherty Street | 3 | 146 | 142 | 831.3067 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
DS07 | Doherty Street - Hydromulch 1000m2 | 1 | 122 | 150 | 2960 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
DSV01 | Dodd St - Geogrid layer | 1 | 111 | 109 | 16668.697 | 0% | 0% | 0% | 31.46% | 84.98% | 84.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
DSV02 | Dodd Street-PV02 Supply and Install Entry pits, RCBC and Concrete Nib Wall and Nib | 8 | 104 | 106 | 12004.176 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
DSV03 | Dodd Street water main replacement Install new 100mm Dia DICL Watermains 3 locations | 9 | 96 | 111265 | 42341 | 0% | 0% | 0% | 0% | 0% | 97.43% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
DSV04 | Dodd Street_ PV04 - Extend Deep Lift AC at Culvert Crossing Anzac Drive | 1 | 113 | 117 | 891.261 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
DSV05 | Dodd Street_PV05 - New Bropit and RCBC arrangement | 4 | 104 | 263 | 5434.44 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
DSV06 | Install new Type A MCC side entry pit, 13m of 450 RCP break in to existing drainage line and install a flush point. | 3 | 262 | 106 | 6552.74 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
DSV07 | Installation Pram Ramps Dodd street | 4 | 116 | 112 | 15632.4433 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 92.73% | 100% | 100% | 100% | 100% | 100% | 100%
DSV08 | Dodd Street - Water main Protection Lurline Street - works completed formal vairation to be provided Refer to email 2 May sent | 1 | 260 | 111 | 2169.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
DSV09 | Vairation to design levels mismatch to road surface - 44m Lurline Street to match levels to existing road surface. | 0 | 94 |  | 325 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
FS00 | Remove and Replace Unsuitable Subgrade Faust Street | 3 | 157 | 268,271FF | 14650.5826 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
FS01 | Excavation of unsuitable subgrade | 2 | 267 | 164 | 4757.55 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100%
FS01A | Additional Asphalt for Variation Faust _PV01 | 0 | 170 |  | 5117.349 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
FS04 | Additional Testing Requirements | 0 | 273 |  | 6310 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
FS05 | Blend Iron stone with 1% cement to stockpile | 1 | 157,267FF |  | 739.125
FS10 | Faust Street - Service Crossing | 1 | 179 | 158 | 8000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
FSXX | Faust Street drw FSC 04 extra over the BOQ | 0 | 152 | 270 | 0
JSV01 | Jupp Street Geotextile wrapping around no fines concrete | 1 | 198 | 202 | 1137.6074 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
JSV02 | Jupp_PV02 - Boundary Pits & Pipes | 2 | 191 | 200 | 2325 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 300% | 100% | 100%
JSV03 | Jupp St - Haul & Place Type 2.3 gravel | 1 | 200 | 195206 | 2264.9223 | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
JSV04 | Jupp St_PV03 - Replace AC watermain crossing at Jupp and Anzac Rd | 6 | 209 | 195 | 23859.3462 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
JSV05 | Jupp_PV04 - Extend Kerb & Channel On Anzac Road | 1 | 195 | 279FF | 691.1193 | 0% | 0% | 0% | 0% | 0% | 0% | 95.33% | 95.33% | 95.33% | 95.33% | 95.33% | 95.33% | 95.33% | 95.33%
JSV06 | Jupp_PV05 - Extend Kerb & Channel on Phaff Street | 1 | 278FF | 196 | 1086.1193 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
SS01 | Sterry_PV01 Sterry Street - Chapman Street Works | 7 | 217 | 241288 | 21720.4724 | 0% | 0% | 0% | 0% | 0% | 0% | 36.51% | 37.58% | 37.58% | 62.85% | 62.85% | 62.85% | 63.93% | 63.93%
SS02 | Area1 and Area 2 Sterry Street - Rock mattress, 2 layers of Geogrid and, geofabric | 0 |  |  | 191104.0703 | 0% | 0% | 0% | 0% | 0% | 0% | 87.39% | 112.9% | 116.5% | 100% | 100% | 100% | 100% | 100%
SS02.34 | Area 1 Additional water service connections (5) | 3 | 241 | 223 | 0
SS02.A1 | Sterry Street - Area 1 Remove & Replace | 12 | 217285 | 284 | 0
SS02.A2 | Sterry Street - Area 2 Remove & Replace | 3 | 283 | 218286 | 0
SS03 | Vairation direction - Removal and Replacement of 150mm Sewer Main Sterry street | 1 | 215 | 283 | 9500 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
SS04 | Cement stabilisation - Sterry Street 250mm depth | 6 | 284 | 218 | 40195.5239 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
SS05 | 7 mm Primer Seal Sterry Street | 1 | 228 | 231FS+5 days | 17187.24 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
SS06 | Additional Chapman Street works - Kerbing and Miscellaneous concrete works Chapman | 1 | 280 | 241290 | 4460 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
SS07 | Construct standard driveway access - Proserpine Secondary School | 3 | 237 | 238 | 465.0248 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
SS08 | Various Concrete works and fencing and gate alterations - day labour rates + materials | 1 | 288 | 241 | 2676
W01 | Waste Disposal | 0 |  |  | 3115 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%

## Budget & Revenue
WBS | Item No | Description | Unit | BAC | Tender Quantity | Contract Quantity | Tender Rate | Tender Total | Contract Total | 2011-10-01 | %C - Oct 11 | 2011-11-01 | %C - Nov 11 | 2011-12-01 | %C - Dec-11 | 2012-01-01 | %C - Jan 12 | 2012-02-01 | %C Feb 12 | 2012-03-01 | %C Mar 12 | 2012-04-01 | %C Apr 12 | 2012-05-01 | %C May 12 | 2012-06-01 | %C Jun 12 | 2012-07-01 | %C Jul 12 | 2012-08-01 | %C Aug 12 | 2012-09-01 | %C Sep 12 | 2012-10-01 | %C Oct 12 | 2012-11-01 | %C Nov 12 | Revenue Oct-11 | Revenue Nov-11 | Revenue Dc-11 | Revenue Jan-12 | Revenue Feb-12 | Revenue Mar-12 | Revenue Apr-12 | Revenue May-12 | Revenue Jun-12 | Revenue Jul-12 | Revenue Aug-12 | Revenue Sep-12 | Revenue Oct-12 | Revenue Nov-12
Contract Items
ANZAC STREET
QUALITY SYSTEM
| CQS | QUALITY SYSTEM REQUIREMENTS
5 | 102. QP1 | Quality System Documents & Records (for entire Package A) | Lump | 39000 | 1 | 1 | 48992.89 | 48992.89 | 48992.89 | 0.04 | 4% | 0.08 | 8% | 0.09 | 9% | 0.14 | 14% | 0.5 | 50% | 0.55 | 55% | 0.6 | 60% | 0.65 | 65% | 0.8 | 80% | 0.9 | 90% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1959.7156 | 3919.4312 | 4409.3601 | 6859.0046 | 24496.445 | 26946.0895 | 29395.734 | 31845.3785 | 39194.312 | 44093.601 | 48992.89 | 48992.89 | 48992.89 | 48992.89
| CQC | QUALITY CONTROL REQUIREMENTS
6 | 104. QCP1 | Quality Verification & Control | Lump | 6460 | 1 | 1 | 8115.23 | 8115.23 | 8115.23 | 0.5 | 50% | 0.5 | 50% | 0.5 | 50% | 0.5 | 50% | 0.5 | 50% | 0.5 | 50% | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 4057.615 | 4057.615 | 4057.615 | 4057.615 | 4057.615 | 4057.615 | 4057.615 | 8115.23 | 8115.23 | 8115.23 | 8115.23 | 8115.23 | 8115.23 | 8115.23
SUB-TOTAL
GENERAL REQUIREMENTS
| C101 | GENERAL
7 | 107. C101(b) | Site Establishment & Disestablishment | Lump | 22050 | 1 | 1 | 22050 | 22050 | 22050 | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 22050 | 22050 | 22050 | 22050 | 22050 | 22050 | 22050 | 22050 | 22050 | 22050 | 22050 | 22050 | 22050 | 22050
SUB-TOTAL
ROAD & EARTHWORKS
| C201 | CONTROL OF TRAFFIC
8 | 449. C201(a) | Control of Traffic | Lump | 11646.24 | 1 | 1 | 14630.33 | 14630.33 | 14630.33 | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 11704.264 | 11704.264 | 11704.264 | 11704.264 | 11704.264 | 11704.264 | 11704.264 | 14630.33 | 14630.33 | 14630.33 | 14630.33 | 14630.33 | 14630.33 | 14630.33
| 112. C201(b) | Provision of Temporary Roadways, Side-tracks and Detours (Provisional) | Lump |  | 1 | 1 |  |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| C213 | EARTHWORKS
9 | 125. C213(b) | General Earthworks Cut | m3 | 2268 | 60 | 60 | 47.49 | 2849.4 | 2849.4 | 60 | 100% | 60 | 100% | 60 | 100% | 60 | 100% | 60 | 100% | 60 | 100% | 60 | 100% | 60 | 100% | 60 | 100% | 60 | 100% | 60 | 100% | 60 | 100% | 60 | 100% | 60 | 100% | 2849.4 | 2849.4 | 2849.4 | 2849.4 | 2849.4 | 2849.4 | 2849.4 | 2849.4 | 2849.4 | 2849.4 | 2849.4 | 2849.4 | 2849.4 | 2849.4
10 | 127. C213(d) | Replace unsuitable material below sub grade with select material complete (Provisional) | m3 | 655.3333 | 10 | 10 | 65.53 | 655.3 | 655.3 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUB-TOTAL
STORMWATER DRAINAGE
| C221 | PIPE DRAINAGE (SUPPLY & INSTALL)
| 314. C221(a) | STEEL REINFORCED CONCRETE
314. C221(a)
| C222 | PRECAST BOX CULVERTS (SUPPLY & INSTALL)
11 | 315. C222(a) | In-Situ reinforced concrete Base Slab for culverts complete | m3 | 2604.1778 | 4 | 4 | 817.86 | 3271.44 | 3271.44 | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 3271.44 | 3271.44 | 3271.44 | 3271.44 | 3271.44 | 3271.44 | 3271.44 | 3271.44 | 3271.44 | 3271.44 | 3271.44 | 3271.44 | 3271.44 | 3271.44
12 | 325. C222(b) | 1200 x 600 | m | 7902.5 | 12 | 12 | 827.28 | 9927.36 | 9927.36 | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 9927.36 | 9927.36 | 9927.36 | 9927.36 | 9927.36 | 9927.36 | 9927.36 | 9927.36 | 9927.36 | 9927.36 | 9927.36 | 9927.36 | 9927.36 | 9927.36
| C223 | DRAINAGE STRUCTURES
13 | 418. C223(a) | Cast in situ Concrete Headwalls & Wingwalls & Aprons complete | m3 | 2733.6 | 3 | 3 | 1144.67 | 3434.01 | 3434.01 | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3434.01 | 3434.01 | 3434.01 | 3434.01 | 3434.01 | 3434.01 | 3434.01 | 3434.01 | 3434.01 | 3434.01 | 3434.01 | 3434.01 | 3434.01 | 3434.01
| C224 | OPEN DRAINS, INCLUDING KERB & CHANNEL
14 | 465. C224(b) | Excavation - Inlet, Outlet & Diversion Channels | m3 | 2268 | 60 | 60 | 47.49 | 2849.4 | 2849.4 |  | 0% | 30 | 50% | 30 | 50% | 30 | 50% | 30 | 50% | 30 | 50% | 30 | 50% | 60 | 100% | 60 | 100% | 60 | 100% | 60 | 100% | 60 | 100% | 60 | 100% | 60 | 100% | 0 | 1424.7 | 1424.7 | 1424.7 | 1424.7 | 1424.7 | 1424.7 | 2849.4 | 2849.4 | 2849.4 | 2849.4 | 2849.4 | 2849.4 | 2849.4
SUB-TOTAL
PAVEMENTS
| C241 | STABILIZATION
15 | 543 | Full service, supply agent and mix complete (Provisional if ordered) | m2 | 5918.8258 | 170 | 170 | 43.74 | 7435.8 | 7435.8 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| C242 | FLEXIBLE PAVEMENTS
16 | 490 | Place only Type 2.1 (cement modified) | m3 | 3798.8716 | 20 | 20 | 238.6 | 4772 | 4772 | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 4772 | 4772 | 4772 | 4772 | 4772 | 4772 | 4772 | 4772 | 4772 | 4772 | 4772 | 4772 | 4772 | 4772
17 | 491 | Place only Type 2.3 (cement modified) | m3 | 2836.8716 | 20 | 20 | 178.17 | 3563.4 | 3563.4 | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 3563.4 | 3563.4 | 3563.4 | 3563.4 | 3563.4 | 3563.4 | 3563.4 | 3563.4 | 3563.4 | 3563.4 | 3563.4 | 3563.4 | 3563.4 | 3563.4
| C244 | SPRAYED BITUMINOUS SURFACING
| C244(a) | Supply & Spray Primer, supply & spread aggregates, Primerbinder (including preparation of surface) complete
18 | 551. C244(a) | (vii) AMC5 | m2 | 10878 | 200 | 200 | 55.75 | 11150 | 11150 | 200 | 100% | 200 | 100% | 200 | 100% | 200 | 100% | 200 | 100% | 200 | 100% | 200 | 100% | 200 | 100% | 200 | 100% | 200 | 100% | 200 | 100% | 200 | 100% | 200 | 100% | 200 | 100% | 11150 | 11150 | 11150 | 11150 | 11150 | 11150 | 11150 | 11150 | 11150 | 11150 | 11150 | 11150 | 11150 | 11150
19 | 555. C244(b) | Supply & Spray Binder - Bitumen (includes PMB's, Adhesion Agent where required and Preparation of Surface) supply & spread aggregates complete | m2 | 10878 | 200 | 200 | 55.75 | 11150 | 11150 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 200 | 100% | 200 | 100% | 200 | 100% | 200 | 100% | 200 | 100% | 200 | 100% | 200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11150 | 11150 | 11150 | 11150 | 11150 | 11150 | 11150
SUB-TOTAL
ROAD FURNISHINGS
| C263 | GUIDE POSTS
20 | 690. C263(a) | Guide Posts complete supply and install | each | 140 | 4 | 4 | 43.97 | 175.88 | 175.88 |  | 0% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 0 | 175.88 | 175.88 | 175.88 | 175.88 | 175.88 | 175.88 | 175.88 | 175.88 | 175.88 | 175.88 | 175.88 | 175.88 | 175.88
SUB-TOTAL
MISCELLANEOUS
| C273 | LANDSCAPE
| C273(a) | Vegetation of Slopes 1 in 3 or Flatter
21 | 830. C273(a) | (i) Grass Seeding | m2 | 269.5 | 100 | 905 | 3.39 | 339 | 3067.95 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 100 | 11.05% | 100 | 11.05% | 100 | 11.05% | 905 | 100% | 905 | 100% | 100 | 11.05% | 100 | 11.05% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339 | 339 | 339 | 3067.95 | 3067.95 | 339 | 339
SUB-TOTAL
SPECIFIED WORKS
22 |  | Special Item - As Constructed Survey and Plans | Lump | 800 | 1 | 1 | 1004.98 | 1004.98 | 1004.98 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 803.984 | 1004.98 | 1004.98 | 1004.98 | 1004.98 | 1004.98 | 1004.98 | 1004.98
SUB-TOTAL
|  | TOTAL | [5 empty] | 156366.42
DOBBINS LANE
QUALITY SYSTEM
| CQC | QUALITY CONTROL REQUIREMENTS
23 | 104. QCP1 | Quality Verification & Control | Lump | 11795 | 1 | 1 | 14817.21 | 14817.21 | 14817.21 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.2 | 20% | 0.5 | 50% | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2963.442 | 7408.605 | 11853.768 | 14817.21 | 14817.21 | 14817.21 | 14817.21
SUB-TOTAL
GENERAL REQUIREMENTS
| C101 | GENERAL
| 107. C101(b) | Site Establishment & Disestablishment | Lump |  | 1 | 1 |  |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUB-TOTAL
ROAD & EARTHWORKS
| C201 | CONTROL OF TRAFFIC
25 | 449. C201(a) | Control of Traffic | Lump | 34938.72 | 1 | 1 | 43890.99 | 43890.99 | 43890.99 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.2 | 20% | 0.4 | 40% | 0.6 | 60% | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 8778.198 | 17556.396 | 26334.594 | 35112.792 | 43890.99 | 43890.99 | 43890.99 | 43890.99
| C211 | CONTROL OF EROSION & SEDIMENTATION
26 | 114. C211(a) | Temporary Erosion & Sedimentation Control (includes supply and installation of all components) | Lump | 11050 | 1 | 1 | 13881.32 | 13881.32 | 13881.32 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.2 | 20% | 0.4 | 40% | 0.6 | 60% | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 2776.264 | 5552.528 | 8328.792 | 11105.056 | 13881.32 | 13881.32 | 13881.32 | 13881.32
| C213 | EARTHWORKS
27 | 125. C213(b) | General Earthworks Cut | m3 | 20828.5297 | 998 | 998 | 26.22 | 26167.56 | 26167.56 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 200 | 20.04% | 998 | 100% | 998 | 100% | 998 | 100% | 998 | 100% | 998 | 100% | 998 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5244 | 26167.56 | 26167.56 | 26167.56 | 26167.56 | 26167.56 | 26167.56
28 | 127. C213(d) | Replace unsuitable material below sub grade with select material complete (PROVISIONAL) | m3 | 655.3333 | 10 | 10 | 65.53 | 655.3 | 655.3 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 10 | 100% | 10 | 100% | 10 | 100% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 655.3 | 655.3 | 655.3 | 0 | 0
SUB-TOTAL
STORMWATER DRAINAGE
| C220 | STORMWATER DRAINAGE - GENERAL
29 | 137 | Removal / Demolition of Drainage Components complete | Lump | 10066.6667 | 1 | 1 | 13646.79 | 13646.79 | 13646.79 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.2 | 20% | 0.9 | 90% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2729.358 | 12282.111 | 13646.79 | 13646.79 | 13646.79 | 13646.79 | 13646.79
30 |  | Alteration to Existing Stormwater Structures (New 225 Upvc at Ch 140 | Lump | 1200 | 1 | 1 | 1507.47 | 1507.47 | 1507.47 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1507.47 | 1507.47 | 1507.47 | 1507.47 | 1507.47
| C221 | PIPE DRAINAGE (SUPPLY & INSTALL)
31 | 229. C221(a) | 225mm dia uPVC | m | 2313 | 16 | 16 | 181.6 | 2905.6 | 2905.6 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 16 | 100% | 16 | 100% | 16 | 100% | 16 | 100% | 16 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2905.6 | 2905.6 | 2905.6 | 2905.6 | 2905.6
32 | 443. C223(b) | (x) Inter-allotment Drainage Pit | each | 3750 | 1 | 1 | 4710.85 | 4710.85 | 4710.85 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2355.425 | 4710.85 | 4710.85 | 4710.85 | 4710.85
| C224 | OPEN DRAINS, INCLUDING KERB & CHANNEL
33 | 466. C224(c) | Concrete Lining of Open Drains | m2 | 356.1444 | 5 | 5 | 89.48 | 447.4 | 447.4 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447.4 | 447.4 | 447.4 | 447.4 | 447.4
34 | 472. C224(h) | (i) Concrete Barrier Kerb & Channel B1 complete | m | 10526.2786 | 198 | 198 | 66.78 | 13222.44 | 13222.44 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 178.2 | 90% | 198 | 100% | 198 | 100% | 198 | 100% | 198 | 100% | 198 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11900.196 | 13222.44 | 13222.44 | 13222.44 | 13222.44 | 13222.44
35 | 475. C224(h) | (iv) Concrete Dish Drain (0.9m wide) complete | m | 6633.57 | 51 | 51 | 163.4 | 8333.4 | 8333.4 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 30 | 58.82% | 51 | 100% | 51 | 100% | 51 | 100% | 51 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4902 | 8333.4 | 8333.4 | 8333.4 | 8333.4
36 | 477. C224(h) | (vi) Concrete Kerb (Type B2) complete | m | 2551.826 | 48 | 48 | 66.78 | 3205.44 | 3205.44 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 48 | 100% | 48 | 100% | 48 | 100% | 48 | 100% | 48 | 100% | 48 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3205.44 | 3205.44 | 3205.44 | 3205.44 | 3205.44 | 3205.44
SUB-TOTAL
SUB-SURFACE DRAINAGE
| C232 | PAVEMENT DRAINS
37 | 508. C232(b) | (i) 100mm dia Slotted Corrugated Plastic Pipe | m | 15356.9917 | 372 | 372 | 51.86 | 19291.92 | 19291.92 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 100 | 26.88% | 372 | 100% | 372 | 100% | 372 | 100% | 372 | 100% | 372 | 100% | 372 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5186 | 19291.92 | 19291.92 | 19291.92 | 19291.92 | 19291.92 | 19291.92
38 | 519. C232(c) | Cleanout Structures | each | 715 | 5 | 5 | 179.64 | 898.2 | 898.2 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2.5 | 50% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449.1 | 898.2 | 898.2 | 898.2 | 898.2
SUB-TOTAL
PAVEMENTS
| C242 | FLEXIBLE PAVEMENTS
39 | 491 | Place only Type 2.3 | m3 | 13363.0414 | 236 | 236 | 71.13 | 16786.68 | 16786.68 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 41 | 17.37% | 236 | 100% | 236 | 100% | 236 | 100% | 236 | 100% | 236 | 100% | 236 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2916.33 | 16786.68 | 16786.68 | 16786.68 | 16786.68 | 16786.68 | 16786.68
40 | 490 | Place only Type 2.1 | m3 | 33426.4325 | 488 | 488 | 85.99 | 41963.12 | 41963.12 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 48.8 | 10% | 365.8 | 74.96% | 488 | 100% | 488 | 100% | 488 | 100% | 488 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4196.312 | 31455.142 | 41963.12 | 41963.12 | 41963.12 | 41963.12
41 | 538 | Special Item - Geogrid layer | m2 | 11638.8864 | 1953 | 1953 | 7.49 | 14627.97 | 14627.97 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 195 | 9.985% | 1953 | 100% | 1953 | 100% | 1953 | 100% | 1953 | 100% | 1953 | 100% | 1953 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1460.55 | 14627.97 | 14627.97 | 14627.97 | 14627.97 | 14627.97 | 14627.97
42 | 539 | Special Item - Geotextile layer | m2 | 3088.6524 | 1953 | 1953 | 1.99 | 3886.47 | 3886.47 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 195 | 9.985% | 1953 | 100% | 1953 | 100% | 1953 | 100% | 1953 | 100% | 1953 | 100% | 1953 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388.05 | 3886.47 | 3886.47 | 3886.47 | 3886.47 | 3886.47 | 3886.47
43 | 551. C244(a) | (vii) AMC5 | m2 | 15430.086 | 1812 | 1812 | 8.73 | 15818.76 | 15818.76 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1812 | 100% | 1812 | 100% | 1812 | 100% | 1812 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15818.76 | 15818.76 | 15818.76 | 15818.76
| C245(c) | Dense Graded Asphalt in Wearing Course
44 | 574. C245(c) | (ii) 14mm Nominal Size | tonne | 50317.05 | 173 | 173 | 298.12 | 51574.76 | 51574.76 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 173 | 100% | 173 | 100% | 173 | 100% | 173 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51574.76 | 51574.76 | 51574.76 | 51574.76
SUB-TOTAL
MISCELLANEOUS
| C271 | MINOR CONCRETE WORKS
45 | 788. C271(c) | (i) 100mm thick concrete footpath | m2 | 3775.1311 | 53 | 53 | 89.48 | 4742.44 | 4742.44 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 53 | 100% | 53 | 100% | 53 | 100% | 53 | 100% | 53 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4742.44 | 4742.44 | 4742.44 | 4742.44 | 4742.44
46 | 789. C271(c) | (ii) Concrete Kerb Ramp | each | 1570 | 2 | 2 | 986.14 | 1972.28 | 1972.28 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1972.28 | 1972.28 | 1972.28 | 1972.28 | 1972.28
47 | 792. C271(c) | (v) Industrial Invert Crossing | each | 1534.57 | 1 | 1 | 1927.77 | 1927.77 | 1927.77 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1927.77 | 1927.77 | 1927.77 | 1927.77 | 1927.77
| C273 | LANDSCAPE
48 | 831. C273(a) | (ii) Turfing | m2 | 1338.75 | 150 | 150 | 11.21 | 1681.5 | 1681.5 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 150 | 100% | 150 | 100% | 150 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1681.5 | 1681.5 | 1681.5
49 |  | Supply and place Imported Topsoil | m3 | 972.5 | 15 | 15 | 81.45 | 1221.75 | 1221.75 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 15 | 100% | 15 | 100% | 15 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1221.75 | 1221.75 | 1221.75
SUB-TOTAL
SPECIFIED WORKS
50 |  | Special Item - As Constructed Survey and Plans | Lump | 4500 | 1 | 1 | 5653.03 | 5653.03 | 5653.03 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.4 | 40% | 0.6 | 60% | 0.6 | 60% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2261.212 | 3391.818 | 3391.818 | 5653.03 | 5653.03 | 5653.03
SUB-TOTAL
|  | TOTAL | [5 empty] | 329438.42
CULTURAL CENTRE CAR PARK
QUALITY SYSTEM
| CQC | QUALITY CONTROL REQUIREMENTS
51 | 104. QCP1 | Quality Verification & Control | Lump | 8360 | 1 | 1 | 10502.06 | 10502.06 | 10502.06 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.1 | 10% | 0.1 | 10% | 0.5 | 50% | 0.85 | 85% | 0.95 | 95% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 1050.206 | 1050.206 | 5251.03 | 8926.751 | 9976.957 | 10502.06 | 10502.06 | 10502.06 | 10502.06
SUB-TOTAL
GENERAL REQUIREMENTS
52 | 449. C201(a) | Control of Traffic | Lump | 11646.24 | 1 | 1 | 14630.33 | 14630.33 | 14630.33 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.2 | 20% | 0.2 | 20% | 0.5 | 50% | 0.85 | 85% | 0.95 | 95% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 2926.066 | 2926.066 | 7315.165 | 12435.7805 | 13898.8135 | 14630.33 | 14630.33 | 14630.33 | 14630.33
SUB-TOTAL
ROAD & EARTHWORKS
| C213 | EARTHWORKS
53 | 125. C213(b) | General Earthworks Cut | m3 | 19053.614 | 869 | 869 | 27.54 | 23932.26 | 23932.26 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 869 | 100% | 869 | 100% | 869 | 100% | 869 | 100% | 869 | 100% | 869 | 100% | 869 | 100% | 869 | 100% | 869 | 100% | 0 | 0 | 0 | 0 | 0 | 23932.26 | 23932.26 | 23932.26 | 23932.26 | 23932.26 | 23932.26 | 23932.26 | 23932.26 | 23932.26
54 | 126. C213(c) | General Earthworks Fill | m3 | 112.2 | 4 | 4 | 35.24 | 140.96 | 140.96 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 0 | 0 | 0 | 0 | 0 | 140.96 | 140.96 | 140.96 | 140.96 | 140.96 | 140.96 | 140.96 | 140.96 | 140.96
55 | 127. C213(d) | Replace unsuitable material below sub grade with select material complete (PROVISIONAL) | m3 | 655.3333 | 10 | 10 | 65.53 | 655.3 | 655.3 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 10 | 100% | 10 | 100% | 10 | 100% | 10 | 100% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 655.3 | 655.3 | 655.3 | 655.3 | 0 | 0
56 |  | Alteration to Existing Stormwater Structures (Break new PVC pipt into existing line and andage) | Lump | 1200 | 1 | 1 | 1507.47 | 1507.47 | 1507.47 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 1507.47 | 1507.47 | 1507.47 | 1507.47 | 1507.47 | 1507.47 | 1507.47 | 1507.47 | 1507.47
57 | 310. C221(a) | UPVC pipes (150mm) supply, install, backfill complete | m | 2628 | 21 | 21 | 157.21 | 3301.41 | 3301.41 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 21 | 100% | 21 | 100% | 21 | 100% | 21 | 100% | 21 | 100% | 21 | 100% | 21 | 100% | 21 | 100% | 21 | 100% | 0 | 0 | 0 | 0 | 0 | 3301.41 | 3301.41 | 3301.41 | 3301.41 | 3301.41 | 3301.41 | 3301.41 | 3301.41 | 3301.41
58 | 314. C221(a) | Connect property drainage pipes | Lump | 3950 | 1 | 1 | 4962.1 | 4962.1 | 4962.1 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4962.1 | 4962.1 | 4962.1 | 4962.1 | 4962.1 | 4962.1 | 4962.1
59 | 459. C223(b) | Construct Complete in place, downpipe extension and overflow grate | each | 2400 | 1 | 1 | 3014.95 | 3014.95 | 3014.95 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 3014.95 | 3014.95 | 3014.95 | 3014.95 | 3014.95 | 3014.95 | 3014.95 | 3014.95 | 3014.95
60 | 472. C224(h) | (i) Concrete Barrier Kerb & Channel B1 complete | m | 4253.0419 | 80 | 80 | 66.78 | 5342.4 | 5342.4 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 80 | 100% | 80 | 100% | 80 | 100% | 80 | 100% | 80 | 100% | 80 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5342.4 | 5342.4 | 5342.4 | 5342.4 | 5342.4 | 5342.4
61 | 475. C224(h) | (iv) Concrete Dish Drain (0.9m wide) complete | m | 1560.84 | 12 | 12 | 163.4 | 1960.8 | 1960.8 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1960.8 | 1960.8 | 1960.8 | 1960.8 | 1960.8 | 1960.8 | 1960.8
62 | 477. C224(h) | (vi) Concrete Kerb (Type B2) complete | m | 4306.2049 | 81 | 81 | 66.78 | 5409.18 | 5409.18 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 81 | 100% | 81 | 100% | 81 | 100% | 81 | 100% | 81 | 100% | 81 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5409.18 | 5409.18 | 5409.18 | 5409.18 | 5409.18 | 5409.18
| C232(b) | Subsoil Drain Pipe
63 | 508. C232(b) | (i) 100mm dia Slotted Corrugated Plastic Pipe | m | 12880.0576 | 312 | 312 | 51.86 | 16180.32 | 16180.32 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 296 | 94.87% | 296 | 94.87% | 312 | 100% | 312 | 100% | 312 | 100% | 312 | 100% | 312 | 100% | 312 | 100% | 312 | 100% | 0 | 0 | 0 | 0 | 0 | 15350.56 | 15350.56 | 16180.32 | 16180.32 | 16180.32 | 16180.32 | 16180.32 | 16180.32 | 16180.32
64 | 519. C232(c) | Cleanout Structures | each | 715 | 5 | 5 | 179.64 | 898.2 | 898.2 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 898.2 | 898.2 | 898.2 | 898.2 | 898.2 | 898.2
SUB-TOTAL
| C242 | FLEXIBLE PAVEMENTS
65 | 490 | Place only Type 2.1 | m3 | 24537.3132 | 314 | 314 | 98.11 | 30806.54 | 30806.54 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 314 | 100% | 314 | 100% | 314 | 100% | 314 | 100% | 314 | 100% | 314 | 100% | 314 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30806.54 | 30806.54 | 30806.54 | 30806.54 | 30806.54 | 30806.54 | 30806.54
66 | 491 | Place only Type 2.3 | m3 | 10588.5116 | 187 | 187 | 71.13 | 13301.31 | 13301.31 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 187 | 100% | 187 | 100% | 187 | 100% | 187 | 100% | 187 | 100% | 187 | 100% | 187 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13301.31 | 13301.31 | 13301.31 | 13301.31 | 13301.31 | 13301.31 | 13301.31
67 | 538 | Special Item - Geogrid layer | m2 | 12532.8101 | 2103 | 2103 | 7.49 | 15751.47 | 15751.47 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1051 | 49.98% | 1051 | 49.98% | 2103 | 100% | 2103 | 100% | 2103 | 100% | 2103 | 100% | 2103 | 100% | 2103 | 100% | 2103 | 100% | 0 | 0 | 0 | 0 | 0 | 7871.99 | 7871.99 | 15751.47 | 15751.47 | 15751.47 | 15751.47 | 15751.47 | 15751.47 | 15751.47
68 | 539 | Special Item - Geotextile layer | m2 | 3325.8761 | 2103 | 2103 | 1.99 | 4184.97 | 4184.97 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1051 | 49.98% | 1051 | 49.98% | 2103 | 100% | 2103 | 100% | 2103 | 100% | 2103 | 100% | 2103 | 100% | 2103 | 100% | 2103 | 100% | 0 | 0 | 0 | 0 | 0 | 2091.49 | 2091.49 | 4184.97 | 4184.97 | 4184.97 | 4184.97 | 4184.97 | 4184.97 | 4184.97
69 | 551. C244(a) | (vii) AMC5 | m2 | 16781.94 | 2103 | 2103 | 8.18 | 17202.54 | 17202.54 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2103 | 100% | 2103 | 100% | 2103 | 100% | 2103 | 100% | 2103 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17202.54 | 17202.54 | 17202.54 | 17202.54 | 17202.54
70 | 574. C245(c) | (ii) 14mm Nominal Size | tonne | 58539.6 | 202 | 202 | 297.04 | 60002.08 | 60002.08 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 202 | 100% | 202 | 100% | 202 | 100% | 202 | 100% | 202 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60002.08 | 60002.08 | 60002.08 | 60002.08 | 60002.08
SUB-TOTAL
| C261 | PAVEMENT MARKINGS
71 | 657. C261(a) | Pavement Marking Paint - Longitudinal Lines including car parking bays | m | 5000 | 434 | 434 | 14.47 | 6279.98 | 6279.98 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 434 | 100% | 434 | 100% | 434 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6279.98 | 6279.98 | 6279.98
72 | 658. C261(b) | Pavement Marking Paint - Transverse Lines, Symbols, Legends, Arrows, Chevrons, Traffic Islands & Kerbs | Item | 1500 | 1 | 1 | 1884.34 | 1884.34 | 1884.34 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1884.34 | 1884.34 | 1884.34
73 | 788. C271(c) | (i) 100mm thick concrete footpath | m2 | 12821.2 | 180 | 180 | 89.48 | 16106.4 | 16106.4 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 180 | 100% | 180 | 100% | 180 | 100% | 180 | 100% | 180 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16106.4 | 16106.4 | 16106.4 | 16106.4 | 16106.4
74 | 789. C271(c) | (ii) Concrete Kerb Ramp | each | 3925 | 5 | 5 | 986.14 | 4930.7 | 4930.7 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4930.7 | 4930.7 | 4930.7 | 4930.7 | 4930.7
75 | 791. C271(c) | (iv) Residential Invert Crossing | each | 620.4533 | 1 | 1 | 779.43 | 779.43 | 779.43 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 779.43 | 779.43 | 779.43 | 779.43 | 779.43
76 | 792. C271(c) | (v) Industrial Invert Crossing | each | 1534.57 | 1 | 1 | 1927.77 | 1927.77 | 1927.77 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1927.77 | 1927.77 | 1927.77 | 1927.77
77 |  | Special Item - Supply & Install Tactile Marking | Lump | 5000 | 1 | 1 | 6281.14 | 6281.14 | 6281.14 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6281.14 | 6281.14 | 6281.14 | 6281.14
SUB-TOTAL
SPECIFIED WORKS
78 |  | Special Item - As Constructed Survey and Plans | Lump | 2500 | 1 | 1 | 3140.57 | 3140.57 | 3140.57 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1570.285 | 3140.57 | 3140.57 | 3140.57 | 3140.57
SUB-TOTAL
|  | TOTAL | [5 empty] | 275016.98
DOBBINS LANE WATER MAIN
79 | 1 | Excavate and backfil all materials for following diameter water mains, approved backfill under roads, testing of backfill compaction, disposal of surplus materials and restoration of surfaces: | m | 7020 | 156 | 156 | 56.53 | 8818.68 | 8818.68 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 100 | 64.1% | 156 | 100% | 156 | 100% | 156 | 100% | 156 | 100% | 156 | 100% | 156 | 100% | 156 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 5653 | 8818.68 | 8818.68 | 8818.68 | 8818.68 | 8818.68 | 8818.68 | 8818.68
| 2 | Supply & place materials, following diameter water mains
80 |  | 100mm dia. DICL Class PN35 | m | 39000 | 156 | 156 | 314.06 | 48993.36 | 48993.36 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 100 | 64.1% | 156 | 100% | 156 | 100% | 156 | 100% | 156 | 100% | 156 | 100% | 156 | 100% | 156 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 31406 | 48993.36 | 48993.36 | 48993.36 | 48993.36 | 48993.36 | 48993.36 | 48993.36
| 3 | Supply materials and install hydrants to the following diameter mains complete including hydrant tee/bend, riser, hydrant box, concrete surround and kerb/pavement marking:
81 |  | 100mm dia. | No. | 4000 | 2 | 2 | 2512.46 | 5024.92 | 5024.92 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 50% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 2512.46 | 5024.92 | 5024.92 | 5024.92 | 5024.92 | 5024.92 | 5024.92 | 5024.92
| 4 | Supply materials and install sluice valves to the following diameter mains complete including jointing, margin setts, boxes and kerb/pavement marking
81.5 |  | 100mm dia. | No. | 6000 | 3 | 3 | 2512.46 | 7537.38 | 7537.38 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1.5 | 50% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 3768.69 | 7537.38 | 7537.38 | 7537.38 | 7537.38 | 7537.38 | 7537.38 | 7537.38
| 5 | Supply materials and install the following internally lined and externally coated DICL fittings including bed, lay, joint, backfill and thrust blocks:
Tee:
82 |  | 100mm x 100mm. | No. | 220 | 1 | 1 | 276.37 | 276.37 | 276.37 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 138.185 | 276.37 | 276.37 | 276.37 | 276.37 | 276.37 | 276.37 | 276.37
Bend:
83 |  | 100mm x 45 degree. | No. | 960 | 6 | 6 | 201 | 1206 | 1206 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 3 | 50% | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 603 | 1206 | 1206 | 1206 | 1206 | 1206 | 1206 | 1206
Gibault:
84 |  | 100mm | No. | 800 | 3 | 3 | 334.99 | 1004.97 | 1004.97 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1.5 | 50% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 502.485 | 1004.97 | 1004.97 | 1004.97 | 1004.97 | 1004.97 | 1004.97 | 1004.97
Thrust Flange:
85 |  | 100mm | No. | 250 | 1 | 1 | 314.06 | 314.06 | 314.06 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 157.03 | 314.06 | 314.06 | 314.06 | 314.06 | 314.06 | 314.06 | 314.06
| 6 | Supply materials and install property service connections
86 |  | Single connection with road crossing | No. | 8400 | 4 | 4 | 2638.08 | 10552.32 | 10552.32 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10552.32 | 10552.32 | 10552.32 | 10552.32 | 10552.32 | 10552.32 | 10552.32
87 |  | Double connection with road crossing | No. | 4320 | 2 | 2 | 2713.45 | 5426.9 | 5426.9 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5426.9 | 5426.9 | 5426.9 | 5426.9 | 5426.9 | 5426.9 | 5426.9
88 | 7 | Sterilisation of mains including supply of chlorine, water for chlorination and bacteriological sampling and testing. | Item | 2000 | 1 | 1 | 2512.46 | 2512.46 | 2512.46 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2512.46 | 2512.46 | 2512.46 | 2512.46 | 2512.46 | 2512.46 | 2512.46
89 | 8 | Locate existing water main and arrange connection of new water main. (Work by WRC). | PC It | 5400 | 1 | 1 | 6783.63 | 6783.63 | 6783.63 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6783.63 | 6783.63 | 6783.63 | 6783.63 | 6783.63 | 6783.63 | 6783.63
90 | 9 | Special Item - As Constructed Survey and Plans | Item | 4000 | 1 | 1 | 5024.91 | 5024.91 | 5024.91 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.5 | 50% | 0.9 | 90% | 0.95 | 95% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2512.455 | 4522.419 | 4773.6645 | 5024.91 | 5024.91 | 5024.91 | 5024.91
|  | TOTAL | [5 empty] | 103475.96
DODD STREET
QUALITY SYSTEM
| CQC | QUALITY CONTROL REQUIREMENTS
91 | 104. QCP1 | Quality Verification & Control | Lump | 13160 | 1 | 1 | 16531.96 | 16531.96 | 16531.96 |  | 0% |  | 0% |  | 0% | 0.25 | 25% | 0.35 | 35% | 0.75 | 75% | 0.85 | 85% | 0.95 | 95% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 4132.99 | 5786.186 | 12398.97 | 14052.166 | 15705.362 | 16531.96 | 16531.96 | 16531.96 | 16531.96 | 16531.96 | 16531.96
SUB-TOTAL
GENERAL REQUIREMENTS
| C101 | GENERAL
| 107. C101(b) | Site Establishment & Disestablishment | Lump |  | 1 | 1 |  |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUB-TOTAL
ROAD & EARTHWORKS
| C201 | CONTROL OF TRAFFIC
92 | 449. C201(a) | Control of Traffic | Lump | 23292.48 | 1 | 1 | 29260.66 | 29260.66 | 29260.66 |  | 0% |  | 0% |  | 0% | 0.25 | 25% | 0.35 | 35% | 0.75 | 75% | 0.85 | 85% | 0.95 | 95% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 7315.165 | 10241.231 | 21945.495 | 24871.561 | 27797.627 | 29260.66 | 29260.66 | 29260.66 | 29260.66 | 29260.66 | 29260.66
| C211 | CONTROL OF EROSION & SEDIMENTATION
93 | 114. C211(a) | Temporary Erosion & Sedimentation Control (includes supply and installation of all components) | Lump | 11050 | 1 | 1 | 13881.32 | 13881.32 | 13881.32 |  | 0% |  | 0% |  | 0% | 0.25 | 25% | 0.35 | 35% | 0.75 | 75% | 0.85 | 85% | 0.95 | 95% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 3470.33 | 4858.462 | 10410.99 | 11799.122 | 13187.254 | 13881.32 | 13881.32 | 13881.32 | 13881.32 | 13881.32 | 13881.32
| C212 | CLEARING & GRUBBING
94 | 113 | Special Item - Demolition of Structure (concrete slabs, culverts, pipes etc) | Lump | 10066.6667 | 1 | 1 | 13646.79 | 13646.79 | 13646.79 |  | 0% |  | 0% |  | 0% | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 6823.395 | 13646.79 | 13646.79 | 13646.79 | 13646.79 | 13646.79 | 13646.79 | 13646.79 | 13646.79 | 13646.79 | 13646.79
| C213 | EARTHWORKS
95 | 125. C213(b) | General Earthworks Cut | m3 | 29655.2414 | 1430 | 1430 | 26.05 | 37251.5 | 37251.5 |  | 0% |  | 0% |  | 0% | 473 | 33.08% | 1073 | 75.03% | 1430 | 100% | 1430 | 100% | 1430 | 100% | 1430 | 100% | 1430 | 100% | 1430 | 100% | 1430 | 100% | 1430 | 100% | 1430 | 100% | 0 | 0 | 0 | 12321.65 | 27951.65 | 37251.5 | 37251.5 | 37251.5 | 37251.5 | 37251.5 | 37251.5 | 37251.5 | 37251.5 | 37251.5
SUB-TOTAL
STORMWATER DRAINAGE
| C220 | STORMWATER DRAINAGE - GENERAL
96 | 137 | Removal / Demolition of Drainage Components complete | Lump | 5490.9091 | 1 | 1 | 6829.54 | 6829.54 | 6829.54 |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 6829.54 | 6829.54 | 6829.54 | 6829.54 | 6829.54 | 6829.54 | 6829.54 | 6829.54 | 6829.54 | 6829.54 | 6829.54
97 | 138 | Alteration to Existing Stormwater Structures (Break new RCP's into existing RCBC - 4 Nos) | Lump | 9600 | 1 | 1 | 12059.79 | 12059.79 | 12059.79 |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 12059.79 | 12059.79 | 12059.79 | 12059.79 | 12059.79 | 12059.79 | 12059.79 | 12059.79 | 12059.79 | 12059.79 | 12059.79
| C221 | PIPE DRAINAGE (SUPPLY & INSTALL)
98 | 158. C221(a) | 375mm dia Class 2, Flush Joint | m | 1893.5897 | 7.32 | 7.32 | 324.36 | 2374.32 | 2374.3152 |  | 0% |  | 0% |  | 0% | 7.32 | 100% | 7.32 | 100% | 7.32 | 100% | 7.32 | 100% | 7.32 | 100% | 7.32 | 100% | 7.32 | 100% | 7.32 | 100% | 7.32 | 100% | 7.32 | 100% | 7.32 | 100% | 0 | 0 | 0 | 2374.3152 | 2374.3152 | 2374.3152 | 2374.3152 | 2374.3152 | 2374.3152 | 2374.3152 | 2374.3152 | 2374.3152 | 2374.3152 | 2374.3152
99 | 158. C221(a) | 375mm dia Class 3, Flush Joint | m | 2668.5073 | 17.08 | 17.08 | 196.38 | 3354.17 | 3354.1704 |  | 0% |  | 0% |  | 0% | 17.08 | 100% | 17.08 | 100% | 17.08 | 100% | 17.08 | 100% | 17.08 | 100% | 17.08 | 100% | 17.08 | 100% | 17.08 | 100% | 17.08 | 100% | 17.08 | 100% | 17.08 | 100% | 0 | 0 | 0 | 3354.1704 | 3354.1704 | 3354.1704 | 3354.1704 | 3354.1704 | 3354.1704 | 3354.1704 | 3354.1704 | 3354.1704 | 3354.1704 | 3354.1704
100 | 314. C221(a) | Renew Property Drainage connections | Lump | 6320 | 1 | 1 | 7939.36 | 7939.36 | 7939.36 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.82 | 82% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 6510.2752 | 7939.36 | 7939.36 | 7939.36 | 7939.36 | 7939.36 | 7939.36 | 7939.36 | 7939.36
| C223 | DRAINAGE STRUCTURES
101 | 443. C223(b) | MCC Type A Gully Pit | each | 14020 | 4 | 4 | 4403.08 | 17612.32 | 17612.32 |  | 0% |  | 0% |  | 0% | 4 | 100% | 3 | 75% | 3 | 75% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 0 | 0 | 0 | 17612.32 | 13209.24 | 13209.24 | 17612.32 | 17612.32 | 17612.32 | 17612.32 | 17612.32 | 17612.32 | 17612.32 | 17612.32
| C224 | OPEN DRAINS, INCLUDING KERB & CHANNEL
102 | 472. C224(h) | (i) Concrete Barrier Kerb & Channel B1 complete | m | 27857.4242 | 524 | 524 | 66.79 | 34997.96 | 34997.96 |  | 0% |  | 0% |  | 0% |  | 0% | 250 | 47.71% | 250 | 47.71% | 524 | 100% | 524 | 100% | 524 | 100% | 524 | 100% | 524 | 100% | 524 | 100% | 524 | 100% | 524 | 100% | 0 | 0 | 0 | 0 | 16697.5 | 16697.5 | 34997.96 | 34997.96 | 34997.96 | 34997.96 | 34997.96 | 34997.96 | 34997.96 | 34997.96
103 | 473. C224(h) | (ii) Concrete Mountable Kerb & Channel M1 complete | m | 2354.94 | 42 | 130 | 70.44 | 2958.48 | 9157.2 |  | 0% |  | 0% |  | 0% |  | 0% | 42 | 32.31% | 42 | 32.31% | 42 | 32.31% | 42 | 32.31% | 42 | 32.31% | 42 | 32.31% | 42 | 32.31% | 42 | 32.31% | 42 | 32.31% | 42 | 32.31% | 0 | 0 | 0 | 0 | 2958.48 | 2958.48 | 2958.48 | 2958.48 | 2958.48 | 2958.48 | 2958.48 | 2958.48 | 2958.48 | 2958.48
SUB-TOTAL
SUB-SURFACE DRAINAGE
| C231 | SUBSOIL & FOUNDATION DRAINS
104 | 508. C232(b) | (i) 100mm dia Slotted Corrugated Plastic Pipe | m | 20269.5778 | 491 | 491 | 51.86 | 25463.26 | 25463.26 |  | 0% |  | 0% |  | 0% |  | 0% | 450 | 91.65% | 450 | 91.65% | 491 | 100% | 491 | 100% | 491 | 100% | 491 | 100% | 491 | 100% | 491 | 100% | 491 | 100% | 491 | 100% | 0 | 0 | 0 | 0 | 23337 | 23337 | 25463.26 | 25463.26 | 25463.26 | 25463.26 | 25463.26 | 25463.26 | 25463.26 | 25463.26
105 | 519. C232(c) | Cleanout Structures | each | 2002 | 14 | 14 | 179.64 | 2514.96 | 2514.96 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 12 | 85.71% | 14 | 100% | 14 | 100% | 14 | 100% | 14 | 100% | 14 | 100% | 14 | 100% | 14 | 100% | 14 | 100% | 0 | 0 | 0 | 0 | 0 | 2155.68 | 2514.96 | 2514.96 | 2514.96 | 2514.96 | 2514.96 | 2514.96 | 2514.96 | 2514.96
SUB-TOTAL
PAVEMENTS
| C242 | FLEXIBLE PAVEMENTS
106 | 491 | Place only Type 2.3 (cement modified) | m3 | 29500.6126 | 521 | 521 | 71.13 | 37058.73 | 37058.73 |  | 0% |  | 0% |  | 0% | 170 | 32.63% | 224 | 42.99% | 312.6 | 60% | 521 | 100% | 521 | 100% | 521 | 100% | 521 | 100% | 521 | 100% | 521 | 100% | 521 | 100% | 521 | 100% | 0 | 0 | 0 | 12092.1 | 15933.12 | 22235.238 | 37058.73 | 37058.73 | 37058.73 | 37058.73 | 37058.73 | 37058.73 | 37058.73 | 37058.73
107 | 490 | Place only Type 2.1 | m3 | 27437.0975 | 345 | 345 | 99.92 | 34472.4 | 34472.4 |  | 0% |  | 0% |  | 0% |  | 0% | 48 | 13.91% | 295 | 85.51% | 345 | 100% | 345 | 100% | 345 | 100% | 345 | 100% | 345 | 100% | 345 | 100% | 345 | 100% | 345 | 100% | 0 | 0 | 0 | 0 | 4796.16 | 29476.4 | 34472.4 | 34472.4 | 34472.4 | 34472.4 | 34472.4 | 34472.4 | 34472.4 | 34472.4
108 | 539 | Special Item - Geotextile layer | m2 | 4423.431 | 2797 | 2797 | 1.99 | 5566.03 | 5566.03 |  | 0% |  | 0% |  | 0% | 880 | 31.46% | 2377 | 84.98% | 2657 | 94.99% | 2797 | 100% | 2797 | 100% | 2797 | 100% | 2797 | 100% | 2797 | 100% | 2797 | 100% | 2797 | 100% | 2797 | 100% | 0 | 0 | 0 | 1751.2 | 4730.23 | 5287.43 | 5566.03 | 5566.03 | 5566.03 | 5566.03 | 5566.03 | 5566.03 | 5566.03 | 5566.03
| C244 | SPRAYED BITUMINOUS SURFACING
| C244(a) | Supply & Spray Primer, supply & spread aggregates, Primerbinder (including preparation of surface) complete
109 | 551. C244(a) | (vii) AMC5 | m2 | 18617.067 | 2466 | 2466 | 7.74 | 19086.84 | 19086.84 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2000 | 81.1% | 2466 | 100% | 2466 | 100% | 2466 | 100% | 2466 | 100% | 2466 | 100% | 2466 | 100% | 2466 | 100% | 2466 | 100% | 0 | 0 | 0 | 0 | 0 | 15480 | 19086.84 | 19086.84 | 19086.84 | 19086.84 | 19086.84 | 19086.84 | 19086.84 | 19086.84
| C245 | ASPHALTIC CONCRETE
| C245(c) | Dense Graded Asphalt in Wearing Course
110 | 574. C245(c) | (ii) 14mm Nominal Size | tonne | 80186.4 | 296 | 296 | 277.67 | 82190.32 | 82190.32 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 296 | 100% | 296 | 100% | 296 | 100% | 296 | 100% | 296 | 100% | 296 | 100% | 296 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82190.32 | 82190.32 | 82190.32 | 82190.32 | 82190.32 | 82190.32 | 82190.32
SUB-TOTAL
ROAD FURNISHINGS
| C261 | PAVEMENT MARKINGS
111 | 658. C261(b) | Pavement Marking Paint - Transverse Lines, Symbols, Legends, Arrows, Chevrons, Traffic Islands & Kerbs | Item | 2000 | 2 | 2 | 1256.23 | 2512.46 | 2512.46 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2512.46 | 2512.46 | 2512.46
112 | 678. C262(g) | Remove and reinstate Existing Signs & Support Structures | Item | 472 | 2 | 2 | 296.47 | 592.94 | 592.94 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 50% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 296.47 | 592.94 | 592.94 | 592.94 | 592.94 | 592.94 | 592.94 | 592.94
SUB-TOTAL
MISCELLANEOUS
| C271 | MINOR CONCRETE WORKS
| C271(c) | Footpaths, Bike paths, Driveways, Median Toppings & Works of Similar Nature
113 | 791. C271(c) | (iv) Residential Invert Crossing | each | 3363.9733 | 7 | 8 | 603.7 | 4225.9 | 4829.6 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 7 | 87.5% | 7 | 87.5% | 7 | 87.5% | 7 | 87.5% | 7 | 87.5% | 7 | 87.5% | 7 | 87.5% | 7 | 87.5% | 7 | 87.5% | 0 | 0 | 0 | 0 | 0 | 4225.9 | 4225.9 | 4225.9 | 4225.9 | 4225.9 | 4225.9 | 4225.9 | 4225.9 | 4225.9
113.5 |  | Residential driveways | m2 |  | 55 | 55 | 89.48 | 4921.4 | 4921.4 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 55 | 100% | 55 | 100% | 55 | 100% | 55 | 100% | 55 | 100% | 55 | 100% | 55 | 100% | 55 | 100% | 55 | 100% | 0 | 0 | 0 | 0 | 0 | 4921.4 | 4921.4 | 4921.4 | 4921.4 | 4921.4 | 4921.4 | 4921.4 | 4921.4 | 4921.4
SUB-TOTAL
SERVICES
| C320 | WATER RETICULATION
|  | Reinstate Existing water main | Lump |  | 1 | 1 |  |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUB-TOTAL
SPECIFIED WORKS
114 | 1300 | Special Item - As Constructed Survey and Plans | Lump | 2500 | 1 | 1 | 3140.57 | 3140.57 | 3140.57 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.8 | 80% | 0.9 | 90% | 0.95 | 95% | 0.95 | 95% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 2512.456 | 2826.513 | 2983.5415 | 2983.5415 | 3140.57 | 3140.57 | 3140.57 | 3140.57
SUB-TOTAL
|  | TOTAL | [5 empty] | 420443.98
DOHERTY STREET
QUALITY SYSTEM
| CQC | QUALITY CONTROL REQUIREMENTS
115 | 104. QCP1 | Quality Verification & Control | Lump | 9760 | 1 | 1 | 12260.78 | 12260.78 | 12260.78 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.1 | 10% | 0.5 | 50% | 0.75 | 75% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1226.078 | 6130.39 | 9195.585 | 12260.78 | 12260.78 | 12260.78
SUB-TOTAL
GENERAL REQUIREMENTS
| C101 | GENERAL
| 107. C101(b) | Site Establishment & Disestablishment | Lump |  | 1 | 1 |  |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUB-TOTAL
ROAD & EARTHWORKS
| C201 | CONTROL OF TRAFFIC
116 | 449. C201(a) | Control of Traffic | Lump | 23292.48 | 1 | 1 | 29260.65 | 29260.65 | 29260.65 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.1 | 10% | 0.5 | 50% | 0.75 | 75% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2926.065 | 14630.325 | 21945.4875 | 29260.65 | 29260.65 | 29260.65
| C213 | EARTHWORKS
117 | 125. C213(b) | General Earthworks Cut | m3 | 13017.3001 | 652 | 652 | 25.08 | 16352.16 | 16352.16 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 326 | 50% | 652 | 100% | 652 | 100% | 652 | 100% | 652 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8176.08 | 16352.16 | 16352.16 | 16352.16 | 16352.16
118 | 126. C213(c) | General Earthworks Fill (Fill behind kerb to boundary) | m3 | 2917.2 | 104 | 104 | 35.24 | 3664.96 | 3664.96 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 104 | 100% | 104 | 100% | 104 | 100% | 104 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3664.96 | 3664.96 | 3664.96 | 3664.96
119 | 127. C213(d) | Replace unsuitable material below sub grade with select material complete (PROVISIONAL) | m3 | 4259.6667 | 65 | 65 | 65.53 | 4259.45 | 4259.45 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 65 | 100% | 65 | 100% | 65 | 100% | 65 | 100% | 65 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4259.45 | 4259.45 | 4259.45 | 4259.45 | 4259.45
SUB-TOTAL
STORMWATER DRAINAGE
| C220 | STORMWATER DRAINAGE - GENERAL
119.5 | 136 | Excavation for Stormwater Drainage Culverts and structures | m3 |  | 100 | 100 | 28.35 | 2835 | 2835 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2835 | 2835 | 2835 | 2835 | 2835
120 | 137 | Removal / Demolition of Drainage Components complete | Lump | 5490.9091 | 2 | 2 | 3414.77 | 6829.54 | 6829.54 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6829.54 | 6829.54 | 6829.54 | 6829.54 | 6829.54
121 |  | Relocate existing kerb adapter and roofwater connection from property | Item | 790 | 2 | 2 | 496.21 | 992.42 | 992.42 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992.42 | 992.42 | 992.42 | 992.42
| C221 | PIPE DRAINAGE (SUPPLY & INSTALL)
122 | C221(a) | STEEL REINFORCED CONCRETE |  | 12899.4519
123 | 167. C221(a) | 450mm Dia Class 2 Flush Joint | m | 2280.6627 | 12.2 | 12.2 | 294.41 | 3591.8 | 3591.802 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 6.1 | 50% | 12.2 | 100% | 12.2 | 100% | 12.2 | 100% | 12.2 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1795.901 | 3591.802 | 3591.802 | 3591.802 | 3591.802
C221(a)
| C221(a) | FIBRE REINFORCED CEMENT
124 | 297. C221(a) | 450mm dia Class 2, Rubber Ring Joint | m | 5354.3514 | 30 | 30 | 224.11 | 6723.3 | 6723.3 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 30 | 100% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6723.3 | 0 | 0 | 0
| C222 | PRECAST BOX CULVERTS (SUPPLY & INSTALL)
125 | 330. C222(b) | 900 x 450 | m | 7752.5 | 41 | 41 | 811.58 | 33274.78 | 33274.78 |  | 0% |  | 0% |  | 0% |  | 0% | 6 | 14.63% | 6 | 14.63% | 6 | 14.63% | 6 | 14.63% | 6 | 14.63% | 9 | 21.95% | 12 | 29.27% | 41 | 100% | 41 | 100% | 41 | 100% | 0 | 0 | 0 | 0 | 4869.48 | 4869.48 | 4869.48 | 4869.48 | 4869.48 | 7304.22 | 9738.96 | 33274.78 | 33274.78 | 33274.78
126 | 334. C222(b) | 1200 x 450 | m | 50229.5 | 70 | 70 | 717.04 | 50192.8 | 50192.8 |  | 0% |  | 0% |  | 0% |  | 0% | 44 | 62.86% | 44 | 62.86% | 44 | 62.86% | 44 | 62.86% | 44 | 62.86% | 70 | 100% | 70 | 100% | 70 | 100% | 70 | 100% | 70 | 100% | 0 | 0 | 0 | 0 | 31549.76 | 31549.76 | 31549.76 | 31549.76 | 31549.76 | 50192.8 | 50192.8 | 50192.8 | 50192.8 | 50192.8
127 | 335. C222(b) | 1200 x 600 | m | 7274.5 | 8 | 8 | 913.84 | 7310.72 | 7310.72 |  | 0% |  | 0% |  | 0% |  | 0% | 5 | 62.5% | 5 | 62.5% | 5 | 62.5% | 5 | 62.5% | 5 | 62.5% | 7.5 | 93.75% | 10 | 125% | 10 | 125% | 10 | 125% | 10 | 125% | 0 | 0 | 0 | 0 | 4569.2 | 4569.2 | 4569.2 | 4569.2 | 4569.2 | 6853.8 | 9138.4 | 9138.4 | 9138.4 | 9138.4
127.5 | 344. C222(b) | 1800x600 | m |  | 1.2 | 1.2 | 913.84 | 1096.61 | 1096.608 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.6 | 50% | 1.2 | 100% | 1.2 | 100% | 1.2 | 100% | 1.2 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 548.304 | 1096.608 | 1096.608 | 1096.608 | 1096.608
| C223 | DRAINAGE STRUCTURES
128 | 418. C223(a) | Cast in situ Concrete Headwalls & Wingwalls & Aprons complete | m3 | 410.158 | 0.63 | 0.63 | 817.86 | 515.25 | 515.2518 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.63 | 100% | 0.63 | 100% | 0.63 | 100% | 0.63 | 100% | 0.63 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515.2518 | 515.2518 | 515.2518 | 515.2518 | 515.2518
| C223(b) | Pits, Dissipators, Channel Basins & Other Supplementary Structures
129 | 445. C223(b) | BRO Pit Gully Pit | each | 27181.3 | 5 | 5 | 6829.18 | 34145.9 | 34145.9 |  | 0% |  | 0% |  | 0% |  | 0% | 2.5 | 50% | 2.5 | 50% | 2.5 | 50% | 2.5 | 50% | 2.5 | 50% | 2.5 | 50% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 0 | 0 | 0 | 0 | 17072.95 | 17072.95 | 17072.95 | 17072.95 | 17072.95 | 17072.95 | 34145.9 | 34145.9 | 34145.9 | 34145.9
130 | 448. C223(b) | (v) Concrete Manholes - Cast Insitu | each | 7500 | 2 | 2 | 4710.85 | 9421.7 | 9421.7 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 50% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4710.85 | 9421.7 | 9421.7 | 9421.7 | 9421.7
| C224 | OPEN DRAINS, INCLUDING KERB & CHANNEL
| C224(h) | Kerb &/or Channel
131 | 472. C224(h) | (i) Concrete Barrier Kerb & Channel B1 complete | m | 1701.2167 | 32 | 32 | 66.78 | 2136.96 | 2136.96 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 32 | 100% | 32 | 100% | 32 | 100% | 32 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2136.96 | 2136.96 | 2136.96 | 2136.96
132 | 473. C224(h) | (ii) Concrete Mountable Kerb & Channel M1 complete | m | 10092.6 | 176 | 176 | 70.44 | 12397.44 | 12397.44 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 176 | 100% | 176 | 100% | 176 | 100% | 176 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12397.44 | 12397.44 | 12397.44 | 12397.44
SUB-TOTAL
SUB-SURFACE DRAINAGE
| C232 | PAVEMENT DRAINS
| C232(b) | Subsoil Drain Pipe
133 | 508. C232(b) | (i) 100mm dia Slotted Corrugated Plastic Pipe | m | 8669.2695 | 210 | 210 | 51.86 | 10890.6 | 10890.6 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 210 | 100% | 210 | 100% | 210 | 100% | 210 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10890.6 | 10890.6 | 10890.6 | 10890.6
134 | 519. C232(c) | Cleanout Structures | each | 858 | 6 | 6 | 179.64 | 1077.84 | 1077.84 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1077.84 | 1077.84 | 1077.84 | 1077.84
SUB-TOTAL
PAVEMENTS
| C242 | FLEXIBLE PAVEMENTS
135 | 491 | Place only Type 2.3 | m3 | 8380.2124 | 142 | 142 | 71.13 | 10100.46 | 10100.46 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 142 | 100% | 142 | 100% | 142 | 100% | 142 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10100.46 | 10100.46 | 10100.46 | 10100.46
136 | 490 | Place only Type 2.1 (828m²) | m3 | 8090.9335 | 124 | 124 | 105.87 | 13127.88 | 13127.88 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 124 | 100% | 124 | 100% | 124 | 100% | 124 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13127.88 | 13127.88 | 13127.88 | 13127.88
137 | 538 | Special item - Geogrid layer | m2 | 1467.6239 | 948 | 948 | 7.49 | 7100.52 | 7100.52 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 474 | 50% | 948 | 100% | 948 | 100% | 948 | 100% | 948 | 100% | 948 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3550.26 | 7100.52 | 7100.52 | 7100.52 | 7100.52 | 7100.52
137.5 | 539 | Special Item - Geotextile layer | m2 |  | 948 | 948 | 1.99 | 1886.52 | 1886.52 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 474 | 50% | 948 | 100% | 948 | 100% | 948 | 100% | 948 | 100% | 948 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 943.26 | 1886.52 | 1886.52 | 1886.52 | 1886.52 | 1886.52
| C244 | SPRAYED BITUMINOUS SURFACING
| C244(a) | Supply & Spray Primer, supply & spread aggregates, Primerbinder (including preparation of surface and precoated aggregate) complete
138 | 551. C244(a) | (vii) AMC5 | m2 | 13597.416 | 828 | 828 | 16.83 | 13935.24 | 13935.24 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 828 | 100% | 828 | 100% | 828 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13935.24 | 13935.24 | 13935.24
| C245 | ASPHALTIC CONCRETE
| C245(c) | Dense Graded Asphalt in Wearing Course
139 | 574. C245(c) | (ii) 14mm Nominal Size | tonne | 33384.96 | 60 | 60 | 344.4 | 20664 | 20664 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 60 | 100% | 60 | 100% | 60 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20664 | 20664 | 20664
SUB-TOTAL
ROAD FURNISHINGS
| C262 | SIGNPOSTING
140 | 678. C262(g) | Remove and reinstate Existing Signs & Support Structures | Item | 1048 | 2 | 2 | 658.26 | 1316.52 | 1316.52 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1316.52 | 1316.52 | 1316.52
| C265 | BOUNDARY FENCING
| C265(a) | Supply & Erection of Boundary Fencing
141 | 750. C265(a) | Supply & Erection of Boundary Fencing (1200 high chainlink star picket fence) | m | 1375 | 11 | 11 | 157.03 | 1727.33 | 1727.33 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 11 | 100% | 11 | 100% | 11 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727.33 | 1727.33 | 1727.33
SUB-TOTAL
MISCELLANEOUS
| C271 | MINOR CONCRETE WORKS
| C271(c) | Footpaths, Bike paths, Driveways, Median Toppings & Works of Similar Nature
142 | 791. C271(c) | (iv) Residential Invert Crossing (? m) | each | 2449.4667 | 5 | 5 | 615.42 | 3077.1 | 3077.1 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3077.1 | 3077.1 | 3077.1 | 3077.1
SUB-TOTAL
SERVICES
| C320 | WATER RETICULATION
143 | 1301 | Service connections | Lump | 7920 | 1 | 1 | 9949.32 | 9949.32 | 9949.32 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7959.456 | 9949.32 | 9949.32 | 9949.32 | 9949.32 | 9949.32
144 | 1302 | Alterations to water main | Lump | 7000 | 1 | 1 | 8793.59 | 8793.59 | 8793.59 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7034.872 | 8793.59 | 8793.59 | 8793.59 | 8793.59 | 8793.59
145 | 1303 | Alterations to valves and hydrant margins | Lump | 1000 | 1 | 1 | 1256.23 | 1256.23 | 1256.23 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1004.984 | 1256.23 | 1256.23 | 1256.23 | 1256.23 | 1256.23
SUB-TOTAL
SPECIFIED WORKS
146 |  | Special Item - As Constructed Survey and Plans | Lump | 2400 | 1 | 1 | 3014.95 | 3014.95 | 3014.95 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.5 | 50% | 0.75 | 75% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1507.475 | 2261.2125 | 3014.95 | 3014.95 | 3014.95
SUB-TOTAL
|  | TOTAL | [5 empty] | 345180.32
FAUST STREET
QUALITY SYSTEM
| CQC | QUALITY CONTROL REQUIREMENTS
147 | 104. QCP1 | Quality Verification & Control | Lump | 10470 | 1 | 1 | 13152.71 | 13152.71 | 13152.71 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6576.355 | 13152.71 | 13152.71 | 13152.71
SUB-TOTAL
GENERAL REQUIREMENTS
| C101 | GENERAL
| 107. C101(b) | Site Establishment & Disestablishment | Lump |  | 1 | 1 |  |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUB-TOTAL
ROAD & EARTHWORKS
| C201 | CONTROL OF TRAFFIC
148 | 449. C201(a) | Control of Traffic | Lump | 34938.72 | 1 | 1 | 43890.99 | 43890.99 | 43890.99 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21945.495 | 43890.99 | 43890.99 | 43890.99
| C211 | CONTROL OF EROSION & SEDIMENTATION
149 | 114. C211(a) | Temporary Erosion & Sedimentation Control (includes supply and installation of all components) | Lump | 11050 | 1 | 1 | 13881.32 | 13881.32 | 13881.32 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6940.66 | 13881.32 | 13881.32 | 13881.32
| C212 | CLEARING & GRUBBING
150 | 119. C212(a) | Clearing and Grubbing (removal of kerb & channel) | Lump | 10066.6667 | 1 | 1 | 13646.79 | 13646.79 | 13646.79 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6823.395 | 13646.79 | 13646.79 | 13646.79
| C213 | EARTHWORKS
151 | 125. C213(b) | General Earthworks Cut | m3 | 13092.3333 | 543 | 543 | 30.28 | 16442.04 | 16442.04 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 271.5 | 50% | 543 | 100% | 543 | 100% | 543 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8221.02 | 16442.04 | 16442.04 | 16442.04
152 | 127. C213(d) | Replace unsuitable material below sub grade with select material complete (provisional) | m3 | 1310.6667 | 20 | 20 | 65.53 | 1310.6 | 1310.6 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 20 | 100% | 20 | 100% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1310.6 | 1310.6 | 0 | 0
SUB-TOTAL
STORMWATER DRAINAGE
| C220 | STORMWATER DRAINAGE - GENERAL
153 | 137 | Removal / Demolition of Drainage Components complete | Lump | 5452.498 | 1 | 1 | 6829.54 | 6829.54 | 6829.54 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3414.77 | 6829.54 | 6829.54 | 6829.54
| C221 | PIPE DRAINAGE (SUPPLY & INSTALL)
| C221(a) | OTHER
154 | 314. C221(a) | Connect property drainage pipes (No. 21) | Lump | 8295 | 1 | 1 | 10420.41 | 10420.41 | 10420.41 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5210.205 | 10420.41 | 10420.41 | 10420.41
| C222 | PRECAST BOX CULVERTS (SUPPLY & INSTALL)
155 | 315. C222(a) | In-Situ reinforced concrete Base Slab for culverts complete | m3 | 1953.1333 | 3 | 3 | 817.86 | 2453.58 | 2453.58 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1.5 | 50% | 3 | 100% | 3 | 100% | 3 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1226.79 | 2453.58 | 2453.58 | 2453.58
156 | 333. C222(b) | 1200 x 300 | m | 8442.852 | 12.4 | 12.4 | 855.33 | 10606.09 | 10606.092 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 6.2 | 50% | 8.2 | 66.13% | 12.4 | 100% | 12.4 | 100% | 12.4 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5303.046 | 7013.706 | 10606.092 | 10606.092 | 10606.092
| C223 | DRAINAGE STRUCTURES
| C223(b) | Pits, Dissipators, Channel Basins & Other Supplementary Structures
157 | 443. C223(b) | MCC Type A Gully Pit | each | 14020 | 4 | 4 | 4403.08 | 17612.32 | 17612.32 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2 | 50% | 2 | 50% | 4 | 100% | 4 | 100% | 4 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8806.16 | 8806.16 | 17612.32 | 17612.32 | 17612.32
| C224 | OPEN DRAINS, INCLUDING KERB & CHANNEL
| C224(h) | Kerb &/or Channel
158 | 472. C224(h) | (i) Concrete Barrier Kerb & Channel B1 complete | m | 25252.436 | 475 | 475 | 66.79 | 31725.25 | 31725.25 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 100 | 21.05% | 475 | 100% | 475 | 100% | 475 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6679 | 31725.25 | 31725.25 | 31725.25
SUB-TOTAL
SUB-SURFACE DRAINAGE
| C231 | SUBSOIL & FOUNDATION DRAINS
159 | 496. C231(b) | Subsoil Drain Pipe - 100mm dia Slotted Corrugated Plastic Pipe complete (provisional quantity) | m | 19609.062 | 475 | 475 | 51.86 | 24633.5 | 24633.5 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 293 | 61.68% | 475 | 100% | 475 | 100% | 475 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15194.98 | 24633.5 | 24633.5 | 24633.5
SUB-TOTAL
PAVEMENTS
| C242 | FLEXIBLE PAVEMENTS
160 | 491 | Place only Type 2.3 (includes cart, place, compact & trim) | m3 | 22392.3302 | 304 | 304 | 92.54 | 28132.16 | 28132.16 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 189 | 62.17% | 304 | 100% | 304 | 100% | 304 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17490.06 | 28132.16 | 28132.16 | 28132.16
161 | 490 | Place only Type 2.1 (includes cart, place, compact & trim) | m3 | 17201.6533 | 181 | 181 | 119.38 | 21607.78 | 21607.78 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 131 | 72.38% | 181 | 100% | 181 | 100% | 181 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15638.78 | 21607.78 | 21607.78 | 21607.78
162 | 538 | Special Item - Geogrid layer | m2 | 9505.3885 | 1595 | 1595 | 7.49 | 11946.55 | 11946.55 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 996 | 62.45% | 1595 | 100% | 1595 | 100% | 1595 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7460.04 | 11946.55 | 11946.55 | 11946.55
163 | 539 | Special Item - Geotextile layer | m2 | 2522.4785 | 1595 | 1595 | 1.99 | 3174.05 | 3174.05 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 996 | 62.45% | 1595 | 100% | 1595 | 100% | 1595 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1982.04 | 3174.05 | 3174.05 | 3174.05
| C244 | SPRAYED BITUMINOUS SURFACING
| C244(a) | Supply & Spray Primer, supply & spread aggregates, Primerbinder (including preparation of surface) complete
164 | 551. C244(a) | (vii) AMC5 | m2 | 14537.124 | 1206 | 1206 | 12.36 | 14906.16 | 14906.16 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1206 | 100% | 1206 | 100% | 1206 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14906.16 | 14906.16 | 14906.16
| C245 | ASPHALTIC CONCRETE
| C245(c) | Dense Graded Asphalt in Wearing Course
165 | 573. C245(c) | (i) 10mm Nominal Size | tonne | 30256.947 | 87 | 87 | 356.48 | 31013.76 | 31013.76 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 87 | 100% | 87 | 100% | 87 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31013.76 | 31013.76 | 31013.76
SUB-TOTAL
ROAD FURNISHINGS
| C261 | PAVEMENT MARKINGS
166 | 657. C261(a) | Pavement Marking Paint - Longitudinal Lines including car parking bays | m | 4000 | 475 | 475 | 10.58 | 5025.5 | 5025.5 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 475 | 100% | 475 | 100% | 475 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5025.5 | 5025.5 | 5025.5
| C262 | SIGNPOSTING
167 | 678. C262(g) | Remove and reinstate Existing Signs & Support Structures | Item | 2832 | 1 | 1 | 3557.64 | 3557.64 | 3557.64 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3557.64 | 3557.64 | 3557.64
SUB-TOTAL
MISCELLANEOUS
| C271 | MINOR CONCRETE WORKS
| C271(c) | Footpaths, Bike paths, Driveways, Median Toppings & Works of Similar Nature
168 | 791. C271(c) | (iv) Residential Invert Crossing | each | 9765.52 | 21 | 21 | 584.18 | 12267.78 | 12267.78 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 6 | 28.57% | 21 | 100% | 21 | 100% | 21 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3505.08 | 12267.78 | 12267.78 | 12267.78
| C273 | LANDSCAPE
| C273(a) | Vegetation of Slopes 1 in 3 or Flatter
169 | 830. C273(a) | (i) Grass Seeding | m2 | 1347.5 | 500 | 500 | 3.39 | 1695 | 1695 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 500 | 100% | 500 | 100% | 500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1695 | 1695 | 1695
170 | 831. C273(a) | (ii) Turfing | m2 | 2231.25 | 250 | 250 | 11.21 | 2802.5 | 2802.5 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 250 | 100% | 250 | 100% | 250 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2802.5 | 2802.5 | 2802.5
| C273(d) | Landscape Planting
171 | 847. C273(d) | (iii) Individual Planting | each | 3000 | 4 | 4 | 942.17 | 3768.68 | 3768.68 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 4 | 100% | 4 | 100% | 4 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3768.68 | 3768.68 | 3768.68
172 | 816 | Supply and place Imported Topsoil | m3 | 2645 | 50 | 50 | 66.45 | 3322.5 | 3322.5 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 50 | 100% | 50 | 100% | 50 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3322.5 | 3322.5 | 3322.5
SUB-TOTAL
SERVICES
| C306 | ROAD OPENINGS & RESTORATION
| C306(a) | Sawcut Existing Pavement / Footpath
173 | 903. C306(a) | Sawcut Bituminous pavement | m | 3000 | 300 | 300 | 12.56 | 3768 | 3768 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 300 | 100% | 300 | 100% | 300 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3768 | 3768 | 3768
| C320 | WATER RETICULATION
174 | 1301 | Service connections | Lump | 29880 | 1 | 1 | 37536.09 | 37536.09 | 37536.09 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.4 | 40% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15014.436 | 37536.09 | 37536.09 | 37536.09
SUB-TOTAL
SPECIFIED WORKS
175 |  | Special Item - As Constructed Survey and Plans | Lump | 2400 | 1 | 1 | 3014.95 | 3014.95 | 3014.95 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.4 | 40% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1205.98 | 3014.95 | 3014.95 | 3014.95
SUB-TOTAL
|  | TOTAL | [5 empty] | 394144.24
JUPP STREET
QUALITY SYSTEM
| CQC | QUALITY CONTROL REQUIREMENTS
176 | 104. QCP1 | Quality Verification & Control | Lump | 9860 | 1 | 1 | 12386.41 | 12386.41 | 12386.41 | 0.25 | 25% | 0.5 | 50% | 0.5 | 50% | 0.6 | 60% | 0.75 | 75% | 0.8 | 80% | 0.9 | 90% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 3096.6025 | 6193.205 | 6193.205 | 7431.846 | 9289.8075 | 9909.128 | 11147.769 | 12386.41 | 12386.41 | 12386.41 | 12386.41 | 12386.41 | 12386.41 | 12386.41
SUB-TOTAL
GENERAL REQUIREMENTS
| C101 | GENERAL
| 107. C101(b) | Site Establishment & Disestablishment | Lump |  | 1 | 1 |  |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUB-TOTAL
ROAD & EARTHWORKS
| C201 | CONTROL OF TRAFFIC
177 | 449. C201(a) | Control of Traffic | Lump | 23292.48 | 1 | 1 | 29260.66 | 29260.66 | 29260.66 | 0.2 | 20% | 0.6 | 60% | 0.6 | 60% | 0.7 | 70% | 0.75 | 75% | 0.8 | 80% | 0.9 | 90% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 5852.132 | 17556.396 | 17556.396 | 20482.462 | 21945.495 | 23408.528 | 26334.594 | 29260.66 | 29260.66 | 29260.66 | 29260.66 | 29260.66 | 29260.66 | 29260.66
| C201(b) | Provision of Temporary Roadways, Side-tracks and Detours | Lump |  | 1 | 1 |  |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| C211 | CONTROL OF EROSION & SEDIMENTATION
178 | 114. C211(a) | Temporary Erosion & Sedimentation Control (includes supply and installation of all components) | Lump | 11050 | 1 | 1 | 13881.32 | 13881.32 | 13881.32 | 0.2 | 20% | 0.6 | 60% | 0.6 | 60% | 0.7 | 70% | 0.75 | 75% | 0.8 | 80% | 0.9 | 90% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 2776.264 | 8328.792 | 8328.792 | 9716.924 | 10410.99 | 11105.056 | 12493.188 | 13881.32 | 13881.32 | 13881.32 | 13881.32 | 13881.32 | 13881.32 | 13881.32
| C212 | CLEARING & GRUBBING
179 | 113 | Special Item - Demolition of Structure (concrete slabs, culverts, pipes etc) | Lump | 10066.6667 | 1 | 1 | 13646.79 | 13646.79 | 13646.79 | 0.6 | 60% | 0.6 | 60% | 0.6 | 60% | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 8188.074 | 8188.074 | 8188.074 | 10917.432 | 13646.79 | 13646.79 | 13646.79 | 13646.79 | 13646.79 | 13646.79 | 13646.79 | 13646.79 | 13646.79 | 13646.79
| C213 | EARTHWORKS
180 | 124. C213(a) | Removal & Stockpiling of Topsoil for reuse (100mm thick nom.) | m3 | 2613.5614 | 155 | 155 | 21.18 | 3282.9 | 3282.9 |  | 0% | 38 | 24.52% | 38 | 24.52% | 138 | 89.03% | 155 | 100% | 155 | 100% | 155 | 100% | 155 | 100% | 155 | 100% | 155 | 100% | 155 | 100% | 155 | 100% | 155 | 100% | 155 | 100% | 0 | 804.84 | 804.84 | 2922.84 | 3282.9 | 3282.9 | 3282.9 | 3282.9 | 3282.9 | 3282.9 | 3282.9 | 3282.9 | 3282.9 | 3282.9
181 | 125. C213(b) | General Earthworks Cut | m3 | 15596.6371 | 775 | 775 | 25.28 | 19592 | 19592 | 324 | 41.81% | 324 | 41.81% | 324 | 41.81% | 724 | 93.42% | 775 | 100% | 775 | 100% | 775 | 100% | 775 | 100% | 775 | 100% | 775 | 100% | 775 | 100% | 775 | 100% | 775 | 100% | 775 | 100% | 8190.72 | 8190.72 | 8190.72 | 18302.72 | 19592 | 19592 | 19592 | 19592 | 19592 | 19592 | 19592 | 19592 | 19592 | 19592
182 | 126. C213(c) | General Earthworks Fill | m3 | 757.35 | 27 | 27 | 35.24 | 951.48 | 951.48 |  | 0% |  | 0% |  | 0% | 20 | 74.07% | 27 | 100% | 27 | 100% | 27 | 100% | 27 | 100% | 27 | 100% | 27 | 100% | 27 | 100% | 27 | 100% | 27 | 100% | 27 | 100% | 0 | 0 | 0 | 704.8 | 951.48 | 951.48 | 951.48 | 951.48 | 951.48 | 951.48 | 951.48 | 951.48 | 951.48 | 951.48
183 | 127. C213(d) | Replace unsuitable material below sub grade with select material complete (PROVISIONAL) | m3 | 1310.6667 | 20 | 20 | 65.53 | 1310.6 | 1310.6 |  | 0% |  | 0% |  | 0% |  | 0% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 0 | 0 | 0 | 0 | 1310.6 | 1310.6 | 1310.6 | 1310.6 | 1310.6 | 1310.6 | 1310.6 | 1310.6 | 1310.6 | 1310.6
SUB-TOTAL
STORMWATER DRAINAGE
| C220 | STORMWATER DRAINAGE - GENERAL
184 | 137 | Removal / Demolition of Drainage Components complete | Lump | 5490.9091 | 1 | 1 | 6829.54 | 6829.54 | 6829.54 | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 0.9 | 90% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 5463.632 | 5463.632 | 5463.632 | 6146.586 | 6829.54 | 6829.54 | 6829.54 | 6829.54 | 6829.54 | 6829.54 | 6829.54 | 6829.54 | 6829.54 | 6829.54
| C221 | PIPE DRAINAGE (SUPPLY & INSTALL)
185 | 314. C221(a) | Connect property drainage pipes ( 7 No.) | Lump | 2765 | 1 | 1 | 3473.47 | 3473.47 | 3473.47 |  | 0% | 0.7 | 70% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 2431.429 | 3473.47 | 3473.47 | 3473.47 | 3473.47 | 3473.47 | 3473.47 | 3473.47 | 3473.47 | 3473.47 | 3473.47 | 3473.47 | 3473.47
| C222 | PRECAST BOX CULVERTS (SUPPLY & INSTALL)
186 | 315. C222(a) | In-Situ reinforced concrete Base Slab for culverts complete | m3 | 1692.7156 | 2.6 | 2.6 | 817.86 | 2126.44 | 2126.436 |  | 0% | 1.3 | 50% | 2.6 | 100% | 2.6 | 100% | 2.6 | 100% | 2.6 | 100% | 2.6 | 100% | 2.6 | 100% | 2.6 | 100% | 2.6 | 100% | 2.6 | 100% | 2.6 | 100% | 2.6 | 100% | 2.6 | 100% | 0 | 1063.218 | 2126.436 | 2126.436 | 2126.436 | 2126.436 | 2126.436 | 2126.436 | 2126.436 | 2126.436 | 2126.436 | 2126.436 | 2126.436 | 2126.436
187 | 325. C222(b) | 750 x 300 | m | 8530.5 | 13.2 | 13.2 | 811.84 | 10716.29 | 10716.288 |  | 0% | 6.6 | 50% | 13.2 | 100% | 13.2 | 100% | 13.2 | 100% | 13.2 | 100% | 13.2 | 100% | 13.2 | 100% | 13.2 | 100% | 13.2 | 100% | 13.2 | 100% | 13.2 | 100% | 13.2 | 100% | 13.2 | 100% | 0 | 5358.144 | 10716.288 | 10716.288 | 10716.288 | 10716.288 | 10716.288 | 10716.288 | 10716.288 | 10716.288 | 10716.288 | 10716.288 | 10716.288 | 10716.288
| C223 | DRAINAGE STRUCTURES
188 | C443. 223(b) | MCC Type A Gully Pit (including chamber) | each | 3505 | 1 | 1 | 4403.08 | 4403.08 | 4403.08 |  | 0% |  | 0% | 0.9 | 90% | 0.9 | 90% | 0.9 | 90% | 0.9 | 90% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 3962.772 | 3962.772 | 3962.772 | 3962.772 | 4403.08 | 4403.08 | 4403.08 | 4403.08 | 4403.08 | 4403.08 | 4403.08 | 4403.08
| C224 | OPEN DRAINS, INCLUDING KERB & CHANNEL
189 | 472. C224(h) | (i) Concrete Barrier Kerb & Channel B1 complete | m | 16640.0263 | 313 | 313 | 66.78 | 20902.14 | 20902.14 |  | 0% | 250 | 79.87% | 250 | 79.87% | 250 | 79.87% | 250 | 79.87% | 313 | 100% | 313 | 100% | 313 | 100% | 313 | 100% | 313 | 100% | 313 | 100% | 313 | 100% | 313 | 100% | 313 | 100% | 0 | 16695 | 16695 | 16695 | 16695 | 20902.14 | 20902.14 | 20902.14 | 20902.14 | 20902.14 | 20902.14 | 20902.14 | 20902.14 | 20902.14
190 | 475. C224(h) | (iv) Concrete Dish Drain (600 wide) complete | m | 1690.91 | 13 | 13 | 163.4 | 2124.2 | 2124.2 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 13 | 100% | 13 | 100% | 13 | 100% | 13 | 100% | 13 | 100% | 13 | 100% | 13 | 100% | 13 | 100% | 13 | 100% | 0 | 0 | 0 | 0 | 0 | 2124.2 | 2124.2 | 2124.2 | 2124.2 | 2124.2 | 2124.2 | 2124.2 | 2124.2 | 2124.2
SUB-TOTAL
SUB-SURFACE DRAINAGE
| C231 | SUBSOIL & FOUNDATION DRAINS
191 | 496. C231(b) | Subsoil Drain Pipe - 100mm dia Slotted Corrugated Plastic Pipe complete | m | 11600.3083 | 281 | 281 | 51.86 | 14572.66 | 14572.66 |  | 0% | 245 | 87.19% | 245 | 87.19% | 281 | 100% | 281 | 100% | 281 | 100% | 281 | 100% | 281 | 100% | 281 | 100% | 281 | 100% | 281 | 100% | 281 | 100% | 281 | 100% | 281 | 100% | 0 | 12705.7 | 12705.7 | 14572.66 | 14572.66 | 14572.66 | 14572.66 | 14572.66 | 14572.66 | 14572.66 | 14572.66 | 14572.66 | 14572.66 | 14572.66
192 |  | Special Item -Subsoil Drain Pipe - 100mm dia Slotted Corrugated Plastic Pipe encased in no fines concrete complete as shown on drawings | m | 16027.7171 | 242 | 242 | 83.2 | 20134.4 | 20134.4 |  | 0% | 242 | 100% | 242 | 100% | 242 | 100% | 242 | 100% | 242 | 100% | 242 | 100% | 242 | 100% | 242 | 100% | 242 | 100% | 242 | 100% | 242 | 100% | 242 | 100% | 242 | 100% | 0 | 20134.4 | 20134.4 | 20134.4 | 20134.4 | 20134.4 | 20134.4 | 20134.4 | 20134.4 | 20134.4 | 20134.4 | 20134.4 | 20134.4 | 20134.4
193 | 519. C232(c) | Cleanout Structures | each | 1859 | 13 | 13 | 179.64 | 2335.32 | 2335.32 |  | 0% | 6.5 | 50% | 6.5 | 50% | 10 | 76.92% | 10 | 76.92% | 13 | 100% | 13 | 100% | 13 | 100% | 13 | 100% | 13 | 100% | 13 | 100% | 13 | 100% | 13 | 100% | 13 | 100% | 0 | 1167.66 | 1167.66 | 1796.4 | 1796.4 | 2335.32 | 2335.32 | 2335.32 | 2335.32 | 2335.32 | 2335.32 | 2335.32 | 2335.32 | 2335.32
SUB-TOTAL
PAVEMENTS
| C242 | FLEXIBLE PAVEMENTS
194 | 491 | Place only Type 2.3 (cement modified) | m3 | 21403.5155 | 378 | 378 | 71.13 | 26887.14 | 26887.14 | 104 | 27.51% | 250 | 66.14% | 250 | 66.14% | 354 | 93.65% | 354 | 93.65% | 359 | 94.97% | 378 | 100% | 378 | 100% | 378 | 100% | 378 | 100% | 378 | 100% | 378 | 100% | 378 | 100% | 378 | 100% | 7397.52 | 17782.5 | 17782.5 | 25180.02 | 25180.02 | 25535.67 | 26887.14 | 26887.14 | 26887.14 | 26887.14 | 26887.14 | 26887.14 | 26887.14 | 26887.14
195 | 490 | Place only Type 2.1 (cement modified) | m3 | 10584.8504 | 127 | 127 | 104.65 | 13290.55 | 13290.55 |  | 0% | 78 | 61.42% | 78 | 61.42% | 78 | 61.42% | 78 | 61.42% | 108 | 85.04% | 127 | 100% | 127 | 100% | 127 | 100% | 127 | 100% | 127 | 100% | 127 | 100% | 127 | 100% | 127 | 100% | 0 | 8162.7 | 8162.7 | 8162.7 | 8162.7 | 11302.2 | 13290.55 | 13290.55 | 13290.55 | 13290.55 | 13290.55 | 13290.55 | 13290.55 | 13290.55
196 | 538 | Special Item - Geogrid layer (PROVISIONAL) | m2 | 7508.9589 | 1260 | 1260 | 7.49 | 9437.4 | 9437.4 | 705 | 55.95% | 705 | 55.95% | 705 | 55.95% | 905 | 71.83% | 1071 | 85% | 1134 | 90% | 1260 | 100% | 1260 | 100% | 1260 | 100% | 1260 | 100% | 1260 | 100% | 1260 | 100% | 1260 | 100% | 1260 | 100% | 5280.45 | 5280.45 | 5280.45 | 6778.45 | 8021.79 | 8493.66 | 9437.4 | 9437.4 | 9437.4 | 9437.4 | 9437.4 | 9437.4 | 9437.4 | 9437.4
197 | 539 | Special Item -Geotextile layer (PROVISIONAL) | m2 | 1992.6789 | 1260 | 1260 | 1.99 | 2507.4 | 2507.4 | 705 | 55.95% | 705 | 55.95% | 705 | 55.95% | 905 | 71.83% | 1071 | 85% | 1134 | 90% | 1260 | 100% | 1260 | 100% | 1260 | 100% | 1260 | 100% | 1260 | 100% | 1260 | 100% | 1260 | 100% | 1260 | 100% | 1402.95 | 1402.95 | 1402.95 | 1800.95 | 2131.29 | 2256.66 | 2507.4 | 2507.4 | 2507.4 | 2507.4 | 2507.4 | 2507.4 | 2507.4 | 2507.4
| C244 | SPRAYED BITUMINOUS SURFACING
| C244(a) | Supply & Spray Primer, supply & spread aggregates, Primerbinder (including preparation of surface) complete
198 | 550. C244(a) | (vi) AMC4 | m2 | 14172.7845 | 1057 | 1057 | 13.74 | 14523.18 | 14523.18 |  | 0% |  | 0% | 735 | 69.54% | 735 | 69.54% | 735 | 69.54% | 735 | 69.54% | 1057 | 100% | 1057 | 100% | 1057 | 100% | 1057 | 100% | 1057 | 100% | 1057 | 100% | 1057 | 100% | 1057 | 100% | 0 | 0 | 10098.9 | 10098.9 | 10098.9 | 10098.9 | 14523.18 | 14523.18 | 14523.18 | 14523.18 | 14523.18 | 14523.18 | 14523.18 | 14523.18
| C245 | ASPHALTIC CONCRETE
| C245(c) | Dense Graded Asphalt in Wearing Course
199 | 574. C245(c) | (ii) 14mm Nominal Size | tonne | 34057.8 | 102 | 102 | 342.25 | 34909.5 | 34909.5 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 102 | 100% | 102 | 100% | 102 | 100% | 102 | 100% | 102 | 100% | 102 | 100% | 102 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34909.5 | 34909.5 | 34909.5 | 34909.5 | 34909.5 | 34909.5 | 34909.5
SUB-TOTAL
MISCELLANEOUS
| C271 | MINOR CONCRETE WORKS
| C271(c) | Footpaths, Bike paths, Driveways, Median Toppings & Works of Similar Nature
200 | 790. C271(c) | (iv) Residential Invert Crossing (3.1m to 4.5m) | each | 5192.9867 | 11 | 11 | 593.05 | 6523.55 | 6523.55 |  | 0% | 8 | 72.73% | 11 | 100% | 11 | 100% | 11 | 100% | 11 | 100% | 11 | 100% | 11 | 100% | 11 | 100% | 11 | 100% | 11 | 100% | 11 | 100% | 11 | 100% | 11 | 100% | 0 | 4744.4 | 6523.55 | 6523.55 | 6523.55 | 6523.55 | 6523.55 | 6523.55 | 6523.55 | 6523.55 | 6523.55 | 6523.55 | 6523.55 | 6523.55
201 | 793. C271(c) | (viii) Hand Placed Concrete Paving (Footpath / Bikeway) | m2 | 6624.2867 | 93 | 93 | 89.48 | 8321.64 | 8321.64 |  | 0% |  | 0% |  | 0% | 93 | 100% | 93 | 100% | 93 | 100% | 93 | 100% | 93 | 100% | 93 | 100% | 93 | 100% | 93 | 100% | 93 | 100% | 93 | 100% | 93 | 100% | 0 | 0 | 0 | 8321.64 | 8321.64 | 8321.64 | 8321.64 | 8321.64 | 8321.64 | 8321.64 | 8321.64 | 8321.64 | 8321.64 | 8321.64
| C273 | LANDSCAPE
| C273(a) | Vegetation of Slopes 1 in 3 or Flatter
202 | 830. C273(a) | (i) Grass Seeding | m2 | 2438.975 | 905 | 905 | 3.39 | 3067.95 | 3067.95 |  | 0% |  | 0% |  | 0% | 905 | 100% | 90.5 | 10% | 452.5 | 50% | 678.5 | 74.97% | 905 | 100% | 905 | 100% | 905 | 100% | 905 | 100% | 905 | 100% | 905 | 100% | 905 | 100% | 0 | 0 | 0 | 3067.95 | 306.795 | 1533.975 | 2300.115 | 3067.95 | 3067.95 | 3067.95 | 3067.95 | 3067.95 | 3067.95 | 3067.95
SUB-TOTAL
SERVICES
| C320 | WATER RETICULATION
203 | 1300 | Supply and install mains and reticulation | Lump | 9200 | 1 | 1 | 11557.3 | 11557.3 | 11557.3 |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 11557.3 | 11557.3 | 11557.3 | 11557.3 | 11557.3 | 11557.3 | 11557.3 | 11557.3 | 11557.3 | 11557.3 | 11557.3
SUB-TOTAL
SPECIFIED WORKS
204 |  | Special Item - As Constructed Survey and Plans | Lump | 2400 | 1 | 1 | 3014.95 | 3014.95 | 3014.95 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 0.95 | 95% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 2411.96 | 2411.96 | 2411.96 | 2864.2025 | 3014.95 | 3014.95 | 3014.95 | 3014.95
SUB-TOTAL
|  | TOTAL | [5 empty] | 315970.26
STERRY STREET
QUALITY SYSTEM
| CQC | QUALITY CONTROL REQUIREMENTS
205 | 104. QCP1 | Quality Verification & Control | Lump | 10350 | 1 | 1 | 13001.96 | 13001.96 | 13001.96 |  | 0% |  | 0% |  | 0% |  | 0% | 0.1 | 10% | 0.1 | 10% | 0.8 | 80% | 0.9 | 90% | 0.95 | 95% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 1300.196 | 1300.196 | 10401.568 | 11701.764 | 12351.862 | 13001.96 | 13001.96 | 13001.96 | 13001.96 | 13001.96
SUB-TOTAL
GENERAL REQUIREMENTS
| C101 | GENERAL
| 107. C101(b) | Site Establishment & Disestablishment | Lump |  | 1 | 1 |  |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUB-TOTAL
ROAD & EARTHWORKS
| C201 | CONTROL OF TRAFFIC
206 | 449. C201(a) | Control of Traffic | Lump | 29115.6 | 1 | 1 | 36575.83 | 36575.83 | 36575.83 |  | 0% |  | 0% |  | 0% |  | 0% | 0.1 | 10% | 0.1 | 10% | 0.8 | 80% | 0.9 | 90% | 0.95 | 95% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 3657.583 | 3657.583 | 29260.664 | 32918.247 | 34747.0385 | 36575.83 | 36575.83 | 36575.83 | 36575.83 | 36575.83
| C211 | CONTROL OF EROSION & SEDIMENTATION
207 | 114. C211(a) | Temporary Erosion & Sedimentation Control (includes supply and installation of all components) | Lump | 11050 | 1 | 1 | 13881.32 | 13881.32 | 13881.32 |  | 0% |  | 0% |  | 0% |  | 0% | 0.1 | 10% | 0.1 | 10% | 0.8 | 80% | 0.9 | 90% | 0.95 | 95% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 1388.132 | 1388.132 | 11105.056 | 12493.188 | 13187.254 | 13881.32 | 13881.32 | 13881.32 | 13881.32 | 13881.32
| C212 | CLEARING & GRUBBING
208 | 113 | Special Item - Demolition of Structure (concrete slabs, culverts, pipes etc) | Lump | 10066.6667 | 1 | 1 | 13646.79 | 13646.79 | 13646.79 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 10917.432 | 13646.79 | 13646.79 | 13646.79 | 13646.79 | 13646.79 | 13646.79 | 13646.79
| C213 | EARTHWORKS
209 | 125. C213(b) | General Earthworks Cut | m3 | 34970.2439 | 1700 | 1700 | 25.84 | 43928 | 43928 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.8 | 0.04706% | 1700 | 100% | 1700 | 100% | 1700 | 100% | 1700 | 100% | 1700 | 100% | 1700 | 100% | 1700 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 20.672 | 43928 | 43928 | 43928 | 43928 | 43928 | 43928 | 43928
SUB-TOTAL
STORMWATER DRAINAGE
| C220 | STORMWATER DRAINAGE - GENERAL
210 | 137 | Removal / Demolition of Drainage Components complete | Lump | 5490.9091 | 1 | 1 | 6829.54 | 6829.54 | 6829.54 |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 6829.54 | 6829.54 | 6829.54 | 6829.54 | 6829.54 | 6829.54 | 6829.54 | 6829.54 | 6829.54 | 6829.54
211 | 138 | Alteration to Existing Stormwater Structures | Lump | 7860 | 1 | 1 | 9873.95 | 9873.95 | 9873.95 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 9873.95 | 9873.95 | 9873.95 | 9873.95 | 9873.95 | 9873.95 | 9873.95 | 9873.95
| C221 | PIPE DRAINAGE (SUPPLY & INSTALL)
212 | 314. C221(a) | Connect property drainage pipes | Lump | 6715 | 1 | 1 | 8435.57 | 8435.57 | 8435.57 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 4217.785 | 8435.57 | 8435.57 | 8435.57 | 8435.57 | 8435.57 | 8435.57 | 8435.57
| C222 | PRECAST BOX CULVERTS (SUPPLY & INSTALL)
213 | 315. C222(a) | In-Situ reinforced concrete Base Slab for culverts complete | m3 | 4557.3111 | 7 | 7 | 817.86 | 5725.02 | 5725.02 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 7 | 100% | 7 | 100% | 7 | 100% | 7 | 100% | 7 | 100% | 7 | 100% | 7 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5725.02 | 5725.02 | 5725.02 | 5725.02 | 5725.02 | 5725.02 | 5725.02
214 | 325. C222(b) | 750 x 300 | m | 12883.6467 | 35 | 35 | 462.42 | 16184.7 | 16184.7 |  | 0% |  | 0% |  | 0% |  | 0% | 35 | 100% | 35 | 100% | 35 | 100% | 35 | 100% | 35 | 100% | 35 | 100% | 35 | 100% | 35 | 100% | 35 | 100% | 35 | 100% | 0 | 0 | 0 | 0 | 16184.7 | 16184.7 | 16184.7 | 16184.7 | 16184.7 | 16184.7 | 16184.7 | 16184.7 | 16184.7 | 16184.7
| C223 | DRAINAGE STRUCTURES
215 | 443. C223(b) | MCC Type A Gully Pit | each | 3505 | 1 | 1 | 4403.08 | 4403.08 | 4403.08 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 2201.54 | 4403.08 | 4403.08 | 4403.08 | 4403.08 | 4403.08 | 4403.08 | 4403.08
| C224 | OPEN DRAINS, INCLUDING KERB & CHANNEL
216 | 472. C224(h) | (i) Concrete Barrier Kerb & Channel B1 complete | m | 7442.8233 | 140 | 140 | 66.78 | 9349.2 | 9349.2 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 140 | 100% | 140 | 100% | 140 | 100% | 140 | 100% | 140 | 100% | 140 | 100% | 140 | 100% | 140 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 9349.2 | 9349.2 | 9349.2 | 9349.2 | 9349.2 | 9349.2 | 9349.2 | 9349.2
SUB-TOTAL
SUB-SURFACE DRAINAGE
| C231 | SUBSOIL & FOUNDATION DRAINS
217 | 496. C231(b) | Subsoil Drain Pipe - 100mm dia Slotted Corrugated Plastic Pipe complete (provisional quantity) | m | 17338.539 | 420 | 420 | 51.86 | 21781.2 | 21781.2 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 21 | 5% | 420 | 100% | 420 | 100% | 420 | 100% | 420 | 100% | 420 | 100% | 420 | 100% | 420 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1089.06 | 21781.2 | 21781.2 | 21781.2 | 21781.2 | 21781.2 | 21781.2 | 21781.2
218 | 519. C232(c) | Cleanout Structures | each | 1716 | 12 | 12 | 179.64 | 2155.68 | 2155.68 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1.2 | 10% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 215.568 | 2155.68 | 2155.68 | 2155.68 | 2155.68 | 2155.68 | 2155.68 | 2155.68
SUB-TOTAL
PAVEMENTS
| C242 | FLEXIBLE PAVEMENTS
219 | 491 | Place only Type 2.3 | m3 | 23498.5686 | 415 | 415 | 71.13 | 29518.95 | 29518.95 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 415 | 100% | 415 | 100% | 415 | 100% | 415 | 100% | 415 | 100% | 415 | 100% | 415 | 100% | 415 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 29518.95 | 29518.95 | 29518.95 | 29518.95 | 29518.95 | 29518.95 | 29518.95 | 29518.95
220 | 493 | Place only Type 2.5 (cement modified) | m3 | 31425.7966 | 555 | 555 | 71.13 | 39477.15 | 39477.15 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 180 | 32.43% | 180 | 32.43% | 180 | 32.43% | 180 | 32.43% | 180 | 32.43% | 180 | 32.43% | 180 | 32.43% | 180 | 32.43% | 0 | 0 | 0 | 0 | 0 | 0 | 12803.4 | 12803.4 | 12803.4 | 12803.4 | 12803.4 | 12803.4 | 12803.4 | 12803.4
221 | 490 | Place only Type 2.1 | m3 | 31590.338 | 405 | 405 | 98.48 | 39884.4 | 39884.4 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 405 | 100% | 405 | 100% | 405 | 100% | 405 | 100% | 405 | 100% | 405 | 100% | 405 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39884.4 | 39884.4 | 39884.4 | 39884.4 | 39884.4 | 39884.4 | 39884.4
222 | 538 | Special Item - Geogrid layer | m2 | 16477.9932 | 2765 | 2765 | 7.49 | 20709.85 | 20709.85 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2765 | 100% | 2765 | 100% | 2765 | 100% | 2765 | 100% | 2765 | 100% | 2765 | 100% | 2765 | 100% | 2765 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 20709.85 | 20709.85 | 20709.85 | 20709.85 | 20709.85 | 20709.85 | 20709.85 | 20709.85
223 | 539 | Special Item - Geotextile layer | m2 | 4372.8232 | 2765 | 2765 | 1.99 | 5502.35 | 5502.35 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2765 | 100% | 2765 | 100% | 2765 | 100% | 2765 | 100% | 2765 | 100% | 2765 | 100% | 2765 | 100% | 2765 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 5502.35 | 5502.35 | 5502.35 | 5502.35 | 5502.35 | 5502.35 | 5502.35 | 5502.35
| C245 | ASPHALTIC CONCRETE
| C245(c) | Dense Graded Asphalt in Wearing Course
224 | 574. C245(c) | (ii) 14mm Nominal Size | tonne | 100970.1 | 310 | 310 | 333.85 | 103493.5 | 103493.5 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 310 | 100% | 310 | 100% | 310 | 100% | 310 | 100% | 310 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103493.5 | 103493.5 | 103493.5 | 103493.5 | 103493.5
SUB-TOTAL
ROAD FURNISHINGS
| C261 | PAVEMENT MARKINGS
225 | 657. C261(a) | Pavement Marking Paint - Longitudinal Lines including car parking bays | m | 5000 | 405 | 405 | 15.51 | 6281.55 | 6281.55 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 405 | 100% | 405 | 100% | 405 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6281.55 | 6281.55 | 6281.55
226 | 658. C261(b) | Pavement Marking Paint - Transverse Lines, Symbols, Legends, Arrows, Chevrons, Traffic Islands & Kerbs | Item | 2000 | 1 | 1 | 2512.46 | 2512.46 | 2512.46 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2512.46 | 2512.46 | 2512.46
| C262 | SIGNPOSTING
227 | 678. C262(g) | Remove and reinstate Existing Signs & Support Structures | Item | 1652 | 1 | 1 | 2075.29 | 2075.29 | 2075.29 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.5 | 50% | 0.5 | 50% | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1037.645 | 1037.645 | 1037.645 | 2075.29 | 2075.29 | 2075.29 | 2075.29 | 2075.29
228 | 679 | Supply & Installation of all Signs (complete) | each | 4215 | 1 | 1 | 5295 | 5295 | 5295 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5295 | 5295 | 5295 | 5295 | 5295
SUB-TOTAL
MISCELLANEOUS
| C271 | MINOR CONCRETE WORKS
| C271(c) | Footpaths, Bike paths, Driveways, Median Toppings & Works of Similar Nature
229 | 789. C271(c) | (ii) Concrete Kerb Ramp (1 No) | each | 785 | 1 | 1 | 986.14 | 986.14 | 986.14 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 986.14 | 986.14 | 986.14 | 986.14 | 986.14 | 986.14 | 986.14
230 | 791. C271(c) | (iv) Residential Invert Crossing (10.5 m) | each | 2493.92 | 3 | 3 | 1044.31 | 3132.93 | 3132.93 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3132.93 | 3132.93 | 3132.93 | 3132.93 | 3132.93 | 3132.93 | 3132.93
231 | C271(c) | (viii) Hand Placed Concrete Paving (Footpath / Bikeway) | m2 | 1282.12 | 18 | 18 | 89.48 | 1610.64 | 1610.64 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 18 | 100% | 18 | 100% | 18 | 100% | 18 | 100% | 18 | 100% | 18 | 100% | 18 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1610.64 | 1610.64 | 1610.64 | 1610.64 | 1610.64 | 1610.64 | 1610.64
| C273 | LANDSCAPE
| C273(a) | Vegetation of Slopes 1 in 3 or Flatter
232 | 831. C273(a) | (ii) Turfing | m2 | 892.5 | 100 | 100 | 11.21 | 1121 | 1121 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1121 | 1121 | 1121 | 1121
SUB-TOTAL
SERVICES
| C320 | WATER RETICULATION
233 | 1300 | Supply and install mains and reticulation | Lump | 8000 | 1 | 1 | 10049.82 | 10049.82 | 10049.82 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 10049.82 | 10049.82 | 10049.82 | 10049.82 | 10049.82 | 10049.82 | 10049.82 | 10049.82
234 | 1301 | Service connections | Lump | 10980 | 1 | 1 | 13793.38 | 13793.38 | 13793.38 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 13793.38 | 13793.38 | 13793.38 | 13793.38 | 13793.38 | 13793.38 | 13793.38 | 13793.38
SUB-TOTAL
SPECIFIED WORKS
235 |  | Special Item - As Constructed Survey and Plans | Lump | 2400 | 1 | 1 | 3014.95 | 3014.95 | 3014.95 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.5 | 50% | 0.7 | 70% | 0.7 | 70% | 0.95 | 95% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1507.475 | 2110.465 | 2110.465 | 2864.2025 | 3014.95 | 3014.95 | 3014.95 | 3014.95
SUB-TOTAL
|  | TOTAL | [5 empty] | 494231.2 | [29 empty] | 126387.5491 | 233953.7102 | 257747.8641 | 406970.5352 | 600102.9331 | 776708.4283 | 1090716.0666 | 1536327.0371 | 1710427.2151 | 2095579.6309 | 2474626.6064 | 2797336.2534 | 2791986.1034 | 2791986.1034
Variations
JSV01 | JUPP_PV01 | Jupp Street Geotextile wrapping around no fines concrete | m | 1137.6074 | 242 | 242 | 5.29 | 1280.18 | 1280.18 |  | 0% | 242 | 100% | 242 | 100% | 242 | 100% | 242 | 100% | 242 | 100% | 242 | 100% | 242 | 100% | 242 | 100% | 242 | 100% | 242 | 100% | 242 | 100% | 242 | 100% | 242 | 100% | 0 | 1280.18 | 1280.18 | 1280.18 | 1280.18 | 1280.18 | 1280.18 | 1280.18 | 1280.18 | 1280.18 | 1280.18 | 1280.18 | 1280.18 | 1280.18
JSV02 | JUPP_PV02 | Jupp_PV02 - Boundary Pits & Pipes | each | 2325 | 1 | 1 | 3099 | 9297 | 9297 |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 3 | 300% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 9297 | 9297 | 9297 | 9297 | 9297 | 9297 | 9297 | 9297 | 27891 | 9297 | 9297
JSV03 | JUPP_PV | Jupp St - Haul & Place Type 2.3 gravel | m³ | 2264.9223 | 40 | 40 | 71.13 | 2845.2 | 2845.2 |  | 0% |  | 0% |  | 0% |  | 0% | 20 | 50% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 0 | 0 | 0 | 0 | 1422.6 | 2845.2 | 2845.2 | 2845.2 | 2845.2 | 2845.2 | 2845.2 | 2845.2 | 2845.2 | 2845.2
JSV04 | JUPP_PV03 | Jupp St_PV03 - Replace AC watermain crossing at Jupp and Anzac Rd |  | 23859.3462 | 1 | 1 | 28143.6818 | 28143.6818 | 28143.6818 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 28143.6818 | 28143.6818 | 28143.6818 | 28143.6818 | 28143.6818 | 28143.6818 | 28143.6818 | 28143.6818
JSV05 | JUPP_PV04 | Jupp_PV04 - Extend Kerb & Channel On Anzac Road |  | 691.1193 | 1 | 1 | 1431.13 | 1431.13 | 1431.13 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.9533 | 95.33% | 0.9533 | 95.33% | 0.9533 | 95.33% | 0.9533 | 95.33% | 0.9533 | 95.33% | 0.9533 | 95.33% | 0.9533 | 95.33% | 0.9533 | 95.33% | 0 | 0 | 0 | 0 | 0 | 0 | 1364.2962 | 1364.2962 | 1364.2962 | 1364.2962 | 1364.2962 | 1364.2962 | 1364.2962 | 1364.2962
JSV06 | JUPP_PV05 | Jupp_PV05 - Extend Kerb & Channel on Phaff Street |  | 1086.1193 | 1 | 1 | 1346.14 | 1346.14 | 1346.14 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1346.14 | 1346.14 | 1346.14 | 1346.14 | 1346.14 | 1346.14 | 1346.14 | 1346.14
DSV01 | DODD_PV01 | Dodd St - Geogrid layer | m² | 16668.697 | 2797 | 2797 | 7.49 | 20949.53 | 20949.53 |  | 0% |  | 0% |  | 0% | 880 | 31.46% | 2377 | 84.98% | 2377 | 84.98% | 2797 | 100% | 2797 | 100% | 2797 | 100% | 2797 | 100% | 2797 | 100% | 2797 | 100% | 2797 | 100% | 2797 | 100% | 0 | 0 | 0 | 6591.2 | 17803.73 | 17803.73 | 20949.53 | 20949.53 | 20949.53 | 20949.53 | 20949.53 | 20949.53 | 20949.53 | 20949.53
DSV02 | DODD_PV02 | Dodd Street-PV02 Supply and Install Entry pits, RCBC and Concrete Nib Wall and Nib |  | 12004.176 | 1 | 1 | 17209.88 | 17209.88 | 17209.88 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 17209.88 | 17209.88 | 17209.88 | 17209.88 | 17209.88 | 17209.88 | 17209.88 | 17209.88 | 17209.88
DSV03 | DODD_PV03 | Dodd Street water main replacement Install new 100mm Dia DICL Watermains 3 locations |  | 42341 | 1 | 1 | 47821.61 | 47821.61 | 47821.61 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.9743 | 97.43% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 46592.5946 | 47821.61 | 47821.61 | 47821.61 | 47821.61 | 47821.61 | 47821.61 | 47821.61 | 47821.61
DSV04 | DODD_PV04 | Dodd Street_ PV04 - Extend Deep Lift AC at Culvert Crossing Anzac Drive | tonne | 891.261 | 3.29 | 3.29 | 277.67 | 913.53 | 913.5343 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 3.29 | 100% | 3.29 | 100% | 3.29 | 100% | 3.29 | 100% | 3.29 | 100% | 3.29 | 100% | 3.29 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 913.5343 | 913.5343 | 913.5343 | 913.5343 | 913.5343 | 913.5343 | 913.5343
DSV05 | DODD_PV05 | Dodd Street_PV05 - New Bropit and RCBC arrangement | item | 5434.44 | 1 | 1 | 9626.4 | 9626.4 | 9626.4 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 9626.4 | 9626.4 | 9626.4 | 9626.4 | 9626.4 | 9626.4 | 9626.4 | 9626.4
DSV06 | DODD_PV06 | Install new Type A MCC side entry pit, 13m of 450 RCP break in to existing drainage line and install a flush point. | item | 6552.74 | 1 | 1 | 10907.12 | 10907.12 | 10907.12 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 10907.12 | 10907.12 | 10907.12 | 10907.12 | 10907.12 | 10907.12 | 10907.12 | 10907.12 | 10907.12
DSV07 | DODD_P0V7 | Installation Pram Ramps Dodd street |  | 15632.4433 | 1 | 1 | 11011.2796 | 11011.2796 | 11011.2796 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.9273 | 92.73% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10210.7596 | 11011.2796 | 11011.2796 | 11011.2796 | 11011.2796 | 11011.2796 | 11011.2796
DSV08 | DODD_PV08 | Dodd Street - Water main Protection Lurline Street - works completed formal vairation to be provided Refer to email 2 May sent | m³ | 2169.2 | 11.6 | 11.6 | 1043 | 12098.8 | 12098.8 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 11.6 | 100% | 11.6 | 100% | 11.6 | 100% | 11.6 | 100% | 11.6 | 100% | 11.6 | 100% | 11.6 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12098.8 | 12098.8 | 12098.8 | 12098.8 | 12098.8 | 12098.8 | 12098.8
DSV09 | DODD_PV09 | Vairation to design levels mismatch to road surface - 44m Lurline Street to match levels to existing road surface. | hr | 325 | 2 | 2 | 375 | 750 | 750 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 0 | 0 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750
CCC01 | CCC_PV01 | CCC_PV01 - Remove and Replace New kerbiing and traffic Islands |  | 2308.0209 | 1 | 1 | 5256.2 | 5256.2 | 5256.2 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.4918 | 49.18% | 0.4918 | 49.18% | 0.4918 | 49.18% | 0.4918 | 49.18% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 2584.9992 | 2584.9992 | 2584.9992 | 2584.9992 | 5256.2 | 5256.2 | 5256.2 | 5256.2 | 5256.2
CCC02 | CCC_PV02 | CCC_PV02 - Cultrual Centre Carpark - Install 600m dish Drain | m | 5723.08 | 44 | 44 | 175.6 | 7726.4 | 7726.4 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 44 | 100% | 44 | 100% | 44 | 100% | 44 | 100% | 44 | 100% | 44 | 100% | 44 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7726.4 | 7726.4 | 7726.4 | 7726.4 | 7726.4 | 7726.4 | 7726.4
CCC03 | CCC_PV03 | CCC_PV03 Cultrual Centre Carpark Insitu Stabilising Carpark - 400m2 completed out 2103m2 | m² | 5486.63 | 400 | 400 | 19.86 | 7944 | 7944 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 400 | 100% | 400 | 100% | 400 | 100% | 400 | 100% | 400 | 100% | 400 | 100% | 400 | 100% | 400 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 7944 | 7944 | 7944 | 7944 | 7944 | 7944 | 7944 | 7944
CCC04 | CCC_PV04 | Unsuitable Subgrade replacement Iron Stone Rock Mattress |  | 45538.5999 | 1 | 1 | 71559.401 | 71559.401 | 71559.401 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71559.401 | 71559.401 | 71559.401 | 71559.401 | 71559.401 | 71559.401 | 71559.401
SS01 | STERRY_PV01 | Sterry_PV01 Sterry Street - Chapman Street Works |  | 21720.4724 | 1 | 1 | 114107.662 | 114107.662 | 114107.662 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.3651 | 36.51% | 0.3758 | 37.58% | 0.3758 | 37.58% | 0.6285 | 62.85% | 0.6285 | 62.85% | 0.6285 | 62.85% | 0.6393 | 63.93% | 0.6393 | 63.93% | 0 | 0 | 0 | 0 | 0 | 0 | 41660.7074 | 42881.6594 | 42881.6594 | 71716.6656 | 71716.6656 | 71716.6656 | 72949.0283 | 72949.0283
SS02 | STERRY_ PV02 | Area1 and Area 2 Sterry Street - Rock mattress, 2 layers of Geogrid and, geofabric |  | 191104.0703 | 1 | 1 | 256458.0748 | 256458.0748 | 256458.0748 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.8739 | 87.39% | 1.1287 | 112.9% | 1.1654 | 116.5% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 224118.7116 | 289464.229 | 298876.2404 | 256458.0748 | 256458.0748 | 256458.0748 | 256458.0748 | 256458.0748
SS03 | STERRY_ PV03 | Vairation direction - Removal and Replacement of 150mm Sewer Main Sterry street | item | 9500 | 1 | 1 | 10938.21 | 10938.21 | 10938.21 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10938.21 | 10938.21 | 10938.21 | 10938.21 | 10938.21 | 10938.21
SS03 | STERRY_03 | Various Concrete works and fencing and gate alterations - day labour rates + materials | item | 9500 | 1 | 1 | 3689.5 | 3689.5 | 3689.5 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3689.5 | 3689.5 | 3689.5 | 3689.5
SS04 | STERRY_PV04 | Cement stabilisation - Sterry Street 250mm depth | m² | 40195.5239 | 2765 | 2765 | 19.4 | 53641 | 53641 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2765 | 100% | 2765 | 100% | 2765 | 100% | 2765 | 100% | 2765 | 100% | 2765 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53641 | 53641 | 53641 | 53641 | 53641 | 53641
SS05 | STERRY_PV05 | 7 mm Primer Seal Sterry Street | m² | 17187.24 | 2765 | 2765 | 8.18 | 22617.7 | 22617.7 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2765 | 100% | 2765 | 100% | 2765 | 100% | 2765 | 100% | 2765 | 100% | 2765 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22617.7 | 22617.7 | 22617.7 | 22617.7 | 22617.7 | 22617.7
SS06 | STERRY_PV06 | Additional Chapman Street works - Kerbing and Miscellaneous concrete works Chapman | m³ | 4460 | 5 | 5 | 1083 | 5415 | 5415 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5415 | 5415 | 5415 | 5415 | 5415 | 5415
SS07 | STERRY_PV07 | Construct standard driveway access - Proserpine Secondary School | each | 465.0248 | 1 | 1 | 1044.31 | 1044.31 | 1044.31 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1044.31 | 1044.31 | 1044.31 | 1044.31 | 1044.31 | 1044.31
DL01 | DOBB_PV01 | Construct three residential property access Dobbins Lane | each | 2493.92 | 3 | 3 | 779.43 | 2338.29 | 2338.29 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2338.29 | 2338.29 | 2338.29 | 2338.29 | 2338.29 | 2338.29
DL02 | DOBB_PV02 | Variation Direction to place an additional layer of Geogrid dobbins lane Ch 190 to Ch 230 - 7.5m widE | m² | 1787.8474 | 300 | 300 | 7.49 | 2247 | 2247 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 300 | 100% | 300 | 100% | 300 | 100% | 300 | 100% | 300 | 100% | 300 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2247 | 2247 | 2247 | 2247 | 2247 | 2247
DL03 | DOBB_PVO3 A | Excavate Unsuitable Subgrade - Blended cement into gravel, import place and compact. | item | 39008.6124 | 1 | 1 | 109011.77 | 109011.77 | 109011.77 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109011.77 | 109011.77 | 109011.77 | 109011.77
DS01 | DOH_PV01 | Variation to water main Doherty street extra over the BOQ | item | 36365 | 1 | 1 | 47514 | 47514 | 47514 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47514 | 47514 | 47514 | 47514 | 47514
DS02 | DOH_PV02 | Pavement Design |  | 22972.4283 | 1 | 1 | 49564.4736 | 49564.4736 | 49564.4736 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49564.4736 | 49564.4736 | 49564.4736 | 49564.4736
DS03 | DOH_PV03 | Replacement of AC sewer main ch 37 | item | 5000 | 1 | 1 | 5914 | 5914 | 5914 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5914 | 5914 | 5914 | 5914
DS04 | DOH_PV04 | Construct Field Inlet Gully Pit Doherty Street | item | 9050 | 1 | 1 | 12325 | 12325 | 12325 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12325 | 12325 | 12325
DS05 | DOH_PV05 | Kerb extension end of Doherty Street | item | 446 | 1 | 1 | 493.08 | 493.08 | 493.08 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 493.08 | 493.08 | 493.08
DS06 | DOH_PV06 | Concrete Driveway 3 Doherty Street | m² | 831.3067 | 8.4 | 8.4 | 89 | 747.6 | 747.6 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 8.4 | 100% | 8.4 | 100% | 8.4 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 747.6 | 747.6 | 747.6
DS07 | DOH_PVO6 | Doherty Street - Hydromulch 1000m2 Turf 60m2 | item | 2960 | 1 | 1 | 4062.6 | 4062.6 | 4062.6 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4062.6 | 4062.6
FS00 | FAUST_PV00 | Remove and Replace Unsuitable Subgrade Faust Street RHS |  | 14650.5826 | 1 | 1 | 33949.3144 | 33949.3144 | 33949.3144 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33949.3144 | 33949.3144 | 33949.3144 | 33949.3144
FS01 | FAUST_PV01 | Faust Street drw FSC 04 extra over the BOQ | item | 4757.55 | 1 | 1 | 78480.4226 | 78480.4226 | 78480.4226 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39240.2113 | 78480.4226 | 78480.4226 | 78480.4226
FS01A | Faust_PVO1A | Additional Asphalt for Variation Faust _PV01 - Asphalt Invoice Plus 12.5% | item | 5117.349 | 1 | 1 | 5850.17 | 5850.17 | 5850.17 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5850.17 | 5850.17
FS03 | FAST_PV03 | Blend Iron stone with 1% cement to stockpile | item |  | 1 | 1 | 1000 | 1000 | 1000 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000
FS04 | FAUST_PV04 | Additional Testing Requirements | item | 6310 | 1 | 1 | 7156.56 | 7156.56 | 7156.56 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7156.56 | 7156.56 | 7156.56 | 7156.56
FS10 | Faust_V10 | Faust Street - Service Crossing | item | 8000 | 1 | 1 | 10000 | 10000 | 10000 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
W01 | Waste_ PV01 | Waste Disposal as per Invoices | item | 3115 | 1 | 1 | 3114.8 | 3114.8 | 3114.8 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3114.8 | 3114.8
[38 empty] | 0 | 1280.18 | 1280.18 | 17168.38 | 29803.51 | 109270.7038 | 427849.4562 | 596924.8205 | 705378.8618 | 741980.9033 | 991506.7326 | 1062906.6239 | 1058572.5566 | 1068572.5566
|  | Total, all contract items and variations |  | 3002076.5565 |  |  |  | 3941880.0115 | [29 empty] | 126387.5491 | 235233.8902 | 259028.0441 | 424138.9152 | 629906.4431 | 885979.1321 | 1518565.5228 | 2133251.8576 | 2415806.0769 | 2837560.5342 | 3466133.339 | 3860242.8773 | 3850558.66 | 3860558.66

## Portfolio WBS
Cost Code | Description | Quantity | Unit | BAC | BAC Rate | Final Qty | Final Cost | Final Rate |  |  |  | 2011-10-01 |  |  |  |  | 2011-11-01 |  |  |  |  | 2011-12-01 |  |  |  |  | 2012-01-01 |  |  |  |  | 2012-02-01 |  |  |  |  | 2012-03-01 |  |  |  |  | 2012-04-01 |  |  |  |  | 2012-05-01 |  |  |  |  | 2012-06-01 |  |  |  |  | 2012-07-01 |  |  |  |  | 2012-08-01 |  |  |  |  | 2012-09-01 |  |  |  |  | 2012-10-01 |  |  |  |  | 2012-11-01
| Totals, all cost codes | SQ |  |  | 0 | AQ | AC |  | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV
11 | Survey - Construction | 135 | hr | 32775 | 242.7778 | 242 | 44729.58 | 184.8347 | 0 | 0 | 0 | 0 | 0 | 30 | 7283.3333 | 14.5 | 2701.68 | 1963.7913 | 45 | 10925 | 14.5 | 2701.68 | 1963.7913 | 60 | 14566.6667 | 20.5 | 3812.38 | 2776.3946 | 75 | 18208.3333 | 41.5 | 7648.38 | 5620.5062 | 90 | 21850 | 49 | 9078.38 | 6636.2603 | 105 | 25491.6667 | 64 | 11980.48 | 8667.7686 | 120 | 29133.3333 | 119 | 21999.28 | 16116.6322 | 135 | 32775 | 119 | 21999.28 | 16116.6322 | 135 | 32775 | 169 | 31311.88 | 22888.3264 | 135 | 32775 | 188 | 34782.13 | 25461.5702 | 135 | 32775 | 230 | 42620.43 | 31149.7934 | 135 | 32775 | 242 | 44729.58 | 32775 | 135 | 32775 | 242 | 44729.58 | 32775 | 0
12 | Survey - As Constructed | 172 | hr | 23900 | 138.9535 | 99 | 18263.07 | 184.4747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2084.3023 | 0 | 0 | 0 | 30 | 4168.6047 | 0 | 0 | 0 | 45 | 6252.907 | 9 | 1634.92 | 2172.7273 | 60 | 8337.2093 | 9 | 1634.92 | 2172.7273 | 75 | 10421.5116 | 9 | 1634.92 | 2172.7273 | 90 | 12505.814 | 43 | 7912.42 | 10380.8081 | 145 | 20148.2558 | 54.5 | 10091.92 | 13157.0707 | 172 | 23900 | 59.5 | 11058.92 | 14364.1414 | 172 | 23900 | 65 | 12071.02 | 15691.9192 | 172 | 23900 | 69.5 | 12825.67 | 16778.2828 | 172 | 23900 | 99 | 18263.07 | 23900 | 0
13 | QA Testing | 1 | item | 25425 | 25425 | 1 | 27869.52 | 27870 | 0.1 | 2542.5 | 0 | 0 | 0 | 0.2 | 5085 | 0.05 | 1591.54 | 1271.25 | 0.3 | 7627.5 | 0.08 | 2350.81 | 2034 | 0.4 | 10170 | 0.1 | 2670.9 | 2542.5 | 0.5 | 12712.5 | 0.15 | 4611.7 | 3813.75 | 0.6 | 15255 | 0.15 | 4611.7 | 3813.75 | 0.7 | 17797.5 | 0.35 | 9695.78 | 8898.75 | 0.8 | 20340 | 0.45 | 12901.68 | 11441.25 | 0.9 | 22882.5 | 0.5 | 14673.95 | 12712.5 | 1 | 25425 | 0.5 | 14673.95 | 12712.5 | 1 | 25425 | 0.85 | 25104.7 | 21611.25 | 1 | 25425 | 0.95 | 27744.07 | 24153.75 | 1 | 25425 | 1 | 27869.52 | 25425 | 1 | 25425 | 1 | 27869.52 | 25425 | 0
15 | Service Locations | 0 | hr | 0 | 0 | 24.5 | 4054.9 | 165.5102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 195 | 0 | 0 | 0 | 1.2 | 195 | 0 | 0 | 0 | 9 | 1480 | 0 | 0 | 0 | 9 | 1480 | 0 | 0 | 0 | 14 | 2282.5 | 0 | 0 | 0 | 17.25 | 2860 | 0 | 0 | 0 | 18.75 | 3107.5 | 0 | 0 | 0 | 24.5 | 4054.9 | 0 | 0 | 0 | 24.5 | 4054.9 | 0 | 0 | 0 | 24.5 | 4054.9 | 0 | 0 | 0 | 24.5 | 4054.9 | 0 | 0
32 | Disposal offsite - Clearing waste | 1 | item | 3115 | 3115 | 1 | 2535.32 | 2535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3115 | 0.75 | 1933.19 | 2336.25 | 1 | 3115 | 0.75 | 1959.34 | 2336.25 | 1 | 3115 | 0.75 | 1987.65 | 2336.25 | 1 | 3115 | 0.75 | 1997.09 | 2336.25 | 1 | 3115 | 0.9 | 2350.36 | 2803.5 | 1 | 3115 | 1 | 2535.32 | 3115 | 1 | 3115 | 1 | 2535.32 | 3115 | 0
33 | Re-spread topsoil | 240 | m3 | 9148.2614 | 38.1178 | 240 | 25138.27 | 104.7417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1524.7102 | 20 | 2940.25 | 762.3551 | 40 | 1524.7102 | 20 | 2940.25 | 762.3551 | 40 | 1524.7102 | 20 | 2940.25 | 762.3551 | 80 | 3049.4205 | 30 | 4770.45 | 1143.5327 | 160 | 6098.8409 | 50 | 7250.785 | 1905.8878 | 240 | 9148.2614 | 60 | 8553.17 | 2287.0653 | 240 | 9148.2614 | 60 | 8553.17 | 2287.0653 | 240 | 9148.2614 | 60 | 8553.17 | 2287.0653 | 240 | 9148.2614 | 80 | 11683.645 | 3049.4205 | 240 | 9148.2614 | 150 | 15479.395 | 5717.6633 | 240 | 9148.2614 | 240 | 25138.27 | 9148.2614 | 240 | 9148.2614 | 240 | 25138.27 | 9148.2614 | 0
41 | Demolition works | 1 | item | 78845.1076 | 78845.1076 | 1 | 12448.88 | 12449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 0 | 0 | 0 | 0 | 330 | 0 | 0 | 0 | 0 | 330 | 0 | 0.25 | 19711.2769 | 0.1 | 1352.8 | 7884.5108 | 0.5 | 39422.5538 | 0.15 | 2167.925 | 11826.7661 | 0.75 | 59133.8307 | 0.15 | 2167.925 | 11826.7661 | 1 | 78845.1076 | 0.55 | 7077.435 | 43364.8092 | 1 | 78845.1076 | 0.55 | 7077.435 | 43364.8092 | 1 | 78845.1076 | 0.9 | 11067.78 | 70960.5969 | 1 | 78845.1076 | 1 | 12448.88 | 78845.1076 | 1 | 78845.1076 | 1 | 12448.88 | 78845.1076 | 1 | 78845.1076 | 1 | 12448.88 | 78845.1076 | 1 | 78845.1076 | 1 | 12448.88 | 78845.1076 | 0
52 | Stockpile to Fill | 0 | m3 | 0 | 0 | 10 | 193.5 | 19.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 193.5 | 0 | 0 | 0 | 10 | 193.5 | 0 | 0 | 0 | 10 | 193.5 | 0 | 0 | 0 | 10 | 193.5 | 0 | 0 | 0 | 10 | 193.5 | 0 | 0 | 0 | 10 | 193.5 | 0 | 0 | 0 | 10 | 193.5 | 0 | 0
53 | Cut to Spoil | 7825 | m3 | 129418.15 | 16.5391 | 7825 | 308767.983 | 39.4592 | 120 | 1984.6873 | 384 | 18346.464 | 6350.9993 | 895 | 14802.4593 | 384 | 37000.539 | 6350.9993 | 895 | 14802.4593 | 384 | 40441.939 | 6350.9993 | 2325 | 38453.3161 | 1257 | 71961.764 | 20789.5993 | 3323 | 54959.2987 | 1908 | 97868.889 | 31556.5278 | 4192 | 69331.7425 | 3134 | 114354.864 | 51833.4162 | 5892 | 97448.1457 | 3134 | 164115.944 | 51833.4162 | 6335 | 104774.9496 | 5721 | 188753.5315 | 94619.9663 | 6987 | 115558.4171 | 6519 | 230001.577 | 107818.1367 | 7825 | 129418.15 | 6780 | 238750.477 | 112134.8316 | 7825 | 129418.15 | 7378 | 274349.877 | 122025.1899 | 7825 | 129418.15 | 7649 | 305562.633 | 126507.2753 | 7825 | 129418.15 | 7825 | 308767.983 | 129418.15 | 7825 | 129418.15 | 7825 | 308767.983 | 129418.15 | 0
57 | Remove & Replace unsuitable | 2605 | m3 | 138016.5175 | 52.9814 | 2605 | 215667.317 | 82.8641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1059.6278 | 20 | 0 | 1059.6278 | 20 | 1059.6278 | 20 | 0 | 1059.6278 | 960 | 50862.1331 | 960 | 42660.3837 | 50862.1331 | 1795 | 95101.5927 | 1795 | 81882.5185 | 95101.5927 | 1805 | 95631.4066 | 1805 | 81882.5185 | 95631.4066 | 2444 | 129486.5139 | 2444 | 146832.5735 | 129486.5139 | 2605 | 138016.5175 | 2605 | 206533.272 | 138016.5175 | 2605 | 138016.5175 | 2605 | 215667.317 | 138016.5175 | 2605 | 138016.5175 | 2605 | 215667.317 | 138016.5175 | 2605 | 138016.5175 | 2605 | 215667.317 | 138016.5175 | 0
61 | Subgrade Preparation | 12767 | m2 | 23173.5496 | 1.8151 | 12767 | 4390.425 | 0.34386 | 200 | 363.0226 | 200 | 530.25 | 363.0226 | 935 | 1697.1308 | 935 | 2080.5 | 1697.1308 | 935 | 1697.1308 | 935 | 2080.5 | 1697.1308 | 935 | 1697.1308 | 935 | 2080.5 | 1697.1308 | 2935 | 5327.3571 | 3180 | 2080.5 | 5772.0598 | 3725 | 6761.2965 | 5223.3333 | 3667.625 | 9480.941 | 5000 | 9075.5658 | 5223.3333 | 3667.625 | 9480.941 | 6500 | 11798.2355 | 9535 | 3667.625 | 17307.1039 | 9000 | 16336.0184 | 10865 | 3667.625 | 19721.2044 | 12767 | 23173.5496 | 11300 | 3667.625 | 20510.7786 | 12767 | 23173.5496 | 12767 | 4390.425 | 23173.5496 | 12767 | 23173.5496 | 12767 | 4390.425 | 23173.5496 | 12767 | 23173.5496 | 12767 | 4390.425 | 23173.5496 | 12767 | 23173.5496 | 12767 | 4390.425 | 23173.5496 | 0
62 | Place & Compact Gravel | 11525 | tonne | 282664.2876 | 24.5262 | 11768.54 | 382852.6255 | 32.5319 | 500 | 12263.0927 | 400 | 3990.07 | 9607.4547 | 1000 | 24526.1855 | 800 | 29107.38 | 19214.9094 | 1200 | 29431.4226 | 1000 | 44215.21 | 24018.6368 | 2200 | 53957.608 | 1900 | 59531.29 | 45635.4099 | 3000 | 73578.5564 | 2700 | 76785.94 | 64850.3193 | 4000 | 98104.7419 | 3521 | 110169.115 | 84569.6201 | 5600 | 137346.6386 | 5100 | 152455.78 | 122495.0475 | 8500 | 208472.5765 | 6810 | 194475.9775 | 163566.9164 | 9500 | 232998.762 | 7830 | 229892.6485 | 188065.9259 | 11000 | 269788.0402 | 9070 | 260952.6235 | 217849.0355 | 11525 | 282664.2876 | 10060 | 333157.8355 | 241627.4859 | 11525 | 282664.2876 | 11768.54 | 382852.6255 | 282664.2876 | 11525 | 282664.2876 | 11768.54 | 382852.6255 | 282664.2876 | 11525 | 282664.2876 | 11768.54 | 382852.6255 | 282664.2876 | 0
63 | Trim All Layers | 15532 | m2 | 39993.7893 | 2.5749 | 15532 | 86275.348 | 5.5547 | 240 | 617.9828 | 240 | 0 | 617.9828 | 240 | 617.9828 | 240 | 4226.71 | 617.9828 | 1122 | 2889.0698 | 1122 | 4226.71 | 2889.0698 | 1122 | 2889.0698 | 1122 | 4226.71 | 2889.0698 | 1122 | 2889.0698 | 1122 | 7927.91 | 2889.0698 | 3522 | 9068.8981 | 1122 | 14756.62 | 2889.0698 | 4467.6 | 11503.7505 | 1122 | 30773.57 | 2889.0698 | 7800 | 20084.4422 | 7785.6 | 36702.47 | 20047.3633 | 9000 | 23174.3564 | 9486 | 46879.845 | 24425.7717 | 10500 | 27036.7492 | 10465.2 | 47698.995 | 26947.1416 | 15532 | 39993.7893 | 12639.6 | 66733.096 | 32546.0662 | 15532 | 39993.7893 | 15532 | 86275.348 | 39993.7893 | 15532 | 39993.7893 | 15532 | 86275.348 | 39993.7893 | 15532 | 39993.7893 | 15532 | 86275.348 | 39993.7893 | 0
64 | Sweep & Prime / Primer seal or Seal | 12767 | m2 | 152157.3375 | 11.918 | 12767 | 274290.025 | 10.0581 | 200 | 2383.6036 | 200 | 1377.5 | 2383.6036 | 200 | 2383.6036 | 200 | 1377.5 | 2383.6036 | 935 | 11143.347 | 935 | 10775.265 | 11143.347 | 935 | 11143.347 | 935 | 10775.265 | 11143.347 | 935 | 11143.347 | 935 | 10775.265 | 11143.347 | 2935 | 34979.3832 | 935 | 10775.265 | 11143.347 | 3723 | 44370.7815 | 935 | 10775.265 | 11143.347 | 6500 | 77467.1179 | 6488 | 72009.515 | 77324.1016 | 7500 | 89385.136 | 7905 | 79412.515 | 94211.9333 | 8750 | 104282.6587 | 8721 | 86553.345 | 103937.0361 | 12767 | 152157.3375 | 10533 | 198423.965 | 125532.485 | 12767 | 152157.3375 | 12767 | 274117.525 | 152157.3375 | 12767 | 152157.3375 | 12767 | 274290.025 | 152157.3375 | 12767 | 152157.3375 | 12767 | 274290.025 | 152157.3375 | 0
65 | Asphalt | 1335.3 | tonne | 374978.967 | 280.82 | 1335.96 | 261664.129 | 305.056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 112328.0063 | 355 | 108392.669 | 99641.8555 | 400 | 112328.0063 | 355 | 108392.669 | 99641.8555 | 900 | 252738.0142 | 824 | 251275.169 | 231281.3773 | 1335.3 | 374978.967 | 1125 | 251275.169 | 315766.4435 | 1335.3 | 374978.967 | 1326 | 258529.919 | 372183.3814 | 1335.3 | 374978.967 | 1335.96 | 261664.129 | 374978.967 | 1335.3 | 374978.967 | 1335.96 | 261664.129 | 374978.967 | 0
66 | Linemarking | 1 | item | 20487.6543 | 20487.6543 | 1 | 4773.75 | 4774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 20487.6543 | 0 | 0 | 0 | 1 | 20487.6543 | 0.45 | 2153 | 9219.4444 | 1 | 20487.6543 | 0.45 | 2153 | 9219.4444 | 1 | 20487.6543 | 1 | 4773.75 | 20487.6543 | 0
67 | Install Road Furniture | 1 | item | 8210 | 8210 | 1 | 2520.95 | 2521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 4105 | 0.1 | 415.45 | 821 | 0.5 | 4105 | 0.1 | 415.45 | 821 | 0.5 | 4105 | 0.25 | 945.7 | 2052.5 | 0.5 | 4105 | 0.5 | 1563.2 | 4105 | 1 | 8210 | 0.5 | 1563.2 | 4105 | 1 | 8210 | 1 | 2520.95 | 8210 | 1 | 8210 | 1 | 2520.95 | 8210 | 1 | 8210 | 1 | 2520.95 | 8210 | 0
68 | Insitu Stabilisation | 3335 | m2 | 47402.5122 | 14.2136 | 3335 | 46094.08 | 13.8213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 985 | 14000.4421 | 985 | 13611.895 | 14000.4421 | 985 | 14000.4421 | 985 | 13611.895 | 14000.4421 | 3335 | 47402.5122 | 3335 | 46094.08 | 47402.5122 |  | 0 | 3335 | 46094.08 | 47402.5122 | 3335 | 47402.5122 | 3335 | 46094.08 | 47402.5122 | 3335 | 47402.5122 | 3335 | 46094.08 | 47402.5122 | 3335 | 47402.5122 | 3335 | 46094.08 | 47402.5122 | 3335 | 47402.5122 | 3335 | 46094.08 | 47402.5122 | 0
71 | Place Kerb & Channel / Inverts | 2278 | m | 104574.58 | 45.9063 | 2278 | 86929.5843 | 38.1607 | 0 | 0 | 0 | 0 | 0 | 250 | 11476.5781 | 250 | 3547.1 | 11476.5781 | 250 | 11476.5781 | 250 | 3547.1 | 11476.5781 | 250 | 11476.5781 | 250 | 3547.1 | 11476.5781 | 542 | 24881.2214 | 250 | 3711.73 | 11476.5781 | 618 | 28370.1012 | 618 | 24033.01 | 28370.1012 | 1124 | 51598.6953 | 900 | 35554.82 | 41315.6813 | 1180 | 54169.4488 | 618 | 39508.57 | 28370.1012 | 1519 | 69731.6888 | 1100 | 44816.72 | 50496.9438 | 2278 | 104574.58 | 1400 | 54736.045 | 64268.8376 | 2278 | 104574.58 | 1600 | 62825.1593 | 73450.1001 | 2278 | 104574.58 | 1700 | 69605.6343 | 78040.7313 | 2278 | 104574.58 | 2100 | 86079.5843 | 96403.2564 | 2278 | 104574.58 | 2278 | 86929.5843 | 104574.58 | 0
72 | Form & Pour Headwalls | 5.63 | m3 | 5599.75 | 994.627 | 5.63 | 13301.4 | 2362.5222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141.4 | 0 | 5.63 | 5599.75 | 1.75 | 4001.4 | 1740.5972 | 5.63 | 5599.75 | 5.63 | 13301.4 | 5599.75 | 5.63 | 5599.75 | 5.63 | 13301.4 | 5599.75 | 5.63 | 5599.75 | 5.63 | 13301.4 | 5599.75 | 5.63 | 5599.75 | 5.63 | 13301.4 | 5599.75 | 5.63 | 5599.75 | 5.63 | 13301.4 | 5599.75 | 5.63 | 5599.75 | 5.63 | 13301.4 | 5599.75 | 5.63 | 5599.75 | 5.63 | 13301.4 | 5599.75 | 5.63 | 5599.75 | 5.63 | 13301.4 | 5599.75 | 5.63 | 5599.75 | 5.63 | 13301.4 | 5599.75 | 5.63 | 5599.75 | 5.63 | 13301.4 | 5599.75 | 5.63 | 5599.75 | 5.63 | 13301.4 | 5599.75 | 0
73 | Form & Place Footpath | 1069 | m2 | 11417.789 | 10.6808 | 1069 | 55980.8 | 52.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 0 | 120 | 1281.6976 | 90 | 4660 | 961.2732 | 120 | 1281.6976 | 100 | 5212.8 | 1068.0813 | 120 | 1281.6976 | 120 | 6172.3 | 1281.6976 | 260 | 2777.0114 | 260 | 13640.675 | 2777.0114 | 400 | 4272.3252 | 400 | 20798.85 | 4272.3252 | 750 | 8010.6097 | 485 | 25310.23 | 5180.1943 | 1069 | 11417.789 | 575 | 29815.23 | 6141.4674 | 1069 | 11417.789 | 750 | 39114.5 | 8010.6097 | 1069 | 11417.789 | 1069 | 55980.8 | 11417.789 | 1069 | 11417.789 | 1069 | 55980.8 | 11417.789 | 0
75 | Saw Cutting | 300 | m | 3000 | 10 | 300 | 8705.77 | 29.02 | 0 | 0 | 0 | 0 | 0 | 90 | 900 | 90 | 2715.72 | 900 | 90 | 900 | 90 | 2715.72 | 900 | 120 | 1200 | 120 | 3652.495 | 1200 | 140 | 1400 | 140 | 4218.095 | 1400 | 150 | 1500 | 150 | 4530.695 | 1500 | 150 | 1500 | 150 | 4530.695 | 1500 | 177 | 1770 | 156 | 4684.745 | 1560 | 177 | 1770 | 160 | 4826.145 | 1600 | 248 | 2480 | 177 | 5321.045 | 1770 | 300 | 3000 | 248 | 7397.32 | 2480 | 300 | 3000 | 300 | 8705.77 | 3000 | 300 | 3000 | 300 | 8705.77 | 3000 | 300 | 3000 | 300 | 8705.77 | 3000 | 0
81 | > 450 | 66.6 | m | 29529.983 | 443.3931 | 66.6 | 19984.005 | 300.0601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300.475 | 0 | 30.42 | 13488.0193 | 30.42 | 8879.99 | 13488.0193 | 30.42 | 13488.0193 | 30.42 | 8879.99 | 13488.0193 | 51.48 | 22825.8787 | 51.48 | 15528.44 | 22825.8787 | 51.48 | 22825.8787 | 51.48 | 15528.44 | 22825.8787 | 51.48 | 22825.8787 | 51.48 | 15528.44 | 22825.8787 | 66.6 | 29529.983 | 51.48 | 15528.44 | 22825.8787 | 66.6 | 29529.983 | 58.5 | 17758.585 | 25938.4986 | 66.6 | 29529.983 | 66.6 | 19882.545 | 29529.983 | 66.6 | 29529.983 | 66.6 | 19984.005 | 29529.983 | 66.6 | 29529.983 | 66.6 | 19984.005 | 29529.983 | 66.6 | 29529.983 | 66.6 | 19984.005 | 29529.983 | 0
85 | Install SW Pits & Chambers | 19 | each | 73110 | 3847.8947 | 19 | 16398.015 | 863.0526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.7 | 0 | 2 | 7695.7895 | 2 | 2064.225 | 7695.7895 | 2 | 7695.7895 | 2 | 2064.225 | 7695.7895 | 5 | 19239.4737 | 3 | 2970.525 | 11543.6842 | 6 | 23087.3684 | 6 | 5692.925 | 23087.3684 | 12 | 46174.7368 | 11 | 9640.315 | 42326.8421 | 14 | 53870.5263 | 11 | 9640.315 | 42326.8421 | 19 | 73110 | 12 | 9923.115 | 46174.7368 | 19 | 73110 | 12 | 9923.115 | 46174.7368 | 19 | 73110 | 12 | 9923.115 | 46174.7368 | 19 | 73110 | 19 | 16398.015 | 73110 | 19 | 73110 | 19 | 16398.015 | 73110 | 0
86 | SW Sub-Contract Works | 1 | item | 17380 | 17380 | 1 | 41911.81 | 41912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71.81 | 0 | 1 | 17380 | 1 | 41911.81 | 17380 | 1 | 17380 | 1 | 41911.81 | 17380 | 1 | 17380 | 1 | 41911.81 | 17380 | 0
87 | Supply & Place Subsoil Drainage | 2803 | m | 113589.215 | 40.5242 | 2803 | 58724.45 | 20.9504 | 0 | 0 | 0 | 0 | 0 | 500 | 20262.079 | 487 | 11174.725 | 19735.265 | 500 | 20262.079 | 487 | 11892.875 | 19735.265 | 500 | 20262.079 | 523 | 14670.175 | 21194.1347 | 1000 | 40524.158 | 973 | 25627 | 39430.0058 | 1400 | 56733.8213 | 1269 | 30238.4 | 51425.1566 | 1400 | 56733.8213 | 1331 | 30238.4 | 53937.6544 | 1800 | 72943.4845 | 1600 | 33913.3 | 64838.6529 | 2400 | 97257.9793 | 2118 | 45796.425 | 85830.1667 | 2803 | 113589.215 | 2200 | 46263.925 | 89153.1477 | 2803 | 113589.215 | 2803 | 58565.375 | 113589.215 | 2803 | 113589.215 | 2803 | 58724.45 | 113589.215 | 2803 | 113589.215 | 2803 | 58724.45 | 113589.215 | 2803 | 113589.215 | 2803 | 58724.45 | 113589.215 | 0
103 | Water Sub-contractor | 1 | item | 282302.4 | 282302.4 | 1 | 287637.5 | 329550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 920 | 0 | 0.15 | 42345.36 | 0.13 | 43097.1 | 36699.312 | 0.25 | 70575.6 | 0.22 | 73213.5 | 62106.528 | 0.5 | 141151.2 | 0.46 | 151583.5 | 129859.104 | 0.6 | 169381.44 | 0.6 | 196911.5 | 169381.44 | 0.7 | 197611.68 | 0.63 | 207821.5 | 177850.512 | 1 | 282302.4 | 0.85 | 280837.5 | 239957.04 | 1 | 282302.4 | 0.98 | 280837.5 | 276656.352 | 1 | 282302.4 | 0.98 | 280837.5 | 276656.352 | 1 | 282302.4 | 1 | 287637.5 | 282302.4 | 0
110 | Electrical & Telecom | 0 | item | 0 | 0 | 1 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 110 | 0 | 0 | 0 | 1 | 110 | 0 | 0 | 0 | 1 | 110 | 0 | 0 | 0 | 1 | 110 | 0 | 0 | 0 | 1 | 110 | 0 | 0 | 0 | 1 | 110 | 0 | 0
120 | Landscaping Sub-contractors | 0 | item | 0 | 0 | 1 | 350 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 350 | 0 | 0 | 0 | 1 | 350 | 0 | 0 | 0 | 1 | 350 | 0 | 0 | 0 | 1 | 350 | 0 | 0
121 | Landscaping Sub-contractors | 3005 | m2 | 14478.475 | 4.8181 | 3005 | 5977.08 | 2.1055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3005 | 14478.475 | 350 | 388.85 | 1686.3448 | 3005 | 14478.475 | 350 | 388.85 | 1686.3448 | 3005 | 14478.475 | 2085 | 4027.08 | 10045.7971 | 3005 | 14478.475 | 3005 | 5977.08 | 14478.475 | 0
141 | Traffic Controllers | 2217 | hr | 195102.96 | 88.0031 | 375 | 38275.73 | 102.0693 | 150 | 13200.4709 | 4 | 392.1 | 2081.0982 | 370 | 32561.1616 | 11.5 | 1169.8 | 5983.1574 | 590 | 51921.8522 | 14 | 1452.6 | 7283.8438 | 810 | 71282.5429 | 14 | 1452.6 | 7283.8438 | 1030 | 90643.2336 | 24 | 2477.75 | 12486.5894 | 1250 | 110003.9242 | 34.5 | 3511.725 | 17949.4723 | 1470 | 129364.6149 | 63.5 | 6481.875 | 33037.4346 | 1690 | 148725.3055 | 154 | 15744.025 | 80122.2822 | 1910 | 168085.9962 | 161 | 16434.625 | 83764.2042 | 2130 | 187446.6869 | 223 | 22795.575 | 116021.2269 | 2217 | 195102.96 | 298 | 30373.01 | 155041.8189 | 2217 | 195102.96 | 367 | 37429.48 | 190940.7635 | 2217 | 195102.96 | 373 | 38098.98 | 194062.4109 | 2217 | 195102.96 | 375 | 38275.73 | 195102.96 | 0
151 | Supply & Place Silt fences | 11050 | m | 55250 | 5 | 1200 | 4825.82 | 4.0217 | 2000 | 10000 | 450 | 1843.575 | 20718.75 | 2000 | 10000 | 500 | 2002.65 | 23020.8333 | 2000 | 10000 | 500 | 2002.65 | 23020.8333 | 2000 | 10000 | 600 | 2374.39 | 27625 | 3000 | 15000 | 600 | 2374.39 | 27625 | 3000 | 15000 | 750 | 2957.665 | 34531.25 | 4000 | 20000 | 750 | 2957.665 | 34531.25 | 5000 | 25000 | 1100 | 4411.67 | 50645.8333 | 7000 | 35000 | 1100 | 4411.67 | 50645.8333 | 9000 | 45000 | 1150 | 4613.72 | 52947.9167 | 11050 | 55250 | 1150 | 4613.72 | 52947.9167 | 11050 | 55250 | 1150 | 4613.72 | 52947.9167 | 11050 | 55250 | 1200 | 4825.82 | 55250 | 11050 | 55250 | 1200 | 4825.82 | 55250 | 0
181 | Place Box Culverts | 202.4 | m | 44837.1667 | 221.5275 | 202.4 | 65321.65 | 325.5534 | 25.2 | 5582.4931 | 12 | 9003.025 | 2658.33 | 25.2 | 5582.4931 | 18.6 | 12534.825 | 4120.4116 | 25.2 | 5582.4931 | 25.2 | 14467.875 | 5582.4931 | 25.2 | 5582.4931 | 25.2 | 14467.875 | 5582.4931 | 64.8 | 14354.9822 | 64.8 | 20079.275 | 14354.9822 | 64.8 | 14354.9822 | 64.8 | 20471.375 | 14354.9822 | 64.8 | 14354.9822 | 64.8 | 20471.375 | 14354.9822 | 64.8 | 14354.9822 | 64.8 | 20471.375 | 14354.9822 | 202.4 | 44837.1667 | 64.8 | 20471.375 | 14354.9822 | 202.4 | 44837.1667 | 202.4 | 64546.375 | 44837.1667 | 202.4 | 44837.1667 | 202.4 | 64546.375 | 44837.1667 | 202.4 | 44837.1667 | 202.4 | 65321.65 | 44837.1667 | 202.4 | 44837.1667 | 202.4 | 65321.65 | 44837.1667 | 202.4 | 44837.1667 | 202.4 | 65321.65 | 44837.1667 | 0
182 | Supply Base Slabs | 0 | item | 0 | 0 | 1 | 570 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 570 | 0 | 0 | 0 | 1 | 570 | 0 | 0 | 0 | 1 | 570 | 0 | 0 | 0 | 1 | 570 | 0 | 0 | 0 | 1 | 570 | 0 | 0 | 0 | 1 | 570 | 0 | 0 | 0 | 1 | 570 | 0 | 0 | 0 | 1 | 570 | 0 | 0 | 0 | 1 | 570 | 0 | 0 | 0 | 1 | 570 | 0 | 0 | 0 | 1 | 570 | 0 | 0
201 | Non Conformance | 0 | item | 0 | 0 | 1 | 13650.62 | 13651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13650.62 | 0 | 0
220 | Protective Work | 0 | item | 0 | 0 | 1 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1500 | 0 | 0 | 0 | 1 | 1500 | 0 | 0 | 0 | 1 | 1500 | 0 | 0 | 0 | 1 | 1500 | 0 | 0 | 0 | 1 | 1500 | 0 | 0 | 0 | 1 | 1500 | 0 | 0
221 | Place Stone / Rock | 1885 | tonne | 29725 | 15.7692 | 1885 | 31753.728 | 17.6414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | 0 | 0 | 0 | 0 | 420 | 0 | 0 | 0 | 0 | 420 | 0 | 1500 | 23653.8462 | 1475 | 31753.728 | 23259.6154 | 1800 | 28384.6154 | 1761 | 31753.728 | 27769.6154 | 1800 | 28384.6154 | 1802 | 31753.728 | 28416.1538 | 1800 | 28384.6154 | 1802 | 31753.728 | 28416.1538 | 1885 | 29725 | 1802 | 31753.728 | 28416.1538 | 1885 | 29725 | 1885 | 31753.728 | 29725 | 1885 | 29725 | 1885 | 31753.728 | 29725 | 1885 | 29725 | 1885 | 31753.728 | 29725 | 0
222 | Supply & Place Geofabrics | 40080 | m2 | 147054.8114 | 3.669 | 40080 | 129487.46 | 3.2307 | 1800 | 6604.258 | 0 | 0 | 0 | 1800 | 6604.258 | 1652 | 11551.5 | 6061.2412 | 1800 | 6604.258 | 1652 | 11551.5 | 6061.2412 | 4000 | 14676.1289 | 3812 | 23754.8 | 13986.3508 | 7500 | 27517.7417 | 7138 | 43750.6 | 26189.552 | 10000 | 36690.3222 | 19400 | 62671.85 | 71179.2251 | 27000 | 99063.87 | 24500 | 80452.86 | 89891.2894 | 34000 | 124747.0955 | 30000 | 99607.46 | 110070.9666 | 38580 | 141551.2631 | 38580 | 123613.56 | 141551.2631 | 38580 | 141551.2631 | 38580 | 126686.96 | 141551.2631 | 40080 | 147054.8114 | 38580 | 128160.96 | 141551.2631 | 40080 | 147054.8114 | 40080 | 129487.46 | 147054.8114 | 40080 | 147054.8114 | 40080 | 129487.46 | 147054.8114 | 40080 | 147054.8114 | 40080 | 129487.46 | 147054.8114 | 0
901 | Project Management | 42 | week | 80857.5 | 1925.1786 | 48 | 658 | 0 | 2 | 3850.3571 | 2 | 405 | 3369.0625 | 6 | 11551.0714 | 6 | 405 | 10107.1875 | 10 | 19251.7857 | 10 | 405 | 16845.3125 | 14 | 26952.5 | 14 | 405 | 23583.4375 | 18 | 34653.2143 | 18 | 405 | 30321.5625 | 22 | 42353.9286 | 22 | 405 | 37059.6875 | 26 | 50054.6429 | 26 | 405 | 43797.8125 | 30 | 57755.3571 | 30 | 405 | 50535.9375 | 34 | 65456.0714 | 34 | 405 | 57274.0625 | 38 | 73156.7857 | 38 | 405 | 64012.1875 | 42 | 80857.5 | 42 | 405 | 70750.3125 | 42 | 80857.5 | 44 | 405 | 74119.375 | 42 | 80857.5 | 46 | 405 | 77488.4375 | 42 | 80857.5 | 48 | 658 | 80857.5 | 0
902 | Project Supervision | 42 | week | 120282.2222 | 2863.8624 | 56 | 150862.3304 | 2705.7143 | 2 | 5727.7249 | 5.2 | 13526.855 | 11169.0635 | 6 | 17183.1746 | 8.5 | 22713.005 | 18257.123 | 10 | 28638.6243 | 10.1 | 27021.605 | 21693.7579 | 14 | 40094.0741 | 12.5 | 33520.41 | 26848.7103 | 18 | 51549.5238 | 16 | 42783.9 | 34366.3492 | 22 | 63004.9735 | 21.1 | 56715.04 | 45320.623 | 26 | 74460.4233 | 26 | 69999.89 | 55845.3175 | 30 | 85915.873 | 31.2 | 84074.65 | 67014.381 | 34 | 97371.3228 | 36.2 | 97646.74 | 77753.8651 | 38 | 108826.7725 | 41.8 | 112695.3154 | 89782.0873 | 42 | 120282.2222 | 47.9 | 129067.9954 | 102884.2579 | 42 | 120282.2222 | 53 | 142999.1354 | 113838.5317 | 42 | 120282.2222 | 55.9 | 150862.3304 | 120067.4325 | 42 | 120282.2222 | 56 | 150862.3304 | 120282.2222 | 0
903 | Project Facilities | 42 | week | 52500 | 1250 | 56 | 14376.32 | 256.7143 | 2 | 2500 | 2.9 | 750.58 | 2718.75 | 6 | 7500 | 6 | 2720.22 | 5625 | 10 | 12500 | 6 | 2720.22 | 5625 | 14 | 17500 | 16.8 | 4272.22 | 15750 | 18 | 22500 | 22.9 | 5837.02 | 21468.75 | 22 | 27500 | 22.9 | 5837.02 | 21468.75 | 26 | 32500 | 23.4 | 5962.02 | 21937.5 | 30 | 37500 | 29.1 | 7419.52 | 27281.25 | 34 | 42500 | 34.7 | 8856.72 | 32531.25 | 38 | 47500 | 39.9 | 10176.72 | 37406.25 | 42 | 52500 | 45.3 | 11540.72 | 42468.75 | 42 | 52500 | 50.6 | 12906.52 | 47437.5 | 42 | 52500 | 56 | 14376.32 | 52500 | 42 | 52500 | 56 | 14376.32 | 52500 | 0
904 | Project Insurance, Fees & Levies | 1 | item | 32500 | 32500 | 1 | 29769.1 | 29769 | 0 | 0 | 0 | 0 | 0 | 0.75 | 24375 | 0.6 | 18281.81 | 19500 | 0.75 | 24375 | 0.6 | 18281.81 | 19500 | 0.75 | 24375 | 0.6 | 18281.81 | 19500 | 0.75 | 24375 | 0.6 | 18893.81 | 19500 | 0.75 | 24375 | 0.7 | 20141.27 | 22750 | 0.75 | 24375 | 0.7 | 21581.27 | 22750 | 0.75 | 24375 | 0.7 | 21800.27 | 22750 | 0.75 | 24375 | 0.8 | 23436.11 | 26000 | 1 | 32500 | 0.9 | 25093.55 | 29250 | 1 | 32500 | 0.9 | 28294.05 | 29250 | 1 | 32500 | 0.9 | 29683.9 | 29250 | 1 | 32500 | 1 | 29769.1 | 32500 | 1 | 32500 | 1 | 29769.1 | 32500 | 0
905 | Small Tools | 0 | item | 0 | 0 | 1 | 13752.069 | 13752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 695.05 | 0 | 0 | 0 | 0.2 | 1275.22 | 0 | 0 | 0 | 0.3 | 1850.066 | 0 | 0 | 0 | 0.4 | 2924.096 | 0 | 0 | 0 | 0.5 | 4223.026 | 0 | 0 | 0 | 0.6 | 7172.926 | 0 | 0 | 0 | 0.7 | 8068.601 | 0 | 0 | 0 | 0.8 | 9756.451 | 0 | 0 | 0 | 0.9 | 11068.731 | 0 | 0 | 0 | 0.9 | 12303.091 | 0 | 0 | 0 | 0.9 | 13382.734 | 0 | 0 | 0 | 1 | 13752.069 | 0 | 0 | 0 | 1 | 13752.069 | 0 | 0
907 | Site Establishment / disestablishment | 1 | item | 18700 | 18700 | 1 | 14352.61 | 14353 | 0.1 | 1870 | 0.1 | 1141.72 | 1870 | 0.2 | 3740 | 0.1 | 1281.52 | 1870 | 0.2 | 3740 | 0.1 | 1281.52 | 1870 | 0.2 | 3740 | 0.1 | 1281.52 | 1870 | 0.3 | 5610 | 0.1 | 1560.94 | 1870 | 0.5 | 9350 | 0.4 | 4882.34 | 7480 | 0.5 | 9350 | 0.6 | 6852.34 | 11220 | 0.6 | 11220 | 0.8 | 9256.14 | 14960 | 0.7 | 13090 | 0.9 | 9949.14 | 16830 | 0.7 | 13090 | 0.9 | 12285.79 | 16830 | 1 | 18700 | 0.95 | 13626.15 | 17765 | 1 | 18700 | 1 | 14152.61 | 18700 | 1 | 18700 | 1 | 14352.61 | 18700 | 1 | 18700 | 1 | 14352.61 | 18700 | 0
908 | Safety Work wear | 0 | item | 0 | 0 | 1 | 413.73 | 413.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65683 | 271.75 | 0 | 0 | 0 | 0.65683 | 271.75 | 0 | 0 | 0 | 0.65683 | 271.75 | 0 | 0 | 0 | 0.65683 | 271.75 | 0 | 0 | 0 | 0.65683 | 271.75 | 0 | 0 | 0 | 1 | 413.73 | 0 | 0 | 0 | 1 | 413.73 | 0 | 0 | 0 | 1 | 413.73 | 0 | 0
911 | Accommodation | 0 | item | 0 | 0 | 1 | 2626.9 | 2626.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.044859 | 117.84 | 0 | 0 | 0 | 0.044859 | 117.84 | 0 | 0 | 0 | 0.044859 | 117.84 | 0 | 0 | 0 | 0.14731 | 386.96 | 0 | 0 | 0 | 0.14731 | 386.96 | 0 | 0 | 0 | 0.14731 | 386.96 | 0 | 0 | 0 | 0.24476 | 642.95 | 0 | 0 | 0 | 0.34221 | 898.94 | 0 | 0 | 0 | 0.34221 | 898.94 | 0 | 0 | 0 | 0.41132 | 1080.5 | 0 | 0 | 0 | 0.41132 | 1080.5 | 0 | 0 | 0 | 0.41132 | 1080.5 | 0 | 0 | 0 | 1 | 2626.9 | 0 | 0
913 | Wet Weather Stand Down | 0 | hr | 0 | 0 | 327 | 13752.765 | 42.0574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.032775 | 450.75 | 0 | 0 | 0 | 0.12402 | 1705.675 | 0 | 0 | 0 | 0.50573 | 6955.15 | 0 | 0 | 0 | 0.50573 | 6955.15 | 0 | 0 | 0 | 0.60562 | 8328.95 | 0 | 0 | 0 | 0.68669 | 9443.95 | 0 | 0 | 0 | 1 | 13752.765 | 0 | 0 | 0 | 1 | 13752.765 | 0 | 0 | 0 | 1 | 13752.765 | 0 | 0 | 0 | 1 | 13752.765 | 0 | 0 | 0 | 1 | 13752.765 | 0 | 0
915 | Maintenance | 0 | item | 0 | 0 | 22 | 925.02 | 42.0464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17197 | 159.075 | 0 | 0 | 0 | 0.17197 | 159.075 | 0 | 0 | 0 | 0.17197 | 159.075 | 0 | 0 | 0 | 0.17197 | 159.075 | 0 | 0 | 0 | 0.17197 | 159.075 | 0 | 0 | 0 | 0.83812 | 775.275 | 0 | 0 | 0 | 0.83812 | 775.275 | 0 | 0 | 0 | 0.83812 | 775.275 | 0 | 0 | 0 | 0.83812 | 775.275 | 0 | 0 | 0 | 1 | 925.02 | 0 | 0
C20 | 20 Mpa | 0 | m3 | 0 | 0 | 2.25 | 372.81 | 165.6933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68614 | 255.8 | 0 | 0 | 0 | 0.68614 | 255.8 | 0 | 0 | 0 | 1 | 372.81 | 0 | 0 | 0 | 1 | 372.81 | 0 | 0 | 0 | 1 | 372.81 | 0 | 0 | 0 | 1 | 372.81 | 0 | 0 | 0 | 1 | 372.81 | 0 | 0 | 0 | 1 | 372.81 | 0 | 0
C25 | 25 Mpa | 50 | m3 | 25033.571 | 500.6714 | 75.96 | 12777.37 | 173.1174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7 | 639.16 | 1219.3814 | 0 | 0 | 4.5 | 786.11 | 1483.0315 | 0 | 0 | 11.4 | 1973.59 | 3757.013 | 6 | 3004.0285 | 11.4 | 1973.59 | 3757.013 | 6 | 3004.0285 | 11.4 | 1973.59 | 3757.013 | 6 | 3004.0285 | 25 | 4072.69 | 8239.0637 | 13 | 6508.7285 | 25 | 4072.69 | 8239.0637 | 20 | 10013.4284 | 29.3 | 4703.09 | 9656.1826 | 37.5 | 18775.1783 | 42.3 | 6955.89 | 13940.4957 | 50 | 25033.571 | 46.8 | 7725.89 | 15423.5272 | 50 | 25033.571 | 72.4 | 12163.27 | 23860.3283 | 50 | 25033.571 | 75.96 | 12777.37 | 25033.571 | 50 | 25033.571 | 75.96 | 12777.37 | 25033.571 | 0
C32 | 32 Mpa | 415.6 | m3 | 32767.072 | 78.8428 | 438.8 | 59600.368 | 183.2748 | 0 | 0 | 0 | 1027.52 | 0 | 42.75 | 3370.5301 | 39.6 | 3727.95 | 2957.1013 | 48.38 | 3814.4152 | 47.4 | 5156.11 | 3539.5606 | 48.38 | 3814.4152 | 45.4 | 5156.11 | 3390.2121 | 84.88 | 6692.1777 | 90.7 | 5156.11 | 6772.9568 | 94.38 | 7441.1844 | 134.6 | 13190.41 | 10051.1575 | 205 | 16162.7761 | 217.2 | 19988.21 | 16219.2526 | 260 | 20499.1307 | 247.6 | 25554.208 | 18489.3506 | 321 | 25308.5421 | 301 | 35339.828 | 22476.9569 | 415.6 | 32767.072 | 347.4 | 42843.938 | 25941.8432 | 415.6 | 32767.072 | 409.6 | 54234.838 | 30586.5832 | 415.6 | 32767.072 | 433.6 | 58636.468 | 32378.7658 | 415.6 | 32767.072 | 438.8 | 59600.368 | 32767.072 | 415.6 | 32767.072 | 438.8 | 59600.368 | 32767.072 | 0
C40 | 40 Mpa | 0 | m3 | 0 | 0 | 7.8 | 1518.62 | 194.6949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6421 | 514.4 | 0 | 0 | 0 | 2.6421 | 514.4 | 0 | 0 | 0 | 2.6421 | 514.4 | 0 | 0 | 0 | 2.6421 | 514.4 | 0 | 0 | 0 | 2.6421 | 514.4 | 0 | 0 | 0 | 2.6421 | 514.4 | 0 | 0 | 0 | 2.6421 | 514.4 | 0 | 0 | 0 | 2.6421 | 514.4 | 0 | 0 | 0 | 7.8 | 1518.62 | 0 | 0 | 0 | 7.8 | 1518.62 | 0 | 0 | 0 | 7.8 | 1518.62 | 0 | 0 | 0 | 7.8 | 1518.62 | 0 | 0 | 0 | 7.8 | 1518.62 | 0 | 0
CKM | Concrete - Keb Mix | 275 | m3 | 53069.0241 | 192.9783 | 111.56 | 21753.955 | 194.9978 | 0 | 0 | 0 | 0 | 0 | 21 | 4052.5437 | 21 | 4036.36 | 9989.6872 | 21 | 4052.5437 | 21 | 4036.36 | 9989.6872 | 21 | 4052.5437 | 21 | 4036.36 | 9989.6872 | 65 | 12543.5875 | 65 | 12347.88 | 30920.4605 | 65 | 12543.5875 | 65 | 12347.88 | 30920.4605 | 100 | 19297.827 | 111.56 | 20965.02 | 53069.0241 | 100 | 19297.827 | 111.56 | 20983.15 | 53069.0241 | 275 | 53069.0241 | 111.56 | 21255.195 | 53069.0241 | 275 | 53069.0241 | 111.56 | 21255.195 | 53069.0241 | 275 | 53069.0241 | 111.56 | 21255.195 | 53069.0241 | 275 | 53069.0241 | 111.56 | 21753.955 | 53069.0241 | 275 | 53069.0241 | 111.56 | 21753.955 | 53069.0241 | 275 | 53069.0241 | 111.56 | 21753.955 | 53069.0241 | 0
CSA | Cement Powder | 40 | tonne | 30143.13 | 753.5783 | 85.5 | 14398.4665 | 197.0724 | 5 | 3767.8913 | 5 | 0 | 1762.7561 | 5 | 3767.8913 | 5 | 0 | 1762.7561 | 5 | 3767.8913 | 5 | 0 | 1762.7561 | 8 | 6028.626 | 7 | 0 | 2467.8586 | 8 | 6028.626 | 7 | 0 | 2467.8586 | 8 | 6028.626 | 7 | 0 | 2467.8586 | 30 | 22607.3475 | 39 | 6089.32 | 13749.4979 | 40 | 30143.13 | 66.5 | 11409.9715 | 23444.6567 | 40 | 30143.13 | 69.5 | 11772.6965 | 24502.3104 | 40 | 30143.13 | 69.5 | 11772.6965 | 24502.3104 | 40 | 30143.13 | 73 | 12407.4665 | 25736.2396 | 40 | 30143.13 | 75.5 | 12407.4665 | 26617.6177 | 40 | 30143.13 | 85.5 | 14398.4665 | 30143.13 | 40 | 30143.13 | 85.5 | 14398.4665 | 30143.13 | 0
CSS | Stabilised Sand | 6 | m3 | 0 | 0 | 27 | 4110.94 | 152.2593 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 21 | 3249 | 0 | 3 | 0 | 21 | 3249 | 0 | 3 | 0 | 21 | 3249 | 0 | 4 | 0 | 25 | 3929.94 | 0 | 6 | 0 | 27 | 4110.94 | 0 | 6 | 0 | 27 | 4110.94 | 0 |  | 0 | 27 | 4110.94 | 0 | 6 | 0 | 27 | 4110.94 | 0 | 6 | 0 | 27 | 4110.94 | 0 | 6 | 0 | 27 | 4110.94 | 0 | 6 | 0 | 27 | 4110.94 | 0 | 6 | 0 | 27 | 4110.94 | 0 | 6 | 0 | 27 | 4110.94 | 0 | 0
QMR | Rock | 1885 | tonne | 69229.03 | 36.7263 | 1885 | 68183.8936 | 36.1719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 55089.4138 | 1475 | 53387.92 | 54171.2569 | 1800 | 66107.2966 | 1761 | 63646.936 | 64674.9718 | 1800 | 66107.2966 | 1802 | 65146.936 | 66180.7491 | 1800 | 66107.2966 | 1802 | 65308.4336 | 66180.7491 | 1885 | 69229.03 | 1802 | 65308.4336 | 66180.7491 | 1885 | 69229.03 | 1885 | 68183.8936 | 69229.03 | 1885 | 69229.03 | 1885 | 68183.8936 | 69229.03 | 1885 | 69229.03 | 1885 | 68183.8936 | 69229.03 | 0
QMS | Sand | 996 | tonne | 15119.56 | 15.1803 | 988.8 | 13323.9074 | 13.4749 | 50 | 759.0141 | 32 | 431.68 | 489.3061 | 150 | 2277.0422 | 141 | 1900.5 | 2156.0052 | 150 | 2277.0422 | 141 | 1900.5 | 2156.0052 | 200 | 3036.0562 | 199 | 2681.4017 | 3042.8726 | 300 | 4554.0843 | 296 | 3998.0249 | 4526.0819 | 430 | 6527.5209 | 427 | 5767.2079 | 6529.1789 | 580 | 8804.5631 | 570 | 7702.1241 | 8715.7658 | 700 | 10626.1968 | 680 | 9183.4229 | 10397.7557 | 830 | 12599.6333 | 833 | 11252.638 | 12737.2507 | 988.8 | 15010.262 | 857 | 11569.6751 | 13104.2303 | 996 | 15119.56 | 988.8 | 13264.1642 | 15119.56 | 996 | 15119.56 | 988.8 | 13323.9074 | 15119.56 | 996 | 15119.56 | 988.8 | 13323.9074 | 15119.56 | 996 | 15119.56 | 988.8 | 13323.9074 | 15119.56 | 0
RFS | Signs | 1 | each | 4620 | 4620 | 1 | 959.07 | 959 | 0.5 | 2310 | 0.4 | 445.2 | 1848 | 0.5 | 2310 | 0.6 | 578.95 | 2772 | 0.5 | 2310 | 0.9 | 870.43 | 4158 | 1 | 4620 | 0.9 | 870.43 | 4158 | 1 | 4620 | 0.9 | 870.43 | 4158 | 1 | 4620 | 1 | 959.07 | 4620 | 1 | 4620 | 1 | 959.07 | 4620 | 1 | 4620 | 1 | 959.07 | 4620 | 1 | 4620 | 1 | 959.07 | 4620 | 1 | 4620 | 1 | 959.07 | 4620 | 1 | 4620 | 1 | 959.07 | 4620 | 1 | 4620 | 1 | 959.07 | 4620 | 1 | 4620 | 1 | 959.07 | 4620 | 1 | 4620 | 1 | 959.07 | 4620 | 0
RSM | Mesh | 1339.2 | m2 | 13862.6 | 10.3514 | 1339.2 | 14373.948 | 10.7333 | 432 | 4471.8065 | 403.2 | 4350 | 4173.686 | 864 | 8943.6129 | 720 | 8180.2 | 7453.0108 | 864 | 8943.6129 | 806.4 | 8558.1 | 8347.3721 | 864 | 8943.6129 | 806.4 | 8558.1 | 8347.3721 | 864 | 8943.6129 | 806.4 | 8558.1 | 8347.3721 | 864 | 8943.6129 | 806.4 | 8558.1 | 8347.3721 | 1123.2 | 11626.6968 | 1022.4 | 11001.6 | 10583.2753 | 1123.2 | 11626.6968 | 1022.4 | 11001.6 | 10583.2753 | 1339.2 | 13862.6 | 1022.4 | 11001.6 | 10583.2753 | 1339.2 | 13862.6 | 1195.2 | 12814.358 | 12371.9979 | 1339.2 | 13862.6 | 1267.2 | 13600.358 | 13117.299 | 1339.2 | 13862.6 | 1339.2 | 14373.948 | 13862.6 | 1339.2 | 13862.6 | 1339.2 | 14373.948 | 13862.6 | 1339.2 | 13862.6 | 1339.2 | 14373.948 | 13862.6 | 0
SWC | RCBC | 202.4 | m | 68168.088 | 336.7989 | 202.4 | 67270 | 332.3617 | 25.2 | 8487.3311 | 0 | 0 | 0 | 25.2 | 8487.3311 | 0 | 0 | 0 | 25.2 | 8487.3311 | 0 | 0 | 0 | 25.2 | 8487.3311 | 0 | 0 | 0 | 43.2 | 14549.7105 | 33.6 | 11100 | 11316.4415 | 43.2 | 14549.7105 | 43.2 | 14604 | 14549.7105 | 43.2 | 14549.7105 | 43.2 | 14604 | 14549.7105 | 43.2 | 14549.7105 | 43.2 | 14604 | 14549.7105 | 43.2 | 14549.7105 | 43.2 | 14604 | 14549.7105 | 202.4 | 68168.088 | 194.4 | 64204 | 65473.6972 | 202.4 | 68168.088 | 194.4 | 64204 | 65473.6972 | 202.4 | 68168.088 | 202.4 | 67270 | 68168.088 | 202.4 | 68168.088 | 202.4 | 67270 | 68168.088 | 202.4 | 68168.088 | 202.4 | 67270 | 68168.088 | 0
SWL | Grates, Frames & Lids | 19 | each | 3000 | 157.8947 | 19 | 8583.04 | 451.7368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 2684.2105 | 0 | 0 | 0 | 17 | 2684.2105 | 0 | 0 | 0 | 17 | 2684.2105 | 5 | 2320 | 789.4737 | 17 | 2684.2105 | 11 | 5253.5 | 1736.8421 | 17 | 2684.2105 | 11 | 5253.5 | 1736.8421 | 17 | 2684.2105 | 13 | 5849.5 | 2052.6316 | 19 | 3000 | 13 | 6128.5 | 2052.6316 | 19 | 3000 | 13 | 6128.5 | 2052.6316 | 19 | 3000 | 19 | 8583.04 | 3000 | 19 | 3000 | 19 | 8583.04 | 3000 | 0
SWP | RCP | 67.86 | m | 32433.92 | 477.9534 | 67.86 | 10551.499 | 155.4819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.7 | 5592.0552 | 28.08 | 1778 | 13420.9324 | 11.7 | 5592.0552 | 11.7 | 1778 | 5592.0552 | 11.7 | 5592.0552 | 11.7 | 1778 | 5592.0552 | 49.14 | 23486.6317 | 49.14 | 7592 | 23486.6317 | 49.14 | 23486.6317 | 49.14 | 7592 | 23486.6317 | 49.14 | 23486.6317 | 49.14 | 7592 | 23486.6317 | 67.86 | 32433.92 | 49.14 | 7592 | 23486.6317 | 67.86 | 32433.92 | 56.16 | 8731.999 | 26841.8648 | 67.86 | 32433.92 | 67.86 | 10551.499 | 32433.92 | 67.86 | 32433.92 | 67.86 | 10551.499 | 32433.92 | 67.86 | 32433.92 | 67.86 | 10551.499 | 32433.92 | 67.86 | 32433.92 | 67.86 | 10551.499 | 32433.92 | 0
SWPC | Pre-cast Pit Tops / backstones | 19 | each | 25742.7 | 1354.8789 | 19 | 13460 | 708.4211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 511.67 | 1354.8789 | 0 | 0 | 1 | 511.67 | 1354.8789 | 17 | 23032.9421 | 17 | 12001.7 | 23032.9421 | 17 | 23032.9421 | 17 | 12001.7 | 23032.9421 | 17 | 23032.9421 | 17 | 12001.7 | 23032.9421 | 17 | 23032.9421 | 17 | 12001.7 | 23032.9421 | 17 | 23032.9421 | 17 | 12001.7 | 23032.9421 | 17 | 23032.9421 | 17 | 12001.7 | 23032.9421 | 17 | 23032.9421 | 17 | 12001.7 | 23032.9421 | 19 | 25742.7 | 19 | 13460 | 25742.7 | 19 | 25742.7 | 19 | 13460 | 25742.7 | 19 | 25742.7 | 19 | 13460 | 25742.7 | 0
WMF | Watermain Fittings | 0 | item | 0 | 0 | 1 | 134.4 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 1 | 134.4 | 0 | 0 | 0 | 1 | 134.4 | 0 | 0 | 0 | 1 | 134.4 | 0 | 0
| Totals, all cost codes |  |  | 3194691.6815 |  |  | 3156786.2267 |  |  | 89286.236 |  | 57561.539 | 72181.8657 |  | 241340.4625 |  | 192294.534 | 188466.4066 |  | 320137.9516 |  | 241449.154 | 238406.4764 |  | 454985.746 |  | 338467.7867 | 333019.8633 |  | 678602.0485 |  | 482125.7399 | 504477.4562 |  | 938526.8396 |  | 688306.0279 | 745457.3372 |  | 1400917.8432 |  | 1064916.9608 | 1090502.9507 |  | 1937707.8169 |  | 1542416.8239 | 1680135.8885 |  | 2276680.8637 |  | 1809587.3055 | 1944256.1474 |  | 2726958.132 |  | 2255080.3026 | 2386117.7515 |  | 3174601.9236 |  | 2727591.5625 | 2747230.4393 |  | 3194691.6815 |  | 3043660.3667 | 3053562.8817 |  | 3194691.6815 |  | 3123351.5617 | 3153427.3036 |  | 3194691.6815 |  | 3156786.2267 | 3194691.6815
|  | PV | EV | AC
| 2011-10-01 | 89286.236 | 72181.8657 | 57561.539
| 2011-11-01 | 241340.4625 | 188466.4066 | 192294.534
| 2011-12-01 | 320137.9516 | 238406.4764 | 241449.154
| 2012-01-01 | 454985.746 | 333019.8633 | 338467.7867
| 2012-02-01 | 678602.0485 | 504477.4562 | 482125.7399
| 2012-03-01 | 938526.8396 | 745457.3372 | 688306.0279
| 2012-04-01 | 1400917.8432 | 1090502.9507 | 1064916.9608
| 2012-05-01 | 1937707.8169 | 1680135.8885 | 1542416.8239
| 2012-06-01 | 2276680.8637 | 1944256.1474 | 1809587.3055
| 2012-07-01 | 2726958.132 | 2386117.7515 | 2255080.3026
| 2012-08-01 | 3174601.9236 | 2747230.4393 | 2727591.5625
| 2012-09-01 | 3194691.6815 | 3053562.8817 | 3043660.3667
| 2012-10-01 | 3194691.6815 | 3153427.3036 | 3123351.5617
| 2012-11-01 | 3194691.6815 | 3194691.6815 | 3156786.2267

## Actual Costs
Date | Description | Resource | Unit | Quantity | Rate | Total | Portfolio WBS | Portfolio WBS | AC | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01
Portfolio WBS 011
2011-11-23 | Inv SI3632343 | Survey |  | 1 | 2701.68 | 2701.68 | 11 | 11 | 44729.58 | 0 | 2701.68 | 2701.68 | 3812.38 | 7648.38 | 9078.38 | 11980.48 | 21999.28 | 21999.28 | 31311.88 | 34782.13 | 42620.43 | 44729.58 | 44729.58
2012-01-23 | Inv No - SI3636328 | Field Density |  | 1 | 742 | 742 | 11 | 12 | 18263.07 | 0 | 0 | 0 | 0 | 0 | 1634.92 | 1634.92 | 1634.92 | 7912.42 | 10091.92 | 11058.92 | 12071.02 | 12825.67 | 18263.07
2012-01-23 | Inv No - SI3636326 | Field Density |  | 1 | 368.7 | 368.7 | 11 | 13 | 27869.52 | 0 | 1591.54 | 2350.81 | 2670.9 | 4611.7 | 4611.7 | 9695.78 | 12901.68 | 14673.95 | 14673.95 | 25104.7 | 27744.07 | 27869.52 | 27869.52
2012-02-22 | Inv No - SI3638506 | Field Survey |  | 1 | 666.5 | 666.5 | 11 | 15 | 4054.9 | 0 | 0 | 0 | 195 | 195 | 1480 | 1480 | 2282.5 | 2860 | 3107.5 | 4054.9 | 4054.9 | 4054.9 | 4054.9
2012-02-22 | Inv No - SI3638507 | Field Survey |  | 1 | 3169.5 | 3169.5 | 11 | 32 | 2535.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1933.19 | 1959.34 | 1987.65 | 1997.09 | 2350.36 | 2535.32 | 2535.32
2012-03-12 | Inv No- SI3639265 | Field Survey |  | 1 | 1430 | 1430 | 11 | 33 | 25138.27 | 0 | 0 | 2940.25 | 2940.25 | 2940.25 | 4770.45 | 7250.785 | 8553.17 | 8553.17 | 8553.17 | 11683.645 | 15479.395 | 25138.27 | 25138.27
2012-04-19 | Inv No - SI3641254 | Field Survey |  | 1 | 781.6 | 781.6 | 11 | 41 | 12448.88 | 0 | 330 | 330 | 330 | 1352.8 | 2167.925 | 2167.925 | 7077.435 | 7077.435 | 11067.78 | 12448.88 | 12448.88 | 12448.88 | 12448.88
2012-04-19 | Inv No - SI3641258 | Field Survey |  | 1 | 1029.5 | 1029.5 | 11 | 52 | 193.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193.5 | 193.5 | 193.5 | 193.5 | 193.5 | 193.5 | 193.5
2012-04-19 | Inv No - SI3641256 | Field Survey |  | 1 | 1091 | 1091 | 11 | 53 | 308767.983 | 18346.464 | 37000.539 | 40441.939 | 71961.764 | 97868.889 | 114354.864 | 164115.944 | 188753.5315 | 230001.577 | 238750.477 | 274349.877 | 305562.633 | 308767.983 | 308767.983
2012-05-21 | Inv No - SI3643241 | Field Survey |  | 1 | 1102.4 | 1102.4 | 11 | 57 | 215667.317 | 0 | 0 | 0 | 0 | 0 | 0 | 42660.3837 | 81882.5185 | 81882.5185 | 146832.5735 | 206533.272 | 215667.317 | 215667.317 | 215667.317
2012-05-21 | Inv No - SI3643249 | Field Survey |  | 1 | 2554.8 | 2554.8 | 11 | 61 | 4390.425 | 530.25 | 2080.5 | 2080.5 | 2080.5 | 2080.5 | 3667.625 | 3667.625 | 3667.625 | 3667.625 | 3667.625 | 4390.425 | 4390.425 | 4390.425 | 4390.425
2012-05-21 | Inv No - SI3643246 | Field Survey |  | 1 | 4954.1 | 4954.1 | 11 | 62 | 382852.6255 | 3990.07 | 29107.38 | 44215.21 | 59531.29 | 76785.94 | 110169.115 | 152455.78 | 194475.9775 | 229892.6485 | 260952.6235 | 333157.8355 | 382852.6255 | 382852.6255 | 382852.6255
2012-05-21 | Inv No - SI3643244 | Field Survey |  | 1 | 1407.5 | 1407.5 | 11 | 63 | 86275.348 | 0 | 4226.71 | 4226.71 | 4226.71 | 7927.91 | 14756.62 | 30773.57 | 36702.47 | 46879.845 | 47698.995 | 66733.096 | 86275.348 | 86275.348 | 86275.348
2012-07-17 | Inv No - SI3656365 | Field Survey |  | 1 | 6777.6 | 6777.6 | 11 | 64 | 274290.025 | 1377.5 | 1377.5 | 10775.265 | 10775.265 | 10775.265 | 10775.265 | 10775.265 | 72009.515 | 79412.515 | 86553.345 | 198423.965 | 274117.525 | 274290.025 | 274290.025
2012-07-26 | Survey Team. Inv No - SI3647089 | Field Survey |  | 1 | 2535 | 2535 | 11 | 65 | 261664.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108392.669 | 108392.669 | 251275.169 | 251275.169 | 258529.919 | 261664.129 | 261664.129
2012-08-15 | Inv No - SI3648210 | Field Survey |  | 1 | 606.1 | 606.1 | 11 | 66 | 4773.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2153 | 2153 | 4773.75
2012-08-16 | Inv No - SI3648242 | Field Survey |  | 1 | 1006.5 | 1006.5 | 11 | 67 | 2520.95 | 0 | 0 | 0 | 0 | 0 | 0 | 415.45 | 415.45 | 945.7 | 1563.2 | 1563.2 | 2520.95 | 2520.95 | 2520.95
2012-08-16 | Inv No - SI3648246 | Field Survey |  | 1 | 1857.65 | 1857.65 | 11 | 68 | 46094.08 | 0 | 0 | 0 | 0 | 0 | 0 | 13611.895 | 13611.895 | 46094.08 | 46094.08 | 46094.08 | 46094.08 | 46094.08 | 46094.08
2012-09-17 | Inv No - SI3649823 | Field Survey |  | 1 | 1859 | 1859 | 11 | 71 | 86929.5843 | 0 | 3547.1 | 3547.1 | 3547.1 | 3711.73 | 24033.01 | 35554.82 | 39508.57 | 44816.72 | 54736.045 | 62825.1593 | 69605.6343 | 86079.5843 | 86929.5843
2012-09-17 | Inv No - SI3649824 | Field Survey |  | 1 | 1625 | 1625 | 11 | 72 | 13301.4 | 0 | 141.4 | 4001.4 | 13301.4 | 13301.4 | 13301.4 | 13301.4 | 13301.4 | 13301.4 | 13301.4 | 13301.4 | 13301.4 | 13301.4 | 13301.4
2012-09-17 | Inv No - SI3649825 | Field Survey |  | 1 | 1292 | 1292 | 11 | 73 | 55980.8 | 0 | 0 | 0 | 360 | 4660 | 5212.8 | 6172.3 | 13640.675 | 20798.85 | 25310.23 | 29815.23 | 39114.5 | 55980.8 | 55980.8
2012-09-17 | Inv No - SI3649822 | Field Survey |  | 1 | 684 | 684 | 11 | 75 | 8705.77 | 0 | 2715.72 | 2715.72 | 3652.495 | 4218.095 | 4530.695 | 4530.695 | 4684.745 | 4826.145 | 5321.045 | 7397.32 | 8705.77 | 8705.77 | 8705.77
2012-09-17 | Inv No - SI3649826 | Field Survey |  | 1 | 2378.3 | 2378.3 | 11 | 81 | 19984.005 | 0 | 0 | 300.475 | 8879.99 | 8879.99 | 15528.44 | 15528.44 | 15528.44 | 15528.44 | 17758.585 | 19882.545 | 19984.005 | 19984.005 | 19984.005
2012-10-18 | Docket No 09888 09890 09891 09893 09894 . Inv No SI3651775 | Field Survey |  | 1 | 754.65 | 754.65 | 11 | 85 | 16398.015 | 0 | 0 | 70.7 | 2064.225 | 2064.225 | 2970.525 | 5692.925 | 9640.315 | 9640.315 | 9923.115 | 9923.115 | 9923.115 | 16398.015 | 16398.015
2012-10-18 | Inv No - SI3651777 | Field Survey |  | 1 | 1354.5 | 1354.5 | 11 | 86 | 41911.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71.81 | 41911.81 | 41911.81 | 41911.81
| Subtotal for 011 |  |  |  |  | 44729.58 |  | 87 | 58724.45 | 0 | 11174.725 | 11892.875 | 14670.175 | 25627 | 30238.4 | 30238.4 | 33913.3 | 45796.425 | 46263.925 | 58565.375 | 58724.45 | 58724.45 | 58724.45
[8 empty] | 103 | 287637.5 | 0 | 0 | 920 | 920 | 920 | 43097.1 | 73213.5 | 151583.5 | 196911.5 | 207821.5 | 280837.5 | 280837.5 | 280837.5 | 287637.5
| Portfolio WBS 012 | [6 empty] | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 110 | 110 | 110 | 110
2012-03-12 | Inv No - SI3639264 | Survey |  | 1 | 1634.92 | 1634.92 | 12 | 120 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 350 | 350
2012-06-15 | Inv No - SI3644798 | Field Survey |  | 1 | 1747.3 | 1747.3 | 12 | 121 | 5977.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388.85 | 388.85 | 4027.08 | 5977.08
2012-06-15 | Inv No - SI3644801 | Field Survey |  | 1 | 944.8 | 944.8 | 12 | 141 | 38275.73 | 392.1 | 1169.8 | 1452.6 | 1452.6 | 2477.75 | 3511.725 | 6481.875 | 15744.025 | 16434.625 | 22795.575 | 30373.01 | 37429.48 | 38098.98 | 38275.73
2012-06-15 | Inv No - SI3644803 | Field Survey |  | 1 | 1908.4 | 1908.4 | 12 | 151 | 4825.82 | 1843.575 | 2002.65 | 2002.65 | 2374.39 | 2374.39 | 2957.665 | 2957.665 | 4411.67 | 4411.67 | 4613.72 | 4613.72 | 4613.72 | 4825.82 | 4825.82
2012-06-15 | Inv No - SI3644799 | Field Survey |  | 1 | 1677 | 1677 | 12 | 181 | 65321.65 | 9003.025 | 12534.825 | 14467.875 | 14467.875 | 20079.275 | 20471.375 | 20471.375 | 20471.375 | 20471.375 | 64546.375 | 64546.375 | 65321.65 | 65321.65 | 65321.65
2012-07-17 | Inv No - SI3646365 | Field Survey |  | 1 | 2179.5 | 2179.5 | 12 | 182 | 570 | 0 | 0 | 0 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570
2012-08-16 | Inv No - SI3648251 | Field Survey |  | 1 | 967 | 967 | 12 | 201 | 13650.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13650.62
2012-09-17 | Inv No - SI3649823 | Field Survey |  | 1 | 609.6 | 609.6 | 12 | 220 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
2012-09-17 | Inv No - SI3649824 | Field Survey |  | 1 | 402.5 | 402.5 | 12 | 221 | 31753.728 | 0 | 0 | 0 | 420 | 420 | 420 | 31753.728 | 31753.728 | 31753.728 | 31753.728 | 31753.728 | 31753.728 | 31753.728 | 31753.728
2012-10-18 | Dockets No - 09888 09890 09891 09893 09894 Inv No - SI3651775 | Field Survey |  | 1 | 754.65 | 754.65 | 12 | 222 | 129487.46 | 0 | 11551.5 | 11551.5 | 23754.8 | 43750.6 | 62671.85 | 80452.86 | 99607.46 | 123613.56 | 126686.96 | 128160.96 | 129487.46 | 129487.46 | 129487.46
2012-11-12 | Doherty Street. | Field Survey |  | 1 | 2329.4 | 2329.4 | 12 | 901 | 658 | 405 | 405 | 405 | 405 | 405 | 405 | 405 | 405 | 405 | 405 | 405 | 405 | 405 | 658
2012-11-12 | Anzac Street | Field Survey |  | 1 | 500 | 500 | 12 | 902 | 150862.3304 | 13526.855 | 22713.005 | 27021.605 | 33520.41 | 42783.9 | 56715.04 | 69999.89 | 84074.65 | 97646.74 | 112695.3154 | 129067.9954 | 142999.1354 | 150862.3304 | 150862.3304
2012-11-12 | Faust Street | Field Survey |  | 1 | 2608 | 2608 | 12 | 903 | 14376.32 | 750.58 | 2720.22 | 2720.22 | 4272.22 | 5837.02 | 5837.02 | 5962.02 | 7419.52 | 8856.72 | 10176.72 | 11540.72 | 12906.52 | 14376.32 | 14376.32
| Subtotal for 012 |  |  |  |  | 18263.07 |  | 904 | 29769.1 | 0 | 18281.81 | 18281.81 | 18281.81 | 18893.81 | 20141.27 | 21581.27 | 21800.27 | 23436.11 | 25093.55 | 28294.05 | 29683.9 | 29769.1 | 29769.1
[8 empty] | 905 | 13752.069 | 0 | 695.05 | 1275.22 | 1850.066 | 2924.096 | 4223.026 | 7172.926 | 8068.601 | 9756.451 | 11068.731 | 12303.091 | 13382.734 | 13752.069 | 13752.069
| Portfolio WBS 013 | [6 empty] | 907 | 14352.61 | 1141.72 | 1281.52 | 1281.52 | 1281.52 | 1560.94 | 4882.34 | 6852.34 | 9256.14 | 9949.14 | 12285.79 | 13626.15 | 14152.61 | 14352.61 | 14352.61
2011-11-25 | Moisture Density Relationship & FD (nuclear Gauge ) Inv No CBW:69122235 | Field Density |  | 1 | 600 | 600 | 13 | 908 | 413.73 | 0 | 0 | 0 | 0 | 0 | 0 | 271.75 | 271.75 | 271.75 | 271.75 | 271.75 | 413.73 | 413.73 | 413.73
2011-11-30 | Inv No 106837 | Field Density |  | 1 | 991.54 | 991.54 | 13 | 911 | 2626.9 | 0 | 117.84 | 117.84 | 117.84 | 386.96 | 386.96 | 386.96 | 642.95 | 898.94 | 898.94 | 1080.5 | 1080.5 | 1080.5 | 2626.9
2011-12-14 | Inv No SI3633896 | Field Density |  | 1 | 446 | 446 | 13 | 913 | 13752.765 | 0 | 0 | 0 | 450.75 | 1705.675 | 6955.15 | 6955.15 | 8328.95 | 9443.95 | 13752.765 | 13752.765 | 13752.765 | 13752.765 | 13752.765
2011-12-21 | Inv No 107125 | Compressive Streght Test |  | 1 | 313.27 | 313.27 | 13 | 915 | 925.02 | 0 | 0 | 0 | 0 | 159.075 | 159.075 | 159.075 | 159.075 | 159.075 | 775.275 | 775.275 | 775.275 | 775.275 | 925.02
2012-01-31 | Inv No - 107480 | Field Density |  | 1 | 320.09 | 320.09 | 13 | C20 - 20Mpa | 372.81 | 0 | 0 | 0 | 0 | 0 | 0 | 255.8 | 255.8 | 372.81 | 372.81 | 372.81 | 372.81 | 372.81 | 372.81
2012-02-29 | Inv No - 107842 | Field Density |  | 1 | 1058.81 | 1058.81 | 13 | C25 | 12777.37 | 0 | 639.16 | 786.11 | 1973.59 | 1973.59 | 1973.59 | 4072.69 | 4072.69 | 4703.09 | 6955.89 | 7725.89 | 12163.27 | 12777.37 | 12777.37
2012-02-29 | Inv No - 107837 | Field Density |  | 1 | 819.63 | 819.63 | 13 | C32 | 59600.368 | 1027.52 | 3727.95 | 5156.11 | 5156.11 | 5156.11 | 13190.41 | 19988.21 | 25554.208 | 35339.828 | 42843.938 | 54234.838 | 58636.468 | 59600.368 | 59600.368
2012-02-29 | Travel to Site. Inv No - 107836 | Field Density |  | 1 | 62.36 | 62.36 | 13 | C40 | 1518.62 | 0 | 514.4 | 514.4 | 514.4 | 514.4 | 514.4 | 514.4 | 514.4 | 514.4 | 1518.62 | 1518.62 | 1518.62 | 1518.62 | 1518.62
2012-04-30 | Inv No - 108595 | Field Density |  | 1 | 1319.18 | 1319.18 | 13 | CKM | 21753.955 | 0 | 4036.36 | 4036.36 | 4036.36 | 12347.88 | 12347.88 | 20965.02 | 20983.15 | 21255.195 | 21255.195 | 21255.195 | 21753.955 | 21753.955 | 21753.955
2012-04-30 | Inv No - 108600 | Field Density |  | 1 | 821 | 821 | 13 | CSA | 14398.4665 | 0 | 0 | 0 | 0 | 0 | 0 | 6089.32 | 11409.9715 | 11772.6965 | 11772.6965 | 12407.4665 | 12407.4665 | 14398.4665 | 14398.4665
2012-04-30 | Inv No - 108599 | Field Density |  | 1 | 2943.9 | 2943.9 | 13 | CSS | 4110.94 | 0 | 3249 | 3249 | 3249 | 3929.94 | 4110.94 | 4110.94 | 4110.94 | 4110.94 | 4110.94 | 4110.94 | 4110.94 | 4110.94 | 4110.94
2012-05-31 | Inv No - 108999 | Field Density |  | 1 | 970.9 | 970.9 | 13 | QMR | 68183.8936 | 0 | 0 | 0 | 0 | 0 | 0 | 53387.92 | 63646.936 | 65146.936 | 65308.4336 | 65308.4336 | 68183.8936 | 68183.8936 | 68183.8936
2012-05-31 | Inv No - 109003 | Field Density |  | 1 | 1220 | 1220 | 13 | QMS | 13323.9074 | 431.68 | 1900.5 | 1900.5 | 2681.4017 | 3998.0249 | 5767.2079 | 7702.1241 | 9183.4229 | 11252.638 | 11569.6751 | 13264.1642 | 13323.9074 | 13323.9074 | 13323.9074
2012-05-31 | Inv No - 108998 | Field Density |  | 1 | 1015 | 1015 | 13 | RFS | 959.07 | 445.2 | 578.95 | 870.43 | 870.43 | 870.43 | 959.07 | 959.07 | 959.07 | 959.07 | 959.07 | 959.07 | 959.07 | 959.07 | 959.07
2012-06-30 | Inv No - 109449 | Field Density |  | 1 | 757.27 | 757.27 | 13 | RSM | 14373.948 | 4350 | 8180.2 | 8558.1 | 8558.1 | 8558.1 | 8558.1 | 11001.6 | 11001.6 | 11001.6 | 12814.358 | 13600.358 | 14373.948 | 14373.948 | 14373.948
2012-06-30 | Inv No - 109451 | Field Density |  | 1 | 1015 | 1015 | 13 | SWC | 67270 | 0 | 0 | 0 | 0 | 11100 | 14604 | 14604 | 14604 | 14604 | 64204 | 64204 | 67270 | 67270 | 67270
2012-08-10 | Inv No - ICR1300457 | Field Density |  | 1 | 343.45 | 343.45 | 13 | SWL | 8583.04 | 0 | 0 | 0 | 0 | 0 | 0 | 2320 | 5253.5 | 5253.5 | 5849.5 | 6128.5 | 6128.5 | 8583.04 | 8583.04
2012-08-10 | Inv No - ICR1300456 | Field Density |  | 1 | 6389.79 | 6389.79 | 13 | SWP | 10551.499 | 0 | 0 | 1778 | 1778 | 1778 | 7592 | 7592 | 7592 | 7592 | 8731.999 | 10551.499 | 10551.499 | 10551.499 | 10551.499
2012-08-31 | Inv No - ICR1300831 | Field Density |  | 1 | 452.17 | 452.17 | 13 | SWPC | 13460 | 0 | 0 | 511.67 | 511.67 | 12001.7 | 12001.7 | 12001.7 | 12001.7 | 12001.7 | 12001.7 | 12001.7 | 13460 | 13460 | 13460
2012-08-31 | Inv No - ICR1300819 | Field Density |  | 1 | 1077.19 | 1077.19 | 13 | WMF | 134.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134.4 | 134.4 | 134.4
2012-08-31 | Inv No - ICR1300829 | Field Density |  | 1 | 2168.15 | 2168.15 | 13 | TOTAL | 3156786.2267 | 57561.539 | 192294.534 | 241449.154 | 338467.7867 | 482125.7399 | 688306.0279 | 1064916.9608 | 1542416.8239 | 1809587.3055 | 2255080.3026 | 2727591.5625 | 3043660.3667 | 3123351.5617 | 3156786.2267
2012-09-30 | Inv No - ICR1301209 | Field Density |  | 1 | 2089.02 | 2089.02 | 13
2012-09-30 | Inv No - ICR1301208 | Field Density |  | 1 | 550.35 | 550.35 | 13
2012-10-31 | Inv No - ICR1301601 | Field Density |  | 1 | 125.45 | 125.45 | 13
| Subtotal for 013 |  |  |  |  | 27869.52
Portfolio WBS 015
2012-01-18 | Worked carried out corner of Lurline drive & Dodd Str. Inv No - 00102754 | Service Locator |  | 1.5 | 130 | 195 | 15
2012-03-07 | Inv No - 102844 | Service Locator |  | 1 | 130 | 130 | 15
2012-03-26 | Inv No - 102889 | Service Locator |  | 7 | 165 | 1155 | 15
2012-05-09 | Inv No - 0168 | Service Locator |  | 1 | 600 | 600 | 15
2012-05-23 | Cable Location carried out on Dobbin Lane. Inv No - 220 | Service Locator |  | 1.5 | 135 | 202.5 | 15
2012-06-19 | Inv No - 0284 | Service Locator |  | 2.5 | 165 | 412.5 | 15
2012-06-29 | Inv No - 305 | Service Locator |  | 1 | 165 | 165 | 15
2012-07-27 | Inv No - 350 | Service Locator |  | 1.5 | 165 | 247.5 | 15
2012-08-20 | Work Carried out on Faust/Compton. Inv No - 0263 | Service Locator |  | 1 | 947.4 | 947.4 | 15
| Subtotal for 015 |  |  |  |  | 4054.9
Portfolio WBS 032
2012-05-22 | Waste-Disposal | Waste Disposal |  | 1 | 1586.01 | 1586.01 | 32
2012-05-22 | Waste-Disposal | Waste Disposal |  | 1 | 247.74 | 247.74 | 32
2012-05-23 | Waste-Disposal | Waste Disposal |  | 1 | 99.44 | 99.44 | 32
2012-06-18 | Waste-Disposal | Waste Disposal |  | 1 | 10.24 | 10.24 | 32
2012-06-30 | Waste-Disposal | Waste Disposal |  | 1 | 15.91 | 15.91 | 32
2012-07-31 | Waste-Disposal | Waste Disposal |  | 1 | 28.31 | 28.31 | 32
2012-08-21 | Waste-Disposal | Waste Disposal |  | 1 | 9.44 | 9.44 | 32
2012-09-20 | Waste-Disposal | Waste Disposal |  | 1 | 320 | 320 | 32
2012-09-30 | Waste-Disposal | Waste Disposal |  | 1 | 33.27 | 33.27 | 32
2012-10-19 | Waste-Disposal | Waste Disposal |  | 1 | 114.79 | 114.79 | 32
2012-10-19 | Waste-Disposal | Waste Disposal |  | 1 | 70.17 | 70.17 | 32
| Subtotal for 032 |  |  |  |  | 2535.32
Portfolio WBS 033
2011-12-09 | 21 Tonne Excavator | Berry Excavations | hr | 2 | 110 | 220 | 33
2011-12-09 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 33
2011-12-09 | Bobcat | Labour | hr | 10 | 90 | 900 | 33
2011-12-12 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 33
2011-12-12 | Truck | Labour | hr | 6 | 65 | 390 | 33
2011-12-12 | Bobcat | Labour | hr | 10 | 90 | 900 | 33
2011-12-12 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 33
2012-03-02 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4.5 | 90 | 405 | 33
2012-03-02 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 33
2012-03-02 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 33
2012-03-05 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 33
2012-03-05 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 33
2012-03-06 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 33
2012-03-08 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 33
2012-03-08 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 33
2012-03-08 | Taylor Earthmoving ( 3t Excavator ) | Taylors Earthmoving | hr | 5.5 | 85 | 467.5 | 33
2012-04-27 | Labour Hire | Labour | hr | 7 | 48 | 336 | 33
2012-04-27 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 33
2012-04-27 | Water Truck Hire | Talbots | hr | 1 | 95 | 95 | 33
2012-04-27 | New Holland Compact Grader - No Operator | NH Grader | hr | 7 | 25.78 | 180.46 | 33
2012-04-27 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 8 | 90 | 720 | 33
2012-04-27 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 33
2012-04-27 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 33
2012-04-27 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 33
2012-04-27 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 33
2012-05-01 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 33
2012-05-11 | ( Bobcat Hire ) | Labour | hr | 3 | 95 | 285 | 33
2012-05-11 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 33
2012-05-11 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 33
2012-05-14 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 33
2012-05-14 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 33
2012-05-14 | New Holland Compact Grader - No Operator | NH Grader | hr | 2 | 25.78 | 51.56 | 33
2012-08-04 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 1.75 | 110 | 192.5 | 33
2012-08-04 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 33
2012-08-04 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 33
2012-08-11 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2.5 | 95 | 237.5 | 33
2012-08-11 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 2.5 | 110 | 275 | 33
2012-08-11 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 33
2012-08-11 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 33
2012-08-11 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 33
2012-08-20 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 33
2012-08-20 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.5 | 110 | 495 | 33
2012-08-20 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 33
2012-08-20 | Plant Operator-Labour Hire | Labour | hr | 4.5 | 48 | 216 | 33
2012-08-20 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 33
2012-08-22 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 33
2012-08-22 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 33
2012-09-07 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 5 | 66.07 | 330.35 | 33
2012-09-07 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 33
2012-09-07 | Truck Hire | Micheal Biles | hr | 3 | 95 | 285 | 33
2012-09-07 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5 | 110 | 550 | 33
2012-09-07 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 33
2012-09-07 | Plant Operator-Labour Hire | Labour | hr | 4.5 | 48 | 216 | 33
2012-09-07 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 33
2012-09-07 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 33
2012-09-10 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 33
2012-09-10 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5 | 110 | 550 | 33
2012-09-24 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 33
2012-09-24 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 33
2012-09-24 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3.5 | 95 | 332.5 | 33
2012-09-24 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3 | 110 | 330 | 33
2012-10-03 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 33
2012-10-03 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 33
2012-10-03 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 8 | 110 | 880 | 33
2012-10-03 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 33
2012-10-03 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 33
2012-10-03 | Plant Operator-Labour Hire | Labour | hr | 8 | 48 | 384 | 33
2012-10-04 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 33
2012-10-04 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 7.5 | 110 | 825 | 33
2012-10-04 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 33
2012-10-04 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 33
2012-10-04 | Plant Operator-Labour Hire | Labour | hr | 8 | 48 | 384 | 33
2012-10-04 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 33
2012-10-05 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 33
2012-10-05 | Plant Operator-Labour Hire | Labour | hr | 2.5 | 48 | 120 | 33
2012-10-05 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 33
2012-10-05 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 2.5 | 110 | 275 | 33
2012-10-05 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 33
2012-10-05 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 33
2012-10-10 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 33
2012-10-10 | Earthmoving & Water Cart | Talbots | hr | 7.5 | 95 | 712.5 | 33
2012-10-10 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 33
2012-10-10 | Plant Operator-Labour Hire | Labour | hr | 8 | 48 | 384 | 33
2012-10-10 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 8 | 110 | 880 | 33
2012-10-11 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.5 | 110 | 495 | 33
2012-10-11 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 33
2012-10-11 | Plant Operator-Labour Hire | Labour | hr | 8 | 48 | 384 | 33
2012-10-11 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 33
2012-10-12 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 33
2012-10-12 | Plant Operator-Labour Hire | Labour | hr | 6.5 | 48 | 312 | 33
| Subtotal for 033 |  |  |  |  | 25138.27
Portfolio WBS 041
2011-11-08 | 21 Tonne Excavator | Berry Excavations | hr | 1 | 110 | 110 | 41
2011-11-09 | Excavator ( 7 Tonne) | Berry Excavations | hr | 2 | 110 | 220 | 41
2012-02-23 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 41
2012-02-23 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 41
2012-02-23 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 41
2012-02-23 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 41
2012-03-02 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 41
2012-03-05 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 41
2012-03-05 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 41
2012-03-05 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 41
2012-03-06 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 41
2012-03-06 | Taylors Earthmoving ( 3t Excavator ) | Taylors Earthmoving | hr | 2 | 85 | 170 | 41
2012-05-14 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 41
2012-05-14 | Hired on the 14/5/2012. Inv No - 285238 | Generator |  | 1 | 64.96 | 64.96 | 41
2012-05-14 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 41
2012-05-14 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 41
2012-05-14 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 41
2012-05-14 | Labour Hire | Labour | hr | 6 | 48 | 288 | 41
2012-05-14 | Truck & Trailer Hire | Micheal Biles | hr | 4 | 130 | 520 | 41
2012-05-15 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 41
2012-05-15 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 41
2012-05-15 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 6 | 90 | 540 | 41
2012-05-15 | Labour Hire | Labour | hr | 6 | 48 | 288 | 41
2012-05-15 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 41
2012-05-15 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 41
2012-05-16 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 41
2012-05-16 | Hired on the 14/5/2012 - 16/5/2012. Inv No - 285417 | Generator |  | 1 | 405 | 405 | 41
2012-05-16 | Labour Hire | Labour | hr | 2.5 | 48 | 120 | 41
2012-05-16 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 6 | 90 | 540 | 41
2012-05-16 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 41
2012-05-16 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 41
2012-07-03 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 41
2012-07-03 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 7.5 | 110 | 825 | 41
2012-07-03 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 41
2012-07-04 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 41
2012-07-04 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 41
2012-07-04 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 2 | 110 | 220 | 41
2012-07-05 | Generator , Heavy Duty Breaker, Point Chisel Breakers . Hired 3/7/2012 - 5/7/2012. Inv No - 292252 | Generator |  | 1 | 366 | 366 | 41
2012-07-26 | Labour Hire ( Achieve Group ) | Labour | hr | 2.5 | 34.81 | 87.025 | 41
2012-07-26 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 41
2012-07-27 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 41
2012-07-27 | Labour Hire ( Achieve Group ) | Labour | hr | 5 | 34.81 | 174.05 | 41
2012-07-28 | Concrtetor Hire | Labour | hr | 3 | 45 | 135 | 41
2012-07-28 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 41
2012-07-28 | Time & Half | Labour | hr | 7 | 45.7 | 319.9 | 41
2012-07-30 | Concrtetor Hire | Labour | hr | 3 | 45 | 135 | 41
2012-07-30 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 41
2012-07-30 | Labour Hire ( Achieve Group ) | Labour | hr | 7 | 34.81 | 243.67 | 41
2012-07-31 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 41
2012-08-02 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 41
2012-08-02 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 41
2012-08-02 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 41
2012-08-02 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 41
2012-08-02 | Labour Hire | Labour | hr | 2 | 48 | 96 | 41
2012-08-03 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 41
2012-08-03 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 41
2012-08-06 | Heavy Duty Breaker, Point Breaker, Generator. Hired 2/8/12 - 6/8/12. Inv No - 296297 | Generator |  | 1 | 366 | 366 | 41
2012-08-15 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 41
| Subtotal for 041 |  |  |  |  | 12448.88
Portfolio WBS 052
2012-05-03 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2.15 | 90 | 193.5 | 52
| Subtotal for 052 |  |  |  |  | 193.5
Portfolio WBS 053
2011-10-13 | Excavator ( 7 Tonne ) | Berry Excavations | hr | 9.25 | 110 | 1017.5 | 53
2011-10-13 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 53
2011-10-13 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 53
2011-10-13 | Berry ( Bogie / Tipper ) | Berry Excavations | hr | 8 | 95 | 760 | 53
2011-10-14 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 53
2011-10-14 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 53
2011-10-18 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2011-10-18 | (10 M Tipper ) | Pollard Earthmoving | hr | 5.5 | 95 | 522.5 | 53
2011-10-18 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2011-10-18 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 6 | 90 | 540 | 53
2011-10-18 | Excavator ( 7 Tonne ) | Berry Excavations | hr | 3.5 | 110 | 385 | 53
2011-10-18 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 53
2011-10-18 | 21 Tonne Excavator | Berry Excavations | hr | 5.5 | 135 | 742.5 | 53
2011-10-18 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 53
2011-10-19 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 90 | 360 | 53
2011-10-19 | Excavator ( 7 Tonne ) | Berry Excavations | hr | 3 | 110 | 330 | 53
2011-10-19 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2011-10-19 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2011-10-19 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2011-10-19 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2011-10-19 | 21 Tonne Excavator | Berry Excavations | hr | 1.5 | 135 | 202.5 | 53
2011-10-19 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2011-10-19 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2011-10-20 | (Water Truck ) | Talbots | hr | 6.5 | 95 | 617.5 | 53
2011-10-21 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2011-10-21 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 53
2011-10-22 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2011-10-24 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 5.5 | 66.07 | 363.385 | 53
2011-10-24 | Excavator ( 7 Tonne ) | Berry Excavations | hr | 2.5 | 110 | 275 | 53
2011-10-24 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2011-10-24 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 53
2011-10-24 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 53
2011-10-24 | (10 M Tipper ) | Pollard Earthmoving | hr | 1.5 | 95 | 142.5 | 53
2011-10-24 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9.5 | 90 | 855 | 53
2011-10-24 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 90 | 360 | 53
2011-10-25 | 21 Tonne Excavator | Berry Excavations | hr | 3.5 | 110 | 385 | 53
2011-10-25 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2011-10-25 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2011-10-25 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 3 | 66.07 | 198.21 | 53
2011-10-25 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 90 | 360 | 53
2011-10-25 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 53
2011-10-25 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2011-10-25 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 90 | 360 | 53
2011-10-25 | Excavator ( 7 Tonne ) | Berry Excavations | hr | 4 | 110 | 440 | 53
2011-10-25 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3.5 | 90 | 315 | 53
2011-10-26 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2011-10-26 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 3 | 66.07 | 198.21 | 53
2011-10-26 | Excavator (7 tonne ) | Berry Excavations | hr | 2.5 | 110 | 275 | 53
2011-10-27 | (10 M Tipper ) | Pollard Earthmoving | hr | 4 | 95 | 380 | 53
2011-10-27 | Excavator (7 tonne ) | Berry Excavations | hr | 7.5 | 110 | 825 | 53
2011-10-27 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 53
2011-10-28 | 21 Tonne Excavator | Berry Excavations | hr | 6.5 | 110 | 715 | 53
2011-10-29 | 21 Tonne Excavator | Berry Excavations | hr | 9 | 122.726 | 1104.534 | 53
2011-10-31 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9 | 90 | 810 | 53
2011-11-02 | ( 10m Tipper ) | Pollard Earthmoving | hr | 9 | 95 | 855 | 53
2011-11-02 | DoyawanaTruck Hire | Doyawana | hr | 5 | 95 | 475 | 53
2011-11-02 | ( Bobcat Hire ) | Labour | hr | 10 | 95 | 950 | 53
2011-11-03 | ( Bobcat Hire ) | Labour | hr | 10.5 | 95 | 997.5 | 53
2011-11-03 | (Truck Hire ) | Labour | hr | 9 | 65 | 585 | 53
2011-11-04 | DoyawanaTruck Hire | Doyawana | hr | 8 | 95 | 760 | 53
2011-11-04 | 21 Tonne Excavator | Berry Excavations | hr | 9 | 110 | 990 | 53
2011-11-04 | ( Bobcat Hire ) | Labour | hr | 3 | 95 | 285 | 53
2011-11-05 | DoyawanaTruck Hire | Doyawana | hr | 4 | 95 | 380 | 53
2011-11-06 | DoyawanaTruck Hire | Doyawana | hr | 4 | 95 | 380 | 53
2011-11-08 | 21 Tonne Excavator | Berry Excavations | hr | 4 | 110 | 440 | 53
2011-11-09 | Excavator ( 7 Tonne) | Berry Excavations | hr | 4 | 110 | 440 | 53
2011-11-10 | Excavator ( 7 Tonne) | Berry Excavations | hr | 5 | 110 | 550 | 53
2011-11-10 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4.5 | 90 | 405 | 53
2011-11-14 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2011-11-14 | Excavator ( 7 Tonne) | Berry Excavations | hr | 5 | 110 | 550 | 53
2011-11-14 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2011-11-14 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2011-11-14 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2011-11-17 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 53
2011-11-17 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 53
2011-11-17 | (Tipper Hire ) | Labour | hr | 10 | 65 | 650 | 53
2011-11-17 | ( Bobcat Hire ) | Labour | hr | 6 | 95 | 570 | 53
2011-11-17 | Excavator 21 Tonne | Berry Excavations | hr | 9 | 140 | 1260 | 53
2011-11-17 | DoyawanaTruck Hire | Doyawana | hr | 10.5 | 95 | 997.5 | 53
2011-11-23 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2011-11-23 | Tipper Hire | Labour | hr | 10 | 65 | 650 | 53
2011-11-23 | Excavator ( 7 Tonne) | Berry Excavations | hr | 9.5 | 110 | 1045 | 53
2011-11-24 | Tipper | Labour | hr | 10 | 65 | 650 | 53
2011-11-24 | Excavator ( 7 Tonne) | Berry Excavations | hr | 9.25 | 110 | 1017.5 | 53
2011-11-24 | Bobcat | Labour | hr | 3 | 95 | 285 | 53
2011-11-24 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2011-11-24 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 53
2011-11-24 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2011-11-25 | DoyawanaTruck Hire | Doyawana | hr | 3 | 95 | 285 | 53
2011-11-25 | Excavator ( 7 Tonne) | Berry Excavations | hr | 2.5 | 110 | 275 | 53
2011-12-07 | 7 Tonne Excavator | Berry Excavations | hr | 7.5 | 110 | 825 | 53
2011-12-07 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9 | 100 | 900 | 53
2011-12-08 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 7.5 | 100 | 750 | 53
2011-12-08 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2011-12-08 | 7 Tonne Excavator | Berry Excavations | hr | 7.5 | 110 | 825 | 53
2011-12-09 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-01-10 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 8.5 | 130 | 1105 | 53
2012-01-10 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9 | 95 | 855 | 53
2012-01-10 | Foreman | Labour | hr | 9.5 | 44.2 | 419.9 | 53
2012-01-10 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-01-11 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 8 | 130 | 1040 | 53
2012-01-11 | Micheal Biles. ( 10m Tipper ) | Micheal Biles | hr | 5.5 | 95 | 522.5 | 53
2012-01-11 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8.5 | 95 | 807.5 | 53
2012-01-11 | Micheal Biles. ( 10m Tipper ) | Micheal Biles | hr | 3 | 125 | 375 | 53
2012-01-11 | Foreman | Labour | hr | 9.5 | 44.2 | 419.9 | 53
2012-01-11 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-01-12 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9 | 130 | 1170 | 53
2012-01-12 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8 | 95 | 760 | 53
2012-01-12 | Foreman | Labour | hr | 9.5 | 44.2 | 419.9 | 53
2012-01-12 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-01-13 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 6 | 130 | 780 | 53
2012-01-13 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 53
2012-01-13 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 53
2012-01-13 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5.5 | 95 | 522.5 | 53
2012-01-16 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-01-16 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-01-16 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-01-16 | Foreman | Labour | hr | 3 | 44.2 | 132.6 | 53
2012-01-18 | Micheal Biles. ( 10m Tipper ) | Micheal Biles | hr | 4.5 | 95 | 427.5 | 53
2012-01-18 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8.5 | 95 | 807.5 | 53
2012-01-18 | 21 Tonne Excavator | Berry Excavations | hr | 4 | 110 | 440 | 53
2012-01-18 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9 | 130 | 1170 | 53
2012-01-18 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-01-18 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-01-19 | Micheal Biles. ( 10m Tipper ) | Micheal Biles | hr | 9.5 | 95 | 902.5 | 53
2012-01-19 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9 | 130 | 1170 | 53
2012-01-19 | 21 Tonne Excavator | Berry Excavations | hr | 2 | 110 | 220 | 53
2012-01-19 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9 | 95 | 855 | 53
2012-01-19 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-01-19 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 53
2012-01-19 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 53
2012-01-20 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-01-20 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 53
2012-01-20 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-01-20 | Micheal Biles. ( 10m Tipper ) | Micheal Biles | hr | 9 | 95 | 855 | 53
2012-01-20 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9 | 95 | 855 | 53
2012-01-20 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9.5 | 130 | 1235 | 53
2012-01-21 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-01-21 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 1 | 130 | 130 | 53
2012-01-21 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-01-21 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2 | 95 | 190 | 53
2012-01-27 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8.5 | 90 | 765 | 53
2012-01-27 | Body Truck Hire | Raymonds Truck Hire | hr | 8.75 | 85 | 743.75 | 53
2012-01-27 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 7.5 | 130 | 975 | 53
2012-01-27 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 53
2012-01-27 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 8 | 90 | 720 | 53
2012-01-27 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 53
2012-01-27 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-01-28 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5 | 130 | 650 | 53
2012-01-28 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-01-28 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 90 | 360 | 53
2012-01-28 | Body Truck | Raymonds Truck Hire | hr | 4 | 85 | 340 | 53
2012-01-28 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 53
2012-01-29 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5 | 90 | 450 | 53
2012-01-30 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 53
2012-01-30 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5 | 130 | 650 | 53
2012-01-30 | Body Truck Hire | Raymonds Truck Hire | hr | 5.75 | 85 | 488.75 | 53
2012-01-31 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 53
2012-01-31 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5 | 130 | 650 | 53
2012-01-31 | Body Truck Hire | Raymonds Truck Hire | hr | 7.15 | 85 | 607.75 | 53
2012-01-31 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-01-31 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-02-01 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5 | 130 | 650 | 53
2012-02-01 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-02-01 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-02-01 | BodyTruck Hire | Raymonds Truck Hire | hr | 3.5 | 85 | 297.5 | 53
2012-02-01 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-02-01 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 53
2012-02-02 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 53
2012-02-02 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-02-02 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-02-02 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-02-02 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-02-02 | Standby Tipper | Micheal Biles | hr | 3 | 45 | 135 | 53
2012-02-06 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-02-06 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 8.5 | 130 | 1105 | 53
2012-02-06 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-02-06 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9 | 95 | 855 | 53
2012-02-06 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 53
2012-02-06 | 21 Tonne Excavator | Berry Excavations | hr | 8.75 | 110 | 962.5 | 53
2012-02-06 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 53
2012-02-07 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 53
2012-02-07 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9 | 130 | 1170 | 53
2012-02-07 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 53
2012-02-07 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8.5 | 95 | 807.5 | 53
2012-02-07 | 21 Tonne Excavator | Berry Excavations | hr | 5 | 110 | 550 | 53
2012-02-07 | (10 M Tipper ) | Pollard Earthmoving | hr | 8.5 | 95 | 807.5 | 53
2012-02-07 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-02-08 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-02-08 | 7 Tonne Excavator | Berry Excavations | hr | 8.25 | 110 | 907.5 | 53
2012-02-08 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9 | 95 | 855 | 53
2012-02-08 | (10 M Tipper ) | Pollard Earthmoving | hr | 8.5 | 95 | 807.5 | 53
2012-02-08 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9 | 130 | 1170 | 53
2012-02-08 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 53
2012-02-08 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 53
2012-02-08 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-02-09 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 7.5 | 130 | 975 | 53
2012-02-09 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8 | 95 | 760 | 53
2012-02-09 | 7 Tonne Excavator | Berry Excavations | hr | 8 | 110 | 880 | 53
2012-02-09 | (10 M Tipper ) | Pollard Earthmoving | hr | 7 | 95 | 665 | 53
2012-02-09 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5.5 | 90 | 495 | 53
2012-02-10 | Truck & Dog Hire | Micheal Biles | hr | 7.5 | 95 | 712.5 | 53
2012-02-10 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-02-10 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5 | 130 | 650 | 53
2012-02-13 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8.5 | 95 | 807.5 | 53
2012-02-13 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-02-13 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 8.5 | 130 | 1105 | 53
2012-02-14 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 7.5 | 95 | 712.5 | 53
2012-02-14 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 6 | 130 | 780 | 53
2012-02-14 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-02-16 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 53
2012-02-16 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-02-16 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 53
2012-02-17 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 53
2012-02-17 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2.5 | 95 | 237.5 | 53
2012-02-20 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 53
2012-02-29 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 53
2012-02-29 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-02-29 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-02-29 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 2 | 130 | 260 | 53
2012-03-01 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9 | 95 | 855 | 53
2012-03-01 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9 | 130 | 1170 | 53
2012-03-01 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 9 | 90 | 810 | 53
2012-03-01 | (10 M Tipper ) | Pollard Earthmoving | hr | 8.5 | 95 | 807.5 | 53
2012-03-01 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 53
2012-03-01 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 53
2012-03-01 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 53
2012-03-01 | Water Truck Hire | Berry Excavations | hr | 9 | 100 | 900 | 53
2012-03-02 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4.5 | 95 | 427.5 | 53
2012-03-02 | (10 M Tipper ) | Pollard Earthmoving | hr | 7.75 | 95 | 736.25 | 53
2012-03-02 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 53
2012-03-02 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 8 | 130 | 1040 | 53
2012-03-02 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-03-03 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 53
2012-03-03 | (10 M Tipper ) | Pollard Earthmoving | hr | 3.5 | 95 | 332.5 | 53
2012-03-05 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5 | 95 | 475 | 53
2012-03-06 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5 | 90 | 450 | 53
2012-03-06 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5.5 | 95 | 522.5 | 53
2012-03-12 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2.5 | 90 | 225 | 53
2012-03-12 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9 | 95 | 855 | 53
2012-03-12 | Taylors Earthmoving 25t Excavator | Taylors Earthmoving | hr | 7.5 | 130 | 975 | 53
2012-03-13 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-03-13 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-03-13 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 53
2012-03-13 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 8 | 90 | 720 | 53
2012-03-13 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 7 | 95 | 665 | 53
2012-03-13 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 53
2012-03-14 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3 | 95 | 285 | 53
2012-03-14 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3.5 | 90 | 315 | 53
2012-03-23 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 53
2012-03-23 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 7 | 90 | 630 | 53
2012-03-23 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-03-23 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-03-23 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 7 | 95 | 665 | 53
2012-04-02 | (10 M Tipper ) | Pollard Earthmoving | hr | 8 | 95 | 760 | 53
2012-04-02 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2 | 95 | 190 | 53
2012-04-02 | Twin Steer Truck Hire | Humphries Pty Ltd | hr | 10.25 | 92.73 | 950.4825 | 53
2012-04-02 | Twin Steer Truck Hire | Humphries Pty Ltd | hr | 10.25 | 92.73 | 950.4825 | 53
2012-04-02 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 11 | 130 | 1430 | 53
2012-04-02 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-04-02 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-04-02 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 53
2012-04-02 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-04-02 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5.5 | 90 | 495 | 53
2012-04-03 | Twin Steer Truck Hire | Humphries Pty Ltd | hr | 6 | 92.73 | 556.38 | 53
2012-04-03 | (10 M Tipper ) | Pollard Earthmoving | hr | 7.5 | 95 | 712.5 | 53
2012-04-03 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 6.5 | 90 | 585 | 53
2012-04-03 | Twin Steer Truck Hire | Humphries Pty Ltd | hr | 6 | 92.73 | 556.38 | 53
2012-04-03 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9.5 | 95 | 902.5 | 53
2012-04-03 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 53
2012-04-03 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 53
2012-04-03 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9.5 | 130 | 1235 | 53
2012-04-03 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 53
2012-04-04 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4.5 | 130 | 585 | 53
2012-04-04 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 53
2012-04-04 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 53
2012-04-04 | Water Truck | Berry Excavations | hr | 5 | 100 | 500 | 53
2012-04-04 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3 | 95 | 285 | 53
2012-04-04 | (10 M Tipper ) | Pollard Earthmoving | hr | 3.5 | 95 | 332.5 | 53
2012-04-04 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 6.5 | 90 | 585 | 53
2012-04-04 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 53
2012-04-04 | Water Truck. Inv No 4924 | Berry Excavations | hr | 10 | 100 | 1000 | 53
2012-04-04 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 53
2012-04-10 | Twin Steer Hire | Humphries Pty Ltd | hr | 7 | 92.73 | 649.11 | 53
2012-04-10 | Twin Steer Hire | Humphries Pty Ltd | hr | 7 | 92.73 | 649.11 | 53
2012-04-10 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 53
2012-04-10 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 6 | 130 | 780 | 53
2012-04-10 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 53
2012-04-11 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 53
2012-04-11 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9.5 | 130 | 1235 | 53
2012-04-11 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9 | 95 | 855 | 53
2012-04-11 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-04-11 | Taylors Earthmoving ( 23t Excabator ) | Taylors Earthmoving | hr | 9.5 | 130 | 1235 | 53
2012-04-11 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-04-11 | Twin Steer Hire | Humphries Pty Ltd | hr | 9.5 | 92.73 | 880.935 | 53
2012-04-11 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5 | 90 | 450 | 53
2012-04-11 | Twin Steer Hire | Humphries Pty Ltd | hr | 9.5 | 92.73 | 880.935 | 53
2012-04-11 | (10 M Tipper ) | Pollard Earthmoving | hr | 9 | 95 | 855 | 53
2012-04-12 | Twin Steer Hire | Humphries Pty Ltd | hr | 8 | 92.73 | 741.84 | 53
2012-04-12 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-04-12 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5 | 90 | 450 | 53
2012-04-12 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 10.5 | 130 | 1365 | 53
2012-04-12 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-04-12 | (10 M Tipper ) | Pollard Earthmoving | hr | 8 | 95 | 760 | 53
2012-04-12 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8 | 95 | 760 | 53
2012-04-12 | taylors Eathmoving ( 23t Excavator ) | Taylors Earthmoving | hr | 10 | 130 | 1300 | 53
2012-04-12 | Twin Steer Hire | Humphries Pty Ltd | hr | 8 | 92.73 | 741.84 | 53
2012-04-13 | (10 M Tipper ) | Pollard Earthmoving | hr | 8 | 95 | 760 | 53
2012-04-13 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8 | 95 | 760 | 53
2012-04-13 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 8 | 130 | 1040 | 53
2012-04-13 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5 | 90 | 450 | 53
2012-04-13 | Twin Steer Hire | Humphries Pty Ltd | hr | 8.5 | 92.73 | 788.205 | 53
2012-04-13 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 53
2012-04-13 | Twin Steer Hire | Humphries Pty Ltd | hr | 8.5 | 92.73 | 788.205 | 53
2012-04-13 | Taylors Earthmoving (23t Excavator ) | Taylors Earthmoving | hr | 10 | 130 | 1300 | 53
2012-04-13 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 53
2012-04-13 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-04-14 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-04-14 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-04-14 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 53
2012-04-14 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-04-16 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 6.5 | 130 | 845 | 53
2012-04-16 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-04-16 | Twin Steer Hire | Humphries Pty Ltd | hr | 8 | 92.73 | 741.84 | 53
2012-04-16 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5 | 90 | 450 | 53
2012-04-16 | Twin Steer Hire | Humphries Pty Ltd | hr | 8 | 92.73 | 741.84 | 53
2012-04-16 | Labour Hire | Labour | hr | 3 | 48 | 144 | 53
2012-04-16 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-04-16 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-04-17 | Twin Steer Hire | Humphries Pty Ltd | hr | 7 | 92.73 | 649.11 | 53
2012-04-17 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-04-17 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-04-17 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4.5 | 130 | 585 | 53
2012-04-17 | Twin Steer Hire | Humphries Pty Ltd | hr | 7 | 92.73 | 649.11 | 53
2012-04-19 | Taylors Earthmoving ( 3t Excavator ) | Taylors Earthmoving | hr | 4 | 85 | 340 | 53
2012-04-19 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 53
2012-04-20 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 7 | 95 | 665 | 53
2012-04-20 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 6.5 | 90 | 585 | 53
2012-04-20 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-04-20 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-04-23 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-04-23 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9 | 95 | 855 | 53
2012-04-23 | (10 M Tipper ) | Pollard Earthmoving | hr | 4.5 | 95 | 427.5 | 53
2012-04-23 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 53
2012-04-23 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-04-23 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-04-23 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5 | 130 | 650 | 53
2012-04-23 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-04-30 | Taylors Excavator ( 3t Excavator ) | Taylors Earthmoving | hr | 5.5 | 85 | 467.5 | 53
2012-04-30 | (Water Truck ) | Talbots | hr | 9.5 | 95 | 902.5 | 53
2012-04-30 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 53
2012-04-30 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4.5 | 95 | 427.5 | 53
2012-04-30 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 53
2012-05-01 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-05-01 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-05-01 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5 | 95 | 475 | 53
2012-05-01 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 53
2012-05-01 | Water Truck Hire | Talbots | hr | 2 | 95 | 190 | 53
2012-05-01 | Labour Hire | Labour | hr | 5 | 48 | 240 | 53
2012-05-09 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4.5 | 95 | 427.5 | 53
2012-05-09 | (Water Truck ) | Talbots | hr | 4.5 | 95 | 427.5 | 53
2012-05-14 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 53
2012-05-14 | Micheal Biles. ( 10m Tipper ) | Micheal Biles | hr | 8 | 95 | 760 | 53
2012-05-17 | Labour Hire | Labour | hr | 4 | 48 | 192 | 53
2012-05-17 | Twin Steer Hire | Humphries Pty Ltd | hr | 11.25 | 92.73 | 1043.2125 | 53
2012-05-17 | Twin Steer Hire | Humphries Pty Ltd | hr | 10 | 92.73 | 927.3 | 53
2012-05-17 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 53
2012-05-17 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5 | 130 | 650 | 53
2012-05-17 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-05-18 | Twin Steer Hire | Humphries Pty Ltd | hr | 4 | 92.73 | 370.92 | 53
2012-05-18 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-05-18 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-05-18 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-05-18 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-05-18 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5 | 130 | 650 | 53
2012-05-18 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 53
2012-05-18 | Labour Hire | Labour | hr | 3 | 48 | 144 | 53
2012-05-19 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-05-19 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 1 | 90 | 90 | 53
2012-05-19 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 2.5 | 130 | 325 | 53
2012-05-19 | (10 M Tipper ) | Pollard Earthmoving | hr | 2 | 95 |  | 53
2012-05-19 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-05-19 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-05-21 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 53
2012-05-21 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9.5 | 130 | 1235 | 53
2012-05-21 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9.5 | 95 | 902.5 | 53
2012-05-21 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 9 | 90 | 810 | 53
2012-05-21 | Labour Hire | Labour | hr | 10 | 48 | 480 | 53
2012-05-21 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 53
2012-05-22 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 53
2012-05-22 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 53
2012-05-22 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-05-22 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9.5 | 130 | 1235 | 53
2012-05-22 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9.5 | 95 | 902.5 | 53
2012-05-23 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 53
2012-05-23 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-05-23 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-05-23 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8.5 | 95 | 807.5 | 53
2012-05-23 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9.5 | 130 | 1235 | 53
2012-05-24 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3.5 | 90 | 315 | 53
2012-05-28 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-05-28 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-05-28 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9.5 | 130 | 1235 | 53
2012-05-28 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2 | 95 | 190 | 53
2012-05-28 | New Holland Compact Grader - No Operator | NH Grader | hr | 1 | 25.78 | 25.78 | 53
2012-05-29 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 53
2012-05-29 | Labour Hire | Labour | hr | 2.5 | 48 | 120 | 53
2012-05-29 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3 | 95 | 285 | 53
2012-05-29 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 2.5 | 130 | 325 | 53
2012-05-29 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 53
2012-05-30 | Labour Hire | Labour | hr | 3 | 48 | 144 | 53
2012-05-30 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-05-30 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-05-30 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 7 | 130 | 910 | 53
2012-05-30 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 6 | 95 | 570 | 53
2012-05-30 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 53
2012-05-31 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-05-31 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-05-31 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-05-31 | Labour Hire | Labour | hr | 3 | 48 | 144 | 53
2012-05-31 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-06-01 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 53
2012-06-01 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 8.5 | 130 | 1105 | 53
2012-06-01 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8 | 95 | 760 | 53
2012-06-01 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 53
2012-06-04 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3.75 | 90 | 337.5 | 53
2012-06-04 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 8.5 | 130 | 1105 | 53
2012-06-04 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 53
2012-06-04 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 6 | 95 | 570 | 53
2012-06-05 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 8.5 | 130 | 1105 | 53
2012-06-05 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 53
2012-06-05 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2 | 95 | 190 | 53
2012-06-05 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 53
2012-06-06 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9.5 | 130 | 1235 | 53
2012-06-06 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 10 | 95 | 950 | 53
2012-06-06 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 53
2012-06-06 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-06-06 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-06-06 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 53
2012-06-07 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 53
2012-06-07 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2.5 | 90 | 225 | 53
2012-06-07 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 53
2012-06-07 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 7 | 95 | 665 | 53
2012-06-07 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 6.5 | 130 | 845 | 53
2012-06-12 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2 | 95 | 190 | 53
2012-06-12 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 53
2012-06-12 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 2 | 130 | 260 | 53
2012-06-13 | Tipper Hire | Humphries Pty Ltd | hr | 10.5 | 82.727 | 868.6335 | 53
2012-06-13 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 53
2012-06-13 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 53
2012-06-13 | Labour Hire | Labour | hr | 9.5 | 48 | 456 | 53
2012-06-13 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-06-13 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9.5 | 95 | 902.5 | 53
2012-06-13 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 6 | 90 | 540 | 53
2012-06-13 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9.5 | 130 | 1235 | 53
2012-06-13 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 53
2012-06-14 | Labour Hire | Labour | hr | 4 | 48 | 192 | 53
2012-06-14 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-06-14 | Tipper Hire | Humphries Pty Ltd | hr | 1 | 82.727 | 82.727 | 53
2012-06-14 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3 | 95 | 285 | 53
2012-06-14 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 3 | 130 | 390 | 53
2012-06-15 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-06-15 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5 | 95 | 475 | 53
2012-06-15 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5 | 90 | 450 | 53
2012-06-15 | Tipper Hire | Humphries Pty Ltd | hr | 5 | 82.727 | 413.635 | 53
2012-06-15 | Labour Hire | Labour | hr | 2 | 48 | 96 | 53
2012-06-15 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 7 | 130 | 910 | 53
2012-06-15 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-06-15 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 53
2012-06-15 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-06-16 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 53
2012-06-16 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 53
2012-06-16 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 53
2012-06-16 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 53
2012-06-16 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 53
2012-06-16 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4 | 130 | 520 | 53
2012-06-18 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 53
2012-06-18 | Tipper Hire | Humphries Pty Ltd | hr | 8.5 | 82.727 | 703.1795 | 53
2012-06-18 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-06-18 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 53
2012-06-18 | Labour Hire | Labour | hr | 4 | 48 | 192 | 53
2012-06-18 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 8 | 130 | 1040 | 53
2012-06-18 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8.5 | 95 | 807.5 | 53
2012-06-18 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 53
2012-06-18 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 6 | 90 | 540 | 53
2012-06-19 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3 | 95 | 285 | 53
2012-06-19 | Tipper Hire | Humphries Pty Ltd | hr | 2 | 82.727 | 165.454 | 53
2012-06-19 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-06-19 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-06-20 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 9.5 | 110 | 1045 | 53
2012-06-20 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9.5 | 130 | 1235 | 53
2012-06-20 | Tipper Hire | Humphries Pty Ltd | hr | 3 | 82.727 | 248.181 | 53
2012-06-20 | Tipper Hire | Humphries Pty Ltd | hr | 4 | 82.727 | 330.908 | 53
2012-06-20 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-06-20 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-06-20 | Labour Hire | Labour | hr | 3 | 48 | 144 | 53
2012-06-20 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-06-20 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-06-21 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8 | 95 | 760 | 53
2012-06-21 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 7.5 | 130 | 975 | 53
2012-06-21 | Tipper Hire | Humphries Pty Ltd | hr | 7.5 | 82.727 | 620.4525 | 53
2012-06-21 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4 | 110 | 440 | 53
2012-06-21 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 53
2012-06-21 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 53
2012-06-21 | Labour Hire | Labour | hr | 1.5 | 48 | 72 | 53
2012-06-21 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 53
2012-06-21 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 53
2012-06-25 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 7 | 130 | 910 | 53
2012-06-25 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 7 | 95 | 665 | 53
2012-06-25 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 1 | 110 | 110 | 53
2012-06-25 | Labour Hire | Labour | hr | 8 | 48 | 384 | 53
2012-06-25 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 53
2012-06-25 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 53
2012-06-28 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-06-28 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 53
2012-06-28 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-06-28 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 6.5 | 130 | 845 | 53
2012-06-29 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-06-29 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-06-29 | Labour Hire | Labour | hr | 4 | 48 | 192 | 53
2012-06-29 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-06-29 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-06-29 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4 | 110 | 440 | 53
2012-07-02 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4 | 110 | 440 | 53
2012-07-04 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4.5 | 95 | 427.5 | 53
2012-07-04 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 53
2012-07-04 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 53
2012-07-04 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 6.75 | 110 | 742.5 | 53
2012-07-26 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2 | 95 | 190 | 53
2012-07-28 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 6.5 | 130 | 845 | 53
2012-07-28 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 6 | 95 | 570 | 53
2012-07-30 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 3.5 | 130 | 455 | 53
2012-07-30 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3 | 95 | 285 | 53
2012-07-30 | (10 M Tipper ) | Pollard Earthmoving | hr | 3.25 | 95 | 308.75 | 53
2012-07-31 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 7.5 | 95 | 712.5 | 53
2012-07-31 | (10 M Tipper ) | Pollard Earthmoving | hr | 7.5 | 95 | 712.5 | 53
2012-07-31 | Allans Earthmoving (Tipper Hire) | Allans Earthmoving | hr | 3 | 95 | 285 | 53
2012-07-31 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5 | 130 | 650 | 53
2012-07-31 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 53
2012-07-31 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 53
2012-07-31 | Water Truck Hire | Pollard Earthmoving | hr | 11 | 100 | 1100 | 53
2012-08-01 | (10 M Tipper ) | Pollard Earthmoving | hr | 3.5 | 95 | 332.5 | 53
2012-08-01 | (10 M Tipper ) | Pollard Earthmoving | hr | 5 | 95 | 475 | 53
2012-08-01 | N K Jepsen Tipper Hire | N K Jepsen Tipper Hire | hr | 4 | 90 | 360 | 53
2012-08-01 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 6.5 | 110 | 715 | 53
2012-08-01 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5 | 95 | 475 | 53
2012-08-01 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-08-01 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-08-01 | Allans Earthmoving (Tipper Hire) | Allans Earthmoving | hr | 5 | 95 | 475 | 53
2012-08-01 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5 | 130 | 650 | 53
2012-08-02 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 53
2012-08-02 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-08-02 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5 | 130 | 650 | 53
2012-08-02 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5.5 | 110 | 605 | 53
2012-08-02 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5 | 95 | 475 | 53
2012-08-02 | Allans Earthmoving (Tipper Hire) | Allans Earthmoving | hr | 5 | 95 | 475 | 53
2012-08-03 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 53
2012-08-03 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4.5 | 95 | 427.5 | 53
2012-08-03 | T Excavator Hire | Watts Excavations | hr | 5 | 110 | 550 | 53
2012-08-03 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2.5 | 95 | 237.5 | 53
2012-08-03 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4.5 | 130 | 585 | 53
2012-08-03 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5 | 95 | 475 | 53
2012-08-03 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 53
2012-08-03 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-08-03 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-08-03 | Labour Hire | Labour | hr | 4 | 48 | 192 | 53
2012-08-04 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 2 | 130 | 260 | 53
2012-08-04 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2 | 95 | 190 | 53
2012-08-04 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3 | 95 | 285 | 53
2012-08-04 | T Excavator Hire | Watts Excavations | hr | 5 | 110 | 550 | 53
2012-08-04 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2 | 95 | 190 | 53
2012-08-06 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5 | 95 | 475 | 53
2012-08-06 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9.5 | 130 | 1235 | 53
2012-08-06 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5.5 | 95 | 522.5 | 53
2012-08-07 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5 | 95 | 475 | 53
2012-08-07 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-08-08 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-08-08 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4 | 130 | 520 | 53
2012-08-09 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4 | 130 | 520 | 53
2012-08-09 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3 | 95 | 285 | 53
2012-08-09 | (10 M Tipper ) | Pollard Earthmoving | hr | 4 | 95 | 380 | 53
2012-08-09 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 53
2012-08-10 | (10 M Tipper ) | Pollard Earthmoving | hr | 4 | 95 | 380 | 53
2012-08-10 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4 | 130 | 520 | 53
2012-08-10 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-08-10 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 53
2012-08-13 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 53
2012-08-13 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-08-13 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4 | 130 | 520 | 53
2012-08-13 | (10 M Tipper ) | Pollard Earthmoving | hr | 4 | 95 | 380 | 53
2012-08-13 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 2 | 110 | 220 | 53
2012-08-14 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-08-14 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 53
2012-08-14 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4 | 130 | 520 | 53
2012-08-14 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 53
2012-08-14 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 6 | 110 | 660 | 53
2012-08-14 | (10 M Tipper ) | Pollard Earthmoving | hr | 4 | 95 | 380 | 53
2012-08-15 | (10 M Tipper ) | Pollard Earthmoving | hr | 3.5 | 95 | 332.5 | 53
2012-08-15 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-08-15 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 2 | 110 | 220 | 53
2012-08-15 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 53
2012-08-15 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-08-15 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-08-15 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4 | 130 | 520 | 53
2012-08-16 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 5 | 135 | 675 | 53
2012-08-17 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 7.5 | 130 | 975 | 53
2012-08-17 | (10 M Tipper ) | Pollard Earthmoving | hr | 7.5 | 95 | 712.5 | 53
2012-08-22 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 3 | 130 | 390 | 53
2012-08-22 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3 | 95 | 285 | 53
2012-08-22 | (10 M Tipper ) | Pollard Earthmoving | hr | 3 | 95 | 285 | 53
2012-08-22 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-08-22 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-08-22 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-08-22 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-08-22 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5 | 110 | 550 | 53
2012-08-23 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5 | 130 | 650 | 53
2012-08-23 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3 | 95 | 285 | 53
2012-08-23 | (10 M Tipper ) | Pollard Earthmoving | hr | 3 | 95 | 285 | 53
2012-08-23 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-08-23 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-08-23 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-08-23 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-08-25 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-08-25 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-08-25 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.75 | 110 | 522.5 | 53
2012-08-27 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 53
2012-08-27 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 53
2012-08-27 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-08-27 | (10 M Tipper ) | Pollard Earthmoving | hr | 4 | 95 | 380 | 53
2012-08-27 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4 | 130 | 520 | 53
2012-08-27 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 53
2012-08-27 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 2 | 110 | 220 | 53
2012-08-28 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3.5 | 95 | 332.5 | 53
2012-08-28 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4 | 130 | 520 | 53
2012-08-28 | (10 M Tipper ) | Pollard Earthmoving | hr | 3.5 | 95 | 332.5 | 53
2012-08-28 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 53
2012-08-28 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 53
2012-08-28 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 53
2012-08-29 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 53
2012-08-29 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 53
2012-08-29 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-08-29 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 3 | 130 | 390 | 53
2012-08-29 | Micheal Biles. ( 10m Tipper ) | Micheal Biles | hr | 3.5 | 95 | 332.5 | 53
2012-08-29 | Earthmoving & Water Cart | Talbots | hr | 4 | 95 | 380 | 53
2012-08-29 | (10 M Tipper ) | Pollard Earthmoving | hr | 3.5 | 95 | 332.5 | 53
2012-08-29 | Plant Operator-Labour Hire | Labour | hr | 2 | 48 | 96 | 53
2012-08-29 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2012-08-31 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 1 | 110 | 110 | 53
2012-08-31 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-08-31 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 53
2012-09-03 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-09-03 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-09-03 | Plant Operator-Labour Hire | Labour | hr | 5 | 48 | 240 | 53
2012-09-03 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.5 | 110 | 495 | 53
2012-09-04 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 2.5 | 135 | 337.5 | 53
2012-09-04 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 53
2012-09-04 | Plant Operator-Labour Hire | Labour | hr | 7.5 | 48 | 360 | 53
2012-09-04 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 7.5 | 110 | 825 | 53
2012-09-04 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-09-04 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-09-06 | Plant Operator-Labour Hire | Labour | hr | 8 | 48 | 384 | 53
2012-09-06 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 7.5 | 95 | 712.5 | 53
2012-09-06 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 53
2012-09-06 | (10 M Tipper ) | Pollard Earthmoving | hr | 3 | 95 | 285 | 53
2012-09-06 | Truck Hire | Micheal Biles | hr | 3 | 95 | 285 | 53
2012-09-06 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 1 | 135 | 135 | 53
2012-09-06 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-09-06 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 9.5 | 110 | 1045 | 53
2012-09-06 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 3 | 130 | 390 | 53
2012-09-07 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-09-07 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.25 | 110 | 467.5 | 53
2012-09-07 | Truck Hire | Micheal Biles | hr | 4.5 | 95 | 427.5 | 53
2012-09-07 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-09-07 | Plant Operator-Labour Hire | Labour | hr | 3 | 48 | 144 | 53
2012-09-07 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-09-07 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-09-10 | Quick Cut Saw & Daimond Blade. Hired 31/8/12 - 10/9/12. Inv No - 300862 | Quick Cut Saw |  | 1 | 762 | 762 | 53
2012-09-10 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4 | 130 | 520 | 53
2012-09-10 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 53
2012-09-10 | Labour Hire ( People Resourcing ) | Labour | hr | 2 | 40.97 | 81.94 | 53
2012-09-10 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-09-10 | Truck Hire (Dry Hire) | Micheal Biles | hr | 2 | 50 | 100 | 53
2012-09-10 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 53
2012-09-10 | (10 M Tipper ) | Pollard Earthmoving | hr | 3 | 95 | 285 | 53
2012-09-10 | Plant Operator-Labour Hire | Labour | hr | 5 | 48 | 240 | 53
2012-09-10 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 53
2012-09-10 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 53
2012-09-10 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.5 | 110 | 495 | 53
2012-09-11 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-09-11 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-09-11 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-09-11 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-09-11 | Plant Operator-Labour Hire | Labour | hr | 4 | 48 | 192 | 53
2012-09-11 | (10 M Tipper ) | Pollard Earthmoving | hr | 4 | 95 | 380 | 53
2012-09-11 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4 | 130 | 520 | 53
2012-09-11 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 53
2012-09-11 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-09-11 | Plant Operator-Labour Hire | Labour | hr | 4 | 48 | 192 | 53
2012-09-11 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-09-11 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-09-11 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-09-11 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-09-11 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-09-12 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-09-12 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-09-12 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2 | 95 | 190 | 53
2012-09-12 | (10 M Tipper ) | Pollard Earthmoving | hr | 4 | 95 | 380 | 53
2012-09-12 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4 | 130 | 520 | 53
2012-09-13 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4 | 130 | 520 | 53
2012-09-13 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-09-13 | (10 M Tipper ) | Pollard Earthmoving | hr | 2 | 95 | 190 | 53
2012-09-13 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5 | 110 | 550 | 53
2012-09-13 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-09-17 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 53
2012-09-17 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 53
2012-09-17 | Plant Operator-Labour Hire | Labour | hr | 5 | 48 | 240 | 53
2012-09-17 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.5 | 110 | 495 | 53
2012-09-17 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 53
2012-09-18 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3 | 110 | 330 | 53
2012-09-19 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 9.5 | 110 | 1045 | 53
2012-09-19 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9 | 95 | 855 | 53
2012-09-19 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-09-19 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2012-09-20 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9.5 | 95 | 902.5 | 53
2012-09-20 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9.5 | 95 | 902.5 | 53
2012-09-21 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8.5 | 95 | 807.5 | 53
2012-09-21 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8.5 | 95 | 807.5 | 53
2012-09-24 | Plant Operator-Labour Hire | Labour | hr | 9 | 48 | 432 | 53
2012-09-24 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3 | 110 | 330 | 53
2012-09-24 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 53
2012-09-24 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 53
2012-09-24 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 53
2012-09-30 | Double Drum Roller. Hired 31/8/12 - 28/9/12. Inv No 303113 | Double Drum Roller |  | 1 | 1893.666 | 1893.666 | 53
2012-09-30 | Dynapac CC 21 Roller. Hired 31/8/12 - 20/9/12. Inv No - 303112 | Dynapac CC21 Roller |  | 1 | 1700 | 1700 | 53
2012-10-08 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3.5 | 95 | 332.5 | 53
2012-10-08 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3.25 | 110 | 357.5 | 53
2012-10-09 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 8.5 | 110 | 935 | 53
2012-10-09 | Plant Operator-Labour Hire | Labour | hr | 8 | 48 | 384 | 53
2012-10-09 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8.5 | 95 | 807.5 | 53
2012-10-09 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 53
2012-10-09 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
| Subtotal for 053 |  |  |  |  | 308767.983
Portfolio WBS 057
2012-04-04 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 6 | 95 | 570 | 57
2012-04-04 | Twin Steer Truck Hire | Humphries Pty Ltd | hr | 6 | 92.73 | 556.38 | 57
2012-04-04 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 6 | 130 | 780 | 57
2012-04-04 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 57
2012-04-04 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 57
2012-04-04 | (10 M Tipper ) | Pollard Earthmoving | hr | 6 | 95 | 570 | 57
2012-04-05 | Water Truck Hire | Berry Excavations | hr | 7.5 | 100 | 750 | 57
2012-04-05 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 6.5 | 90 | 585 | 57
2012-04-05 | Twin Steer Hire | Humphries Pty Ltd | hr | 5 | 92.73 | 463.65 | 57
2012-04-05 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 10 | 130 | 1300 | 57
2012-04-05 | Truck & Trailer Hire | Pollard Earthmoving | hr | 8 | 140 | 1120 | 57
2012-04-05 | (10 M Tipper ) | Pollard Earthmoving | hr | 7 | 95 | 665 | 57
2012-04-05 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 7.5 | 95 | 712.5 | 57
2012-04-05 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-04-05 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-04-05 | Twim Steer Hire | Humphries Pty Ltd | hr | 5 | 92.73 | 463.65 | 57
2012-04-05 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-04-05 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-04-05 | Truck & Dog Hire | Talbots | hr | 11.25 | 95 | 1068.75 | 57
2012-04-05 | Taylors Earthmoving ( 23t Excavator ) | Taylors Earthmoving | hr | 10 | 130 | 1300 | 57
2012-04-05 | Truck & Dog Hire | Ace One Truck Hire | hr | 11 | 145 | 1595 | 57
2012-04-10 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3 | 95 | 285 | 57
2012-04-10 | (10 M Tipper ) | Pollard Earthmoving | hr | 7 | 95 | 665 | 57
2012-04-10 | Twin Steer Hire | Humphries Pty Ltd | hr | 4 | 92.73 | 370.92 | 57
2012-04-10 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 57
2012-04-10 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 57
2012-04-10 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4.5 | 130 | 585 | 57
2012-04-10 | Truck & Trailer Hire | Pollard Earthmoving | hr | 3 | 140 | 420 | 57
2012-04-10 | Truck & Dog Hire | Talbots | hr | 11 | 130 | 1430 | 57
2012-04-10 | Truck & Dog Hire | Ace One Truck Hire | hr | 10.5 | 145 | 1522.5 | 57
2012-04-10 | Truck & Dog Hire | J & S Truck Hire |  | 8 | 150 | 1200 | 57
2012-04-10 | Twin Steer Hire | Humphries Pty Ltd | hr | 4 | 92.73 | 370.92 | 57
2012-04-10 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 7 | 90 | 630 | 57
2012-04-10 | Water Truck Hire | Berry Excavations | hr | 5.5 | 100 | 550 | 57
2012-04-10 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 57
2012-04-10 | Taylors Earthmoving (23t Excavator ) | Taylors Earthmoving | hr | 10.5 | 130 | 1365 | 57
2012-04-10 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 57
2012-04-11 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 57
2012-04-11 | Truck & Dog Hire | Talbots | hr | 3 | 130 | 390 | 57
2012-04-11 | Truck & Dog Hire | J & S Truck Hire |  | 3 | 150 | 450 | 57
2012-04-11 | Truck & Dog Hire | Ace One Truck Hire | hr | 3.5 | 145 | 507.5 | 57
2012-04-11 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 57
2012-04-11 | Truck & Trailer Hire | Pollard Earthmoving | hr | 3 | 140 | 420 | 57
2012-04-11 | Water Truck Hire | Berry Excavations | hr | 5 | 100 | 500 | 57
2012-04-11 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 57
2012-04-11 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 57
2012-04-11 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 57
2012-04-12 | Water Truck Hire | Berry Excavations | hr | 5 | 100 | 500 | 57
2012-04-12 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 57
2012-04-12 | Excavator ( 5 Tonner ) | Berry Excavations | hr | 8.5 | 100 | 850 | 57
2012-04-12 | Truck & Dog Hire | Ace One Truck Hire | hr | 6 | 145 | 870 | 57
2012-04-12 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 57
2012-04-12 | Truck & Dog Hire | J & S Truck Hire |  | 7 | 150 | 1050 | 57
2012-04-12 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 57
2012-04-12 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2.5 | 90 | 225 | 57
2012-04-12 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 57
2012-04-12 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 57
2012-04-13 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 57
2012-04-13 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 57
2012-04-13 | Truck & Dog Hire | Talbots | hr | 7.5 | 130 | 975 | 57
2012-04-13 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 57
2012-04-13 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 57
2012-04-13 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2.5 | 90 | 225 | 57
2012-04-13 | Truck & Dog Hire | Ace One Truck Hire | hr | 6.5 | 145 | 942.5 | 57
2012-04-13 | Truck & Dog Hire | J & S Truck Hire |  | 7 | 150 | 1050 | 57
2012-04-13 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 3 | 130 | 390 | 57
2012-04-16 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 57
2012-04-16 | Labour Hire | Labour | hr | 3 | 48 | 144 | 57
2012-04-16 | Truck & Dog Hire | Ace One Truck Hire | hr | 2.5 | 145 | 362.5 | 57
2012-04-16 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 1 | 130 | 130 | 57
2012-04-16 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 57
2012-04-16 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 57
2012-04-17 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 57
2012-04-17 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 57
2012-04-17 | Truck & Dog Hire | Ace One Truck Hire | hr | 8 | 145 | 1160 | 57
2012-04-17 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 3 | 130 | 390 | 57
2012-04-18 | Truck & Dog Hire | Ace One Truck Hire | hr | 7 | 145 | 1015 | 57
2012-04-18 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 57
2012-04-18 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 57
2012-04-18 | Water Truck Hire | Humphries Pty Ltd | hr | 1.75 | 136.365 | 238.6387 | 57
2012-04-18 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 57
2012-04-18 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 57
2012-04-18 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 6.5 | 130 | 845 | 57
2012-04-30 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 57
2012-04-30 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2 | 95 | 190 | 57
2012-04-30 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 57
2012-04-30 | Labour Hire | Labour | hr | 2 | 48 | 96 | 57
2012-05-01 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9.5 | 130 | 1235 | 57
2012-05-01 | Labour Hire | Labour | hr | 5 | 48 | 240 | 57
2012-05-01 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-05-01 | Twin Steer Hire | Humphries Pty Ltd | hr | 10.25 | 92.729 | 950.4723 | 57
2012-05-01 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 57
2012-05-01 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 57
2012-05-01 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5 | 95 | 475 | 57
2012-05-01 | Earthmoving Hire ( 24t ) | Banks Earthmoving | hr | 9.5 | 145 | 1377.5 | 57
2012-05-01 | Twin Steer Hire | Humphries Pty Ltd | hr | 10 | 92.72 | 927.2 | 57
2012-05-01 | Water Truck Hire | Talbots | hr | 3 | 95 | 285 | 57
2012-05-01 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-05-02 | Grader Hire | Humphries Pty Ltd | hr | 9.5 | 100 | 950 | 57
2012-05-02 | Twin Steer | Humphries Pty Ltd | hr | 10 | 92.73 | 927.3 | 57
2012-05-02 | Twin Steer | Humphries Pty Ltd | hr | 10 | 92.73 | 927.3 | 57
2012-05-02 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 10 | 95 | 950 | 57
2012-05-03 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5.5 | 95 | 522.5 | 57
2012-05-03 | Water Truck Hire | Talbots | hr | 5 | 95 | 475 | 57
2012-05-03 | Twin Steer Hire | Humphries Pty Ltd | hr | 9.75 | 92.73 | 904.1175 | 57
2012-05-03 | Twin Steer Hire | Humphries Pty Ltd | hr | 9.75 | 92.73 | 904.1175 | 57
2012-05-03 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-05-03 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-05-03 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 57
2012-05-03 | Labour Hire | Labour | hr | 9.5 | 48 | 456 | 57
2012-05-03 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 57
2012-05-03 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 8 | 130 | 1040 | 57
2012-05-03 | Earthmoving Hire ( 24t ) | Banks Earthmoving | hr | 9.5 | 145 | 1377.5 | 57
2012-05-03 | Earthmoving Hire 24T | Banks Earthmoving | hr | 9.5 | 145 | 1377.5 | 57
2012-05-03 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 57
2012-05-04 | Twin Steer Hire | Humphries Pty Ltd | hr | 6 | 92.73 | 556.38 | 57
2012-05-04 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 57
2012-05-04 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 57
2012-05-04 | Grader Hire | Humphries Pty Ltd | hr | 9 | 100 | 900 | 57
2012-05-04 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-05-04 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 6.5 | 95 | 617.5 | 57
2012-05-04 | Earthmoving Hire 24t | Banks Earthmoving | hr | 9.5 | 145 | 1377.5 | 57
2012-05-04 | Twin Steer Hire | Humphries Pty Ltd | hr | 6 | 92.73 | 556.38 | 57
2012-05-04 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 57
2012-05-04 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 57
2012-05-04 | Labour Hire | Labour | hr | 9.5 | 48 | 456 | 57
2012-05-04 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 1 | 120 | 120 | 57
2012-05-08 | Twin Steer Hire | Humphries Pty Ltd | hr | 4.75 | 92.73 | 440.4675 | 57
2012-05-08 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5 | 90 | 450 | 57
2012-05-08 | Labour Hire | Labour | hr | 5 | 48 | 240 | 57
2012-05-08 | (Water Truck ) | Talbots | hr | 7.5 | 95 | 712.5 | 57
2012-05-08 | Twin Steer Hire | Humphries Pty Ltd | hr | 5 | 92.73 | 463.65 | 57
2012-05-08 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5.5 | 95 | 522.5 | 57
2012-05-08 | Grader Hire | Humphries Pty Ltd | hr | 5 | 100 | 500 | 57
2012-05-08 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-05-08 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-05-10 | Pad Foot Roller - Dry. Hired on the 2/5/2012 - 8/5/2012. Inv No 284764 | PF Roller |  | 5 | 365 | 1825 | 57
2012-05-17 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 57
2012-05-17 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 8 | 90 | 720 | 57
2012-05-17 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 57
2012-05-17 | Truck & Dog Hire | Ace One Truck Hire | hr | 8 | 145 | 1160 | 57
2012-05-17 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 57
2012-05-17 | Labour Hire | Labour | hr | 4.5 | 48 | 216 | 57
2012-05-17 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 6 | 130 | 780 | 57
2012-05-18 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 6 | 130 | 780 | 57
2012-05-18 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 57
2012-05-18 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 57
2012-05-18 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 57
2012-05-18 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 57
2012-05-18 | Truck & Dog Hire | Ace One Truck Hire | hr | 9.5 | 145 | 1377.5 | 57
2012-05-18 | Labour Hire | Labour | hr | 4.5 | 48 | 216 | 57
2012-05-18 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 57
2012-05-19 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 57
2012-05-19 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 57
2012-05-19 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4 | 130 | 520 | 57
2012-05-19 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 57
2012-05-19 | Truck & Dog Hire | Talbots | hr | 2 | 130 | 260 | 57
2012-05-19 | (10 M Tipper ) | Pollard Earthmoving | hr | 4 | 95 |  | 57
2012-05-19 | Labour Hire | Labour | hr | 7 | 48 | 336 | 57
2012-05-19 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 57
2012-05-24 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 57
2012-05-24 | Labour Hire | Labour | hr | 3.5 | 48 | 168 | 57
2012-05-24 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 57
2012-07-04 | Labour Hire | Labour | hr | 8.5 | 48 | 408 | 57
2012-07-04 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 57
2012-07-04 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 57
2012-07-04 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5.5 | 130 | 715 | 57
2012-07-04 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 57
2012-07-05 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9 | 95 | 855 | 57
2012-07-06 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 6.5 | 95 | 617.5 | 57
2012-07-06 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 9.25 | 110 | 1017.5 | 57
2012-07-16 | (10 M Tipper ) | Pollard Earthmoving | hr | 5 | 95 | 475 | 57
2012-07-16 | Bulk GP / GB Cement. Inv No - 21272448 | Cement |  | 60 | 9.5 | 570 | 57
2012-07-16 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 6 | 110 | 660 | 57
2012-07-16 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-07-16 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 57
2012-07-16 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 57
2012-07-16 | Labour Hire | Labour | hr | 10 | 48 | 480 | 57
2012-07-16 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 10 | 130 | 1300 | 57
2012-07-16 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9 | 95 | 855 | 57
2012-07-16 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 57
2012-07-17 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.25 | 110 | 467.5 | 57
2012-07-17 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 57
2012-07-17 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-07-17 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-07-17 | Labour Hire | Labour | hr | 5 | 48 | 240 | 57
2012-07-17 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4 | 130 | 520 | 57
2012-07-17 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-07-17 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-07-19 | (10 M Tipper ) | Pollard Earthmoving | hr | 6 | 95 | 570 | 57
2012-07-19 | Earthmoving & Water Cart | Talbots | hr | 8 | 95 | 760 | 57
2012-07-19 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 57
2012-07-19 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 7 | 110 | 770 | 57
2012-07-19 | Bulk GP / GB Cement. Inv No - 21272578 | Cement |  | 1 | 649.09 | 649.09 | 57
2012-07-19 | Labour Hire | Labour | hr | 8 | 48 | 384 | 57
2012-07-19 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 57
2012-07-19 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 6 | 95 | 570 | 57
2012-07-19 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 57
2012-07-19 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 7 | 130 | 910 | 57
2012-07-19 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 57
2012-07-20 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9 | 130 | 1170 | 57
2012-07-20 | (10 M Tipper ) | Pollard Earthmoving | hr | 6 | 95 | 570 | 57
2012-07-20 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8 | 95 | 760 | 57
2012-07-20 | Labour Hire | Labour | hr | 9.5 | 48 | 456 | 57
2012-07-20 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-07-20 | Earthmoving & Water Cart | Talbots | hr | 7.5 | 95 | 712.5 | 57
2012-07-20 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-07-20 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 9.5 | 110 | 1045 | 57
2012-07-20 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-07-20 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-07-21 | Bulk GP / GB Cement. Inv No - 21272650 | Cement |  | 1 | 262.72 | 262.72 | 57
2012-07-21 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 57
2012-07-21 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 7 | 110 | 770 | 57
2012-07-21 | Earthmoving & Water Cart | Talbots | hr | 7.5 | 95 | 712.5 | 57
2012-07-21 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 6.5 | 95 | 617.5 | 57
2012-07-21 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 6.5 | 95 | 617.5 | 57
2012-07-21 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 57
2012-07-21 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 7 | 130 | 910 | 57
2012-07-21 | Labour Hire | Labour | hr | 7 | 48 | 336 | 57
2012-07-22 | Time & Half | Labour | hr | 3 | 45.7 | 137.1 | 57
2012-07-23 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 6.5 | 95 | 617.5 | 57
2012-07-23 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 8 | 130 | 1040 | 57
2012-07-23 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-07-23 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 9.5 | 110 | 1045 | 57
2012-07-23 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-07-23 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-07-23 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-07-23 | (10 M Tipper ) | Pollard Earthmoving | hr | 6.75 | 95 | 641.25 | 57
2012-07-23 | Earthmoving & Water Cart | Talbots | hr | 7.5 | 95 | 712.5 | 57
2012-07-23 | Labour Hire | Labour | hr | 9.5 | 48 | 456 | 57
2012-07-24 | Bulk GP / GB Cement. Inv No - 21272744 | Cement |  | 1 | 108.81 | 108.81 | 57
2012-07-24 | (10 M Tipper ) | Pollard Earthmoving | hr | 8.5 | 95 | 807.5 | 57
2012-07-24 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-07-24 | New Holland Compact Grader - No Operator | NH Grader | hr | 2.5 | 25.78 | 64.45 | 57
2012-07-24 | Earthmoving & Water Cart | Talbots | hr | 7 | 95 | 665 | 57
2012-07-24 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 9.5 | 110 | 1045 | 57
2012-07-24 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-07-24 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8.5 | 95 | 807.5 | 57
2012-07-24 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-07-24 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9 | 130 | 1170 | 57
2012-07-24 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 57
2012-07-25 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 10 | 130 | 1300 | 57
2012-07-25 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 57
2012-07-25 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9.5 | 95 | 902.5 | 57
2012-07-25 | (10 M Tipper ) | Pollard Earthmoving | hr | 9.5 | 95 | 902.5 | 57
2012-07-25 | Earthmoving & Water Cart | Talbots | hr | 6.5 | 95 | 617.5 | 57
2012-07-25 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 9.75 | 110 | 1072.5 | 57
2012-07-25 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 57
2012-07-25 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 57
2012-07-25 | Bulk GP / GB Cement. Inv No - 21272790 | Cement |  | 1 | 734.54 | 734.54 | 57
2012-07-26 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 9.5 | 110 | 1045 | 57
2012-07-26 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9.5 | 130 | 1235 | 57
2012-07-26 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 57
2012-07-26 | (10 M Tipper ) | Pollard Earthmoving | hr | 8.5 | 95 | 807.5 | 57
2012-07-26 | Labour Hire ( Achieve Group ) | Labour | hr | 2 | 34.81 | 69.62 | 57
2012-07-26 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 57
2012-07-26 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-07-26 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-07-26 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9.5 | 95 | 902.5 | 57
2012-07-26 | Allans Earthmoving (Tipper Hire) | Allans Earthmoving | hr | 9.5 | 95 | 902.5 | 57
2012-07-27 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-07-27 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 6 | 95 | 570 | 57
2012-07-27 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 57
2012-07-27 | Earthmoving & Water Cart | Talbots | hr | 5 | 95 | 475 | 57
2012-07-27 | Bulk GP / GB Cement. Inv No - 21272888 | Cement |  | 1 | 525 | 525 | 57
2012-07-27 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-07-27 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 57
2012-07-27 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5 | 110 | 550 | 57
2012-07-27 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 7 | 130 | 910 | 57
2012-07-27 | (10 M Tipper ) | Pollard Earthmoving | hr | 7 | 95 | 665 | 57
2012-07-31 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4 | 110 | 440 | 57
2012-07-31 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5 | 130 | 650 | 57
2012-07-31 | Allans Earthmoving (Tipper Hire) | Allans Earthmoving | hr | 2 | 95 | 190 | 57
2012-07-31 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4.5 | 95 | 427.5 | 57
2012-07-31 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2 | 95 | 190 | 57
2012-07-31 | Double Drum Roller. Inv No - 295261 | Double Drum Roller |  | 9 | 247 | 2223 | 57
2012-07-31 | Pad Foot Roller - Dry Hire Hired 7/7/12 - 31/7/12. Inv No - 295263 | PF Roller |  | 6 | 325 | 1950 | 57
2012-07-31 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 57
2012-07-31 | (10 M Tipper ) | Pollard Earthmoving | hr | 2 | 95 | 190 | 57
2012-08-01 | Grader Hire | Humphries Pty Ltd | hr | 3 | 100 | 300 | 57
2012-08-01 | Allans Earthmoving (Tipper Hire) | Allans Earthmoving | hr | 3.5 | 95 | 332.5 | 57
2012-08-01 | N K Jepsen Tipper Hire | N K Jepsen Tipper Hire | hr | 4.5 | 90 | 405 | 57
2012-08-01 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8.5 | 95 | 807.5 | 57
2012-08-01 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 57
2012-08-01 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3.5 | 95 | 332.5 | 57
2012-08-01 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4.5 | 130 | 585 | 57
2012-08-01 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 57
2012-08-01 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 57
2012-08-01 | Labour Hire | Labour | hr | 10 | 48 | 480 | 57
2012-08-01 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 57
2012-08-01 | 11T Excavator Hire | Watts Excavations | day | 7.5 | 110 | 825 | 57
2012-08-01 | Water Truck Hire | Tom Hurst | hr | 9 | 90 | 810 | 57
2012-08-02 | Allans Earthmoving (Tipper Hire) | Allans Earthmoving | hr | 5 | 95 | 475 | 57
2012-08-02 | (10 M Tipper ) | Pollard Earthmoving | hr | 3 | 95 | 285 | 57
2012-08-02 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3 | 95 | 285 | 57
2012-08-02 | Earthmoving & Water Cart | Talbots | hr | 4.5 | 95 | 427.5 | 57
2012-08-02 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5 | 130 | 650 | 57
2012-08-02 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-08-02 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5 | 95 | 475 | 57
2012-08-02 | Labour Hire | Labour | hr | 2 | 48 | 96 | 57
2012-08-03 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5 | 110 | 550 | 57
2012-08-03 | Earthmoving & Water Cart | Talbots | hr | 4.5 | 95 | 427.5 | 57
2012-08-03 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2 | 95 | 190 | 57
2012-08-03 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 57
2012-08-03 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5 | 130 | 650 | 57
2012-08-03 | (10 M Tipper ) | Pollard Earthmoving | hr | 4.5 | 95 | 427.5 | 57
2012-08-03 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5 | 95 | 475 | 57
2012-08-04 | (10 M Tipper ) | Pollard Earthmoving | hr | 3 | 95 | 285 | 57
2012-08-04 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4.5 | 130 | 585 | 57
2012-08-04 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3 | 95 | 285 | 57
2012-08-04 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 57
2012-08-04 | Earthmoving & Water Cart | Talbots | hr | 4 | 95 | 380 | 57
2012-08-04 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 57
2012-08-06 | 11T Excavator Hire | Watts Excavations | hr | 9.5 | 110 | 1045 | 57
2012-08-06 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 | 365 | 57
2012-08-07 | Earthmoving & Water Cart | Talbots | hr | 5 | 95 | 475 | 57
2012-08-07 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 | 365 | 57
2012-08-07 | 11T Excavator Hire | Watts Excavations | hr | 9.5 | 110 | 1045 | 57
2012-08-07 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 3 | 130 | 390 | 57
2012-08-07 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 57
2012-08-07 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5 | 95 | 475 | 57
2012-08-07 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 57
2012-08-08 | (10 M Tipper ) | Pollard Earthmoving | hr | 6.5 | 95 | 617.5 | 57
2012-08-08 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 6.5 | 95 | 617.5 | 57
2012-08-08 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-08-08 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4 | 130 | 520 | 57
2012-08-08 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 | 365 | 57
2012-08-08 | 11T Excavator Hire | Watts Excavations | hr | 8.5 | 110 | 935 | 57
2012-08-09 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3 | 95 | 285 | 57
2012-08-09 | Grader Hire | Humphries Pty Ltd | hr | 2.5 | 100 | 250 | 57
2012-08-09 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5.5 | 130 | 715 | 57
2012-08-09 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 | 365 | 57
2012-08-09 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-08-09 | (10 M Tipper ) | Pollard Earthmoving | hr | 5 | 95 | 475 | 57
2012-08-10 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 6 | 95 | 570 | 57
2012-08-10 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 57
2012-08-10 | Earthmoving & Water Cart | Talbots | hr | 3.5 | 95 | 332.5 | 57
2012-08-10 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 6.5 | 130 | 845 | 57
2012-08-10 | (10 M Tipper ) | Pollard Earthmoving | hr | 6 | 95 | 570 | 57
2012-08-13 | Truck Hire | Humphries Pty Ltd | hr | 7.5 | 87.273 | 654.5475 | 57
2012-08-13 | Backhoe Hire | Talbots | hr | 8 | 95 | 760 | 57
2012-08-13 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 6 | 110 | 660 | 57
2012-08-13 | Earthmoving & Water Cart | Talbots | hr | 4 | 95 | 380 | 57
2012-08-13 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4.5 | 95 | 427.5 | 57
2012-08-13 | (10 M Tipper ) | Pollard Earthmoving | hr | 4.5 | 95 | 427.5 | 57
2012-08-13 | Semi Side Tipper Hire | Talbots | hr | 9 | 130 | 1170 | 57
2012-08-13 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-08-13 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4.5 | 130 | 585 | 57
2012-08-14 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 57
2012-08-14 | (10 M Tipper ) | Pollard Earthmoving | hr | 5 | 95 | 475 | 57
2012-08-14 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5 | 95 | 475 | 57
2012-08-14 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3.5 | 110 | 385 | 57
2012-08-14 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5.5 | 130 | 715 | 57
2012-08-14 | Earthmoving & Water Cart | Talbots | hr | 4 | 95 | 380 | 57
2012-08-15 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3 | 110 | 330 | 57
2012-08-15 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5 | 130 | 650 | 57
2012-08-15 | (10 M Tipper ) | Pollard Earthmoving | hr | 5 | 95 | 475 | 57
2012-08-15 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5 | 95 | 475 | 57
2012-08-15 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 57
2012-08-15 | Earthmoving & Water Cart | Talbots | hr | 3 | 95 | 285 | 57
2012-08-16 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 | 365 | 57
2012-08-17 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 | 365 | 57
2012-08-18 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 | 365 | 57
2012-08-21 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-08-21 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-08-21 | Plant Operator-Labour Hire | Labour | hr | 3 | 48 | 144 | 57
2012-08-21 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-08-21 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5.5 | 95 | 522.5 | 57
2012-08-21 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 | 365 | 57
2012-08-21 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5 | 110 | 550 | 57
2012-08-21 | (10 M Tipper ) | Pollard Earthmoving | hr | 5.5 | 95 | 522.5 | 57
2012-08-22 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3 | 95 | 285 | 57
2012-08-22 | (10 M Tipper ) | Pollard Earthmoving | hr | 3 | 95 | 285 | 57
2012-08-22 | Earthmoving & Water Cart | Talbots | hr | 5.5 | 95 | 522.5 | 57
2012-08-22 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 57
2012-08-22 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 57
2012-08-22 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4.5 | 130 | 585 | 57
2012-08-22 | Water Truck Hire | Talbots | hr | 7.5 | 95 | 712.5 | 57
2012-08-22 | N K Jepsen Tipper Hire | N K Jepsen Tipper Hire | hr | 5.5 | 130 | 715 | 57
2012-08-22 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 | 365 | 57
2012-08-22 | Truck & Dog Hire | Humphries Pty Ltd | hr | 5.5 | 107.27 | 589.985 | 57
2012-08-23 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 57
2012-08-23 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 57
2012-08-23 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4.5 | 130 | 585 | 57
2012-08-23 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3 | 95 | 285 | 57
2012-08-23 | (10 M Tipper ) | Pollard Earthmoving | hr | 3 | 95 | 285 | 57
2012-08-23 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 | 365 | 57
2012-08-24 | Earthmoving & Water Cart | Talbots | hr | 2 | 95 | 190 | 57
2012-08-24 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 57
2012-08-24 | Plant Operator-Labour Hire | Labour | hr | 5.5 | 48 | 264 | 57
2012-08-24 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 57
2012-08-24 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 57
2012-08-24 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 57
2012-08-24 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.5 | 110 | 495 | 57
2012-08-27 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5 | 95 | 475 | 57
2012-08-27 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 57
2012-08-27 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 3.5 | 130 | 455 | 57
2012-08-27 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.5 | 110 | 495 | 57
2012-08-27 | (10 M Tipper ) | Pollard Earthmoving | hr | 5 | 95 | 475 | 57
2012-08-27 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 57
2012-08-28 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 2.5 | 110 | 275 | 57
2012-08-28 | Earthmoving & Water Cart | Talbots | hr | 3 | 95 | 285 | 57
2012-08-28 | (10 M Tipper ) | Pollard Earthmoving | hr | 5 | 95 | 475 | 57
2012-08-28 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 57
2012-08-28 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 3.5 | 130 | 455 | 57
2012-08-28 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5 | 95 | 475 | 57
2012-08-29 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4 | 130 | 520 | 57
2012-08-29 | (10 M Tipper ) | Pollard Earthmoving | hr | 4 | 95 | 380 | 57
2012-08-29 | Micheal Biles. ( 10m Tipper ) | Micheal Biles | hr | 4 | 95 | 380 | 57
2012-08-29 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 57
2012-08-29 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 57
2012-08-29 | Plant Operator-Labour Hire | Labour | hr | 2 | 48 | 96 | 57
2012-08-29 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-08-29 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 57
2012-08-30 | (10 M Tipper ) | Pollard Earthmoving | hr | 6 | 95 | 570 | 57
2012-08-30 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 6 | 110 | 660 | 57
2012-08-30 | Pad Foot Roller - Dry. Hired 31/7/12 - 24/8/12. Inv No - 298887 | PF Roller |  | 1 | 2166.666 | 2166.666 | 57
2012-08-30 | Earthmoving & Water Cart | Talbots | hr | 3 | 95 | 285 | 57
2012-08-31 | Micheal Biles. ( 10m Tipper ) | Micheal Biles | hr | 4.5 | 95 | 427.5 | 57
2012-08-31 | Earthmoving & Water Cart | Talbots | hr | 3 | 95 | 285 | 57
2012-08-31 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-08-31 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 57
2012-08-31 | Plant Operator-Labour Hire | Labour | hr | 5 | 48 | 240 | 57
2012-08-31 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5 | 110 | 550 | 57
2012-08-31 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-08-31 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 57
2012-09-06 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5 | 130 | 650 | 57
2012-09-06 | Truck Hire | Micheal Biles | hr | 5.5 | 95 | 522.5 | 57
2012-09-06 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 57
2012-09-06 | (10 M Tipper ) | Pollard Earthmoving | hr | 5 | 95 | 475 | 57
2012-09-06 | Plant Operator-Labour Hire | Labour | hr | 2 | 48 | 96 | 57
2012-09-07 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 57
2012-09-07 | Plant Operator-Labour Hire | Labour | hr | 2.5 | 48 | 120 | 57
2012-09-07 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 57
2012-09-07 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 2.5 | 130 | 325 | 57
2012-09-07 | Earthmoving & Water Cart | Talbots | hr | 3 | 95 | 285 | 57
2012-09-07 | Truck Hire | Micheal Biles | hr | 1 | 95 | 95 | 57
2012-09-07 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 57
2012-09-07 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 57
2012-09-07 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 3 | 66.07 | 198.21 | 57
2012-09-10 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-09-10 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 57
2012-09-10 | Plant Operator-Labour Hire | Labour | hr | 5 | 48 | 240 | 57
2012-09-10 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4.5 | 130 | 585 | 57
2012-09-10 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3.5 | 95 | 332.5 | 57
2012-09-10 | Labour Hire ( People Resourcing ) | Labour | hr | 3 | 40.97 | 122.91 | 57
2012-09-10 | Truck Hire Dry Hire | Micheal Biles | hr | 3 | 50 | 150 | 57
2012-09-10 | (10 M Tipper ) | Pollard Earthmoving | hr | 5 | 95 | 475 | 57
2012-09-11 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4.5 | 130 | 585 | 57
2012-09-11 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-09-11 | (10 M Tipper ) | Pollard Earthmoving | hr | 4.5 | 95 | 427.5 | 57
2012-09-11 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 57
2012-09-11 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-09-12 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 57
2012-09-12 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4.5 | 130 | 585 | 57
2012-09-12 | (10 M Tipper ) | Pollard Earthmoving | hr | 4 | 95 | 380 | 57
2012-09-12 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3.5 | 95 | 332.5 | 57
2012-09-12 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-09-13 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 57
2012-09-13 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 57
2012-09-13 | (10 M Tipper ) | Pollard Earthmoving | hr | 2 | 95 | 190 | 57
| Subtotal for 057 |  |  |  |  | 215667.317
Portfolio WBS 061
2011-10-28 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 61
2011-10-29 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 61
2011-10-29 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 61
2011-11-22 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 61
2011-11-22 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 61
2011-11-22 | Tipper Hire | Labour | hr | 4.5 | 65 | 292.5 | 61
2011-11-22 | Excavator ( 7 Tonne) | Berry Excavations | hr | 3.5 | 140 | 490 | 61
2011-11-22 | Bobcat | Labour | hr | 2.5 | 95 | 237.5 | 61
2011-11-22 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 61
2012-03-03 | Taylors Earthmoving (3t Excavator ) | Taylors Earthmoving | hr | 3 | 85 | 255 | 61
2012-03-03 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 61
2012-03-03 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 61
2012-03-03 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 61
2012-03-12 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 61
2012-03-12 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 61
2012-03-12 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 61
2012-03-12 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 61
2012-03-12 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 61
2012-08-15 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 61
2012-08-15 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 61
2012-08-15 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4 | 110 | 440 | 61
| Subtotal for 061 |  |  |  |  | 4390.425
Portfolio WBS 062
2011-10-25 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 1.5 | 66.07 | 99.105 | 62
2011-10-25 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2011-10-25 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2011-10-25 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2011-10-25 | Plate Compactor - Dry Vibrating Rammer Inv - 259690 | Plate Compactor |  | 1 | 159.51 | 159.51 | 62
2011-10-25 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4.5 | 90 | 405 | 62
2011-10-26 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 1.5 | 66.07 | 99.105 | 62
2011-10-27 | (Water Truck ) | Talbots | hr | 9 | 95 | 855 | 62
2011-10-31 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-31 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-31 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 62
2011-10-31 | 21 Tonne Excavator | Berry Excavations | hr | 9 | 110 | 990 | 62
2011-11-01 | ( Bobcat Hire ) | Labour | hr | 10 | 95 | 950 | 62
2011-11-01 | Excavator ( 7 Tonne ) | Berry Excavations | hr | 7 | 110 | 770 | 62
2011-11-01 | DoyawanaTruck Hire | Doyawana | hr | 9.5 | 95 | 902.5 | 62
2011-11-01 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2011-11-01 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-11-02 | Excavator ( 7 Tonne ) | Berry Excavations | hr | 8 | 110 | 880 | 62
2011-11-02 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-11-02 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-11-10 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2011-11-10 | Foreman | Labour | hr | 9.5 | 44.2 | 419.9 | 62
2011-11-10 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2011-11-10 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3.5 | 90 | 315 | 62
2011-11-10 | Excavator ( 7 Tonne) | Berry Excavations | hr | 3.75 | 110 | 412.5 | 62
2011-11-14 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2011-11-14 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2011-11-14 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2011-11-14 | Excavator ( 7 Tonne) | Berry Excavations | hr | 3.5 | 110 | 385 | 62
2011-11-14 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2011-11-18 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2011-11-18 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 62
2011-11-18 | DoyawanaTruck Hire | Doyawana | hr | 7.5 | 95 | 712.5 | 62
2011-11-18 | ( Bobcat Hire ) | Labour | hr | 2 | 95 | 190 | 62
2011-11-19 | DoyawanaTruck Hire | Doyawana | hr | 7.5 | 95 | 712.5 | 62
2011-11-21 | DoyawanaTruck Hire | Doyawana | hr | 9.5 | 95 | 902.5 | 62
2011-11-23 | Bobcat | Labour | hr | 5 | 95 | 475 | 62
2011-11-23 | DoyawanaTruck Hire | Doyawana | hr | 10 | 95 | 950 | 62
2011-11-23 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2011-11-23 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2011-11-23 | Hire of tipper from foxdale Quarry to Jupp Street Inv No - 18970 | Tipper |  | 6.5 | 145 | 942.5 | 62
2011-11-28 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2011-11-28 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2011-11-28 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2011-11-29 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2011-11-29 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2011-11-29 | DoyawanaTruck Hire | Doyawana | hr | 4 | 95 | 380 | 62
2011-11-29 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2011-11-30 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 62
2011-11-30 | Hire from the 30/11/2011 to the 30/11/2011 Inv No 265610 | Vibrating Rammer |  | 1 | 79.51 | 79.51 | 62
2011-11-30 | Hire From the 31/10/2011 to the 30/11/2011 Inv No 7775893 | Multi Tyre Roller |  | 1 | 10001 | 10001 | 62
2011-11-30 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 62
2011-12-01 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 62
2011-12-01 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 62
2011-12-02 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 62
2011-12-02 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 62
2011-12-05 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2011-12-05 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2011-12-07 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2011-12-07 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2011-12-09 | 7 Tonne Excavator | Berry Excavations | hr | 5.5 | 110 | 605 | 62
2011-12-09 | Stabilised Sand Inv No 8834 | Stabilised Sand |  | 1 | 358.33 | 358.33 | 62
2011-12-09 | Truck | Labour | hr | 4 | 65 | 260 | 62
2011-12-10 | Vibrating Rammer ( Flexi Hire ) Hired from the30/11/2011 to the 10/12/2011 Inv No 267003 | Vibrating Rammer |  | 1 | 493.91 | 493.91 | 62
2011-12-12 | Bedding Sand Inv No 4428 | Sand |  | 1 | 69.29 | 69.29 | 62
2011-12-31 | Hire from the 30/11/2011 to the 31/12/2011. Inv No 269588 | Double Drum Roller |  | 1 | 2520 | 2520 | 62
2011-12-31 | Coates 12H Grader Hire Hire from the 30/11/2011 to the 31/12/2011 Inv No - 9194232 | Grader |  | 1 | 9281.25 | 9281.25 | 62
2012-01-23 | Coates 12H Grader Hire . Hired from the 31/12/2011 to the 19/01/2012 . Inv No - 9268059 | Grader |  | 1 | 8274.68 | 8274.68 | 62
2012-01-23 | Labour Hire ( People Resourcing ) | Labour | hr | 8.5 | 40.97 | 348.245 | 62
2012-01-23 | Micheal Biles. ( 10m Tipper ) | Micheal Biles | hr | 6 | 125 | 750 | 62
2012-01-23 | Truck & Trailer Hire | Raymonds Truck Hire | hr | 6.5 | 125 | 812.5 | 62
2012-01-23 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-01-23 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-01-23 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-01-23 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-01-23 | S.A & M.L Mackenzie ( Grader Hire ) | Mackenzie Earthmoving | hr | 6 | 145 | 870 | 62
2012-01-24 | Truck & Trailer Hire | Humphries Pty Ltd | hr | 6 | 113.19 | 679.14 | 62
2012-01-24 | Truck & Trailer Hire | Raymonds Truck Hire | hr | 9.5 | 125 | 1187.5 | 62
2012-01-24 | S.A & M.L Mackenzie ( Grader Hire ) | Mackenzie Earthmoving | hr | 7 | 145 | 1015 | 62
2012-01-24 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2012-01-24 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2012-01-24 | Labour Hire ( People Resourcing ) | Labour | hr | 9.5 | 40.97 | 389.215 | 62
2012-02-03 | New Holland Compact Grader - No Operator | NH Grader | hr | 5.5 | 25.78 | 141.79 | 62
2012-02-06 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3.5 | 90 | 315 | 62
2012-02-06 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-02-06 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-02-06 | Truck & Dog Hire | Micheal Biles | hr | 8.5 | 125 | 1062.5 | 62
2012-02-06 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2012-02-07 | Truck & Dog Hire | Micheal Biles | hr | 9.5 | 125 | 1187.5 | 62
2012-02-07 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 62
2012-02-07 | New Holland Compact Grader - No Operator | NH Grader | hr | 8 | 25.78 | 206.24 | 62
2012-02-07 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-02-07 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-02-07 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2012-02-08 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-02-08 | Truck & Dog Hire | Micheal Biles | hr | 9 | 125 | 1125 | 62
2012-02-08 | New Holland Compact Grader - No Operator | NH Grader | hr | 3.5 | 25.78 | 90.23 | 62
2012-02-08 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2.15 | 90 | 193.5 | 62
2012-02-08 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-02-10 | Vibrating Rammer ( Flexi Hire ) . Hire from the 2/2/12 to the 10/2/12. Inv No 273688 | Vibrating Rammer |  | 1 | 573.43 | 573.43 | 62
2012-02-13 | Truck | Micheal Biles | hr | 8 | 125 | 1000 | 62
2012-02-13 | New Holland Compact Grader - No Operator | NH Grader | hr | 5 | 25.78 | 128.9 | 62
2012-02-13 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-02-16 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 62
2012-02-16 | Water / Tipper | Berry Excavations | hr | 6 | 100 | 600 | 62
2012-02-17 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-02-17 | Water / Tipper | Berry Excavations | hr | 5.5 | 100 | 550 | 62
2012-02-20 | Water / Tipper | Berry Excavations | hr | 5.5 | 100 | 550 | 62
2012-02-23 | Truck Hire | Micheal Biles | hr | 3 | 125 | 375 | 62
2012-02-23 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-02-28 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2012-02-28 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 62
2012-02-28 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-02-29 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 62
2012-02-29 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-02-29 | Dynapac CC21 Roller. Hired from the 31/01/12 - 29/02/12. Inv No - 276343 | Dynapac Roller |  | 1 | 5100 | 5100 | 62
2012-02-29 | Double Drum Roller, Plus Delivery. Hired from the 23/02/12 - 29/02/12. Inv No 276347 | Double Drum Roller |  | 1 | 889.91 | 889.91 | 62
2012-02-29 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-02-29 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-03-02 | Water Truck | Berry Excavations | hr | 9 | 100 | 900 | 62
2012-03-02 | Grader | Humphries Pty Ltd | hr | 6 | 100 | 600 | 62
2012-03-03 | Grader Hire | Humphries Pty Ltd | hr | 6.5 | 100 | 650 | 62
2012-03-03 | Water Truck Hire | Berry Excavations | hr | 7 | 100 | 700 | 62
2012-03-03 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2 | 95 | 190 | 62
2012-03-03 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-03-05 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 62
2012-03-05 | Grader Hire | Humphries Pty Ltd | hr | 8.5 | 100 | 850 | 62
2012-03-05 | Water Truck Hire | Berry Excavations | hr | 10 | 100 | 1000 | 62
2012-03-05 | Truck & Trailor Hire | Humphries Pty Ltd | hr | 5.5 | 102.73 | 565.015 | 62
2012-03-05 | Taylors Earthmoving (3t Excavator ) | Taylors Earthmoving | hr | 9.5 | 85 | 807.5 | 62
2012-03-05 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2012-03-05 | Twin Steer Hire | Humphries Pty Ltd | hr | 5 | 92.73 | 463.65 | 62
2012-03-05 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 62
2012-03-06 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2012-03-06 | Taylors Earthmoving ( 3t Excavator ) | Taylors Earthmoving | hr | 1.5 | 85 | 127.5 | 62
2012-03-06 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2012-03-06 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2012-03-06 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 62
2012-03-06 | Water Truck Hire | Berry Excavations | hr | 10 | 100 | 1000 | 62
2012-03-06 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 62
2012-03-06 | Grader | Humphries Pty Ltd | hr | 6.5 | 100 | 650 | 62
2012-03-07 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 62
2012-03-07 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 62
2012-03-07 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 62
2012-03-08 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 62
2012-03-08 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 62
2012-03-08 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 62
2012-03-08 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 62
2012-03-09 | Truck & Dot Hire | Humphries Pty Ltd | hr | 6.5 | 102.73 | 667.745 | 62
2012-03-09 | Truck & Dog Hire | Humphries Pty Ltd | hr | 6.5 | 102.73 | 667.745 | 62
2012-03-09 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2012-03-09 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2012-03-09 | Grader Hire | Humphries Pty Ltd | hr | 10 | 100 | 1000 | 62
2012-03-09 | Twin Steer Hire | Humphries Pty Ltd | hr | 6.5 | 92.73 | 602.745 | 62
2012-03-10 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2012-03-10 | Water Truck Hire | Berry Excavations | hr | 6 | 100 | 600 | 62
2012-03-10 | Grader Hire | Humphries Pty Ltd | hr | 2.5 | 100 | 250 | 62
2012-03-12 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-03-12 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-03-12 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-03-13 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2012-03-13 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2012-03-14 | Humpries Twin Steer Hire | Humphries Pty Ltd | hr | 2 | 92.73 | 185.46 | 62
2012-03-14 | Humpries Truck & Dog Hire | Humphries Pty Ltd | hr | 2 | 102.73 | 205.46 | 62
2012-03-14 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-03-14 | Humphries Grader Hire | Humphries Pty Ltd | hr | 2.5 | 100 | 250 | 62
2012-03-14 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-03-14 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-03-14 | Humpries Truck Hire | Humphries Pty Ltd | hr | 2 | 82.725 | 165.45 | 62
2012-03-14 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-03-15 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 62
2012-03-15 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 62
2012-03-15 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 62
2012-03-16 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 62
2012-03-16 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 62
2012-03-16 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 62
2012-03-19 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 62
2012-03-19 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 62
2012-03-19 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 62
2012-03-23 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-03-28 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-03-28 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-03-28 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 62
2012-03-28 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-03-30 | Hired from the 29/2/2012 to the 31/3/2012. Inv No - 279426 | Dynapac CC21 Roller |  | 1 | 5700 | 5700 | 62
2012-03-30 | Grader Hire | Humphries Pty Ltd | hr | 9.5 | 100 | 950 | 62
2012-03-30 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2012-03-30 | Water Truck | Berry Excavations | hr | 3 | 100 | 300 | 62
2012-03-30 | Double Drum Roller. Hired from the 29/2/2012 to the 31/3/2012. Inv No - 279430 | Double Drum Roller |  | 1 | 4693 | 4693 | 62
2012-03-30 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2012-03-30 | Twin Steer Hire | Humphries Pty Ltd | hr | 7 | 92.73 | 649.11 | 62
2012-03-30 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 7.5 | 90 | 675 | 62
2012-03-30 | Twin Stee Hire | Humphries Pty Ltd | hr | 6.5 | 92.73 | 602.745 | 62
2012-04-02 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 62
2012-04-02 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 62
2012-04-02 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 62
2012-04-02 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 62
2012-04-03 | Twin Steer Truck Hire | Humphries Pty Ltd | hr | 4 | 92.73 | 370.92 | 62
2012-04-03 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2012-04-03 | Twin Steer Truck Hire | Humphries Pty Ltd | hr | 4 | 92.73 | 370.92 | 62
2012-04-03 | Grader Hire | Humphries Pty Ltd | hr | 6 | 100 | 600 | 62
2012-04-03 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 62
2012-04-04 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 62
2012-04-04 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 62
2012-04-04 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3.5 | 90 | 315 | 62
2012-04-04 | Twin Steer Truck Hire | Humphries Pty Ltd | hr | 11 | 92.73 | 1020.03 | 62
2012-04-04 | Twin Steer Truck Hire | Humphries Pty Ltd | hr | 5.5 | 92.73 | 510.015 | 62
2012-04-04 | Grader Hire | Humphries Pty Ltd | hr | 8 | 100 | 800 | 62
2012-04-04 | Water Truck | Berry Excavations | hr | 5 | 100 | 500 | 62
2012-04-04 | Hired from the 31/3/12 to the 4/4/2012. Inv No - 280613 | Double Drum Roller |  | 1 | 553.28 | 553.28 | 62
2012-04-04 | Truck & Dog Hire | Ace One Truck Hire | hr | 8 | 145 | 1160 | 62
2012-04-04 | Water Truck | Berry Excavations | hr | 2 | 100 | 200 | 62
2012-04-05 | Vibrating Rammer ( Flexi Hire ) . Hired from the 31/3/2012 to the 5/4/2012. Inv No - 280840 | Vibrating Rammer |  | 1 | 358.4 | 358.4 | 62
2012-04-10 | Grader Hire | Humphries Pty Ltd | hr | 5 | 100 | 500 | 62
2012-04-10 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3.5 | 90 | 315 | 62
2012-04-10 | Water Truck Hire | Berry Excavations | hr | 3 | 100 | 300 | 62
2012-04-10 | (10 M Tipper ) | Pollard Earthmoving | hr | 3 | 95 | 285 | 62
2012-04-10 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3.5 | 95 | 332.5 | 62
2012-04-11 | Truck & Trailer Hire | Pollard Earthmoving | hr | 4.5 | 140 | 630 | 62
2012-04-11 | Grader Hire | Humphries Pty Ltd | hr | 9.5 | 100 | 950 | 62
2012-04-11 | Truck & Dog Hire | J & S Truck Hire |  | 6.5 | 150 | 975 | 62
2012-04-11 | Truck & Dog Hire | Ace One Truck Hire | hr | 6.5 | 145 | 942.5 | 62
2012-04-11 | Excavator ( 5t ) | Berry Excavations | hr | 8.5 | 100 | 850 | 62
2012-04-11 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2.5 | 90 | 225 | 62
2012-04-11 | Water Truck Hire | Berry Excavations | hr | 5 | 100 | 500 | 62
2012-04-11 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2012-04-11 | Truck & Dog Hire | Talbots | hr | 5 | 130 | 650 | 62
2012-04-12 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 62
2012-04-12 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-04-12 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-04-12 | Water Truck Hire | Berry Excavations | hr | 5 | 100 | 500 | 62
2012-04-12 | Grader Hire | Humphries Pty Ltd | hr | 4.5 | 100 | 450 | 62
2012-04-12 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2.5 | 90 | 225 | 62
2012-04-12 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2 | 95 | 190 | 62
2012-04-12 | (10 M Tipper ) | Pollard Earthmoving | hr | 2.5 | 95 | 237.5 | 62
2012-04-13 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-04-13 | Grader Hire | Humphries Pty Ltd | hr | 6.5 | 100 | 650 | 62
2012-04-13 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-04-13 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2.5 | 95 | 237.5 | 62
2012-04-13 | (10 M Tipper ) | Pollard Earthmoving | hr | 2.5 | 95 | 237.5 | 62
2012-04-13 | Truck & Dog Hire | Talbots | hr | 4 | 130 | 520 | 62
2012-04-13 | Truck & Dog Hire | Ace One Truck Hire | hr | 4 | 145 | 580 | 62
2012-04-13 | Truck & Dog Hire | J & S Truck Hire |  | 4 | 150 | 600 | 62
2012-04-13 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2.5 | 90 | 225 | 62
2012-04-13 | Water Truck Hire | Berry Excavations | hr | 5.5 | 100 | 550 | 62
2012-04-14 | Twin Steer Hire | Humphries Pty Ltd | hr | 5.5 | 92.73 | 510.015 | 62
2012-04-14 | Grader Hire | Humphries Pty Ltd | hr | 6.5 | 100 | 650 | 62
2012-04-14 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2.5 | 90 | 225 | 62
2012-04-14 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-04-14 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-04-14 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-04-14 | Twin Steer Hire | Humphries Pty Ltd | hr | 4 | 92.73 | 370.92 | 62
2012-04-14 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-04-16 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-04-16 | Labour Hire | Labour | hr | 4 | 48 | 192 | 62
2012-04-16 | Truck & Dog Hire | Ace One Truck Hire | hr | 2.5 | 145 | 362.5 | 62
2012-04-16 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 62
2012-04-16 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-04-16 | Grader Hire | Humphries Pty Ltd | hr | 9 | 100 | 900 | 62
2012-04-18 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-04-18 | Grader Hire | Humphries Pty Ltd | hr | 5.5 | 100 | 550 | 62
2012-04-18 | Labour Hire | Labour | hr | 6 | 48 | 288 | 62
2012-04-18 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-04-18 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 62
2012-04-18 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-04-18 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-04-19 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 62
2012-04-19 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2012-04-19 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4.5 | 90 | 405 | 62
2012-04-19 | Labour Hire | Labour | hr | 5 | 48 | 240 | 62
2012-04-19 | Grader Hire | Humphries Pty Ltd | hr | 5 | 100 | 500 | 62
2012-04-19 | Water Truck Hire | Talbots | hr | 5 | 95 | 475 | 62
2012-04-19 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 62
2012-04-19 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2012-04-20 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2012-04-20 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2012-04-20 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2012-04-20 | Grader Hire | Humphries Pty Ltd | hr | 7 | 100 | 700 | 62
2012-04-20 | Water Truck Hire | Talbots | hr | 8 | 95 | 760 | 62
2012-04-20 | Twin Steer | Humphries Pty Ltd | hr | 4 | 92.73 | 370.92 | 62
2012-04-20 | Labour Hire | Labour | hr | 6 | 48 | 288 | 62
2012-04-20 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2012-04-23 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2012-04-23 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 4 | 130 | 520 | 62
2012-04-23 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-04-23 | Labour Hire | Labour | hr | 3.5 | 48 | 168 | 62
2012-04-23 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-04-23 | Side Tipper | Steve Banks | hr | 2.5 | 150 | 375 | 62
2012-04-23 | Water Truck Hire | Talbots | hr | 5 | 95 | 475 | 62
2012-04-23 | Grader Hire | Humphries Pty Ltd | hr | 7 | 100 | 700 | 62
2012-04-23 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 62
2012-04-23 | Side Tipper | Steve Banks | hr | 2.5 | 150 | 375 | 62
2012-04-24 | Water Truck Hire | Talbots | hr | 2 | 95 | 190 | 62
2012-04-24 | New Holland Compact Grader - No Operator | NH Grader | hr | 2 | 25.78 | 51.56 | 62
2012-04-24 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 62
2012-04-26 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2012-04-26 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-04-26 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 62
2012-04-26 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 62
2012-04-26 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 62
2012-04-26 | Water Truck Hire | Talbots | hr | 3 | 95 | 285 | 62
2012-04-26 | New Holland Compact Grader - No Operator | NH Grader | hr | 2 | 25.78 | 51.56 | 62
2012-04-26 | New Holland Compact Grader - No Operator | NH Grader | hr | 5 | 25.78 | 128.9 | 62
2012-04-26 | Labour Hire | Labour | hr | 7 | 48 | 336 | 62
2012-04-26 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2012-04-30 | Dynapac CC 21 Roller. Hired from the 31/3/2012 - 30/4/2012. Inv No - 283186 | Dynapac CC21 Roller |  | 1 | 3150 | 3150 | 62
2012-04-30 | Vibrating Rammer ( Flexi Hire ). Hired on the 19/4/2012 - 30/4/2012. Inv No - 283192 | Vibrating Rammer |  | 1 | 716.8 | 716.8 | 62
2012-05-01 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-05-01 | Vibrating Rammer ( Flexi Hire ) Hired from the 30/4/2012 - 1/5/2012. Inv No - 284071 | Vibrating Rammer |  | 1 | 71.68 | 71.68 | 62
2012-05-01 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-05-01 | Water Truck Hire | Talbots | hr | 5.5 | 95 | 522.5 | 62
2012-05-01 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 62
2012-05-02 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9.5 | 130 | 1235 | 62
2012-05-02 | Water Truck Hire | Talbots | hr | 11 | 95 | 1045 | 62
2012-05-03 | Grader Hire | Humphries Pty Ltd | hr | 9 | 100 | 900 | 62
2012-05-03 | Water Truck Hire | Talbots | hr | 5.5 | 95 | 522.5 | 62
2012-05-11 | Twin Steer Hire | Humphries Pty Ltd | hr | 8.75 | 92.73 | 811.3875 | 62
2012-05-11 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2012-05-11 | Labour Hire | Labour | hr | 9.5 | 48 | 456 | 62
2012-05-11 | Grader Hire | Humphries Pty Ltd | hr | 9 | 100 | 900 | 62
2012-05-11 | Twin Steer Hire | Humphries Pty Ltd | hr | 8.75 | 92.73 | 811.3875 | 62
2012-05-11 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 9 | 90 | 810 | 62
2012-05-11 | (Water Truck ) | Talbots | hr | 10 | 95 | 950 | 62
2012-05-11 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2012-05-12 | Vibrating Rammer ( Flexi Hire ) . Hired from the 11/5/2012 - 12/5/2012. Inv No - 285035 | Vibrating Rammer |  | 1 | 84.71 | 84.71 | 62
2012-05-14 | (Water Truck ) | Talbots | hr | 10 | 95 | 950 | 62
2012-05-14 | Labour Hire | Labour | hr | 3.5 | 48 | 168 | 62
2012-05-14 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 62
2012-05-15 | (Water Truck ) | Talbots | hr | 9.5 | 95 | 902.5 | 62
2012-05-16 | (Water Truck ) | Talbots | hr | 9.5 | 95 | 902.5 | 62
2012-05-17 | New Holland Compact Grader - No Operator | NH Grader | hr | 2 | 25.78 | 51.56 | 62
2012-05-17 | Labour Hire | Labour | hr | 2 | 48 | 96 | 62
2012-05-17 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2.5 | 90 | 225 | 62
2012-05-17 | (Water Truck ) | Talbots | hr | 9.5 | 95 | 902.5 | 62
2012-05-18 | Earthmoving & Water Cart | Talbots | hr | 4 | 95 | 380 | 62
2012-05-18 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-05-18 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-05-18 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-05-18 | New Holland Compact Grader - No Operator | NH Grader | hr | 2 | 25.78 | 51.56 | 62
2012-05-18 | Twin Steer Hire | Humphries Pty Ltd | hr | 11.25 | 92.73 | 1043.2125 | 62
2012-05-18 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-05-18 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 62
2012-05-18 | Labour Hire | Labour | hr | 3 | 48 | 144 | 62
2012-05-18 | Twin Steer Hire | Humphries Pty Ltd | hr | 11.5 | 92.73 | 1066.395 | 62
2012-05-19 | (Water Truck ) | Talbots | hr | 7.5 | 95 | 712.5 | 62
2012-05-19 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 62
2012-05-19 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 62
2012-05-19 | (10 M Tipper ) | Pollard Earthmoving | hr | 2 | 95 |  | 62
2012-05-21 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2012-05-21 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2012-05-21 | (Water Truck ) | Talbots | hr | 10 | 95 | 950 | 62
2012-05-21 | Truck & Dog Hire | Humphries Pty Ltd | hr | 4.5 | 102.73 | 462.285 | 62
2012-05-21 | Grader Hire | Humphries Pty Ltd | hr | 8 | 100 | 800 | 62
2012-05-21 | Truck & Dog Hire | Humphries Pty Ltd | hr | 5 | 113.19 | 565.95 | 62
2012-05-21 | Twin Steer Truck Hire | Humphries Pty Ltd | hr | 3 | 92.73 | 278.19 | 62
2012-05-21 | Twin Steer Truck Hire | Humphries Pty Ltd | hr | 4 | 92.73 | 370.92 | 62
2012-05-21 | Float | Humphries Pty Ltd | hr | 1 | 125 | 125 | 62
2012-05-22 | Truck & Dog Hire | Humphries Pty Ltd | hr | 2 | 102.73 | 205.46 | 62
2012-05-22 | Twin Steer Truck Hire | Humphries Pty Ltd | hr | 5.5 | 92.73 | 510.015 | 62
2012-05-22 | Labour Hire | Labour | hr | 9.5 | 48 | 456 | 62
2012-05-22 | Twin Steer Truck Hire | Humphries Pty Ltd | hr | 5.25 | 92.73 | 486.8325 | 62
2012-05-22 | (Water Truck ) | Talbots | hr | 10.5 | 95 | 997.5 | 62
2012-05-22 | Twin Steer Truck Hire | Humphries Pty Ltd | hr | 1.75 | 92.73 | 162.2775 | 62
2012-05-22 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2012-05-22 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2012-05-22 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 62
2012-05-22 | Grader Hire | Humphries Pty Ltd | hr | 9 | 100 | 900 | 62
2012-05-23 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2012-05-23 | Twin Steer Truck Hire | Humphries Pty Ltd | hr | 8.25 | 92.73 | 765.0225 | 62
2012-05-23 | Grader Hire | Humphries Pty Ltd | hr | 9 | 100 | 900 | 62
2012-05-23 | Labour Hire | Labour | hr | 9.5 | 48 | 456 | 62
2012-05-23 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 6 | 90 | 540 | 62
2012-05-23 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2012-05-23 | (Water Truck ) | Talbots | hr | 10 | 95 | 950 | 62
2012-05-24 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2012-05-24 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2012-05-24 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2012-05-24 | New Holland Compact Grader - No Operator | NH Grader | hr | 2 | 25.78 | 51.56 | 62
2012-05-24 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 62
2012-05-24 | Labour Hire | Labour | hr | 6 | 48 | 288 | 62
2012-05-24 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 3 | 130 | 390 | 62
2012-05-24 | (Water Truck ) | Talbots | hr | 4 | 95 | 380 | 62
2012-05-24 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2012-05-24 | Twin Steer Truck Hire | Humphries Pty Ltd | hr | 2.25 | 92.73 | 208.6425 | 62
2012-05-24 | Twin Steer Truck Hire | Humphries Pty Ltd | hr | 2.25 | 92.73 | 208.6425 | 62
2012-05-29 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 62
2012-05-29 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-05-29 | New Holland Compact Grader - No Operator | NH Grader | hr | 2.5 | 25.78 | 64.45 | 62
2012-05-29 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 7 | 130 | 910 | 62
2012-05-29 | Labour Hire | Labour | hr | 3 | 48 | 144 | 62
2012-05-29 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 6.5 | 95 | 617.5 | 62
2012-05-29 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 62
2012-05-29 | Earthmoving & Water Cart | Talbots | hr | 10.5 | 95 | 997.5 | 62
2012-05-29 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 62
2012-05-29 | Twin Steer | Humphries Pty Ltd | hr | 5.25 | 92.73 | 486.8325 | 62
2012-05-30 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-05-30 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-05-30 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 2.5 | 130 | 325 | 62
2012-05-30 | Labour Hire | Labour | hr | 7 | 48 | 336 | 62
2012-05-30 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-05-30 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 1 | 90 | 90 | 62
2012-05-30 | Grader Hire | Humphries Pty Ltd | hr | 6.5 | 100 | 650 | 62
2012-05-30 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3 | 95 | 285 | 62
2012-05-30 | Earthmoving & Water Cart | Talbots | hr | 10 | 95 | 950 | 62
2012-05-30 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 62
2012-06-02 | Labour Hire | Labour | hr | 4 | 48 | 192 | 62
2012-06-02 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-06-02 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-06-02 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 62
2012-06-04 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2 | 95 | 190 | 62
2012-06-05 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2 | 95 | 190 | 62
2012-06-05 | Earthmoving & Water Cart | Talbots | hr | 4 | 95 | 380 | 62
2012-06-06 | Grader Hire | Humphries Pty Ltd | hr | 6 | 100 | 600 | 62
2012-06-06 | Twin Steer | Humphries Pty Ltd | hr | 2.75 | 92.73 | 255.0075 | 62
2012-06-06 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2012-06-06 | Labour Hire | Labour | hr | 6.5 | 48 | 312 | 62
2012-06-06 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-06-06 | Earthmoving & Water Cart | Talbots | hr | 8.5 | 95 | 807.5 | 62
2012-06-06 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5 | 90 | 450 | 62
2012-06-07 | New Holland Compact Grader - No Operator | NH Grader | hr | 4 | 25.78 | 103.12 | 62
2012-06-07 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-06-07 | Grader Hire | Humphries Pty Ltd | hr | 6 | 100 | 600 | 62
2012-06-07 | Earthmoving & Water Cart | Talbots | hr | 5 | 95 | 475 | 62
2012-06-07 | Labour Hire | Labour | hr | 3 | 48 | 144 | 62
2012-06-08 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-06-08 | Earthmoving & Water Cart | Talbots | hr | 6 | 95 | 570 | 62
2012-06-12 | New Holland Compact Grader - No Operator | NH Grader | hr | 3 | 25.78 | 77.34 | 62
2012-06-12 | Truck Hire | Humphries Pty Ltd | hr | 5.5 | 82.727 | 454.9985 | 62
2012-06-12 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 62
2012-06-12 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 62
2012-06-12 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 62
2012-06-12 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 7 | 95 | 665 | 62
2012-06-12 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 7.5 | 130 | 975 | 62
2012-06-12 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 62
2012-06-12 | Earthmoving & Water Cart | Talbots | hr | 10 | 95 | 950 | 62
2012-06-13 | Earthmoving & Water Cart | Talbots | hr | 10.5 | 95 | 997.5 | 62
2012-06-14 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2012-06-14 | New Holland Compact Grader - No Operator | NH Grader | hr | 3 | 25.78 | 77.34 | 62
2012-06-14 | Labour Hire | Labour | hr | 1.5 | 48 | 72 | 62
2012-06-14 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2012-06-14 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2012-06-14 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 62
2012-06-14 | Earthmoving & Water Cart | Talbots | hr | 9.5 | 95 | 902.5 | 62
2012-06-14 | Truck Hire | Humphries Pty Ltd | hr | 5.5 | 82.727 | 454.9985 | 62
2012-06-14 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5.5 | 130 | 715 | 62
2012-06-14 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 62
2012-06-15 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 62
2012-06-15 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 2 | 130 | 260 | 62
2012-06-15 | Truck Hire | Humphries Pty Ltd | hr | 4 | 82.727 | 330.908 | 62
2012-06-15 | Earthmoving & Water Cart | Talbots | hr | 9 | 95 | 855 | 62
2012-06-15 | New Holland Compact Grader - No Operator | NH Grader | hr | 4 | 25.78 | 103.12 | 62
2012-06-15 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-06-15 | Labour Hire | Labour | hr | 4 | 48 | 192 | 62
2012-06-15 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-06-15 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-06-16 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 2 | 130 | 260 | 62
2012-06-16 | New Holland Compact Grader - No Operator | NH Grader | hr | 2 | 25.78 | 51.56 | 62
2012-06-16 | Earthmoving & Water Cart | Talbots | hr | 6 | 95 | 570 | 62
2012-06-16 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2 | 95 | 190 | 62
2012-06-16 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-06-16 | Labour Hire | Labour | hr | 5.5 | 48 | 264 | 62
2012-06-16 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-06-16 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4.5 | 90 | 405 | 62
2012-06-18 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 62
2012-06-18 | Labour Hire | Labour | hr | 3.5 | 48 | 168 | 62
2012-06-18 | Water Cart Hire | Talbots | hr | 9 | 95 | 855 | 62
2012-06-18 | Grader Hire | Humphries Pty Ltd | hr | 9 | 100 | 900 | 62
2012-06-19 | Tipper Hire | Humphries Pty Ltd | hr | 6 | 82.727 | 496.362 | 62
2012-06-19 | Tipper Hire | Humphries Pty Ltd | hr | 1.5 | 82.727 | 124.0905 | 62
2012-06-19 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 9 | 130 | 1170 | 62
2012-06-19 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 62
2012-06-19 | Labour Hire | Labour | hr | 7 | 48 | 336 | 62
2012-06-19 | Water Cart Hire | Talbots | hr | 9.5 | 95 | 902.5 | 62
2012-06-19 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5.5 | 95 | 522.5 | 62
2012-06-20 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-06-20 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2012-06-20 | Labour Hire | Labour | hr | 6.5 | 48 | 312 | 62
2012-06-20 | Water Truck Hire | Talbots | hr | 4.5 | 95 | 427.5 | 62
2012-06-20 | Grader Hire | Humphries Pty Ltd | hr | 9 | 100 | 900 | 62
2012-06-20 | Tipper Hire | Humphries Pty Ltd | hr | 6.5 | 82.727 | 537.7255 | 62
2012-06-20 | Tipper Hire | Humphries Pty Ltd | hr | 6.5 | 82.727 | 537.7255 | 62
2012-06-21 | Water Cart Hire | Talbots | hr | 5.5 | 95 | 522.5 | 62
2012-06-21 | Grader Hire | Humphries Pty Ltd | hr | 8 | 100 | 800 | 62
2012-06-25 | Earthmoving & Water Cart | Talbots | hr | 4 | 95 | 380 | 62
2012-06-28 | Earthmoving & Water Cart | Talbots | hr | 1.5 | 95 | 142.5 | 62
2012-06-29 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-06-29 | Earthmoving & Water Cart | Talbots | hr | 7.5 | 95 | 712.5 | 62
2012-06-29 | Vibrating Rammer ( Flexi Hire ) Hired 16/6/2012 - 29/6/2012. Inv No - 290647 | Vibrating Rammer |  | 1 | 837.2 | 837.2 | 62
2012-06-29 | Labour Hire | Labour | hr | 3 | 48 | 144 | 62
2012-06-29 | Grader Hire | Humphries Pty Ltd | hr | 6.5 | 100 | 650 | 62
2012-06-30 | Earthmoving & Water Cart | Talbots | hr | 2.5 | 95 | 237.5 | 62
2012-06-30 | Dynapac CC 21 Roller. Hired 31/5/2012 - 30/6/2012. Inv No - 291189 | Dynapac CC21 Roller |  | 1 | 3300 | 3300 | 62
2012-07-02 | Earthmoving & Water Cart | Talbots | hr | 7.5 | 95 | 712.5 | 62
2012-07-03 | Labour Hire | Labour | hr | 9.5 | 48 | 456 | 62
2012-07-03 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2012-07-03 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2012-07-03 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8 | 95 | 760 | 62
2012-07-03 | Tipper Hire | Humphries Pty Ltd | hr | 7 | 87.27 | 610.89 | 62
2012-07-03 | Earthmoving & Water Cart | Talbots | hr | 9 | 95 | 855 | 62
2012-07-03 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 2 | 110 | 220 | 62
2012-07-03 | Tipper Hire | Humphries Pty Ltd | hr | 6 | 87.27 | 523.62 | 62
2012-07-03 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9 | 95 | 855 | 62
2012-07-03 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8 | 95 | 760 | 62
2012-07-03 | Grader Hire | Humphries Pty Ltd | hr | 9 | 100 | 900 | 62
2012-07-04 | Earthmoving & Water Cart | Talbots | hr | 9 | 95 | 855 | 62
2012-07-05 | Earthmoving & Water Cart | Talbots | hr | 5.5 | 95 | 522.5 | 62
2012-07-06 | Earthmoving & Water Cart | Talbots | hr | 6.5 | 95 | 617.5 | 62
2012-07-11 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-07-11 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-07-11 | Labour Hire | Labour | hr | 2.5 | 48 | 120 | 62
2012-07-11 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 62
2012-07-11 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 62
2012-07-11 | Labour Hire ( Achieve Group ) | Labour | hr | 2 | 34.81 | 69.62 | 62
2012-07-13 | New Holland Compact Grader - No Operator | NH Grader | hr | 2.5 | 25.78 | 64.45 | 62
2012-07-13 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-07-13 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-07-13 | Labour Hire | Labour | hr | 3 | 48 | 144 | 62
2012-07-16 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 62
2012-07-16 | New Holland Compact Grader - No Operator | NH Grader | hr | 1.5 | 25.78 | 38.67 | 62
2012-07-17 | Earthmoving & Water Cart | Talbots | hr | 5 | 95 | 475 | 62
2012-07-27 | Allans Earthmoving (Tipper Hire) | Allans Earthmoving | hr | 6 | 95 | 570 | 62
2012-07-27 | Labour Hire | Labour | hr | 10 | 48 | 480 | 62
2012-07-27 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 6 | 95 | 570 | 62
2012-07-27 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2012-07-27 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2012-07-27 | Earthmoving & Water Cart | Talbots | hr | 4.75 | 95 | 451.25 | 62
2012-07-28 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-07-28 | Earthmoving & Water Cart | Talbots | hr | 7.25 | 95 | 688.75 | 62
2012-07-28 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 7 | 95 | 665 | 62
2012-07-28 | Labour Hire | Labour | hr | 8 | 48 | 384 | 62
2012-07-30 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 62
2012-07-30 | Earthmoving & Water Cart | Talbots | hr | 10 | 95 | 950 | 62
2012-07-30 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5.5 | 95 | 522.5 | 62
2012-07-30 | Allans Earthmoving (Tipper Hire) | Allans Earthmoving | hr | 5.5 | 95 | 522.5 | 62
2012-07-30 | Labour Hire | Labour | hr | 9.5 | 48 | 456 | 62
2012-07-31 | Concrtetor Hire | Labour | hr | 9.5 | 45 | 427.5 | 62
2012-07-31 | Labour Hire | Labour | hr | 10.5 | 48 | 504 | 62
2012-07-31 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5 | 95 | 475 | 62
2012-07-31 | Pad Foot Roller - Dry Hired 7/7/12 - 31/7/12. Inv No - 295263 | PF Roller |  | 6 | 325 | 1950 | 62
2012-07-31 | Double Drum Roller. Inv No - 295261 | Double Drum Roller |  | 9 | 247 | 2223 | 62
2012-07-31 | Allans Earthmoving (Tipper Hire) | Allans Earthmoving | hr | 5 | 95 | 475 | 62
2012-07-31 | Earthmoving & Water Cart | Talbots | hr | 9 | 95 | 855 | 62
2012-07-31 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5.75 | 110 | 632.5 | 62
2012-07-31 | Dynapac CC 21 Roller. Hired 30/6/12 - 31/7/12. Inv No - 295257 | Dynapac CC21 Roller |  | 17 | 300 | 5100 | 62
2012-07-31 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2012-08-01 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 | 365 | 62
2012-08-02 | Earthmoving & Water Cart | Talbots | hr | 5 | 95 | 475 | 62
2012-08-02 | 11 T Excavator Hire | Watts Excavations | hr | 6.5 | 110 | 715 | 62
2012-08-02 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 | 365 | 62
2012-08-02 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 7 | 95 | 665 | 62
2012-08-02 | Labour Hire | Labour | hr | 7 | 48 | 336 | 62
2012-08-02 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 62
2012-08-02 | (10 M Tipper ) | Pollard Earthmoving | hr | 7 | 95 | 665 | 62
2012-08-02 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5 | 110 | 550 | 62
2012-08-03 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 | 365 | 62
2012-08-03 | Grader Hire | Humphries Pty Ltd | hr | 9.5 | 100 | 950 | 62
2012-08-03 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-08-03 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-08-03 | (10 M Tipper ) | Pollard Earthmoving | hr | 5 | 95 | 475 | 62
2012-08-03 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.5 | 110 | 495 | 62
2012-08-03 | T Excavator Hire | Watts Excavations | hr | 4.5 | 110 | 495 | 62
2012-08-03 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2012-08-03 | Labour Hire | Labour | hr | 7 | 48 | 336 | 62
2012-08-03 | Earthmoving & Water Cart | Talbots | hr | 6.5 | 95 | 617.5 | 62
2012-08-04 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 62
2012-08-04 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 | 365 | 62
2012-08-04 | Labour Hire | Labour | hr | 7 | 48 | 336 | 62
2012-08-04 | Grader Hire | Humphries Pty Ltd | hr | 6 | 100 | 600 | 62
2012-08-04 | Earthmoving & Water Cart | Talbots | hr | 3.5 | 95 | 332.5 | 62
2012-08-04 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 62
2012-08-04 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2012-08-04 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4 | 110 | 440 | 62
2012-08-04 | (10 M Tipper ) | Pollard Earthmoving | hr | 2.5 | 95 | 237.5 | 62
2012-08-06 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4.5 | 95 | 427.5 | 62
2012-08-06 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 62
2012-08-06 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5 | 110 | 550 | 62
2012-08-06 | Grader Hire | Humphries Pty Ltd | hr | 6.5 | 100 | 650 | 62
2012-08-06 | Earthmoving & Water Cart | Talbots | hr | 10.5 | 95 | 997.5 | 62
2012-08-06 | Labour Hire | Labour | hr | 7 | 48 | 336 | 62
2012-08-06 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 62
2012-08-06 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 62
2012-08-06 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 62
2012-08-06 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-08-07 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5 | 110 | 550 | 62
2012-08-07 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 62
2012-08-07 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 62
2012-08-07 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 62
2012-08-07 | Grader Hire | Humphries Pty Ltd | hr | 4 | 100 | 400 | 62
2012-08-07 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 62
2012-08-07 | Earthmoving & Water Cart | Talbots | hr | 5 | 95 | 475 | 62
2012-08-07 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 62
2012-08-07 | Labour Hire | Labour | hr | 3 | 48 | 144 | 62
2012-08-08 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2 | 95 | 190 | 62
2012-08-08 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5 | 110 | 550 | 62
2012-08-08 | (10 M Tipper ) | Pollard Earthmoving | hr | 2 | 95 | 190 | 62
2012-08-08 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 62
2012-08-08 | Grader Hire | Humphries Pty Ltd | hr | 2 | 100 | 200 | 62
2012-08-08 | Labour Hire | Labour | hr | 2.5 | 48 | 120 | 62
2012-08-08 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 62
2012-08-08 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 62
2012-08-08 | Earthmoving & Water Cart | Talbots | hr | 2 | 95 | 190 | 62
2012-08-09 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3 | 110 | 330 | 62
2012-08-09 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2.5 | 95 | 237.5 | 62
2012-08-09 | Earthmoving & Water Cart | Talbots | hr | 2 | 95 | 190 | 62
2012-08-10 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 7 | 110 | 770 | 62
2012-08-10 | Earthmoving & Water Cart | Talbots | hr | 5 | 95 | 475 | 62
2012-08-10 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 62
2012-08-10 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 62
2012-08-10 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2012-08-11 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4 | 110 | 440 | 62
2012-08-11 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 62
2012-08-11 | Earthmoving & Water Cart | Talbots | hr | 7.5 | 95 | 712.5 | 62
2012-08-13 | Earthmoving & Water Cart | Talbots | hr | 5.5 | 95 | 522.5 | 62
2012-08-13 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 | 365 | 62
2012-08-13 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 1 | 95 | 95 | 62
2012-08-13 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 1 | 130 | 130 | 62
2012-08-13 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 62
2012-08-13 | (10 M Tipper ) | Pollard Earthmoving | hr | 1.5 | 95 | 142.5 | 62
2012-08-13 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 1.5 | 110 | 165 | 62
2012-08-14 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 | 365 | 62
2012-08-14 | Earthmoving & Water Cart | Talbots | hr | 5.5 | 95 | 522.5 | 62
2012-08-15 | Earthmoving & Water Cart | Talbots | hr | 5.5 | 95 | 522.5 | 62
2012-08-15 | Vibrating Rammer ( Flexi Hire ).Hired 7/8/12 - 15/8/12. Inv No - 297270 | Vibrating Rammer |  | 1 | 407.2 | 407.2 | 62
2012-08-15 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 | 365 | 62
2012-08-16 | Earthmoving & Water Cart | Talbots | hr | 5 | 95 | 475 | 62
2012-08-17 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-08-17 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 9 | 135 | 1215 | 62
2012-08-17 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-08-17 | Operator-Labour | Labour | hr | 7.5 | 48 | 360 | 62
2012-08-17 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 62
2012-08-17 | Truck & Dog Hire | Humphries Pty Ltd | hr | 6 | 125.45 | 752.7 | 62
2012-08-17 | Truck Hire | Humphries Pty Ltd | hr | 5.5 | 87.272 | 479.996 | 62
2012-08-17 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.25 | 110 | 467.5 | 62
2012-08-17 | Earthmoving & Water Cart | Talbots | hr | 9.5 | 95 | 902.5 | 62
2012-08-18 | Earthmoving & Water Cart | Talbots | hr | 5.5 | 95 | 522.5 | 62
2012-08-19 | Earthmoving & Water Cart | Talbots | hr | 5 | 95 | 475 | 62
2012-08-20 | Earthmoving & Water Cart | Talbots | hr | 4 | 95 | 380 | 62
2012-08-20 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2012-08-20 | Plant Operator-Labour Hire | Labour | hr | 3 | 48 | 144 | 62
2012-08-20 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2012-08-20 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5 | 110 | 550 | 62
2012-08-20 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 62
2012-08-21 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 6.5 | 130 | 845 | 62
2012-08-21 | Earthmoving Hire | Banks Earthmoving | hr | 5.25 | 150 | 787.5 | 62
2012-08-21 | Earthmoving & Water Cart | Talbots | hr | 7.5 | 95 | 712.5 | 62
2012-08-21 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 5 | 135 | 675 | 62
2012-08-21 | Plant Operator-Labour Hire | Labour | hr | 5 | 48 | 240 | 62
2012-08-21 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2012-08-22 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-08-22 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-08-22 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.5 | 110 | 495 | 62
2012-08-22 | Earthmoving & Water Cart Semi Tipper Hire | Talbots | hr | 5.5 | 130 | 715 | 62
2012-08-22 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2 | 95 | 190 | 62
2012-08-22 | (10 M Tipper ) | Pollard Earthmoving | hr | 2.5 | 95 | 237.5 | 62
2012-08-23 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 3 | 135 | 405 | 62
2012-08-23 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-08-23 | Earthmiving & Water Cart | Talbots | hr | 9.5 | 95 | 902.5 | 62
2012-08-23 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3.75 | 110 | 412.5 | 62
2012-08-23 | (10 M Tipper ) | Pollard Earthmoving | hr | 3 | 95 | 285 | 62
2012-08-23 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2.5 | 95 | 237.5 | 62
2012-08-23 | Plant Operator-Labour Hire | Labour | hr | 3.5 | 48 | 168 | 62
2012-08-23 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 62
2012-08-23 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-08-24 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-08-24 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 2 | 110 | 220 | 62
2012-08-24 | Earthmoving & Water Cart | Talbots | hr | 3.5 | 95 | 332.5 | 62
2012-08-24 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-08-24 | Plant Operator-Labour Hire | Labour | hr | 2 | 48 | 96 | 62
2012-08-24 | S/D Roller - 13T - Dry Hire ( Flexi Hire ) Hired 30/6/2012 - 16/7/2012. Inv No 293883 | SD Roller -13T |  | 11 | 300 | 3300 | 62
2012-08-24 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-08-24 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-08-27 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 6 | 135 | 810 | 62
2012-08-27 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-08-27 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-08-27 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3 | 110 | 330 | 62
2012-08-27 | N K Jepsen Tipper Hire | N K Jepsen Tipper Hire | hr | 7 | 130 | 910 | 62
2012-08-27 | Semi Tipper Hire | Humphries Pty Ltd | hr | 5.5 | 107.27 | 589.985 | 62
2012-08-27 | Earthmoving & Water Cart | Talbots | hr | 7 | 95 | 665 | 62
2012-08-28 | New Holland Compact Grader - No Operator | NH Grader | hr | 3 | 25.78 | 77.34 | 62
2012-08-28 | Earthmoving & Water Cart | Talbots | hr | 5.5 | 95 | 522.5 | 62
2012-08-28 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 62
2012-08-28 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 4.5 | 135 | 607.5 | 62
2012-08-28 | Truck & Dog Hire | Micheal Biles | hr | 8.5 | 125 | 1062.5 | 62
2012-08-29 | Earthmoving & Water Cart | Talbots | hr | 5.5 | 95 | 522.5 | 62
2012-08-30 | Pad Foot Roller - Dry. Hired 31/7/12 - 24/8/12. Inv No - 298887 | PF Roller |  | 1 | 2166.666 | 2166.666 | 62
2012-08-30 | Earthmoving & Water Cart | Talbots | hr | 6 | 95 | 570 | 62
2012-08-30 | (10 M Tipper ) | Pollard Earthmoving | hr | 2 | 95 | 190 | 62
2012-08-31 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 5 | 135 | 675 | 62
2012-08-31 | Dynapac CC 21 Roller. Hired 31/7/12 - 31/8/12. Inv No - 299458 | Dynapac CC21 Roller |  | 26 | 300 | 7800 | 62
2012-08-31 | Double Drum Roller. Hired 31/7/12 - 31/8/12. Inv No - 299459 | Double Drum Roller |  | 26 | 247 | 6422 | 62
2012-08-31 | Earthmoving & Water Cart | Talbots | hr | 6.5 | 95 | 617.5 | 62
2012-09-01 | Plant Operator-Labour Hire | Labour | hr | 7 | 48 | 336 | 62
2012-09-01 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2012-09-01 | Earthmoving & Water Cart | Talbots | hr | 7 | 95 | 665 | 62
2012-09-01 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 5 | 135 | 675 | 62
2012-09-03 | Earthmoving & Water Cart | Talbots | hr | 5 | 95 | 475 | 62
2012-09-04 | Plant Operator-Labour Hire | Labour | hr | 2.5 | 48 | 120 | 62
2012-09-04 | Earthmoving & Water Cart | Talbots | hr | 8.5 | 95 | 807.5 | 62
2012-09-04 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 62
2012-09-04 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 2 | 110 | 220 | 62
2012-09-05 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2012-09-05 | Plant Operator-Labour Hire | Labour | hr | 10 | 48 | 480 | 62
2012-09-05 | Earthmoving & Water Cart | Talbots | hr | 10.5 | 95 | 997.5 | 62
2012-09-05 | Truck & Dog Hire | Micheal Biles | hr | 4.5 | 125 | 562.5 | 62
2012-09-05 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4 | 110 | 440 | 62
2012-09-05 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2012-09-05 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-09-06 | Earthmoving & Water Cart | Talbots | hr | 10.5 | 95 | 997.5 | 62
2012-09-07 | Earthmoving & Water Cart | Talbots | hr | 6 | 95 | 570 | 62
2012-09-10 | Earthmoving & Water Cart | Talbots | hr | 8 | 95 | 760 | 62
2012-09-11 | Micheal Biles. ( 10m Tipper ) | Micheal Biles | hr | 9.5 | 95 | 902.5 | 62
2012-09-11 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 9.75 | 110 | 1072.5 | 62
2012-09-11 | Earthmoving & Water Cart | Talbots | hr | 10 | 95 | 950 | 62
2012-09-12 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 9 | 66.07 | 594.63 | 62
2012-09-12 | Earthmoving & Water Cart | Talbots | hr | 10 | 95 | 950 | 62
2012-09-12 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-09-12 | Plant Operator-Labour Hire | Labour | hr | 6 | 48 | 288 | 62
2012-09-12 | New Holland Compact Grader - No Operator | NH Grader | hr | 5 | 25.78 | 128.9 | 62
2012-09-12 | Micheal Biles. ( 10m Tipper ) | Micheal Biles | hr | 10 | 95 | 950 | 62
2012-09-12 | (10 M Tipper ) | Pollard Earthmoving | hr | 1 | 95 | 95 | 62
2012-09-12 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 3 | 95 | 285 | 62
2012-09-12 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 9.75 | 110 | 1072.5 | 62
2012-09-12 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2012-09-12 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 5 | 135 | 675 | 62
2012-09-12 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2012-09-13 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 9 | 66.07 | 594.63 | 62
2012-09-13 | Micheal Biles. ( 10m Tipper ) | Micheal Biles | hr | 5.5 | 95 | 522.5 | 62
2012-09-13 | Plant Operator-Labour Hire | Labour | hr | 6 | 48 | 288 | 62
2012-09-13 | Earthmoving & Water Cart | Talbots | hr | 5.5 | 95 | 522.5 | 62
2012-09-13 | (10 M Tipper ) | Pollard Earthmoving | hr | 1 | 95 | 95 | 62
2012-09-13 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-09-13 | New Holland Compact Grader - No Operator | NH Grader | hr | 5 | 25.78 | 128.9 | 62
2012-09-13 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 5 | 135 | 675 | 62
2012-09-13 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2012-09-13 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2012-09-13 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 1.5 | 110 | 165 | 62
2012-09-14 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 62
2012-09-14 | Truck Hire | Micheal Biles | hr | 6 | 95 | 570 | 62
2012-09-14 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 62
2012-09-14 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 62
2012-09-14 | (10 M Tipper ) | Pollard Earthmoving | hr | 6 | 95 | 570 | 62
2012-09-14 | New Holland Compact Grader - No Operator | NH Grader | hr | 6 | 25.78 | 154.68 | 62
2012-09-14 | Earthmoving & Water Cart | Talbots | hr | 9 | 95 | 855 | 62
2012-09-14 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 7.5 | 110 | 825 | 62
2012-09-14 | Plant Operator-Labour Hire | Labour | hr | 9.5 | 48 | 456 | 62
2012-09-14 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 62
2012-09-14 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 62
2012-09-14 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 8 | 135 | 1080 | 62
2012-09-14 | Project Supervisor | Supervisor | hr | 9 | 71.81 | 646.29 | 62
2012-09-14 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 8 | 66.07 | 528.56 | 62
2012-09-15 | Earthmoving & Water Cart | Talbots | hr | 6 | 95 | 570 | 62
2012-09-17 | Earthmoving & Water Cart | Talbots | hr | 9.5 | 95 | 902.5 | 62
2012-09-18 | Inv No - 5103 | Humphries Pty Ltd | hr | 3.5 | 125.45 | 439.075 | 62
2012-09-18 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4 | 110 | 440 | 62
2012-09-18 | Earthmoving & Water Cart | Talbots | hr | 7 | 95 | 665 | 62
2012-09-18 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2012-09-18 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 3 | 135 | 405 | 62
2012-09-18 | Plant Operator-Labour Hire | Labour | hr | 5 | 48 | 240 | 62
2012-09-18 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2012-09-19 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-09-19 | Plant Operator-Labour Hire | Labour | hr | 4 | 48 | 192 | 62
2012-09-19 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-09-19 | Earthmoving & Water Cart | Talbots | hr | 7.5 | 95 | 712.5 | 62
2012-09-19 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 4 | 135 | 540 | 62
2012-09-20 | Earthmoving & Water Cart | Talbots | hr | 5 | 95 | 475 | 62
2012-09-20 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-09-20 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-09-20 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-09-20 | Plant Operator-Labour Hire | Labour | hr | 10.5 | 48 | 504 | 62
2012-09-20 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 3 | 135 | 405 | 62
2012-09-20 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3 | 110 | 330 | 62
2012-09-21 | Plant Operator-Labour Hire | Labour | hr | 4 | 48 | 192 | 62
2012-09-21 | Earthmoving & Water Cart | Talbots | hr | 9 | 95 | 855 | 62
2012-09-21 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5 | 110 | 550 | 62
2012-09-21 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 2 | 66.07 | 132.14 | 62
2012-09-21 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 62
2012-09-21 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 62
2012-09-24 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-09-24 | Earthmoving & Water Cart | Talbots | hr | 9 | 95 | 855 | 62
2012-09-24 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 2 | 110 | 220 | 62
2012-09-24 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2012-09-25 | New Holland Compact Grader - No Operator | NH Grader | hr | 2 | 25.78 | 51.56 | 62
2012-09-25 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 62
2012-09-25 | Plant Operator-Labour Hire | Labour | hr | 9 | 48 | 432 | 62
2012-09-25 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 62
2012-09-25 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 62
2012-09-25 | Earthmoving & Water Cart | Talbots | hr | 9 | 95 | 855 | 62
2012-09-25 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 8.5 | 110 | 935 | 62
2012-09-26 | New Holland Compact Grader - No Operator | NH Grader | hr | 5 | 25.78 | 128.9 | 62
2012-09-26 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 9 | 110 | 990 | 62
2012-09-26 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 62
2012-09-26 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2012-09-26 | Plant Operator-Labour Hire | Labour | hr | 10 | 48 | 480 | 62
2012-09-26 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2012-09-26 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 62
2012-09-26 | Earthmoving & Water Cart | Talbots | hr | 10 | 95 | 950 | 62
2012-09-27 | Earthmoving & Water Cart | Talbots | hr | 6.5 | 95 | 617.5 | 62
2012-09-30 | Dynapac CC 21 Roller. Hired 31/8/12 - 20/9/12. Inv No - 303112 | Dynapac CC21 Roller |  | 1 | 1700 | 1700 | 62
| Subtotal for 062 |  |  |  |  | 382852.6255
Portfolio WBS 063
2011-11-15 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 63
2011-11-15 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 63
2011-11-15 | Foreman | Labour | hr | 9.5 | 44.2 | 419.9 | 63
2011-11-15 | DoyawanaTruck Hire | Doyawana | hr | 5 | 95 | 475 | 63
2011-11-15 | Excavator ( 7 Tonne) | Berry Excavations | hr | 5.5 | 110 | 605 | 63
2011-11-15 | Truck Hire | Labour | hr | 4 | 65 | 260 | 63
2011-11-16 | Excavator 21 Tonne | Berry Excavations | hr | 3 | 140 | 420 | 63
2011-11-16 | ( Bobcat Hire ) | Labour | hr | 2 | 95 | 190 | 63
2011-11-16 | Labour Hire | Labour | hr | 1 | 40 | 40 | 63
2011-11-17 | New Holland Compact Grader - No Operator | NH Grader | hr | 2 | 25.78 | 51.56 | 63
2011-11-24 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 63
2011-11-24 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 63
2011-11-24 | DoyawanaTruck Hire | Doyawana | hr | 10 | 95 | 950 | 63
2011-11-24 | Bobcat | Labour | hr | 3 | 95 | 285 | 63
2012-02-16 | Water / Tipper | Berry Excavations | hr | 3 | 100 | 300 | 63
2012-02-16 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 63
2012-02-16 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 63
2012-02-16 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 63
2012-02-17 | Water / Tipper | Berry Excavations | hr | 3.5 | 100 | 350 | 63
2012-02-20 | Water / Tipper | Berry Excavations | hr | 3.5 | 100 | 350 | 63
2012-02-29 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 63
2012-02-29 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5 | 90 | 450 | 63
2012-02-29 | Grader Hire | Humphries Pty Ltd | hr | 8.5 | 100 | 850 | 63
2012-02-29 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 63
2012-02-29 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 63
2012-02-29 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 63
2012-02-29 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 63
2012-03-07 | Hired from 5/3/12 - 7/3/12 . Inv No - 9458775 | Portable Vibrator Shaft |  | 1 | 245.12 | 245.12 | 63
2012-03-10 | Grader Hire | Humphries Pty Ltd | hr | 2 | 100 | 200 | 63
2012-03-10 | Taylor Earthmoving ( 3t Excavator ) | Taylors Earthmoving | hr | 5 | 85 | 425 | 63
2012-03-10 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 63
2012-03-30 | Grader Hire | Humphries Pty Ltd | hr | 6.5 | 100 | 650 | 63
2012-03-30 | Water Truck | Berry Excavations | hr | 7 | 100 | 700 | 63
2012-03-30 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 63
2012-03-30 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 63
2012-03-30 | Truck & Dog Hire | Humphries Pty Ltd | hr | 1 | 113.19 | 113.19 | 63
2012-03-30 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 63
2012-03-31 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 63
2012-03-31 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 63
2012-03-31 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 63
2012-03-31 | Grader Hire | Humphries Pty Ltd | hr | 9.5 | 100 | 950 | 63
2012-03-31 | Water Truck | Berry Excavations | hr | 10 | 100 | 1000 | 63
2012-03-31 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 9 | 90 | 810 | 63
2012-04-10 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 63
2012-04-10 | Grader HIre | Humphries Pty Ltd | hr | 4 | 100 | 400 | 63
2012-04-10 | Water Truck Hire | Berry Excavations | hr | 2 | 100 | 200 | 63
2012-04-11 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 63
2012-04-18 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 63
2012-04-18 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 63
2012-04-18 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 63
2012-04-18 | Labour Hire | Labour | hr | 4.5 | 48 | 216 | 63
2012-04-18 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 63
2012-04-18 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 63
2012-04-18 | Grader Hire | Humphries Pty Ltd | hr | 4 | 100 | 400 | 63
2012-04-19 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 63
2012-04-19 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 63
2012-04-19 | Labour Hire | Labour | hr | 4.5 | 48 | 216 | 63
2012-04-19 | Grader Hire | Humphries Pty Ltd | hr | 4 | 100 | 400 | 63
2012-04-19 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 63
2012-04-19 | Water Truck Hire | Talbots | hr | 4.5 | 95 | 427.5 | 63
2012-04-19 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 63
2012-04-20 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 63
2012-04-20 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 63
2012-04-23 | Labour Hire | Labour | hr | 6 | 48 | 288 | 63
2012-04-23 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 6 | 90 | 540 | 63
2012-04-23 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 63
2012-04-23 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 63
2012-04-23 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 63
2012-04-23 | Spreader Truck | Ivecko Spreader Truck | hr | 1 | 2500 | 2500 | 63
2012-04-24 | Grader Hire | Humphries Pty Ltd | hr | 9.5 | 100 | 950 | 63
2012-04-24 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5 | 90 | 450 | 63
2012-04-24 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 63
2012-04-24 | Labour Hire | Labour | hr | 7 | 48 | 336 | 63
2012-04-24 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 63
2012-04-24 | Water Truck Hire | Talbots | hr | 3 | 95 | 285 | 63
2012-04-24 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 63
2012-04-26 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5 | 90 | 450 | 63
2012-04-26 | Water Truck Hire | Talbots | hr | 3 | 95 | 285 | 63
2012-04-27 | Double Drum Roller. Hired on the 18/4/2012 - 24/4/2012. Inv No - 282621 | Double Drum Roller |  | 1 | 1576.4 | 1576.4 | 63
2012-04-30 | Dynapac CC 21 Roller. Hired from the 31/3/2012 - 30/4/2012. Inv No - 283186 | Dynapac CC21 Roller |  | 1 | 3150 | 3150 | 63
2012-05-09 | (Water Truck ) | Talbots | hr | 5 | 95 | 475 | 63
2012-05-09 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 63
2012-05-09 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 63
2012-05-09 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 63
2012-05-09 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 63
2012-05-09 | Labour Hire | Labour | hr | 8 | 48 | 384 | 63
2012-05-09 | Grader Hire | Humphries Pty Ltd | hr | 9 | 100 | 900 | 63
2012-05-10 | (Water Truck ) | Talbots | hr | 5 | 95 | 475 | 63
2012-05-10 | Grader Hire | Humphries Pty Ltd | hr | 6.5 | 100 | 650 | 63
2012-05-10 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 63
2012-05-10 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 63
2012-05-10 | Labour Hire | Labour | hr | 8 | 48 | 384 | 63
2012-05-10 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 63
2012-05-10 | (Water Truck ) | Talbots | hr | 5.5 | 95 | 522.5 | 63
2012-05-10 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5 | 90 | 450 | 63
2012-05-10 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 63
2012-05-17 | Standpipe Water Consumption. Inv no - 5996 | Water Consumption |  | 4 | 25 | 100 | 63
2012-06-04 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 63
2012-06-04 | Grader Hire | Humphries Pty Ltd | hr | 2 | 100 | 200 | 63
2012-06-04 | Labour Hire | Labour | hr | 2 | 48 | 96 | 63
2012-06-05 | Labour Hire | Labour | hr | 3 | 48 | 144 | 63
2012-06-05 | Grader Hire | Humphries Pty Ltd | hr | 2 | 100 | 200 | 63
2012-06-05 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 63
2012-06-05 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 63
2012-06-06 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 63
2012-06-06 | Earthmoving & Water Cart | Talbots | hr | 2 | 95 | 190 | 63
2012-06-06 | Grader Hire | Humphries Pty Ltd | hr | 3 | 100 | 300 | 63
2012-06-06 | Labour Hire | Labour | hr | 3 | 48 | 144 | 63
2012-06-06 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 63
2012-06-07 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 63
2012-06-07 | Grader Hire | Humphries Pty Ltd | hr | 3 | 100 | 300 | 63
2012-06-07 | Labour Hire | Labour | hr | 6.5 | 48 | 312 | 63
2012-06-07 | Earthmoving & Water Cart | Talbots | hr | 5.5 | 95 | 522.5 | 63
2012-06-07 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 63
2012-06-08 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 63
2012-06-08 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 63
2012-06-08 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 63
2012-06-08 | Labour Hire | Labour | hr | 5 | 48 | 240 | 63
2012-06-08 | Grader Hire | Humphries Pty Ltd | hr | 5.5 | 100 | 550 | 63
2012-06-08 | Earthmoving & Water Cart | Talbots | hr | 3.5 | 95 | 332.5 | 63
2012-06-19 | Grader Hire | Humphries Pty Ltd | hr | 2 | 100 | 200 | 63
2012-06-19 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 63
2012-06-19 | Labour Hire | Labour | hr | 2.5 | 48 | 120 | 63
2012-06-19 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 63
2012-06-19 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 6 | 110 | 660 | 63
2012-06-21 | Labour Hire | Labour | hr | 3 | 48 | 144 | 63
2012-06-21 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 63
2012-06-30 | Dynapac CC 21 Roller. Hired 31/5/2012 - 30/6/2012. Inv No - 291189 | Dynapac CC21 Roller |  | 1 | 3300 | 3300 | 63
2012-07-02 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 63
2012-07-02 | Labour Hire | Labour | hr | 4.5 | 48 | 216 | 63
2012-07-24 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 63
2012-07-25 | Earthmoving & Water Cart | Talbots | hr | 3 | 95 | 285 | 63
2012-08-06 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 63
2012-08-06 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 63
2012-08-06 | Labour Hire | Labour | hr | 3.5 | 48 | 168 | 63
2012-08-06 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 63
2012-08-06 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 63
2012-08-06 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.75 | 110 | 522.5 | 63
2012-08-06 | Grader Hire | Humphries Pty Ltd | hr | 3 | 100 | 300 | 63
2012-08-07 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 63
2012-08-07 | Grader Hire | Humphries Pty Ltd | hr | 5 | 100 | 500 | 63
2012-08-07 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 63
2012-08-07 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 63
2012-08-07 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.5 | 110 | 495 | 63
2012-08-07 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 6.5 | 130 | 845 | 63
2012-08-07 | Labour Hire | Labour | hr | 7 | 48 | 336 | 63
2012-08-08 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.75 | 110 | 522.5 | 63
2012-08-08 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 63
2012-08-08 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 63
2012-08-08 | Grader Hire | Humphries Pty Ltd | hr | 7.5 | 100 | 750 | 63
2012-08-08 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 63
2012-08-08 | Earthmoving & Water Cart | Talbots | hr | 7 | 95 | 665 | 63
2012-08-08 | Labour Hire | Labour | hr | 8 | 48 | 384 | 63
2012-08-09 | Grader Hire | Humphries Pty Ltd | hr | 7 | 100 | 700 | 63
2012-08-09 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 63
2012-08-09 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 6.5 | 110 | 715 | 63
2012-08-09 | Earthmoving & Water Cart | Talbots | hr | 8 | 95 | 760 | 63
2012-08-09 | Labour Hire | Labour | hr | 10 | 48 | 480 | 63
2012-08-09 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 63
2012-08-09 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 63
2012-08-09 | ( Bobcat Hire ) | Labour | hr | 3 | 95 | 285 | 63
2012-08-10 | Labour Hire ( Achieve Group ) | Labour | hr | 6 | 34.81 | 208.86 | 63
2012-08-10 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 63
2012-08-10 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 | 365 | 63
2012-08-10 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3 | 110 | 330 | 63
2012-08-10 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 63
2012-08-10 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 63
2012-08-10 | Earthmoving & Water Cart | Talbots | hr | 2 | 95 | 190 | 63
2012-08-11 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 63
2012-08-11 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 | 365 | 63
2012-08-11 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 63
2012-08-11 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 63
2012-08-16 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3 | 110 | 330 | 63
2012-08-16 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 4 | 135 | 540 | 63
2012-08-16 | Operator-Labour | Labour | hr | 4 | 48 | 192 | 63
2012-08-16 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 63
2012-08-24 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 63
2012-08-24 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 5 | 135 | 675 | 63
2012-08-24 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 2 | 110 | 220 | 63
2012-08-24 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 63
2012-08-24 | Plant Operator-Labour Hire | Labour | hr | 2 | 48 | 96 | 63
2012-08-24 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 63
2012-08-24 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 63
2012-08-24 | Earthmoving & Water Cart | Talbots | hr | 2 | 95 | 190 | 63
2012-08-27 | Earthmoving & Water Cart | Talbots | hr | 3 | 95 | 285 | 63
2012-08-27 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 3 | 135 | 405 | 63
2012-08-27 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 63
2012-08-27 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 63
2012-08-30 | Pad Foot Roller - Dry. Hired 31/7/12 - 24/8/12. Inv No - 298887 | PF Roller |  | 1 | 2166.666 | 2166.666 | 63
2012-09-01 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 6 | 110 | 660 | 63
2012-09-01 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 63
2012-09-03 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 63
2012-09-03 | Plant Operator-Labour Hire | Labour | hr | 5 | 48 | 240 | 63
2012-09-03 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 3 | 135 | 405 | 63
2012-09-03 | Earthmoving & Water Cart | Talbots | hr | 3 | 95 | 285 | 63
2012-09-03 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5 | 110 | 550 | 63
2012-09-11 | Plant Operator-Labour Hire | Labour | hr | 6.5 | 48 | 312 | 63
2012-09-11 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 63
2012-09-11 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 63
2012-09-11 | Plant Operator-Labour Hire | Labour | hr | 6.5 | 48 | 312 | 63
2012-09-11 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 6 | 135 | 810 | 63
2012-09-11 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 6 | 135 | 810 | 63
2012-09-11 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 63
2012-09-11 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 63
2012-09-12 | New Holland Compact Grader - No Operator | NH Grader | hr | 5 | 25.78 | 128.9 | 63
2012-09-12 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 63
2012-09-12 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 63
2012-09-12 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 4 | 135 | 540 | 63
2012-09-12 | Plant Operator-Labour Hire | Labour | hr | 4.5 | 48 | 216 | 63
2012-09-13 | Plant Operator-Labour Hire | Labour | hr | 4.5 | 48 | 216 | 63
2012-09-13 | Earthmoving & Water Cart | Talbots | hr | 3 | 95 | 285 | 63
2012-09-13 | New Holland Compact Grader - No Operator | NH Grader | hr | 5 | 25.78 | 128.9 | 63
2012-09-13 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 4 | 135 | 540 | 63
2012-09-13 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 63
2012-09-13 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 63
2012-09-13 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3 | 110 | 330 | 63
2012-09-15 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 63
2012-09-15 | New Holland Compact Grader - No Operator | NH Grader | hr | 4.5 | 25.78 | 116.01 | 63
2012-09-15 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5 | 110 | 550 | 63
2012-09-15 | Project Supervisor | Supervisor | hr | 5 | 71.81 | 359.05 | 63
2012-09-15 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 63
2012-09-15 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 63
2012-09-17 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 63
2012-09-17 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5 | 110 | 550 | 63
2012-09-17 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 5 | 135 | 675 | 63
2012-09-17 | Plant Operator-Labour Hire | Labour | hr | 5 | 48 | 240 | 63
2012-09-18 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 4.5 | 135 | 607.5 | 63
2012-09-18 | Plant Operator-Labour Hire | Labour | hr | 4.5 | 48 | 216 | 63
2012-09-18 | Earthmoving & Water Cart | Talbots | hr | 2 | 95 | 190 | 63
2012-09-18 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 63
2012-09-18 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 1.5 | 110 | 165 | 63
2012-09-18 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 63
2012-09-19 | Plant Operator-Labour Hire | Labour | hr | 2 | 48 | 96 | 63
2012-09-19 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 63
2012-09-19 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 63
2012-09-19 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 2 | 135 | 270 | 63
2012-09-19 | Earthmoving & Water Cart | Talbots | hr | 2 | 95 | 190 | 63
2012-09-20 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 3 | 66.07 | 198.21 | 63
2012-09-30 | Double Drum Roller. Hired 31/8/12 - 28/9/12. Inv No - 303113 | Double Drum Roller |  | 1 | 1893.666 | 1893.666 | 63
2012-09-30 | Dynapac CC 21 Roller Hired 31/8/12 - 20/9/12. Invoice No - 303112 | Dynapac CC21 Roller |  | 1 | 1700 | 1700 | 63
2012-09-30 | Double Drum Roller. Hired 31/8/12 - 28/9/12. Inv No - 303113 | Double Drum Roller |  | 1 | 1893.666 | 1893.666 | 63
| Subtotal for 063 |  |  |  |  | 86275.348
Portfolio WBS 064
2011-10-31 | ANZAC Ave - Inv 265044 | Seal Visit One |  | 190 | 7.25 | 1377.5 | 64
2011-12-08 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 64
2011-12-15 | Bobcat | Labour | hr | 5 | 90 | 450 | 64
2011-12-15 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 64
2011-12-15 | Labour Hire ( Best Employment ) | Labour | hr | 3.5 | 39 | 136.5 | 64
2011-12-15 | Truck | Labour | hr | 1 | 65 | 65 | 64
2011-12-16 | 7mm Primer Seal - Inv 5458379 | 7mm Primer Seal |  | 642 | 12.77 | 8198.34 | 64
2011-12-20 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 64
2012-05-01 | Inv No - AQMKB4009-001 | Primerseal |  | 1 | 11849 | 11849 | 64
2012-05-08 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 5 | 130 | 650 | 64
2012-05-08 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 64
2012-05-08 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2012-05-08 | (Water Truck ) | Talbots | hr | 2 | 95 | 190 | 64
2012-05-08 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2012-05-08 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 64
2012-05-08 | New Holland Compact Grader - No Operator | NH Grader | hr | 2 | 25.78 | 51.56 | 64
2012-05-08 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 64
2012-05-08 | Labour Hire | Labour | hr | 4 | 48 | 192 | 64
2012-05-08 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 64
2012-05-09 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 64
2012-05-09 | New Holland Compact Grader - No Operator | NH Grader | hr | 1 | 25.78 | 25.78 | 64
2012-05-09 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 64
2012-05-09 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5 | 90 | 450 | 64
2012-05-10 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 64
2012-05-10 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 64
2012-05-10 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 64
2012-05-10 | New Holland Compact Grader - No Operator | NH Grader | hr | 1 | 25.78 | 25.78 | 64
2012-05-10 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 64
2012-05-10 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 64
2012-05-29 | Primerseal. Inv No - AQMKB4009-002 | Primerseal |  | 1 | 44845.88 | 44845.88 | 64
2012-06-28 | Primerseal. Inv No - AQMKB4009-003 | Primerseal |  | 1 | 7403 | 7403 | 64
2012-07-23 | Primerseal. Inv No - AQMKB4009-004 | Primerseal |  | 1 | 7140.83 | 7140.83 | 64
2012-08-28 | Primerseal. Inv No - AQMKB4009-005 | Primerseal |  | 1 | 19922.85 | 19922.85 | 64
2012-08-31 | Asphalt. Inv No - 6296253 RI | Asphalt |  | 1 | 91947.77 | 91947.77 | 64
2012-09-20 | Spreader Truck | Ivecko Spreader Truck | hr | 1 | 2500 | 2500 | 64
2012-09-20 | Earthmoving & Water Cart | Talbots | hr | 5 | 95 | 475 | 64
2012-09-20 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 64
2012-09-20 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 64
2012-09-20 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 6.5 | 110 | 715 | 64
2012-09-21 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 64
2012-09-21 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 64
2012-09-21 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2012-09-21 | Plant Operator-Labour Hire | Labour | hr | 5 | 48 | 240 | 64
2012-09-21 | Labour Hire ( People Resourcing ) | Labour | hr | 10 | 40.97 | 409.7 | 64
2012-09-21 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 64
2012-09-21 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 64
2012-09-21 | New Holland Compact Grader - No Operator | NH Grader | hr | 4 | 25.78 | 103.12 | 64
2012-09-25 | Primerseal. (Faust Doherty & Dobbins). Inv No - AQMKB4009-007 | Primerseal |  | 1 | 14887 | 14887 | 64
2012-09-28 | Asphalt. Inv No - 6358239 RI | Asphalt |  | 1 | 53930.89 | 53930.89 | 64
2012-09-30 | Hired 20/9/12 - 21/9/12. Inv No 303115 | Multi Tyre Roller |  | 2 | 315 | 630 | 64
2012-10-16 | Sweeper with Bobcat. Inv No - 01071 | Sweeper |  | 1.5 | 115 | 172.5 | 64
| Subtotal for 064 |  |  |  |  | 274290.025
Portfolio WBS 065
2012-05-14 | Primerseal. Inv No- 6053291 RI | Asphalt |  | 69.7 | 299.51 | 20875.847 | 65
2012-05-14 | Primerseal. Inv No 6053291 RI. | Asphalt |  | 292.2 | 299.51 | 87516.822 | 65
2012-07-23 | Earthmoving & Water Cart | Talbots | hr | 2 | 95 | 190 | 65
2012-07-24 | Earthmoving & Water Cart | Talbots | hr | 3 | 95 | 285 | 65
2012-07-26 | Earthmoving & Water Cart | Talbots | hr | 3 | 95 | 285 | 65
2012-07-31 | Asphalt. Inv No - 6224194 RI | Asphalt |  | 1 | 142122.5 | 142122.5 | 65
2012-09-27 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 65
2012-09-27 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 65
2012-09-28 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 65
2012-09-28 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 65
2012-09-28 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 9 | 110 | 990 | 65
2012-09-28 | ( Bobcat Hire ) | Labour | hr | 8.5 | 95 | 807.5 | 65
2012-09-28 | Plant Operator-Labour Hire | Labour | hr | 10 | 48 | 480 | 65
2012-09-30 | Asphalt. Inv No - 6371704 RI | Asphalt |  | 1 | 3740 | 3740 | 65
2012-10-02 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 65
2012-10-02 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 65
2012-10-02 | Plant Operator-Labour Hire | Labour | hr | 7 | 48 | 336 | 65
2012-10-02 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 65
2012-10-02 | S/D Roller - 3T - Dry Hire ( Flexi Hire ) | SD Roller - 3T | day | 1 | 365 | 365 | 65
2012-10-02 | ( Bobcat Hire ) | Labour | hr | 3 | 95 | 285 | 65
2012-10-02 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 7 | 110 | 770 | 65
2012-10-02 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 65
2012-10-25 | Screening. Inv No - 7551 | Asphalt |  | 1 | 388.41 | 388.41 | 65
| Subtotal for 065 |  |  |  |  | 261664.129
Portfolio WBS 066
2012-09-25 | Carpark at Dobbins Lane | Line Marking |  | 1 | 2153 | 2153 | 66
2012-11-22 | Line Marking at Sterry St & Chapman St Proserpine | Line Marking |  | 1 | 1652 | 1652 | 66
2012-11-22 | Line Marking of White Piano Keys at Dobbins Lane | Line Marking |  | 1 | 968.75 | 968.75 | 66
| Subtotal for 066 |  |  |  |  | 4773.75
Portfolio WBS 067
2012-04-30 | Labour Hire | Labour | hr | 3.5 | 48 | 168 | 67
2012-04-30 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 67
2012-04-30 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 67
2012-06-27 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 67
2012-06-27 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 67
2012-06-28 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 67
2012-07-26 | Earthmoving & Water Cart | Talbots | hr | 6.5 | 95 | 617.5 | 67
2012-09-11 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 67
2012-09-11 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4.5 | 95 | 427.5 | 67
2012-09-11 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 67
2012-09-11 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 67
| Subtotal for 067 |  |  |  |  | 2520.95
Portfolio WBS 068
2012-04-19 | Taylors Earthmoving ( 3t Excavator ) | Taylors Earthmoving | hr | 3.5 | 85 | 297.5 | 68
2012-04-19 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 68
2012-04-23 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 68
2012-04-24 | Taylors Earthmoving ( 3t Excavator ) | Taylors Earthmoving | hr | 6 | 85 | 510 | 68
2012-04-24 | BCLA Pty Ltd. | Tractor Profiller | day | 1 | 2500 | 2500 | 68
2012-04-24 | Spreader Truck | Ivecko Spreader Truck | hr | 1 | 2500 | 2500 | 68
2012-04-24 | Labour Hire | Labour | hr | 2 | 48 | 96 | 68
2012-04-24 | Water Truck Hire | Talbots | hr | 3 | 95 | 285 | 68
2012-04-24 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 68
2012-04-24 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 68
2012-04-24 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 68
2012-04-26 | Spreader Truck | Ivecko Spreader Truck | hr | 1 | 2500 | 2500 | 68
2012-04-26 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 68
2012-04-26 | Labour Hire | Labour | hr | 2.5 | 48 | 120 | 68
2012-04-26 | BCLA Pty Ltd. | Tractor Profiller | day | 1 | 2500 | 2500 | 68
2012-04-26 | Water Truck Hire | Talbots | hr | 4 | 95 | 380 | 68
2012-04-26 | Taylors Ëxcavator (3T) | Taylors Earthmoving | hr | 4 | 85 | 340 | 68
2012-04-26 | New Holland Compact Grader - No Operator | NH Grader | hr | 4 | 25.78 | 103.12 | 68
2012-04-27 | Water Truck Hire | Talbots | hr | 2 | 95 | 190 | 68
2012-06-01 | New Holland Compact Grader - No Operator | NH Grader | hr | 2 | 25.78 | 51.56 | 68
2012-06-01 | Spreader Truck | Ivecko Spreader Truck | hr | 1 | 2500 | 2500 | 68
2012-06-01 | Water Truck Hire | Tom Hurst | hr | 5 | 90 | 450 | 68
2012-06-01 | Grader Hire | Humphries Pty Ltd | hr | 8.5 | 100 | 850 | 68
2012-06-01 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5 | 90 | 450 | 68
2012-06-01 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 68
2012-06-01 | Labour Hire | Labour | hr | 10 | 48 | 480 | 68
2012-06-01 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 68
2012-06-01 | BCLA Pty Ltd. | Tractor Profiller | day | 1 | 2500 | 2500 | 68
2012-06-01 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 68
2012-06-02 | Grader Hire | Humphries Pty Ltd | hr | 2 | 100 | 200 | 68
2012-06-04 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 2 | 95 | 190 | 68
2012-06-04 | Spreader Truck | Ivecko Spreader Truck | hr | 1 | 2500 | 2500 | 68
2012-06-04 | BCLA Pty Ltd. | Tractor Profiller | day | 1 | 2500 | 2500 | 68
2012-06-04 | Grader Hire | Humphries Pty Ltd | hr | 7.5 | 100 | 750 | 68
2012-06-04 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5 | 90 | 450 | 68
2012-06-04 | Water Truck Hire | Tom Hurst | hr | 11.5 | 90 | 1035 | 68
2012-06-04 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 68
2012-06-04 | Labour Hire | Labour | hr | 11.5 | 35.35 | 406.525 | 68
2012-06-04 | Labour Hire | Labour | hr | 8.5 | 48 | 408 | 68
2012-06-04 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 68
2012-06-04 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 68
2012-06-04 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 68
2012-06-05 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 68
2012-06-05 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 68
2012-06-05 | Labour Hire | Labour | hr | 7 | 48 | 336 | 68
2012-06-05 | BCLA Pty Ltd. | Tractor Profiller | day | 1 | 2500 | 2500 | 68
2012-06-05 | Spreader Truck | Ivecko Spreader Truck | hr | 1 | 2500 | 2500 | 68
2012-06-05 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 6 | 95 | 570 | 68
2012-06-05 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5 | 90 | 450 | 68
2012-06-05 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 68
2012-06-05 | Earthmoving & Water Cart | Talbots | hr | 7 | 95 | 665 | 68
2012-06-05 | Grader Hire | Humphries Pty Ltd | hr | 5 | 100 | 500 | 68
2012-06-06 | Pad Foot Roller - Dry. Hired 1/6/2012 - 6/6/2012. Inv No - 288519 | PF Roller |  | 4 | 315 | 1260 | 68
2012-06-30 | Double Drum Roller. Hired 4/6/2012 - 30/6/2012. Inv No - 291194 | Double Drum Roller |  | 20 | 247 | 4940 | 68
| Subtotal for 068 |  |  |  |  | 46094.08
Portfolio WBS 071
2011-11-14 | B1 & M1 Powder Coated Aluminium Kerb Adaptors Docket No 15004 Inv - 198851 | Kerb Adaptors |  | 1 | 2749.5 | 2749.5 | 71
2011-11-16 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 71
2011-11-16 | Foreman | Labour | hr | 2.5 | 44.2 | 110.5 | 71
2011-11-16 | DoyawanaTruck Hire | Doyawana | hr | 5 | 95 | 475 | 71
2012-02-29 | Plus Damage Waiver & Daimond Blade. Hired on the 29/02/12. Inv No - 276348 | Concrete Saw |  | 1 | 164.63 | 164.63 | 71
2012-03-02 | Hired from the 29/2/12 - 2/3/12. Inv No 276826 | Quick Cut Saw |  | 1 | 329.28 | 329.28 | 71
2012-03-03 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 71
2012-03-03 | Taylors Earthmoving ( 3t Excavator ) | Taylors Earthmoving | hr | 3.5 | 85 | 297.5 | 71
2012-03-05 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 71
2012-03-05 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 71
2012-03-05 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5 | 90 | 450 | 71
2012-03-05 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 71
2012-03-07 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 1 | 90 | 90 | 71
2012-03-08 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 1.75 | 90 | 157.5 | 71
2012-03-21 | Inv No - 198339 | Kerb Subbie |  | 1 | 14540 | 14540 | 71
2012-04-01 | Driveways, Cerb Crossing, Set & Place Pit Walls. Inv No - 956526 | Concrete Subbie |  | 1 | 7981.81 | 7981.81 | 71
2012-04-13 | Inv No - 198341 | Kerb Subbie |  | 177 | 20 | 3540 | 71
2012-05-01 | Set & Finish of Kerb. Inv No - 0956529 | Concrete Subbie |  | 1 | 1700 | 1700 | 71
2012-05-03 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 1 | 90 | 90 | 71
2012-05-03 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 71
2012-05-03 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 71
2012-05-03 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 71
2012-05-03 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 5 | 90 | 450 | 71
2012-05-04 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 71
2012-05-04 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 71
2012-05-04 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3.5 | 90 | 315 | 71
2012-05-05 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 1.5 | 90 | 135 | 71
2012-05-05 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 71
2012-05-15 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 71
2012-06-01 | Inv No - 956533 | Concrete Subbie |  | 1 | 3750 | 3750 | 71
2012-06-25 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 71
2012-06-25 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 2 | 110 | 220 | 71
2012-06-25 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 71
2012-06-28 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 71
2012-06-28 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 71
2012-06-29 | Set and pour kerb and chanel in Chapman St. Inv No - 85 | Concrete Subbie |  | 1 | 1020 | 1020 | 71
2012-07-05 | Labour Hire | Labour | hr | 3 | 48 | 144 | 71
2012-07-05 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 71
2012-07-05 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 71
2012-07-05 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 71
2012-07-05 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 71
2012-07-06 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 71
2012-07-06 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 71
2012-07-06 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 71
2012-07-06 | Labour Hire | Labour | hr | 7 | 48 | 336 | 71
2012-07-09 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 2.75 | 110 | 302.5 | 71
2012-07-09 | Labour Hire ( Achieve Group ) | Labour | hr | 5 | 34.81 | 174.05 | 71
2012-07-09 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 71
2012-07-09 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 71
2012-07-09 | Labour Hire | Labour | hr | 3 | 48 | 144 | 71
2012-07-14 | Inv No - 198400 | Kerb Subbie |  | 1 | 2060 | 2060 | 71
2012-07-19 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 71
2012-07-19 | Labour Hire ( Achieve Group ) | Labour | hr | 4 | 34.81 | 139.24 | 71
2012-07-19 | Concrtetor Hire | Labour | hr | 7.5 | 45 | 337.5 | 71
2012-07-20 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 71
2012-07-20 | Concrtetor Hire | Labour | hr | 7.5 | 45 | 337.5 | 71
2012-07-20 | Labour Hire ( Achieve Group ) | Labour | hr | 5.5 | 34.81 | 191.455 | 71
2012-07-21 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 71
2012-07-21 | Labour Hire ( Achieve Group ) | Labour | hr | 5.5 | 34.81 | 191.455 | 71
2012-07-22 | Double Time | Labour | hr | 2.5 | 60.66 | 151.65 | 71
2012-07-23 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 71
2012-07-23 | Labour Hire ( Achieve Group ) | Labour | hr | 7 | 34.81 | 243.67 | 71
2012-07-23 | Concrtetor Hire | Labour | hr | 7.5 | 45 | 337.5 | 71
2012-07-26 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 71
2012-07-26 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 71
2012-07-27 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3.25 | 110 | 357.5 | 71
2012-07-27 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 71
2012-07-27 | Labour Hire ( Achieve Group ) | Labour | hr | 4 | 34.81 | 139.24 | 71
2012-07-27 | Concrtetor Hire | Labour | hr | 4 | 45 | 180 | 71
2012-07-28 | Double Time | Labour | hr | 4 | 60.66 | 242.64 | 71
2012-07-28 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 71
2012-07-28 | Concrtetor Hire | Labour | hr | 4 | 45 | 180 | 71
2012-08-01 | Set & Place Finish concrete Kerb . Inv No - 0956544 | Concrete Subbie |  | 1 | 1020 | 1020 | 71
2012-08-03 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 71
2012-08-03 | Concrtetor Hire | Labour | hr | 4 | 45 | 180 | 71
2012-08-03 | Labour Hire ( Achieve Group ) | Labour | hr | 4 | 34.81 | 139.24 | 71
2012-08-04 | Concrtetor Hire | Labour | hr | 6.5 | 45 | 292.5 | 71
2012-08-04 | Labour Hire ( Achieve Group ) | Labour | hr | 6.5 | 34.81 | 226.265 | 71
2012-08-04 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 71
2012-08-04 | Over Time | Labour | hr | 1.585 | 45.7 | 72.4345 | 71
2012-08-06 | Labour Hire ( Achieve Group ) | Labour | hr | 9 | 34.81 | 313.29 | 71
2012-08-06 | Over Time | Labour | hr | 1.544 | 45.7 | 70.5608 | 71
2012-08-06 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 71
2012-08-06 | Concrtetor Hire | Labour | hr | 9 | 45 | 405 | 71
2012-08-07 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 71
2012-08-07 | Over Time | Labour | hr | 1.585 | 45.7 | 72.4345 | 71
2012-08-07 | Concrtetor Hire | Labour | hr | 9 | 45 | 405 | 71
2012-08-07 | Labour Hire ( Achieve Group ) | Labour | hr | 9 | 34.81 | 313.29 | 71
2012-08-08 | Concrtetor Hire | Labour | hr | 9.5 | 45 | 427.5 | 71
2012-08-08 | Over Time | Labour | hr | 1.585 | 45.7 | 72.4345 | 71
2012-08-08 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 71
2012-08-08 | Labour Hire ( Achieve Group ) | Labour | hr | 9.5 | 34.81 | 330.695 | 71
2012-08-09 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 71
2012-08-09 | Labour Hire ( Achieve Group ) | Labour | hr | 9.5 | 34.81 | 330.695 | 71
2012-08-09 | Concrtetor Hire | Labour | hr | 9.5 | 45 | 427.5 | 71
2012-08-29 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 71
2012-08-29 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3.5 | 110 | 385 | 71
2012-08-29 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 71
2012-08-31 | Quick Cut Saw & Daimond Blade. Hired 28/8/12 - 31/8/12. Inv No - 299463 | Quick Cut Saw |  | 1 | 608 | 608 | 71
2012-09-05 | Dkt No 40628085, 40628086, 40628088, 40628092. Inv No - QM8692191 | Kerb Machine |  | 1 | 3949 | 3949 | 71
2012-09-05 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5.5 | 110 | 605 | 71
2012-09-05 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 71
2012-09-05 | 12H Grader - Allciv Pty Ltd | 12H Grader- Allciv Ptd Lt | hr | 9 | 135 | 1215 | 71
2012-09-10 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 71
2012-09-21 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 71
2012-09-21 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3.25 | 110 | 357.5 | 71
2012-09-21 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 71
2012-10-01 | Set place & Finish Kerb Channell. Inv No - 57 | Concrete Subbie |  | 1 | 1360 | 1360 | 71
2012-10-08 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 71
2012-10-08 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 71
2012-10-08 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5 | 110 | 550 | 71
2012-10-08 | Plant Operator-Labour Hire | Labour | hr | 6 | 48 | 288 | 71
2012-10-08 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 5 | 95 | 475 | 71
2012-10-08 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 71
2012-10-09 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 71
2012-10-24 | 98 l/m of Kerb & Gutter. Faust Street. Inv No - 0177276 | Kerb Adaptors |  | 1 | 1960 | 1960 | 71
2012-10-24 | 450 l/m of Kerb & 22 Kerb adaptors Faust & Doherty Street. Inv No - 0177279 | Kerb Subbie |  | 1 | 9440 | 9440 | 71
2012-10-30 | Place Set & Finish Speed Inhibiter & Kerb. Dobbins Lane | Concrete Subbie |  | 1 | 1800 | 1800 | 71
2012-11-30 | Set Place & Finish Kerb Channell, Doherty Street | Concrete Subbie |  | 1 | 850 | 850 | 71
2012-03-01 | Dobbins Lane 183 L/M of Kerb & Gutter & 6 Kerb Adaptors (See Comment) | Kerb Subbie |  | 1 | 3750 | 3750 | 71
| Subtotal for 071 |  |  |  |  | 86929.5843
Portfolio WBS 072
2011-11-09 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 72
2011-11-09 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 72
2011-12-01 | Hedwalls Anzac Rd - Inv 956507 | Concrete Subbie |  | 1 | 1850 | 1850 | 72
2011-12-01 | Headwalls - Jupp St Inv 956507 | Concrete Subbie |  | 1 | 2010 | 2010 | 72
2012-01-07 | Inv No - 956509. | Concrete Subbie |  | 1 | 9300 | 9300 | 72
| Subtotal for 072 |  |  |  |  | 13301.4
Portfolio WBS 073
2012-01-07 | Inv No - 956510 | Concrete Subbie |  | 1 | 360 | 360 | 73
2012-02-07 | Inv No - 956510 | Concrete Subbie |  | 1 | 280 | 280 | 73
2012-02-07 | Slab on Ground Inv No - 956510. | Concrete Subbie |  | 1 | 4020 | 4020 | 73
2012-03-02 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 73
2012-03-02 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 73
2012-03-02 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 73
2012-03-02 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 73
2012-04-17 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 73
2012-04-17 | Labour Hire | Labour | hr | 3 | 48 | 144 | 73
2012-04-17 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 73
2012-04-17 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 73
2012-04-30 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 73
2012-04-30 | Labour Hire | Labour | hr | 4 | 48 | 192 | 73
2012-05-01 | Place & Set Footpath. Inv No - 0956529 | Concrete Subbie |  | 1 | 1250 | 1250 | 73
2012-05-01 | Concrete Pipe Encacement , form edgeboard, driveway crossovers. Inv No - 0956527 | Concrete Subbie |  | 1 | 5860 | 5860 | 73
2012-05-16 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 73
2012-05-16 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 73
2012-06-01 | Inv No - 956534 | Concrete Subbie |  | 1 | 2280 | 2280 | 73
2012-06-01 | Place & Set Pram Ramps & Footpaths. Inv No - 956531 | Concrete Subbie |  | 1 | 910 | 910 | 73
2012-06-06 | Inv No - 0758 | Tactiles |  | 1 | 656 | 656 | 73
2012-06-25 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 73
2012-06-25 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 73
2012-06-25 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4 | 110 | 440 | 73
2012-06-26 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 73
2012-06-26 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 73
2012-06-26 | Labour Hire | Labour | hr | 2.5 | 48 | 120 | 73
2012-06-26 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 73
2012-06-26 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 2 | 110 | 220 | 73
2012-06-27 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.75 | 110 | 522.5 | 73
2012-06-27 | Labour Hire | Labour | hr | 5 | 48 | 240 | 73
2012-06-27 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 73
2012-06-28 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 9.5 | 110 | 1045 | 73
2012-07-02 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 73
2012-07-02 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 73
2012-07-02 | Labour Hire | Labour | hr | 4 | 48 | 192 | 73
2012-07-02 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 73
2012-07-09 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 73
2012-07-09 | Labour Hire | Labour | hr | 2.5 | 48 | 120 | 73
2012-07-09 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 73
2012-07-09 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3 | 110 | 330 | 73
2012-07-09 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 73
2012-07-09 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 73
2012-07-21 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 73
2012-07-21 | Concrtetor Hire | Labour | hr | 5.5 | 45 | 247.5 | 73
2012-07-21 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 73
2012-07-24 | Labour Hire ( Achieve Group ) | Labour | hr | 7 | 34.81 | 243.67 | 73
2012-07-24 | Concrtetor Hire | Labour | hr | 8.5 | 45 | 382.5 | 73
2012-07-24 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 73
2012-07-25 | Concrtetor Hire | Labour | hr | 7 | 45 | 315 | 73
2012-07-25 | Labour Hire ( Achieve Group ) | Labour | hr | 6 | 34.81 | 208.86 | 73
2012-07-25 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 73
2012-07-26 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 73
2012-07-26 | Labour Hire ( Achieve Group ) | Labour | hr | 5 | 34.81 | 174.05 | 73
2012-07-26 | Concrtetor Hire | Labour | hr | 5.5 | 45 | 247.5 | 73
2012-08-01 | Set Place & Finish of concrete paths & pram ramps. Set Place & Finish path entrance to nursing Home. Inv No - 0956545 | Concrete Subbie |  | 1 | 2485 | 2485 | 73
2012-08-01 | Set & Place concrete hob wall, Set & Place concrete footpat, Set and Place Driveways. Inv No - 0956455 | Concrete Subbie |  | 1 | 2020 | 2020 | 73
2012-09-01 | Set & Pour Paths ( Dobbins Lane). Inv No - 52 | Concrete Subbie |  | 1 | 3367.27 | 3367.27 | 73
2012-09-01 | Set & Pour kerbs Pran Ramps Hobwall & Paths. Dobbins Lane. Inv No - 51 | Concrete Subbie |  | 1 | 5932 | 5932 | 73
2012-10-01 | Set & Place Concrete crossovers & Driveways. Inv No - 57 | Concrete Subbie |  | 1 | 12297 | 12297 | 73
2012-10-04 | Compressor Trailer & Air Hoses. Inv No - 304268 | Compressor |  | 1 | 394 | 394 | 73
2012-10-04 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 73
2012-10-04 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 73
2012-10-05 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 73
2012-10-05 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 73
2012-10-16 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3.5 | 110 | 385 | 73
2012-10-16 | Inv No - 0768 | Tactiles |  | 1 | 2275 | 2275 | 73
2012-10-22 | Inv No - 0769 | Tactiles |  | 1 | 124 | 124 | 73
2012-10-30 | Place Set & Finish Pram Ram & Path, Dobbins Lane | Concrete Subbie |  | 1 | 755 | 755 | 73
| Subtotal for 073 |  |  |  |  | 55980.8
Portfolio WBS 075
2011-11-07 | Inv No - 1403 | Concrete Subbie |  | 1 | 2715.72 | 2715.72 | 75
2012-01-25 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 75
2012-01-28 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 75
2012-01-28 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 75
2012-01-28 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 75
2012-01-31 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 75
2012-01-31 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 75
2012-02-09 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 75
2012-02-11 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 75
2012-02-11 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 75
2012-02-11 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 75
2012-03-29 | Inv No - 1507 | Concrete Subbie |  | 1 | 312.6 | 312.6 | 75
2012-05-31 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 75
2012-05-31 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 75
2012-05-31 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 75
2012-05-31 | Labour Hire | Labour | hr | 1 | 48 | 48 | 75
2012-06-25 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 75
2012-06-25 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 75
2012-07-06 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 75
2012-07-06 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 75
2012-08-02 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 75
2012-08-10 | Saw Cutting. Inv No - 1625 | Concrete Subbie |  | 1 | 463.8 | 463.8 | 75
2012-08-27 | Saw Cutting. Inv No - 01632 | Concrete Subbie |  | 1 | 1453.4 | 1453.4 | 75
2012-09-06 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 75
2012-09-06 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 75
2012-09-13 | Saw Cutting. Inv No - 01660 | Concrete Subbie |  | 1 | 1061 | 1061 | 75
| Subtotal for 075 |  |  |  |  | 8705.77
Portfolio WBS 081
2011-12-20 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 81
2012-01-12 | Excavator ( 7 Tonne ) | Berry Excavations | hr | 9 | 110 | 990 | 81
2012-01-12 | Labour Hire ( People Resourcing ) | Labour | hr | 9.5 | 40.97 | 389.215 | 81
2012-01-12 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2012-01-12 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2.5 | 90 | 225 | 81
2012-01-13 | Labour Hire ( People Resourcing ) | Labour | hr | 6 | 40.97 | 245.82 | 81
2012-01-13 | Hessian Sand bags. Tran No- 08416249 | Sand Bags |  | 1 | 105.45 | 105.45 | 81
2012-01-13 | Excavator ( 7 Tonne ) | Berry Excavations | hr | 6 | 110 | 660 | 81
2012-01-13 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 81
2012-01-18 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2012-01-18 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2012-01-18 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2012-01-18 | 21 Tonne Excavator | Berry Excavations | hr | 5 | 110 | 550 | 81
2012-01-19 | Labour Hire ( People Resourcing ) | Labour | hr | 9.5 | 40.97 | 389.215 | 81
2012-01-19 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 81
2012-01-19 | Sand Bags & Star Pickets. Trans / No 08423958 | Sand Bags |  | 1 | 393.35 | 393.35 | 81
2012-01-19 | 21 Tonne Excavator | Berry Excavations | hr | 4.25 | 110 | 467.5 | 81
2012-01-19 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 81
2012-01-20 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 81
2012-01-20 | 21 Tonne Excavator | Berry Excavations | hr | 7 | 110 | 770 | 81
2012-01-20 | Labour Hire ( People Resourcing ) | Labour | hr | 9.5 | 40.97 | 389.215 | 81
2012-01-20 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 81
2012-01-21 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 81
2012-01-21 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 81
2012-01-21 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 81
2012-01-21 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 81
2012-03-02 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 81
2012-03-02 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 81
2012-03-06 | Taylors Earthmoving (3t Excavator ) | Taylors Earthmoving | hr | 6 | 85 | 510 | 81
2012-03-06 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 81
2012-03-23 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 81
2012-03-23 | Taylor Earthmoving ( 3 t Excavator ) | Taylors Earthmoving | hr | 7 | 85 | 595 | 81
2012-03-23 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 81
2012-03-27 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 8 | 90 | 720 | 81
2012-03-27 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2012-03-27 | Taylors Earthmoving ( 3t Excavator ) | Taylors Earthmoving | hr | 7.5 | 85 | 637.5 | 81
2012-03-27 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2012-03-27 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2012-03-27 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2012-03-28 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 81
2012-03-28 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 81
2012-03-28 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2012-03-28 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 6 | 90 | 540 | 81
2012-03-28 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 81
2012-03-30 | Vibrating Rammer ( Flexi Hire ) . Inv No - 279432 | Vibrating Rammer |  | 1 | 358.4 | 358.4 | 81
2012-07-26 | Pvc S/W Pipes. Inv No - 143756444 | Pvc S/W Pipe |  | 1 | 146.17 | 146.17 | 81
2012-07-28 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 81
2012-07-28 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 81
2012-07-28 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 7.75 | 110 | 852.5 | 81
2012-07-28 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 81
2012-07-30 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 81
2012-07-30 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5.25 | 110 | 577.5 | 81
2012-08-08 | Pvc S/W Pipes. Inv No - 14375670 | Pvc S/W Pipe |  | 1 | 324.81 | 324.81 | 81
2012-08-31 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 81
2012-08-31 | Plant Operator-Labour Hire | Labour | hr | 2 | 48 | 96 | 81
2012-08-31 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 81
2012-08-31 | Micheal Biles. ( 10m Tipper ) | Micheal Biles | hr | 5 | 95 | 475 | 81
2012-08-31 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 7 | 130 | 910 | 81
2012-09-10 | Pvc S/W Pipes. Inv No - 143758132 | Pvc S/W Pipe |  | 1 | 101.46 | 101.46 | 81
| Subtotal for 081 |  |  |  |  | 19984.005
Portfolio WBS 085
2011-12-09 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 85
2012-01-19 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 85
2012-01-19 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 85
2012-01-19 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 85
2012-01-19 | 21 Tonne Excavator | Berry Excavations | hr | 2 | 110 | 220 | 85
2012-01-20 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 85
2012-01-20 | 21 Tonne Excavator | Berry Excavations | hr | 2.5 | 110 | 275 | 85
2012-01-23 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 85
2012-01-23 | 21 Tonne Excavator | Berry Excavations | hr | 3.5 | 110 | 385 | 85
2012-01-23 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 85
2012-01-23 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 85
2012-01-25 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 85
2012-03-08 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 85
2012-03-08 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 85
2012-03-08 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 85
2012-03-28 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 1 | 90 | 90 | 85
2012-03-28 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 85
2012-03-28 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 85
2012-03-29 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 85
2012-03-29 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 85
2012-04-16 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 85
2012-04-16 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 85
2012-04-17 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 6 | 90 | 540 | 85
2012-04-17 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 85
2012-04-17 | Labour Hire | Labour | hr | 6.5 | 48 | 312 | 85
2012-04-17 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 85
2012-04-18 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3.5 | 90 | 315 | 85
2012-04-18 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 85
2012-04-18 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 85
2012-04-26 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 85
2012-04-26 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 85
2012-05-01 | Set Place & Fisish of Culverts. Rase Wall & Lid. Inv No- 0956529 | Concrete Subbie |  | 1 | 2520 | 2520 | 85
2012-05-16 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 85
2012-05-16 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 85
2012-05-16 | Labour Hire | Labour | hr | 6 | 48 | 288 | 85
2012-05-16 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 85
2012-05-16 | Brush Cutter & Harness. Inv No - 285418 | Brush Cutter |  | 1 | 57.24 | 57.24 | 85
2012-05-16 | Drill Hammer & Drills. Hired on the 16/5/2012. Inv No - 285418 | Drill Hammer |  | 1 | 57 | 57 | 85
2012-05-16 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 85
2012-05-17 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 85
2012-05-17 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 85
2012-07-02 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 85
2012-07-02 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 85
2012-10-02 | Plant Operator-Labour Hire | Labour | hr | 3.5 | 48 | 168 | 85
2012-10-02 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 85
2012-10-02 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 85
2012-10-02 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3 | 110 | 330 | 85
2012-10-05 | Plant Operator-Labour Hire | Labour | hr | 4 | 48 | 192 | 85
2012-10-05 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 85
2012-10-05 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4 | 110 | 440 | 85
2012-10-05 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 85
2012-10-30 | Place Set & Finsh of Stormwater Pit, Doherty St | Concrete Subbie |  | 1 | 4850 | 4850 | 85
| Subtotal for 085 |  |  |  |  | 16398.015
Portfolio WBS 086
2012-08-17 | SW Sub - Contractors. Inv No 137903 | SW Sub - Contractors |  | 1 | 71.81 | 71.81 | 86
2012-09-30 | SW Sub - Contractors. Inv No - | SW Sub - Contractors |  | 1 | 41840 | 41840 | 86
| Subtotal for 086 |  |  |  |  | 41911.81
Portfolio WBS 087
2011-11-01 | Agg Line Inv- 14916 | Agg - Line |  | 1 | 590 | 590 | 87
2011-11-03 | DoyawanaTruck Hire | Doyawana | hr | 5 | 95 | 475 | 87
2011-11-03 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 87
2011-11-04 | ( Bobcat Hire ) | Labour | hr | 2 | 95 | 190 | 87
2011-11-04 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 87
2011-11-08 | 21 Tonne Excavator | Berry Excavations | hr | 4 | 110 | 440 | 87
2011-11-09 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2011-11-09 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2011-11-09 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2011-11-09 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 87
2011-11-09 | Excavator ( 7 Tonne) | Berry Excavations | hr | 2 | 110 | 220 | 87
2011-11-09 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 87
2011-11-16 | Tipper (Wet Hire) Dock No 7823,7824 Inv - 6778 | Tipper |  | 1 | 1982.5 | 1982.5 | 87
2011-11-18 | (Tipper Hire ) | Labour | hr | 8 | 65 | 520 | 87
2011-11-18 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 87
2011-11-18 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 87
2011-11-18 | Excavator 21 Tonne | Berry Excavations | hr | 7.5 | 140 | 1050 | 87
2011-11-18 | Foreman | Labour | hr | 8.5 | 44.2 | 375.7 | 87
2011-11-19 | (Tipper Hire ) | Labour | hr | 5.5 | 65 | 357.5 | 87
2011-11-19 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 87
2011-11-19 | Excavator 21 Tonne | Berry Excavations | hr | 6.5 | 140 | 910 | 87
2011-11-19 | Foreman | Labour | hr | 7.5 | 44.2 | 331.5 | 87
2011-11-19 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 87
2011-11-21 | Excavator 21 tonne | Berry Excavations | hr | 5.5 | 140 | 770 | 87
2011-11-21 | Tipper Hire | Labour | hr | 4.5 | 65 | 292.5 | 87
2011-11-21 | Bobcat | Labour | hr | 1.5 | 95 | 142.5 | 87
2011-11-21 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 87
2011-11-21 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 87
2011-12-08 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 87
2011-12-08 | 5 - Cast Iron Valve Boxes with Lids Inv No 15178 Inv No 20076 | Valve Box & Surround |  | 5 | 80 | 400 | 87
2011-12-09 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 87
2011-12-09 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 87
2012-01-27 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 87
2012-01-27 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 87
2012-01-27 | 21 Tonne Excavator | Berry Excavations | hr | 6.25 | 110 | 687.5 | 87
2012-01-30 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 87
2012-01-30 | 21 Tonne Excavator | Berry Excavations | hr | 5 | 110 | 550 | 87
2012-01-31 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 87
2012-01-31 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 87
2012-01-31 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 87
2012-01-31 | 21 Tonne Excavator | Berry Excavations | hr | 5 | 110 | 550 | 87
2012-02-03 | 20mm Agg , 10 Percent Powder. Inv No 9143 | Cement Powder |  | 1 | 510 | 510 | 87
2012-02-08 | Inv No - 20349 | Drainage Agg |  | 4 | 229 | 916 | 87
2012-02-08 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 87
2012-02-08 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 6 | 90 | 540 | 87
2012-02-08 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 87
2012-02-08 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 87
2012-02-10 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 87
2012-02-10 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3.5 | 90 | 315 | 87
2012-02-10 | 7 Tonne Excavator | Berry Excavations | hr | 7 | 110 | 770 | 87
2012-02-10 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 87
2012-02-10 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 87
2012-02-10 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 87
2012-02-10 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 87
2012-02-13 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 6.5 | 90 | 585 | 87
2012-02-13 | 7 Tonne Excavator | Berry Excavations | hr | 7.75 | 110 | 852.5 | 87
2012-02-13 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 87
2012-02-13 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 87
2012-02-13 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 87
2012-02-14 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 8.5 | 90 | 765 | 87
2012-02-14 | 21 Tonne Excavator | Berry Excavations | hr | 8.5 | 110 | 935 | 87
2012-02-14 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 87
2012-02-14 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 87
2012-02-14 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 87
2012-02-17 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 87
2012-02-23 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3.75 | 90 | 337.5 | 87
2012-02-23 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 87
2012-02-23 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 87
2012-02-23 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 87
2012-02-23 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 87
2012-02-28 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-02-28 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 87
2012-02-28 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-03-08 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 87
2012-03-08 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 87
2012-03-08 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 87
2012-03-09 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 87
2012-03-09 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 87
2012-03-09 | Taylor Earthmoving ( 3t Excavator ) | Taylors Earthmoving | hr | 10.5 | 85 | 892.5 | 87
2012-03-09 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 87
2012-03-09 | Water Truck Hire | Berry Excavations | hr | 10 | 100 | 1000 | 87
2012-03-12 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 87
2012-03-29 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 87
2012-03-29 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 9 | 90 | 810 | 87
2012-03-29 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 87
2012-03-29 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 87
2012-03-29 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 87
2012-05-28 | Labour Hire | Labour | hr | 9.5 | 48 | 456 | 87
2012-05-28 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 87
2012-05-28 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 7.5 | 90 | 675 | 87
2012-05-28 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 87
2012-05-29 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 87
2012-05-29 | Labour Hire | Labour | hr | 4 | 48 | 192 | 87
2012-05-29 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 87
2012-05-30 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 87
2012-05-30 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-05-30 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 8.85 | 90 | 796.5 | 87
2012-06-02 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 87
2012-06-02 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 87
2012-06-05 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 87
2012-06-07 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 87
2012-06-07 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 87
2012-06-07 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2.5 | 90 | 225 | 87
2012-06-08 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 87
2012-06-08 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-06-08 | Labour Hire | Labour | hr | 3 | 48 | 144 | 87
2012-06-08 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 6 | 90 | 540 | 87
2012-06-08 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 87
2012-06-12 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 87
2012-06-12 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 87
2012-06-12 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 87
2012-06-12 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 87
2012-06-13 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-06-13 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 87
2012-06-13 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-06-13 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-06-14 | Plumbrs Mates Inspection Covers. Inv No - 21030 | Plumbers Mates |  | 1 | 1720 | 1720 | 87
2012-06-14 | Labour Hire | Labour | hr | 4 | 48 | 192 | 87
2012-06-14 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-06-14 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 8.5 | 90 | 765 | 87
2012-06-14 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 87
2012-06-14 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-06-14 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-06-15 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-06-15 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 87
2012-06-15 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-06-15 | Labour Hire | Labour | hr | 3 | 48 | 144 | 87
2012-06-15 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-06-16 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 87
2012-06-16 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 87
2012-06-16 | Labour Hire | Labour | hr | 1 | 48 | 48 | 87
2012-06-18 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-06-18 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-06-18 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 87
2012-06-19 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 87
2012-06-19 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-06-19 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-06-19 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3.5 | 110 | 385 | 87
2012-06-21 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 87
2012-06-21 | Labour Hire | Labour | hr | 4 | 48 | 192 | 87
2012-06-21 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.5 | 110 | 495 | 87
2012-06-21 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 87
2012-06-28 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 87
2012-06-28 | Labour Hire | Labour | hr | 9.5 | 48 | 456 | 87
2012-06-28 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-06-28 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-06-28 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-06-28 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 6 | 95 | 570 | 87
2012-06-29 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-06-29 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3 | 110 | 330 | 87
2012-06-29 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-06-29 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 87
2012-06-29 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 87
2012-07-02 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.25 | 110 | 467.5 | 87
2012-08-06 | 100 x 100mm Socked Ag-Line. Inv No - 21367 | Agg - Line |  | 1 | 259 | 259 | 87
2012-08-16 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 87
2012-08-16 | Inv No - 21451 | Agg - Line |  | 1 | 259 | 259 | 87
2012-08-16 | Operator-Labour | Labour | hr | 7 | 48 | 336 | 87
2012-08-16 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 87
2012-08-16 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 7.5 | 110 | 825 | 87
2012-08-16 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 87
2012-08-16 | Earthmoving & Water Cart | Talbots | hr | 2 | 95 | 190 | 87
2012-08-17 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 6 | 110 | 660 | 87
2012-08-17 | Taylors Earthmoving ( 25 t Excavator ) | Taylors Earthmoving | hr | 2 | 130 | 260 | 87
2012-08-17 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 87
2012-08-17 | Operator-Labour | Labour | hr | 3.5 | 48 | 168 | 87
2012-08-18 | Operator-Labour | Labour | hr | 5 | 48 | 240 | 87
2012-08-18 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 87
2012-08-18 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.5 | 110 | 495 | 87
2012-08-21 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 87
2012-08-21 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4.5 | 110 | 495 | 87
2012-08-21 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 87
2012-08-21 | Plant Operator-Labour Hire | Labour | hr | 2 | 48 | 96 | 87
2012-08-21 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 87
2012-08-21 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 87
2012-08-23 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 6 | 110 | 660 | 87
2012-08-23 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 87
2012-08-23 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 87
2012-08-23 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 87
2012-08-28 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 87
2012-08-28 | Inv No - 21535 | Agg - Line |  | 3 | 259 | 777 | 87
2012-08-28 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 87
2012-08-28 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 8 | 110 | 880 | 87
2012-08-29 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 87
2012-08-29 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 6 | 110 | 660 | 87
2012-08-29 | Plant Operator-Labour Hire | Labour | hr | 6 | 48 | 288 | 87
2012-08-30 | Micheal Biles. ( 10m Tipper ) | Micheal Biles | hr | 7.5 | 95 | 712.5 | 87
2012-08-30 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3.5 | 110 | 385 | 87
2012-08-31 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 3.75 | 110 | 412.5 | 87
2012-08-31 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 87
2012-08-31 | Plant Operator-Labour Hire | Labour | hr | 3.5 | 48 | 168 | 87
2012-09-03 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 87
| Subtotal for 087 |  |  |  |  | 58724.45
Portfolio WBS 103
2011-12-23 | Inv No - 131 | SW Sub - Contractors |  | 1 | 920 | 920 | 103
2012-03-13 | Inv No - 561 | SW Sub - Contractors |  | 1 | 14705.7 | 14705.7 | 103
2012-03-29 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 8 | 95 | 760 | 103
2012-03-31 | Inv No - 257 | SW Sub - Contractors |  | 1 | 26711.4 | 26711.4 | 103
2012-04-02 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 7.5 | 95 | 712.5 | 103
2012-04-20 | Inv No - 87 | SW Sub - Contractors |  | 1 | 18603.9 | 18603.9 | 103
2012-04-20 | Inv No - 89 | SW Sub - Contractors |  | 1 | 10800 | 10800 | 103
2012-05-23 | SW Sub - Contractors. Civil Works for Dobbins Lane, Inv No - 391 | SW Sub - Contractors |  | 1 | 78370 | 78370 | 103
2012-06-26 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 4 | 110 | 440 | 103
2012-06-29 | SW Sub - Contractors. Progress Claim Stormwater at Doherty street. Inv No - 405 | SW Sub - Contractors |  | 1 | 20800 | 20800 | 103
2012-06-29 | SW Sub - Contractors. Progress Claim on the Watermain on Doherty Street. Inv No - 404 | SW Sub - Contractors |  | 1 | 15000 | 15000 | 103
2012-06-29 | P2 Plastic Teltra Pit - Concrete Cover. Inv No 21115 | Teltra Pit & Cover |  | 1 | 110 | 110 | 103
2012-06-29 | SW Sub - Contractors. Sewermain on Sterry Street. Inv no 411 | SW Sub - Contractors |  | 1 | 8978 | 8978 | 103
2012-07-30 | SW Sub - Contractors. Inv No - 418 | SW Sub - Contractors |  | 1 | 1800 | 1800 | 103
2012-07-30 | SW Sub - Contractors. Inv No 418 | SW Sub - Contractors |  | 1 | 9110 | 9110 | 103
2012-08-31 | SW Sub - Contractors. Inv No - 0438 | SW Sub - Contractors |  | 1 | 12800 | 12800 | 103
2012-08-31 | SW Sub - Contractors. Inv No - 0439 | SW Sub - Contractors |  | 1 | 740 | 740 | 103
2012-08-31 | SW Sub - Contractors Inv No 0437 | SW Sub - Contractors |  | 1 | 2031 | 2031 | 103
2012-08-31 | SW Sub - Contractors. Inv No - 0440 | SW Sub - Contractors |  | 1 | 57445 | 57445 | 103
2012-11-30 | SW Sub - Contractors Claim for completion of works done on the rising main on Faust Street Proserpine. | SW Sub - Contractors |  | 1 | 6800 | 6800 | 103
| Subtotal for 103 |  |  |  |  | 287637.5
Portfolio WBS 110
2012-06-29 | P2 Plastic Teltra Pit - Concrete Cover. Inv No - 21115 | Teltra Pit & Cover |  | 1 | 110 | 110 | 110
| Subtotal for 110 |  |  |  |  | 110
Portfolio WBS 120
2012-08-18 | Cough. Inv No 750 | Turf |  | 100 | 3.5 | 350 | 120
| Subtotal for 120 |  |  |  |  | 350
Portfolio WBS 121
2012-08-17 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 121
2012-08-17 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 121
2012-10-17 | DoyawanaTruck Hire | Doyawana | hr | 5.5 | 95 | 522.5 | 121
2012-10-18 | DoyawanaTruck Hire | Doyawana | hr | 3.5 | 95 | 332.5 | 121
2012-10-18 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 5 | 110 | 550 | 121
2012-10-18 | Inv No - 750 | Turf Subbie |  | 100 | 3.5 | 350 | 121
2012-10-18 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 121
2012-10-19 | DoyawanaTruck Hire | Doyawana | hr | 1 | 100 | 100 | 121
2012-10-19 | DoyawanaTruck Hire | Doyawana | hr | 2 | 95 | 190 | 121
2012-10-19 | Inv No - 819 | Turf Subbie |  | 150 | 3.3 | 495 | 121
2012-10-22 | DoyawanaTruck Hire | Doyawana | hr | 2 | 100 | 200 | 121
2012-10-23 | DoyawanaTruck Hire | Doyawana | hr | 2 | 100 | 200 | 121
2012-10-24 | DoyawanaTruck Hire | Doyawana | hr | 1 | 100 | 100 | 121
2012-10-25 | Project Supervisor | Supervisor | hr | 1 | 71.81 | 71.81 | 121
2012-10-25 | DoyawanaTruck Hire | Doyawana | hr | 1 | 100 | 100 | 121
2012-10-26 | Project Supervisor | Supervisor | hr | 2 | 71.81 | 143.62 | 121
2012-11-30 | For the Hydromulching at yyour Faust & Doherty St Project | Hydromulching |  | 1 | 1950 | 1950 | 121
| Subtotal for 121 |  |  |  |  | 5977.08
Portfolio WBS 141
2011-10-11 | Traffic Controller with Vehicle Inv - 00019641 | Traffic Controller |  | 2 | 90 | 180 | 141
2011-10-18 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 141
2011-11-16 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 141
2011-11-17 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 141
2011-11-18 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 141
2011-11-21 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 141
2011-12-08 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 141
2012-02-11 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 141
2012-02-16 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 141
2012-02-17 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 141
2012-02-20 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 141
2012-03-01 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 141
2012-03-02 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 141
2012-03-13 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 141
2012-03-13 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 141
2012-03-16 | 2 x TC's + Ute, Signs & Comms. Inv No - 20653 | Traffic Control Crew |  | 1 | 380 | 380 | 141
2012-04-10 | 2 x TC's + Ute, Signs & Comms. Inv No - 20906 | Traffic Control Crew |  | 1 | 1472.8 | 1472.8 | 141
2012-04-26 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 141
2012-04-26 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 141
2012-04-30 | 2 x TC's + Ute, Signs & Comms. Inv No - 21153 | Traffic Control Crew |  | 1 | 1249.9 | 1249.9 | 141
2012-05-09 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 141
2012-05-24 | 2 x TC's + Ute, Signs & Comms. Inv No - BIH17703 | Traffic Control Crew |  | 1 | 8944 | 8944 | 141
2012-06-27 | 2 x TC's + Ute, Signs & Comms. Inv No - 21992 | Traffic Control Crew |  | 1 | 690.6 | 690.6 | 141
2012-07-27 | 2 x TC's + Ute, Signs & Comms. Inv No - 250 | Traffic Control Crew |  | 1 | 5148.2 | 5148.2 | 141
2012-07-31 | 2 x TC's + Ute, Signs & Comms. Inv No - 0361 | Traffic Control Crew |  | 1 | 1212.75 | 1212.75 | 141
2012-08-17 | 2 x TC's + Ute, Signs & Comms. Inv No - 0567 | Traffic Control Crew |  | 1 | 755.45 | 755.45 | 141
2012-08-19 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 141
2012-08-19 | 2 x TC's + Ute, Signs & Comms. Inv No - 21826 | Traffic Control Crew |  | 16 | 87 | 1392 | 141
2012-08-31 | 2 x TC's + Ute, Signs & Comms. Inv No - 0761 | Traffic Control Crew |  | 1 | 4628.1 | 4628.1 | 141
2012-08-31 | XH Stackable Barriers. Hired 2/8/12 - 31/8/12. Inv No - 299462 | Stackable Barriers |  | 30 | 21.427 | 642.81 | 141
2012-09-04 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 141
2012-09-20 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 141
2012-09-20 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 141
2012-09-27 | Plant Operator-Labour Hire | Labour | hr | 8.5 | 48 | 408 | 141
2012-09-27 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 141
2012-09-27 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 141
2012-09-28 | XH Stackable Barriers & Delivery Hired 31/8/12 - 27/9/12. Inv No - 302828 | Stackable Barriers |  | 1 | 617.12 | 617.12 | 141
2012-09-30 | Hired 31/8/2012 - 30/9/2012. Inv No - 30314 | Traffic Lights |  | 29 | 158 | 4582 | 141
2012-10-04 | Traffic Control Device. Hired 30/9/12 - 3/10/12. Inv No 304194 | Traffic Lights |  | 1 | 316 | 316 | 141
2012-10-08 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 141
2012-10-08 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 141
2012-11-07 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 141
| Subtotal for 141 |  |  |  |  | 38275.73
Portfolio WBS 151
2011-10-13 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 151
2011-10-13 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 151
2011-10-14 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 151
2011-10-14 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 151
2011-10-14 | Excavator ( 7 Tonne ) | Berry Excavations | hr | 4.5 | 95 | 427.5 | 151
2011-10-14 | Berry ( Boggie / Tipper ) | Berry Excavations | hr | 5 | 110 | 550 | 151
2011-10-17 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 151
2011-10-17 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 151
2011-11-29 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 151
2011-11-29 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 151
2011-11-29 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 151
2012-01-12 | Inv No 6721 | Aggregate |  | 1 | 60 | 60 | 151
2012-01-16 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 151
2012-01-16 | Labour Hire ( People Resourcing ) | Labour | hr | 2 | 40.97 | 81.94 | 151
2012-01-16 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 151
2012-01-16 | Foreman | Labour | hr | 2 | 44.2 | 88.4 | 151
2012-03-22 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 151
2012-03-22 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 151
2012-03-22 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 151
2012-03-26 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 151
2012-03-26 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 151
2012-03-26 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 151
2012-05-15 | Labour Hire | Labour | hr | 3.35 | 48 | 160.8 | 151
2012-05-15 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 151
2012-05-15 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 151
2012-05-15 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 151
2012-05-15 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 3 | 90 | 270 | 151
2012-05-24 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 151
2012-05-24 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 151
2012-05-25 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 151
2012-05-25 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 151
2012-05-25 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 151
2012-05-25 | Labour Hire | Labour | hr | 2 | 48 | 96 | 151
2012-05-25 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 151
2012-05-25 | New Holland Compact Grader - No Operator | NH Grader | hr | 1 | 25.78 | 25.78 | 151
2012-07-10 | Labour Hire | Labour | hr | 1 | 48 | 48 | 151
2012-07-10 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 151
2012-07-10 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 151
2012-07-12 | Labour Hire | Labour | hr | 1 | 48 | 48 | 151
2012-07-12 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 151
2012-10-02 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 151
2012-10-02 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 151
| Subtotal for 151 |  |  |  |  | 4825.82
Portfolio WBS 181
2011-10-12 | Excavator ( 7 Tonne ) | Berry Excavations | hr | 7.5 | 110 | 825 | 181
2011-10-12 | Berry ( Bogie / Tipper ) | Berry Excavations | hr | 8 | 95 | 760 | 181
2011-10-12 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 181
2011-10-14 | RCBC Crowns, Bar Chairs Dock 14795 Inv - 19658 | Cement |  | 1 | 5317.9 | 5317.9 | 181
2011-10-18 | Excavator ( 7 Tonne ) | Berry Excavations | hr | 2.5 | 110 | 275 | 181
2011-10-18 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 181
2011-10-18 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 181
2011-10-19 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 181
2011-10-19 | Excavator ( 7 Tonne ) | Berry Excavations | hr | 2 | 110 | 220 | 181
2011-10-19 | Bulk GP / GB Cement Inv - 19703 | Cement |  | 2 | 100 | 200 | 181
2011-10-19 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 181
2011-10-19 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 181
2011-10-19 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 181
2011-10-19 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 181
2011-10-19 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 181
2011-10-20 | Plate Compactor - Dry Hire Inv - 259080 | Plate Compactor |  | 1 | 79.5 | 79.5 | 181
2011-11-01 | Slab on Ground - Inv 50 | Concrete Subbie |  | 1 | 2250 | 2250 | 181
2011-11-21 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 181
2011-11-21 | Foreman | Labour | hr | 3 | 44.2 | 132.6 | 181
2011-11-21 | Tipper Hire | Labour | hr | 3 | 65 | 195 | 181
2011-11-21 | Excavator 21 Tonne | Berry Excavations | hr | 3 | 140 | 420 | 181
2011-11-21 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 181
2011-11-24 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 181
2011-11-24 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 181
2011-11-24 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 181
2011-11-25 | Excavator ( 7 Tonne ) | Berry Excavations | hr | 1 | 110 | 110 | 181
2011-12-02 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 9 | 100 | 900 | 181
2011-12-02 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 181
2011-12-02 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 181
2011-12-08 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 181
2011-12-09 | 21 Tonne Excavator | Berry Excavations | hr | 2 | 110 | 220 | 181
2011-12-09 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 181
2011-12-09 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 181
2012-02-16 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 181
2012-02-16 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 181
2012-02-16 | Berry Excavations ( 7t Ex ) | Berry Excavations | hr | 7.5 | 110 | 825 | 181
2012-02-17 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 181
2012-02-17 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 181
2012-02-17 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 181
2012-02-17 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4 | 95 | 380 | 181
2012-02-17 | Berry Excavations ( 7t Exc ) | Berry Excavations | hr | 6.5 | 110 | 715 | 181
2012-02-17 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2.5 | 90 | 225 | 181
2012-02-20 | ( 10 M Tipper ) | Lovell Earthmoving | hr | 4.5 | 95 | 427.5 | 181
2012-02-20 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 4 | 90 | 360 | 181
2012-02-20 | Berry Excavations ( 7t Exc ) | Berry Excavations | hr | 7 | 110 | 770 | 181
2012-02-20 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 181
2012-02-20 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 181
2012-03-12 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 2 | 90 | 180 | 181
2012-03-12 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 181
2012-03-12 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 181
2012-03-12 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 181
2012-07-30 | SW Sub - Contractors. Inv No - 418 | SW Sub - Contractors |  | 1 | 44075 | 44075 | 181
2012-09-17 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 181
2012-09-17 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 181
2012-09-19 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 181
2012-09-19 | Plant Operator-Labour Hire | Labour | hr | 4 | 48 | 192 | 181
2012-09-19 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 181
| Subtotal for 181 |  |  |  |  | 65321.65
Portfolio WBS 182
2012-01-07 | Inv No -956510 | Concrete Subbie |  | 1 | 570 | 570 | 182
| Subtotal for 182 |  |  |  |  | 570
Portfolio WBS 201
2012-11-30 | Backhoe - Hire (Chris Brown) | Back Hoe | hr | 9 | 95 | 855 | 201
2012-11-30 | Shovel & Broom x 2 | Small Tools |  | 1 | 131.63 | 131.63 | 201
2012-11-30 | Tipper Hire - Profiling & Removing Dig-Out (Chris Brown) | Tipper | hr | 7 | 65 | 455 | 201
2012-11-30 | Tipper Hire | Tipper | hr | 7 | 65 | 455 | 201
2012-11-30 | Backhoe - Hire | Back Hoe | hr | 9 | 95 | 855 | 201
2012-11-30 | Rags, Glovew, Buckets,Screed & Rake | Small Tools |  | 1 | 1 | 164.31 | 201
2012-11-30 | Backhoe - Hire | Back Hoe | hr | 8.5 | 95 | 807.5 | 201
2012-11-30 | Tipper Hire | Tipper | hr | 8 | 65 | 520 | 201
2012-11-30 | Watering Can (Chris Brown) | Small Tools |  | 1 | 7.27 | 7.27 | 201
2012-11-30 | 2 x TC's + Ute, Signs & Comms ( Chris Brown) | Traffic Control Crew |  | 53 | 62 | 3286 | 201
2012-11-30 | Allciv - Paveline Emulsion Sprayer | Paveline Truck | hr | 2 | 67 | 134 | 201
2012-11-30 | Asphalt. | Asphalt |  | 16 | 160.5 | 2568 | 201
2012-11-30 | Laymor Broom Hire | Laymor Broom |  | 1 | 260 | 260 | 201
2012-11-30 | Repairs | Emulsion |  | 1 | 328 | 328 | 201
2012-11-30 | Faust Street Pipeline Crossing | Field Density |  | 1 | 2823.91 | 2823.91 | 201
| Subtotal for 201 |  |  |  |  | 13650.62
Portfolio WBS 220
2012-06-01 | Place Set & Fisish of Concrete Pip Encasement. Inv No - 956531 | Conduit Subbie |  | 1 | 1500 | 1500 | 220
| Subtotal for 220 |  |  |  |  | 1500
Portfolio WBS 221
2012-01-07 | Inv No - 956512 | Concrete Subbie |  | 1 | 420 | 420 | 221
2012-04-05 | Tensar Triax Grid. 3.80M X 75M. Inv No - CD201218068 | Tensar Triax Grid |  | 6811.68 | 4.6 | 31333.728 | 221
| Subtotal for 221 |  |  |  |  | 31753.728
Portfolio WBS 222
2011-11-24 | Class D Geotextile 4.00M x 100M. Inv No - CD201207670 | Class D Geotextile |  | 1600 | 2.25 | 3600 | 222
2011-11-24 | 3.80M x 75M tensar Triax Grid. Inv No - CD201207670 | Tensar Triax Grid |  | 1710 | 4.65 | 7951.5 | 222
2012-01-13 | 3.80M x 75M tensar Triax Grid. Inv No - Cd201212423 | Tensar Triax Grid |  | 1710 | 4.65 | 7951.5 | 222
2012-01-13 | A34-Bidim 6.00M x150M. Inv No - CD201212423 | A34 |  | 2700 | 1.47 | 3969 | 222
2012-01-23 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-01-23 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-01-23 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-01-23 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-02-01 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-02-01 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-02-01 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-02-09 | A34-Bidim 6.00M x150M. Inv No - CD201214094 | A34 |  | 3600 | 1.47 | 5292 | 222
2012-02-09 | 3.80M x 75M tensar Triax Grid. Inv No - CD201214094 | Tensar Triax Grid |  | 3135 | 4.6 | 14421 | 222
2012-02-13 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-03-02 | A29-Bidim 6.00M x 150M. Inv No - CD201215705 | A29 |  | 4500 | 1.1 | 4950 | 222
2012-03-02 | 3.80M x 75M tensar Triax Grid. Inv No - CD201215705 | Tensar Triax Grid |  | 1710 | 4.6 | 7866 | 222
2012-03-02 | A24 - Bidum 3.00M x 75M. Inv No - CD201215705 | A24 |  | 1575 | 1.1 | 1732.5 | 222
2012-03-05 | A34- Bidim 6.00M x150M. Inv No - CD201215804 | A34 |  | 1 | 4196 | 4196 | 222
2012-03-29 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 222
2012-03-29 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-04-10 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 222
2012-04-10 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 222
2012-04-10 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 222
2012-04-11 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 222
2012-04-11 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 222
2012-04-12 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-04-12 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-04-12 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-04-13 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-04-13 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-04-13 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-04-13 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-04-14 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-04-16 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-04-16 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-04-17 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-04-17 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-04-24 | Bidin A34 6.00M X 150M. Inv No - CD201219162 | A34 |  | 1 | 9026.25 | 9026.25 | 222
2012-04-24 | Bidim A34 6.00M X 150M. Inv No - CD201219166 | A34 |  | 1 | 5895 | 5895 | 222
2012-04-27 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 222
2012-04-27 | Labour Hire | Labour | hr | 2.5 | 48 | 120 | 222
2012-04-27 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 222
2012-04-27 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 222
2012-04-27 | Mcdowall Earthmoving (Backhoe Hire ) | McDowall Earthmoving | hr | 1 | 90 | 90 | 222
2012-04-27 | New Holland Compact Grader - No Operator | NH Grader | hr | 2 | 25.78 | 51.56 | 222
2012-04-27 | Water Truck Hire | Talbots | hr | 8 | 95 | 760 | 222
2012-05-02 | Inv No - CD201219684 | SS30 3.80M x 100M |  | 1710 | 4.25 | 7267.5 | 222
2012-05-02 | Freight Charges. SS30 3.80M x 100M. Inv No - CD201219682 | SS30 3.80M x 100M |  | 1 | 307.5 | 307.5 | 222
2012-05-04 | Taylors Earthmoving (3t) | Taylors Earthmoving | hr | 4 | 85 | 340 | 222
2012-05-17 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 222
2012-05-17 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 222
2012-05-17 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 222
2012-05-17 | Labour Hire | Labour | hr | 1 | 48 | 48 | 222
2012-05-18 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 222
2012-05-18 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 222
2012-05-18 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 222
2012-05-18 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 222
2012-05-18 | Labour Hire | Labour | hr | 1 | 48 | 48 | 222
2012-05-19 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 222
2012-05-19 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 222
2012-05-19 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 222
2012-05-24 | Freight Charges. Inv No - CD201221417 | A34 |  | 1 | 90 | 90 | 222
2012-05-24 | 3.80M x 75M Tensar Triax Grid. Inv No - CD201221418 | Tensar Triax Grid |  | 2280 | 4.6 | 10488 | 222
2012-06-18 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-06-18 | Labour Hire | Labour | hr | 2 | 48 | 96 | 222
2012-06-18 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-06-18 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-06-20 | 3.80M x 75M tensar Triax Grid. Inv No - CD201223240 | Tensar Triax Grid |  | 1 | 19765 | 19765 | 222
2012-06-20 | 3.80M x 75M tensar Triax Grid. Inv No - CD201223247 | Tensar Triax Grid |  | 855 | 4.6 | 3933 | 222
2012-07-03 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-07-03 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 222
2012-07-17 | A34-Bidim 6.00M x150M. Inv No - CD201301199 | A34 |  | 2 | 1466 | 2932 | 222
2012-08-16 | A29-Bidim 6.00M x 150M. Inv No - CD201303396 | A29 |  | 1 | 1354 | 1354 | 222
2012-08-20 | Plant Operator-Labour Hire | Labour | hr | 2.5 | 48 | 120 | 222
2012-09-06 | A29-Bidim 6.00M x 150M. Inv No - CD201304934. | A29 |  | 1 | 1326.5 | 1326.5 | 222
| Subtotal for 222 |  |  |  |  | 129487.46
Portfolio WBS 901
2011-10-12 | Work Place Health & Safety Officer | WHSO | week | 4 | 45 | 180 | 901
2011-10-19 | Work Place Health & Safety Officer | WHSO | week | 5 | 45 | 225 | 901
2012-11-30 | Technical Officer. Week Ending 24/2/13 | Technical Officer |  | 1.5 | 46 | 69 | 901
2012-11-30 | Technical Officer. Week Ending 3/3/13 | Technical Officer |  | 2 | 46 | 92 | 901
2012-11-30 | Technical Officer. Week Ending 17/3/13 | Technical Officer |  | 1 | 46 | 46 | 901
2012-11-30 | Technical Officer. Week Ending 12/5/13 | Technical Officer |  | 1 | 46 | 46 | 901
| Subtotal for 901 |  |  |  |  | 658
Portfolio WBS 902
2011-10-10 | Project Supervisor | Foreman | day | 1 | 580 | 580 | 902
2011-10-11 | Project Supervisor | Foreman | day | 1 | 580 | 580 | 902
2011-10-12 | Project Supervisor | Foreman | day | 1 | 580 | 580 | 902
2011-10-13 | Project Supervisor | Foreman | day | 1 | 580 | 580 | 902
2011-10-14 | Project Supervisor | Foreman | day | 1 | 580 | 580 | 902
2011-10-17 | Project Supervisor | Foreman | day | 1 | 580 | 580 | 902
2011-10-18 | ( Foreman ) | Foreman | day | 1 | 580 | 580 | 902
2011-10-18 | Ford Ranger 4WD Utility | Ford Utility | hr | 6 | 11.67 | 70.02 | 902
2011-10-18 | Project Supervisor | Supervisor | hr | 7 | 71.81 | 502.67 | 902
2011-10-19 | Project Supervisor | Supervisor | hr | 15 | 71.81 | 1077.15 | 902
2011-10-19 | Ford Ranger 4WD Utility | Ford Utility | hr | 9 | 11.67 | 105.03 | 902
2011-10-19 | ( Foreman ) | Foreman | day | 1 | 580 | 580 | 902
2011-10-19 | ( Foreman ) | Foreman | day | 1 | 580 | 580 | 902
2011-10-21 | Project Supervisor | Supervisor | hr | 6 | 71.81 | 430.86 | 902
2011-10-22 | Project Supervisor | Supervisor | hr | 2 | 71.81 | 143.62 | 902
2011-10-24 | Ford Ranger 4WD Utility | Ford Utility | hr | 10 | 11.67 | 116.7 | 902
2011-10-24 | Project Supervisor | Supervisor | hr | 10.5 | 71.81 | 754.005 | 902
2011-10-24 | ( Foreman ) | Foreman | day | 1 | 580 | 580 | 902
2011-10-25 | Ford Ranger 4WD Utility | Ford Utility | hr | 10 | 11.67 | 116.7 | 902
2011-10-25 | ( Foreman ) | Foreman | day | 1 | 580 | 580 | 902
2011-10-26 | Ford Ranger 4WD Utility | Ford Utility | hr | 5 | 11.67 | 58.35 | 902
2011-10-26 | ( Foreman ) | Foreman | day | 1 | 580 | 580 | 902
2011-10-27 | ( Foreman ) | Foreman | day | 1 | 580 | 580 | 902
2011-10-27 | Ford Ranger 4WD Utility | Ford Utility | hr | 10 | 11.67 | 116.7 | 902
2011-10-28 | ( Foreman ) | Foreman | day | 1 | 580 | 580 | 902
2011-10-28 | Ford Ranger 4WD Utility | Ford Utility | hr | 5 | 11.67 | 58.35 | 902
2011-10-29 | Ford Ranger 4WD Utility | Ford Utility | hr | 5 | 11.67 | 58.35 | 902
2011-10-29 | ( Foreman ) | Foreman | day | 1 | 580 | 580 | 902
2011-10-29 | Ford Ranger 4WD Utility | Ford Utility | hr | 5 | 11.67 | 58.35 | 902
2011-10-29 | ( Foreman ) | Foreman | day | 1 | 580 | 580 | 902
2011-10-31 | ( Foreman ) | Foreman | day | 1 | 580 | 580 | 902
2011-11-01 | ( Foreman ) | Foreman | day | 1 | 580 | 580 | 902
2011-11-02 | Foreman | Foreman | day | 0.6 | 580 | 348 | 902
2011-11-09 | Project Supervisor | Supervisor | hr | 5 | 71.81 | 359.05 | 902
2011-11-14 | Project Supervisor | Supervisor | hr | 8.5 | 71.81 | 610.385 | 902
2011-11-15 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2011-11-16 | Project Supervisor | Supervisor | hr | 6 | 71.81 | 430.86 | 902
2011-11-17 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2011-11-18 | Project Supervisor | Supervisor | hr | 8.5 | 71.81 | 610.385 | 902
2011-11-19 | Project Supervisor | Supervisor | hr | 7.5 | 71.81 | 538.575 | 902
2011-11-21 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2011-11-22 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2011-11-23 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2011-11-24 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2011-11-25 | Project Supervisor | Supervisor | hr | 4 | 71.81 | 287.24 | 902
2011-11-28 | Project Supervisor | Supervisor | hr | 3 | 71.81 | 215.43 | 902
2011-11-29 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2011-11-30 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2011-12-01 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2011-12-02 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2011-12-05 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2011-12-07 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2011-12-08 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2011-12-09 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2011-12-12 | Project Supervisor | Supervisor | hr | 5.5 | 71.81 | 394.955 | 902
2012-01-10 | Project Supervisor | Supervisor | hr | 5 | 71.81 | 359.05 | 902
2012-01-11 | Project Supervisor | Supervisor | hr | 4.5 | 71.81 | 323.145 | 902
2012-01-12 | Project Supervisor | Supervisor | hr | 5 | 71.81 | 359.05 | 902
2012-01-13 | Project Supervisor | Supervisor | hr | 5.5 | 71.81 | 394.955 | 902
2012-01-16 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-01-18 | Project Supervisor | Supervisor | hr | 7.5 | 71.81 | 538.575 | 902
2012-01-19 | Project Supervisor | Supervisor | hr | 7.5 | 71.81 | 538.575 | 902
2012-01-20 | Project Supervisor | Supervisor | hr | 6.5 | 71.81 | 466.765 | 902
2012-01-21 | Project Supervisor | Supervisor | hr | 6.5 | 71.81 | 466.765 | 902
2012-01-23 | Project Supervisor | Supervisor | hr | 5 | 71.81 | 359.05 | 902
2012-01-24 | Project Supervisor | Supervisor | hr | 5 | 71.81 | 359.05 | 902
2012-01-25 | Project Supervisor | Supervisor | hr | 4 | 71.81 | 287.24 | 902
2012-01-27 | Project Supervisor | Supervisor | hr | 6 | 71.81 | 430.86 | 902
2012-01-28 | Project Supervisor | Supervisor | hr | 4.5 | 71.81 | 323.145 | 902
2012-01-30 | Project Supervisor | Supervisor | hr | 3 | 71.81 | 215.43 | 902
2012-01-31 | Project Supervisor | Supervisor | hr | 7 | 71.81 | 502.67 | 902
2012-02-01 | Project Supervisor | Supervisor | hr | 7 | 71.81 | 502.67 | 902
2012-02-02 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-02-03 | Project Supervisor | Supervisor | hr | 6.5 | 71.81 | 466.765 | 902
2012-02-06 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-02-07 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-02-08 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-02-10 | Project Supervisor | Supervisor | hr | 8.5 | 71.81 | 610.385 | 902
2012-02-11 | Project Supervisor | Supervisor | hr | 5 | 71.81 | 359.05 | 902
2012-02-13 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-02-14 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-02-16 | Project Supervisor | Supervisor | hr | 8.5 | 71.81 | 610.385 | 902
2012-02-17 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-02-20 | Project Supervisor | Supervisor | hr | 8.5 | 71.81 | 610.385 | 902
2012-02-23 | Project Supervisor | Supervisor | hr | 3 | 71.81 | 215.43 | 902
2012-02-24 | Project Supervisor | Supervisor | hr | 6 | 71.81 | 430.86 | 902
2012-02-28 | Project Supervisor | Supervisor | hr | 4 | 71.81 | 287.24 | 902
2012-02-29 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-03-01 | Project Supervisor | Supervisor | hr | 10.5 | 71.81 | 754.005 | 902
2012-03-02 | Project Supervisor | Supervisor | hr | 8.5 | 71.81 | 610.385 | 902
2012-03-03 | Project Supervisor | Supervisor | hr | 3 | 71.81 | 215.43 | 902
2012-03-05 | Project Supervisor | Supervisor | hr | 6 | 71.81 | 430.86 | 902
2012-03-06 | Project Supervisor | Supervisor | hr | 6 | 71.81 | 430.86 | 902
2012-03-07 | Project Supervisor | Supervisor | hr | 6 | 71.81 | 430.86 | 902
2012-03-08 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-03-09 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-03-10 | Project Supervisor | Supervisor | hr | 5 | 71.81 | 359.05 | 902
2012-03-12 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-03-13 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-03-14 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-03-15 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-03-16 | Project Supervisor | Supervisor | hr | 6 | 71.81 | 430.86 | 902
2012-03-19 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-03-20 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-03-21 | Project Supervisor | Supervisor | hr | 5.5 | 71.81 | 394.955 | 902
2012-03-22 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-03-23 | Project Supervisor | Supervisor | hr | 7.5 | 71.81 | 538.575 | 902
2012-03-26 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-03-27 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-03-28 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-03-29 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-03-30 | Project Supervisor | Supervisor | hr | 10.5 | 71.81 | 754.005 | 902
2012-03-31 | Project Supervisor | Supervisor | hr | 6 | 71.81 | 430.86 | 902
2012-04-01 | Project Supervisor | Supervisor | hr | 3 | 71.81 | 215.43 | 902
2012-04-02 | Project Supervisor | Supervisor | hr | 3 | 71.81 | 215.43 | 902
2012-04-03 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-04-04 | Project Supervisor | Supervisor | hr | 10.5 | 71.81 | 754.005 | 902
2012-04-05 | Project Supervisor | Supervisor | hr | 10.5 | 71.81 | 754.005 | 902
2012-04-10 | Project Supervisor | Supervisor | hr | 11.5 | 71.81 | 825.815 | 902
2012-04-11 | Project Supervisor | Supervisor | hr | 10.5 | 71.81 | 754.005 | 902
2012-04-12 | Project Supervisor | Supervisor | hr | 11 | 71.81 | 789.91 | 902
2012-04-13 | Project Supervisor | Supervisor | hr | 11.5 | 71.81 | 825.815 | 902
2012-04-14 | Project Supervisor | Supervisor | hr | 7 | 71.81 | 502.67 | 902
2012-04-16 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-04-17 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-04-18 | Project Supervisor | Supervisor | hr | 10.5 | 71.81 | 754.005 | 902
2012-04-19 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-04-20 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-04-23 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-04-24 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-04-26 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-04-27 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-04-30 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-05-01 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-05-03 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-05-04 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-05-05 | Project Supervisor | Supervisor | hr | 4 | 71.81 | 287.24 | 902
2012-05-08 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-05-09 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-05-10 | Project Supervisor | Supervisor | hr | 6.5 | 71.81 | 466.765 | 902
2012-05-11 | Project Supervisor | Supervisor | hr | 6.5 | 71.81 | 466.765 | 902
2012-05-14 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-05-15 | Project Supervisor | Supervisor | hr | 1 | 71.81 | 71.81 | 902
2012-05-16 | Project Supervisor | Supervisor | hr | 8.5 | 71.81 | 610.385 | 902
2012-05-17 | Project Supervisor | Supervisor | hr | 11.5 | 71.81 | 825.815 | 902
2012-05-18 | Project Supervisor | Supervisor | hr | 11.5 | 71.81 | 825.815 | 902
2012-05-19 | Project Supervisor | Supervisor | hr | 7 | 71.81 | 502.67 | 902
2012-05-21 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-05-22 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-05-23 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-05-24 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-05-25 | Project Supervisor | Supervisor | hr | 6.5 | 71.81 | 466.765 | 902
2012-05-28 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-05-29 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-05-30 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-05-31 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-06-01 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-06-02 | Project Supervisor | Supervisor | hr | 4 | 71.81 | 287.24 | 902
2012-06-04 | Project Supervisor | Supervisor | hr | 11.5 | 71.81 | 825.815 | 902
2012-06-05 | Project Supervisor | Supervisor | hr | 10.5 | 71.81 | 754.005 | 902
2012-06-06 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-06-07 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-06-08 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-06-12 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-06-13 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-06-14 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-06-15 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-06-16 | Project Supervisor | Supervisor | hr | 6.5 | 71.81 | 466.765 | 902
2012-06-18 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-06-19 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-06-20 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-06-21 | Project Supervisor | Supervisor | hr | 8.5 | 71.81 | 610.385 | 902
2012-06-25 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-06-26 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-06-27 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-06-28 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-06-29 | Project Supervisor | Supervisor | hr | 7 | 71.81 | 502.67 | 902
2012-06-30 | Project Supervisor | Supervisor | hr | 4 | 71.81 | 287.24 | 902
2012-07-02 | Project Supervisor | Supervisor | hr | 12.561 | 71.81 | 902.0054 | 902
2012-07-03 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-07-04 | Project Supervisor | Supervisor | hr | 9 | 71.81 | 646.29 | 902
2012-07-05 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-07-06 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-07-09 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-07-10 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-07-11 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-07-12 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-07-13 | Project Supervisor | Supervisor | hr | 6.5 | 71.81 | 466.765 | 902
2012-07-16 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-07-17 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-07-18 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-07-19 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-07-20 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-07-21 | Project Supervisor | Supervisor | hr | 7 | 71.81 | 502.67 | 902
2012-07-23 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-07-24 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-07-25 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-07-26 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-07-27 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-07-28 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-07-30 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-07-31 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-08-01 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-08-02 | Project Supervisor | Supervisor | hr | 10.5 | 71.81 | 754.005 | 902
2012-08-03 | Project Supervisor | Supervisor | hr | 10.5 | 71.81 | 754.005 | 902
2012-08-04 | Project Supervisor | Supervisor | hr | 6.5 | 71.81 | 466.765 | 902
2012-08-06 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-08-07 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-08-08 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-08-09 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-08-10 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-08-11 | Project Supervisor | Supervisor | hr | 6.5 | 71.81 | 466.765 | 902
2012-08-13 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-08-14 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-08-15 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-08-16 | Project Supervisor | Supervisor | hr | 10.5 | 71.81 | 754.005 | 902
2012-08-17 | Project Supervisor | Supervisor | hr | 10.5 | 71.81 | 754.005 | 902
2012-08-18 | Project Supervisor | Supervisor | hr | 4.5 | 71.81 | 323.145 | 902
2012-08-19 | Project Supervisor | Supervisor | hr | 5 | 71.81 | 359.05 | 902
2012-08-20 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-08-21 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-08-22 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-08-23 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-08-24 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-08-27 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-08-28 | Project Supervisor | Supervisor | hr | 1 | 71.81 | 71.81 | 902
2012-08-29 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-08-31 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-09-01 | Project Supervisor | Supervisor | hr | 6.5 | 71.81 | 466.765 | 902
2012-09-03 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-09-04 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-09-05 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-09-06 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-09-07 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-09-10 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-09-11 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-09-11 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-09-12 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-09-13 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-09-17 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-09-18 | Project Supervisor | Supervisor | hr | 9 | 71.81 | 646.29 | 902
2012-09-19 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-09-20 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-09-21 | Project Supervisor | Supervisor | hr | 8.5 | 71.81 | 610.385 | 902
2012-09-24 | Project Supervisor | Supervisor | hr | 8.5 | 71.81 | 610.385 | 902
2012-09-25 | Project Supervisor | Supervisor | hr | 8.5 | 71.81 | 610.385 | 902
2012-09-26 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-09-27 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-09-28 | Project Supervisor | Supervisor | hr | 9.5 | 71.81 | 682.195 | 902
2012-10-02 | Project Supervisor | Supervisor | hr | 10 | 71.81 | 718.1 | 902
2012-10-03 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-10-04 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-10-05 | Project Supervisor | Supervisor | hr | 6.5 | 71.81 | 466.765 | 902
2012-10-08 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-10-09 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-10-10 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-10-11 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-10-12 | Project Supervisor | Supervisor | hr | 6.5 | 71.81 | 466.765 | 902
2012-10-15 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-10-17 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-10-18 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-10-19 | Project Supervisor | Supervisor | hr | 6.5 | 71.81 | 466.765 | 902
2012-10-22 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
| Subtotal for 902 |  |  |  |  | 150862.3304
Portfolio WBS 903
2011-10-06 | fire Extinguisher Dock - 082286946 | Small Tools |  | 1 | 73.46 | 73.46 | 903
2011-10-11 | Bolt & Nut Hex, Tool Box Jumbo Dock - 08293497 | Small Tools |  | 1 | 138.25 | 138.25 | 903
2011-10-17 | Makita Friver Drill Inv -21263156 | Small Tools |  | 1 | 291.13 | 291.13 | 903
2011-10-18 | Shackle, Notice board Inv - 21263190 | Small Tools |  | 1 | 34.59 | 34.59 | 903
2011-10-19 | Hessian Sandbags Inv - 8301784 | Small Tools |  | 1 | 52.65 | 52.65 | 903
2011-10-27 | Petrolatkum Dux Tape Inv - 1588247 | Small Tools |  | 5 | 23.1 | 115.5 | 903
2011-10-31 | Weed Mat Pins Inv - 21263621 | Small Tools |  | 1 | 45 | 45 | 903
2011-11-02 | Petrolatum Dux Tape Inv - 8311782 | Small Tools |  | 5 | 23.1 | 115.5 | 903
2011-11-03 | DWV Junction, Duct Tape Inv - 21263803 | Small Tools |  | 1 | 75.81 | 75.81 | 903
2011-11-04 | Sledge Hammer,Club Wood Hammer INv - 21263839 | Small Tools |  | 1 | 110.63 | 110.63 | 903
2011-11-04 | Barrow Kelso Inv - 21263831 | Small Tools |  | 1 | 285.4 | 285.4 | 903
2011-11-05 | Hoe Mortar Inv - 21263849 | Small Tools |  | 1 | 62.3 | 62.3 | 903
2011-11-19 | Office Floor Rent Receipt No 581184 | Accommodation |  | 1 | 1320 | 1320 | 903
2012-01-18 | Proserpine Shed Rent - 1/1/12 to 1/2/12 | Crib Facilities |  | 1 | 1452 | 1452 | 903
2012-01-31 | Spring Water 15 Lts. Inv No - Feb | Spring Water |  | 8 | 12.5 | 100 | 903
2012-02-14 | Spring Water 15 Lts. Inv No - Feb | Spring Water |  | 8 | 12.5 | 100 | 903
2012-02-20 | Monthly Rental on 45-47 Anzac Rd Proserpine. 1/02/2012 to the 29/02/2012. Inv No - 1109 | Crib Facilities |  | 1 | 1320 | 1320 | 903
2012-02-28 | Spring Water 15 Lts. Inv No - Feb | Spring Water |  | 10 | 12.5 | 125 | 903
2012-02-28 | Spring Water Cooler Rental 15 Lts. Inv No - Feb | Spring Water |  | 1 | 19.8 | 19.8 | 903
2012-04-05 | Spring Water 15 Lts. Inv No - March | Spring Water |  | 10 | 12.5 | 125 | 903
2012-05-02 | Monthly Rental of 45-47 Anzac Rd Proserpine. 1/5/2012 to the 31/5/2012. | Crib Facilities |  | 1 | 1320 | 1320 | 903
2012-05-25 | Spring Water 15 Lts. Inv No - May | Spring Water |  | 11 | 12.5 | 137.5 | 903
2012-06-05 | Monthly Rental of 45-47 Anzac Rd Proserpine. 1/6/2012 to the 30/6/2012. Inv No 78 | Crib Facilities |  | 1 | 1320 | 1320 | 903
2012-06-23 | Spring Water 15 Lts. Inv No- June | Spring Water |  | 1 | 117.2 | 117.2 | 903
2012-07-29 | Site Office & Tiolet, 1 Pump out during project. 1/7/2012 - 31/7/2012. Inv No - 90 | Crib Facilities |  | 1 | 1320 | 1320 | 903
2012-08-06 | Monthly Rental of 45-47 Anzac Rd Proserpine. 1/08/2012 to 31/08/2012. Inv No - 103 | Crib Facilities |  | 1 | 1320 | 1320 | 903
2012-08-31 | Spring Water 15 Lts. Inv No - Aug | Spring Water |  | 1 | 44 | 44 | 903
2012-09-04 | Monthly Rental of 45-47 Anzac Rd Proserpine. 1/9/12 - 30/9/12. Inv No - 119 | Crib Facilities |  | 1 | 1320 | 1320 | 903
2012-09-21 | Spring Water 15 Lts. | Spring Water |  | 1 | 45.8 | 45.8 | 903
2012-10-02 | 45-47 Anzac Rd Proserpine. 1/10/12 - 31/10/12. Inv No 131 | Crib Facilities |  | 1 | 1320 | 1320 | 903
2012-10-31 | Spring Water 15 Lts. | Spring Water |  | 1 | 149.8 | 149.8 | 903
| Subtotal for 903 |  |  |  |  | 14376.32
Portfolio WBS 904
2011-11-14 | Insurance Brokers Inv - 10958526 | Insurance |  | 1 | 8881.81 | 8881.81 | 904
2011-11-14 | Insurance Brokers Inv - 10958525 | Insurance |  | 1 | 9400 | 9400 | 904
2012-02-29 | Dynapac CC21 Roller. Damage Waiver. Inv No 276343 | Insurance |  | 1 | 612 | 612 | 904
2012-03-30 | Double Drum Roller. Damage Waiver. Inv No - 279430 | Insurance |  | 1 | 563.16 | 563.16 | 904
2012-03-30 | Dynapac CC 21 Roller. Damage Waiver. Inv No - 279426 | Insurance |  | 1 | 684.3 | 684.3 | 904
2012-04-30 | Dynapac CC 21 Roller. Damage Waiver. Inv No - 279426 | Dynapac CC21 Roller |  | 1 | 684 | 684 | 904
2012-04-30 | Dynapac CC 21 Roller. Damage Waiver Hired from the 31/3/2012 - 30/4/2012. Inv No - 283186 | Insurance |  | 1 | 756 | 756 | 904
2012-05-10 | Pad Foot Roller - Dry. Damage Waiver. Inv No - 284764 | Insurance |  | 1 | 219 | 219 | 904
2012-06-06 | Damage Waiver Padfoot Roller & Mack Truck. Inv No - 288519 | Insurance |  | 1 | 151.2 | 151.2 | 904
2012-06-29 | Damage Waiver, Vibrating Rammer. Inv No - 290647 | Insurance |  | 1 | 99.84 | 99.84 | 904
2012-06-30 | Damage Waiver, Dynapac CC21 Roller. Inv No - 291189 | Insurance |  | 1 | 792 | 792 | 904
2012-06-30 | Damage Waiver Double Drum Roller. Inv No - 291194 | Insurance |  | 1 | 592.8 | 592.8 | 904
2012-07-05 | Damage Waiver , Generator. Hired 3/7/2012 - 5/7/2012. Inv No - 292252 | Insurance |  | 1 | 43.92 | 43.92 | 904
2012-07-31 | Damage Waiver. Dynapac CC21 Roller. Hired 30/6/12 - 31/7/12. Inv No - 295257 | Insurance |  | 1 | 612 | 612 | 904
2012-07-31 | Damage Waiver. Padfoot Roller. Hired 7/7/12 - 31/7/12. Inv No - 295263 | Insurance |  | 1 | 468 | 468 | 904
2012-07-31 | Damage Waiver. Double Drum Roller. Inv No - 295261 | Insurance |  | 1 | 533.52 | 533.52 | 904
2012-08-06 | Damage Waiver. Generator. Hired 2/8/12 - 6/8/12. Inv No - 296297 | Insurance |  | 1 | 43.92 | 43.92 | 904
2012-08-15 | Damage Waiver. Vibrating Rammer. Inv No - 297270 | Insurance |  | 1 | 48.24 | 48.24 | 904
2012-08-24 | Damage Waiver. 13T Smooth Drum Roller. Hired 30/6/2012 - 16/7/2012. Inv No - 293883 | Insurance |  | 1 | 396 | 396 | 904
2012-08-30 | Damage Waiver. Padfoot Roller. Inv No - 298887 | Insurance |  | 1 | 780 | 780 | 904
2012-08-30 | Damage Waiver, Multityre Roller. Inv No - 303115 | Insurance |  | 1 | 75.6 | 75.6 | 904
2012-08-31 | Insurance Brokers. Quickcut Saw & Blade. Inv No - 299463 | Insurance |  | 1 | 72.96 | 72.96 | 904
2012-08-31 | Damage Waiver. Double Drum Roller. Inv No - 299459 | Insurance |  | 1 | 770.64 | 770.64 | 904
2012-08-31 | Damage Waiver. Dynapac CC21 Roller. Inv No - 299458 | Insurance |  | 1 | 936 | 936 | 904
2012-08-31 | Damage Wiaver. Stackable Barriers. Inv No - 299462 | Insurance |  | 1 | 77.14 | 77.14 | 904
2012-09-10 | Damage Waiver. Quickcut Saw. Inv No - 300862 | Insurance |  | 1 | 91.44 | 91.44 | 904
2012-09-28 | Damage Waiver, Stackable Barriers. Inv No - 302828 | Insurance |  | 1 | 66.85 | 66.85 | 904
2012-09-30 | Damage Waiver. Double Drum Roller. Inv No - 303113 | Insurance |  | 1 | 681.72 | 681.72 | 904
2012-09-30 | Damage Waiver. Solar Traffic Lights. Inv No - 303114 | Insurance |  | 1 | 549.84 | 549.84 | 904
2012-10-04 | Damage Waiver, Compressor. Inv No - 304268 | Insurance |  | 1 | 47.28 | 47.28 | 904
2012-10-04 | Damage Waiver. Traffic Lightrs. Inv No - 304194 | Insurance |  | 1 | 37.92 | 37.92 | 904
| Subtotal for 904 |  |  |  |  | 29769.1
Portfolio WBS 905
2011-11-16 | Cement QCL 20, 20kg Bags Inv No 21264228 | Small Tools |  | 1 | 180.4 | 180.4 | 905
2011-11-17 | PVC Pipe PVC Slovent Cement Inv No 21264281 | Small Tools |  | 1 | 44.09 | 44.09 | 905
2011-11-17 | Saw Hand Jack Inv No - 21264284 | Small Tools |  | 1 | 15.04 | 15.04 | 905
2011-11-17 | Plumbers Pals Bolted Trap Scre Inv No 21264285 | Small Tools |  | 1 | 90.13 | 90.13 | 905
2011-11-17 | Pipe Connectors Inv No - 21264303 | Small Tools |  | 1 | 14.59 | 14.59 | 905
2011-11-24 | Medalist SQ Mouth Shovel, Batteries Inv No 21264051 | Small Tools |  | 1 | 104.59 | 104.59 | 905
2011-11-25 | Ramset Anchors, Cable Ties Inv No 21264660 | Small Tools |  | 1 | 113.54 | 113.54 | 905
2011-11-26 | Ramset Dynabolts Inv No - 21264699 | Small Tools |  | 1 | 16.18 | 16.18 | 905
2011-11-30 | Brush Paint,Dustpan Inv No 21264839 | Small Tools |  | 1 | 17.4 | 17.4 | 905
2011-11-30 | Bug Spray, Cleaners, Polyglazse,Mop&Bucket Ect Inv No- 21264836 | Small Tools |  | 1 | 99.09 | 99.09 | 905
2011-12-08 | Steel Round Dowel Galv Inv No - 21265186 | Small Tools |  | 1 | 27.5 | 27.5 | 905
2011-12-08 | Garden Edging Icon, Steel Plastic Chairs. Inv No - 21265188 | Small Tools |  | 1 | 62 | 62 | 905
2011-12-19 | Straps Octopus, Drill Bit Inv No - 21265586 | Small Tools |  | 1 | 28.86 | 28.86 | 905
2011-12-20 | Rainwater Pit, Driver nuts, cable ties, spade Inv No 21265634 | Small Tools |  | 1 | 382.72 | 382.72 | 905
2011-12-20 | BBQ Jumbuck Inv No - 8467/26347 | Small Tools |  | 1 | 79.09 | 79.09 | 905
2012-01-13 | Camlock, Tread tape. Inv No- 134266 | Small Tools |  | 1 | 56.73 | 56.73 | 905
2012-01-16 | Nail Belt Steel. Inv No - 08419297 | Small Tools |  | 1 | 93.98 |  | 905
2012-01-18 | Cable Ties. Inv No - 21266452 | Small Tools |  | 1 | 20.77 | 20.77 | 905
2012-01-20 | Cement. Inv No - 21266518 | Small Tools |  | 1 | 36.09 | 36.09 | 905
2012-01-27 | Spray & Mark. Inv No - 21266734 | Small Tools |  | 1 | 64.9 | 64.9 | 905
2012-01-27 | Plumbers Pals. Inv No - 20433778 | Small Tools |  | 1 | 90.136 | 90.136 | 905
2012-01-27 | Plumbers Pals Inv no - 20433778 | Small Tools |  | 1 | 90.13 | 90.13 | 905
2012-01-31 | Bricklayers Line Tape measure, Safeyt Barriers, Fence Post Holes Shovel Ect. Inv No - 21266818 | Small Tools |  | 1 | 216.09 | 216.09 | 905
2012-02-09 | DWV Juntion. Inv No - 21267177. | Small Tools |  | 1 | 34.13 | 34.13 | 905
2012-02-10 | Dutch Hoe. Inv No - 600007 | Small Tools |  | 1 | 19 | 19 | 905
2012-02-10 | Poly head, Hammer. Inv No - 600023 | Small Tools |  | 1 | 45.54 | 45.54 | 905
2012-02-14 | Safety Mesh Barrier. Inv No - 08458546 | Small Tools |  | 1 | 163.63 | 163.63 | 905
2012-02-14 | Fence Posts. Inv No - 08458546 | Small Tools |  | 1 | 212.18 | 212.18 | 905
2012-02-14 | Cap Reo 12mm to 16mm. Inv No 08458546 | Small Tools |  | 1 | 27.2 | 27.2 | 905
2012-02-16 | Hard Hat Protector, Cement QCL Type. Inv No - 21267400 | Small Tools |  | 1 | 114.45 | 114.45 | 905
2012-02-23 | Cement QCL Type. Inv No - 21267667 | Small Tools |  | 1 | 362.72 | 362.72 | 905
2012-02-29 | Cement QCL - 20 kg Bags. Inv No - 21267819 | Small Tools |  | 1 | 90.68 | 90.68 | 905
2012-02-29 | Joining Tape. Inv No - 21267829 | Small Tools |  | 1 | 4.5 | 4.5 | 905
2012-03-01 | Chin, Hook Cup. Inv No - 21267852 | Small Tools |  | 1 | 14.77 | 14.77 | 905
2012-03-02 | Plumbers Pals Bolted Tape Screws. Inv No - 20435125 | Small Tools |  | 1 | 126.13 | 126.13 | 905
2012-03-02 | PVC Fit. Inv No 21267925 | Small Tools |  | 1 | 1.59 | 1.59 | 905
2012-03-02 | Steel Bar Chairs. Hand Saw. Inv No - 21267905 | Small Tools |  | 1 | 100.9 | 100.9 | 905
2012-03-02 | Tape Measure. PVC Pipe, Ect. Inv No - 21267901 | Small Tools |  | 1 | 164.09 | 164.09 | 905
2012-03-02 | PVC Fit . Inv No - 21267903 | Small Tools |  | 1 | 4.27 | 4.27 | 905
2012-03-05 | Garbage bags, Hack Saw Black, Spray & Mark. Inv No - 2126981 | Small Tools |  | 1 | 125.04 | 125.04 | 905
2012-03-08 | Cable Ties. Inv No - 21268154 | Small Tools |  | 1 | 13.86 | 13.86 | 905
2012-03-23 | Solvent cement, DWV Juntion.Bend, Push on Cap. Inv No - 20435857 | Small Tools |  | 1 | 255.22 | 255.22 | 905
2012-03-23 | Cable Ties. Inv No - 21268613 | Small Tools |  | 1 | 18.54 | 18.54 | 905
2012-03-23 | Bolt Cutter. Inv No - 21268595 | Small Tools |  | 1 | 59.68 | 59.68 | 905
2012-03-26 | Diamond Blade 400mm. Trans No - 08511151 | Small Tools |  | 1 | 156.36 | 156.36 | 905
2012-03-27 | DWV Bend. Inv No - 21268720 | Small Tools |  | 1 | 13.72 | 13.72 | 905
2012-03-27 | PVC Pipe. Inv No - 21268735 | Small Tools |  | 1 | 24.59 | 24.59 | 905
2012-03-27 | DWV Bend. Inv No - 21268739 | Small Tools |  | 1 | 2.5 | 2.5 | 905
2012-03-27 | DWV Invert Level Tapper, Jointing Tape. Inv No - 20435981 | Small Tools |  | 1 | 56.95 | 56.95 | 905
2012-03-27 | Tap Measures. Inv No - 21268740 | Small Tools |  | 1 | 48.59 | 48.59 | 905
2012-03-29 | Rigger Gloves, Buckets, Cable Ties, Crayons, Gumboots, Shovel. Inv No - 21268825 | Small Tools |  | 1 | 112.13 | 112.13 | 905
2012-04-02 | Steel Bar, Cable Ties, Fence Post, Barricade Mesh. Inv No - 21268968 | Small Tools |  | 1 | 433.81 | 433.81 | 905
2012-04-03 | Line Trimmer. Inv No - 21268991 | Small Tools |  | 1 | 11.4 | 11.4 | 905
2012-04-03 | Weed Mat, Fence Post, Mesh. Inv No - 21269003 | Small Tools |  | 1 | 214.72 | 214.72 | 905
2012-04-04 | Bair Chairs, Shovel Post. Inv No - 21270059 | Small Tools |  | 1 | 62.95 | 62.95 | 905
2012-04-05 | Fence Posts,Enamel Matt, Paint Brushes. Inv No - 21269123 | Small Tools |  | 1 | 97.81 | 97.81 | 905
2012-04-05 | Cement 20 kg, Mineral Turps . Inv No - 21269129 | Small Tools |  | 1 | 368.72 | 368.72 | 905
2012-04-10 | Fence Post, Safety Barrier Netting. Inv No - 21269197 | Small Tools |  | 1 | 224.22 | 224.22 | 905
2012-04-11 | Trenching Shovel. Inv No - 21269233 | Small Tools |  | 1 | 66.72 | 66.72 | 905
2012-04-11 | Rechargeable batteries, cable Ties, Toilet paper. Inv No - 21269226 | Small Tools |  | 1 | 90.36 | 90.36 | 905
2012-04-12 | Deformed Steel. Inv No - 21269268 | Small Tools |  | 1 | 128.86 | 128.86 | 905
2012-04-13 | Tool Box Professional, Knife Retractable. Inv No - 1620161 | Small Tools |  | 1 | 236.63 | 236.63 | 905
2012-04-14 | Cable Ties, Fiesta HC Plates Set, Bromms. Inv No - 21269350 | Small Signs |  | 1 | 45.72 | 45.72 | 905
2012-04-18 | 20kg Cement, Diamond Blade. Trans No - 08539846 | Small Tools |  | 1 | 482.82 | 482.82 | 905
2012-04-20 | Dowl Galv Steel. Inv No - 20436890 | Small Tools |  | 1 | 171.81 | 171.81 | 905
2012-04-20 | Deformed Steel. Inv No - 21269593 | Small Tools |  | 1 | 107.4 | 107.4 | 905
2012-04-30 | Bags Hessian Sandbags. Inv No - 8557960 | Small Tools |  | 1 | 52.73 | 52.73 | 905
2012-04-30 | Cement, Duct Tape, PVC Pipe, Inv No - 21269851 | Small Tools |  | 1 | 119.68 | 119.68 | 905
2012-04-30 | DWV Coupling, DWV Coupling, Solvent Cement. Inv No - 21269835 | Small Tools |  | 1 | 33.54 | 33.54 | 905
2012-05-01 | Hessian Sandbags. Inv No - 08559199 | Small Tools |  | 1 | 52.72 | 52.72 | 905
2012-05-04 | Bar Chairs, Shovels. Inv No - 21270059 | Small Tools |  | 1 | 62.95 | 62.95 | 905
2012-05-11 | Tape Measure, Cable Ties. Inv No - 21270242 | Small Tools |  | 1 | 36.04 | 36.04 | 905
2012-05-14 | Bair Chair, Spray & Mark Paint. Inv No - 130960 | Small Tools |  | 1 | 93.95 | 93.95 | 905
2012-05-15 | Wrecking Bar, Adjustable Wrench,Hammer, Fence Barricade & Exterior Ply. Inv No - 21270391 | Small Tools |  | 1 | 140.22 | 140.22 | 905
2012-05-22 | Cable Ties, Cement, Rake Handle. Inv No - 21270630 | Small Tools |  | 1 | 141.9 | 141.9 | 905
2012-05-24 | Spray & Mark Paint. Inv No - 20438134 | Small Tools |  | 1 | 72.86 | 72.86 | 905
2012-05-24 | Hydraflume Tubing. Inv No - 21270737 | Small Tools |  | 1 | 214.77 | 214.77 | 905
2012-05-24 | Jointing Tape. Inv No - 21270727 | Small Tools |  | 1 | 13.45 | 13.45 | 905
2012-05-24 | Cleaning Wipes Hand Wash, Disinfectand, Toilet Paper. Inv No - 21270712 | Small Tools |  | 1 | 35.045 | 35.045 | 905
2012-05-30 | Cable Ties, Barier Plastic. Inv No - 21270929 | Small Tools |  | 1 | 31.77 | 31.77 | 905
2012-06-07 | Drill Bits. Inv No - 21271181 | Small Tools |  | 1 | 59.5 | 59.5 | 905
2012-06-12 | Jointing Tape, Cable Ties, Barricade Mesh, PVC Pipe. Inv No - 21271277 | Small Tools |  | 1 | 142.95 | 142.95 | 905
2012-06-15 | Cable Ties, Barricade Mesh. Inv No - 21271419 | Small Tools |  | 1 | 126 | 126 | 905
2012-06-16 | Cable Ties. Inv No 21271442 | Small Tools |  | 1 | 27.68 | 27.68 | 905
2012-06-18 | Weed Mat Pins, Cable Ties. Inv No - 21271520 | Small Tools |  | 1 | 84 | 84 | 905
2012-06-19 | N32 Concrete. Inv No - 10140 | N32 |  | 1 | 353.55 | 353.55 | 905
2012-06-20 | Tie Downs, Cable Ties, Steel Bar Chairs, Barricade. Ect. Inv No - 21270622 | Small Tools |  | 1 | 375.36 | 375.36 | 905
2012-06-27 | Steel Plastic Bar Chairs. Inv No - 21271836 | Small Tools |  | 1 | 56.09 | 56.09 | 905
2012-06-27 | Poamjoint Stickyback. Inv No - 21271837 | Small Tools |  | 1 | 44.27 | 44.27 | 905
2012-06-28 | PVC Pipe. Inv No - 21271887 | Small Tools |  | 1 | 49.22 | 49.22 | 905
2012-06-28 | PVC Solvent Cement, PVC Fit. Inv No - 21271882 | Small Tools |  | 1 | 24.63 | 24.63 | 905
2012-06-29 | Hand Saw, Diamond Blade. Inv No - 8639217 | Small Tools |  | 1 | 344.6 | 344.6 | 905
2012-07-03 | Jumper Leads 50mm W/Flex 4 Mtrs. Inv No - I-75931 | Small Tools |  | 1 | 176 | 176 | 905
2012-07-06 | Steel Dowel, Ramset, Knife Blade, Cut Wheel. Inv No - 21272156 | Small Tools |  | 1 | 335.81 | 335.81 | 905
2012-07-09 | Steel Dowel, Hammer, Clamp. Inv No - 21272213 | Small Tools |  | 1 | 522.95 | 522.95 | 905
2012-07-24 | Magnesuim Cement, Cement Trowel. Inv No - 21272736 | Small Tools |  | 1 | 70.86 | 70.86 | 905
2012-07-25 | Bar Chairs. Inv No - 231272805 | Small Tools |  | 1 | 47.72 | 47.72 | 905
2012-07-30 | Screws, Saddle Pipe. Inv No - 21272986 | Small Tools |  | 1 | 35.09 | 35.09 | 905
2012-07-30 | Sandbags. Inv No - 21272950 | Small Tools |  | 1 | 9.45 | 9.45 | 905
2012-07-30 | Mini coil rope, Reflective tape. Inv No 21272968 | Small Tools |  | 1 | 39 | 39 | 905
2012-07-30 | Makita Drill. Inv No - 21272943 | Small Tools |  | 1 | 75.4 | 75.4 | 905
2012-08-01 | Spray & Mark Paint. Inv No - 21273048 | Small Tools |  | 1 | 30.36 | 30.36 | 905
2012-08-01 | Screws & Toilet Paper. Inv No - 21273085 | Small Tools |  | 1 | 31.04 | 31.04 | 905
2012-08-02 | Formply structural & Screws. Inv No - 21273101 | Small Tools |  | 1 | 259.68 | 259.68 | 905
2012-08-08 | Sheet Ribbed Mesh, Steel Plastic Bar Chairs. Inv No - 21273288 | Small Tools |  | 1 | 451.5 | 451.5 | 905
2012-08-08 | Fortress Brass Padlock. Inv No - 21273306 | Small Tools |  | 1 | 36.94 | 36.94 | 905
2012-08-15 | Fence Panel. Inv No - 1643367 | Small Tools |  | 2 | 80 | 160 | 905
2012-08-15 | Bolts Hex Head & Bolts. Inv No - 21273531 | Small Tools |  | 1 | 29.31 | 29.31 | 905
2012-08-16 | PVC Fit, Tape Jointing, Spray & Mark, Toilet Paper. Inv No - 21273580 | Small Tools |  | 1 | 75.77 | 75.77 | 905
2012-08-18 | Cup Head Galv Bolt, Landscape Broom. Inv No - 21273643 | Small Tools |  | 1 | 32.13 | 32.13 | 905
2012-08-29 | Bar Chairs & Cable Ties. Inv No - 21273960 | Small Tools |  | 1 | 92.36 | 92.36 | 905
2012-08-29 | Post Hole Shovel. Inv No - 21273963 | Small Tools |  | 1 | 35.27 | 35.27 | 905
2012-09-06 | Mesh, Cable Tiew, Frofessional Level. Inv No - 21274208 | Small Tools |  | 1 | 119 | 119 | 905
2012-09-06 | Mineral Turps. Inv No - 21274216 | Small Tools |  | 1 | 15.7 | 15.7 | 905
2012-09-07 | Gold Aluminuim Number. Inv no 21274249 | Small Tools |  | 1 | 5.863 | 5.863 | 905
2012-09-07 | Small Colourbond Letter Box. Inv No - 20442797 | Small Tools |  | 1 | 21.77 | 21.77 | 905
2012-09-11 | Orange Barricade Mesh. Inv No - 21274361 | Small Tools |  | 1 | 59.95 | 59.95 | 905
2012-09-26 | Mineral Turps & Csr Carle Sealant. Inv No - 21274860 | Small Tools |  | 1 | 84.81 | 84.81 | 905
2012-09-27 | Gloves PVC Chemical & Hoe Swan Steel Shaft. Inv No - 21274864 | Small Tools |  | 1 | 35.27 | 35.27 | 905
2012-09-28 | Cement 20Kg Bag. Inv No - 21274911 | Cement |  | 1 | 9.09 | 9.09 | 905
2012-09-28 | Watering Cans & Gloves. Inv No - 21274910 | Small Tools |  | 1 | 40.59 | 40.59 | 905
2012-09-30 | Damage Waiver. Inv No - 303112 | Insurance |  | 1 | 612 | 612 | 905
2012-09-30 | Damage Waiver, Multirtyre Roller. Inv No - 303115 | Insurance |  | 1 | 75.6 | 75.6 | 905
2012-10-02 | Sandbags. Inv No - 21274991 | Small Tools |  | 1 | 47.27 | 47.27 | 905
2012-10-04 | Safety Specs Ultralite. Inv No - 21275105 | Small Tools |  | 1 | 26.54 | 26.54 | 905
2012-10-09 | Mesh & Render Mesh. Inv No - 21275240 | Small Tools |  | 1 | 88.27 | 88.27 | 905
2012-10-11 | Masonry Wheel D/C. Inv No - 21275356 | Small Tools |  | 1 | 6.045 | 12.085 | 905
2012-10-11 | Masonry Wheel. Inv No - 21275354 | Small Tools |  | 1 | 44.45 | 44.45 | 905
2012-10-11 | Ramset Dynabolt. Inv No - 130007 | Small Tools |  | 1 | 9.45 | 9.45 | 905
2012-10-16 | Sheet Ribbed Mesh. Inv No - 21275517 | Mesh |  | 1 | 141.27 | 141.27 | 905
| Subtotal for 905 |  |  |  |  | 13752.069
Portfolio WBS 907
2011-10-03 | Paint Enamel Spray Inv - 20429101 | Small Tools |  | 1 | 15.1 | 15.1 | 907
2011-10-12 | Screws Tek Hex Inv - 21262992 | Small Tools |  | 1 | 23.25 | 23.25 | 907
2011-10-12 | Mini Float Proserpine Inv - 4827 | Float |  | 1.5 | 100 | 150 | 907
2011-10-13 | Cable Ties Inv - 21263044 | Small Tools |  | 1 | 20.77 | 20.77 | 907
2011-10-14 | Steel Round Dowel Galv, Visqueen Black Inv- 20429676 | Small Tools |  | 1 | 231.95 | 231.95 | 907
2011-10-18 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 907
2011-10-18 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 907
2011-10-19 | Rain Coat Inv 21263230 | Small Tools |  | 1 | 30.45 | 30.45 | 907
2011-10-24 | Fence Post Inv - 21263395 | Small Tools |  | 1 | 427.4 | 427.4 | 907
2011-10-27 | Chalk, Knife Classic, Chalk Refill Inv - 21263550 | Small Tools |  | 1 | 47.22 | 47.22 | 907
2011-10-27 | Stanley Fatmax Chalk Line, Fat Builders Pencils Inv - 21263546 | Small Tools |  | 1 | 37.09 | 37.09 | 907
2011-10-31 | Steel N12 Deformed Inv - 21263633 | Small Tools |  | 1 | 17.09 | 17.09 | 907
2011-11-15 | Hand Towel Dispenser Inv - 73245/01 | Small Tools |  | 2 | 69.9 | 139.8 | 907
2012-02-06 | Mr Clean, Cable Wipes,Tape Measure, Steel Roudn Dowel Ect. Inv No 21267018 | Small Tools |  | 1 | 158.52 | 158.52 | 907
2012-02-29 | Notice of works. Inv No 75221 | Advertising |  | 1 | 120.9 | 120.9 | 907
2012-03-03 | Transport | Taylors Earthmoving | hr | 1 | 180 | 180 | 907
2012-03-08 | Transport of Excavator | Taylors Earthmoving | hr | 1 | 120 | 120 | 907
2012-03-20 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 907
2012-03-20 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 907
2012-03-21 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 907
2012-03-21 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 907
2012-03-31 | Hired from the 28/2/2012 to 27/3/2012. Inv No - 89 | Ute - Hire |  | 1 | 1440 | 1440 | 907
2012-03-31 | Hired from the 30/1/12 to 28/2/2012. Inv No 89 | Ute - Hire |  | 1 | 1440 | 1440 | 907
2012-04-02 | Float | Humphries Pty Ltd | hr | 1 | 125 | 125 | 907
2012-04-04 | Float | Humphries Pty Ltd | hr | 2 | 125 | 250 | 907
2012-04-14 | Float | Humphries Pty Ltd | hr | 1 | 125 | 125 | 907
2012-04-21 | H.T Gourlay & P.R Gourlay | H.T Gourlay & P.R Gourlay | hr | 3 | 100 | 300 | 907
2012-04-23 | H.T Gourlay & P.R Gourlay | H.T Gourlay & P.R Gourlay | hr | 4 | 100 | 400 | 907
2012-04-23 | Float | Humphries Pty Ltd | hr | 2 | 125 | 250 | 907
2012-04-27 | H.T Gourlay & P.R Gourlay | H.T Gourlay & P.R Gourlay | hr | 4 | 100 | 400 | 907
2012-04-30 | Tilt Tray Hire | Taylors Earthmoving | hr | 1 | 120 | 120 | 907
2012-05-10 | Inv No - 284764 | Float |  | 1 | 250 | 250 | 907
2012-05-10 | Transport Pad Foot Roller. & Diesel Fuel. Hired on the 2/5/2012 - 8/5/2012. Inv No - 284764 | Float |  | 1 | 283.8 | 283.8 | 907
2012-05-16 | Float | Humphries Pty Ltd | hr | 1 | 125 | 125 | 907
2012-05-28 | Float | Humphries Pty Ltd | hr | 1 | 125 | 125 | 907
2012-05-31 | Hired 1/5/2012 - 31/5/2012 . Inv No - 48 | Ute - Hire |  | 1 | 1620 | 1620 | 907
2012-06-06 | Transport Pad Foot Roller, Hired 1/6/2012 - 6/6/2012. Inv No - 288519 | Float |  | 2 | 130 | 260 | 907
2012-06-23 | Move Roller from Bowen to Proserpine. Inv No - 1740 | Float |  | 3 | 121 | 363 | 907
2012-06-30 | float Double Drum Roller. Inv No - 291194 | Float |  | 1 | 70 | 70 | 907
2012-07-30 | Float Hire from Roberts St to Doherty St | Humphries Pty Ltd | hr | 1 | 125 | 125 | 907
2012-07-30 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 907
2012-07-30 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 907
2012-07-31 | Transport Pad Foot Roller, Inv No - 295263 | Float |  | 1 | 100 | 100 | 907
2012-07-31 | Hited 1/7/12 - 27/7/12. Inv No - 85 | Ute - Hire |  | 1 | 1440 | 1440 | 907
2012-08-01 | Cable Ties, Shovel, Tape Measure. Inv No - 21273043 | Small Tools |  | 1 | 105.36 | 105.36 | 907
2012-08-06 | Float of Excavator from Roberts St to Council Pit | Humphries Pty Ltd | hr | 1 | 125 | 125 | 907
2012-08-08 | Trasport of Grader from Mackay to Proserpine. Inv No - 27113 | Float |  | 1 | 700 | 700 | 907
2012-08-09 | Float Watts Excavator from Gravel pit to Kelsey Cr | Humphries Pty Ltd | hr | 2 | 125 | 250 | 907
2012-08-30 | Transport Fad Foot Roller. Hired 31/7/12 - 24/8/12. Inv No 298887 | Float |  | 1 | 100 | 100 | 907
2012-08-31 | Delivery on Stackable Barriers. Inv No - 299462 | Float |  | 1 | 60 | 60 | 907
2012-09-10 | Diamond Blade. Inv No - 08742450 | Small Tools |  | 1 | 326.46 | 326.46 | 907
2012-09-30 | Deliver to site, Multityre Roller. Inv No - 303115 | Float |  | 1 | 200 | 200 | 907
2012-10-03 | Pickup of Traffic Lights & Roller. Inv No - 304106 | Float |  | 1 | 70 | 70 | 907
2012-10-05 | Float, Multi Tyre Roller. Inv No - 304436 | Float |  | 1 | 130 | 130 | 907
| Subtotal for 907 |  |  |  |  | 14352.61
Portfolio WBS 908
2012-04-04 | Ear Plugs, Gloves, Refletors, Safety Sunglasses, Safety Vest & Sunscreen. Inv No - 92387/01 | Safety Workwear |  | 1 | 194.36 | 194.36 | 908
2012-04-11 | Restock of Kit. Anzac Rd. Inv No - 176 | First Aid |  | 1 | 77.39 | 77.39 | 908
2012-09-24 | Safety Workwear & ect. Gloves, Earplugs & Glassses. Inv No - 119648/01 | Safety Workwear |  | 1 | 141.98 | 141.98 | 908
| Subtotal for 908 |  |  |  |  | 413.73
Portfolio WBS 911
2011-11-08 | From the 10/10/11 to th 7/11/2011 Acc No 17613663 | Electricity |  | 1 | 117.84 | 117.84 | 911
2012-02-09 | Billing Period from the 7/11/11 to the 8/02/12. Acc/ No 17613663 | Electricity |  | 1 | 269.12 | 269.12 | 911
2012-05-10 | Billing Period from the 8/2/2012 - 9/5/2012. Inv No - 17613663 | Electricity |  | 1 | 255.99 | 255.99 | 911
2012-06-05 | 1/47 Anzac Rd. Acc/No 17613663 | Electricity |  | 1 | 255.99 | 255.99 | 911
2012-08-07 | Electicity to Accommodation 1/47 Anzac Rd Proserpine. Acc/No 17613663 | Electricity |  | 1 | 181.56 | 181.56 | 911
2012-11-05 | 45-47 Anzac Rd Proserpine. 1/11/2012 - 30/11/2012. Inv No - 146 | Crib Facilities |  | 1 | 1320 | 1320 | 911
2012-11-08 | Electicity to Accommodation 1/47 Anzac Rd Proserpine. Billing Period 6/8/12 - 7/11/12 | Electricity |  | 1 | 226.4 | 226.4 | 911
| Subtotal for 911 |  |  |  |  | 2626.9
Portfolio WBS 913
2012-01-16 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 913
2012-01-16 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 913
2012-01-16 | Foreman | Labour | hr | 3 | 44.2 | 132.6 | 913
2012-01-16 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 913
2012-02-02 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 913
2012-02-02 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 913
2012-02-02 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 913
2012-02-03 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 913
2012-02-03 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 913
2012-02-24 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 913
2012-02-24 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 913
2012-02-24 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 913
2012-03-07 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 913
2012-03-07 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 913
2012-03-14 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 913
2012-03-14 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 913
2012-03-14 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 913
2012-03-15 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 913
2012-03-15 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 913
2012-03-15 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 913
2012-03-16 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 913
2012-03-16 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 913
2012-03-16 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 913
2012-03-19 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 913
2012-03-19 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 913
2012-03-19 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 913
2012-03-20 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 913
2012-03-20 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 913
2012-03-20 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 913
2012-03-21 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 913
2012-03-21 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 913
2012-03-21 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 913
2012-03-22 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 913
2012-03-22 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 913
2012-03-22 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 913
2012-03-26 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 913
2012-03-26 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 913
2012-03-26 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 913
2012-05-25 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 913
2012-05-25 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 913
2012-05-25 | Labour Hire | Labour | hr | 4 | 48 | 192 | 913
2012-05-25 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 913
2012-05-25 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 913
2012-05-31 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 913
2012-05-31 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 913
2012-05-31 | Labour Hire | Labour | hr | 4 | 48 | 192 | 913
2012-05-31 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 913
2012-06-26 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 913
2012-06-26 | Labour Hire | Labour | hr | 5.5 | 48 | 264 | 913
2012-06-26 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 913
2012-06-27 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 913
2012-06-27 | Labour Hire | Labour | hr | 3 | 48 | 144 | 913
2012-06-27 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 913
2012-06-27 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 913
2012-07-09 | Labour Hire | Labour | hr | 2.5 | 48 | 120 | 913
2012-07-09 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 913
2012-07-09 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 913
2012-07-09 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 913
2012-07-10 | Labour Hire | Labour | hr | 7 | 48 | 336 | 913
2012-07-10 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 913
2012-07-10 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 913
2012-07-11 | Labour Hire | Labour | hr | 5.5 | 48 | 264 | 913
2012-07-11 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 913
2012-07-11 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 913
2012-07-12 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 913
2012-07-12 | Labour Hire | Labour | hr | 7 | 48 | 336 | 913
2012-07-13 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 913
2012-07-13 | Labour Hire | Labour | hr | 3 | 48 | 144 | 913
2012-07-13 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 913
2012-07-17 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 913
2012-07-17 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 913
2012-07-17 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 913
2012-07-17 | Labour Hire | Labour | hr | 3 | 48 | 144 | 913
2012-07-18 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 913
2012-07-18 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 913
2012-07-18 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 913
2012-07-18 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 913
2012-07-18 | Labour Hire | Labour | hr | 4 | 48 | 192 | 913
2012-07-18 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 913
2012-07-18 | Labour Hire ( Achieve Group ) | Labour | hr | 4 | 34.81 | 139.24 | 913
| Subtotal for 913 |  |  |  |  | 13752.765
Portfolio WBS 915
2012-02-24 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 915
2012-02-24 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 915
2012-02-24 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 915
2012-07-18 | Labour Hire | Labour | hr | 4 | 48 | 192 | 915
2012-07-18 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 915
2012-07-18 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 915
2012-07-18 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 915
2012-11-30 | Labour Hire (Inspecting road damage with David & Anita) | Labour | hr | 1.5 | 35.35 | 53.025 | 915
2012-11-30 | Shovel Steel x 2 | Small Tools |  | 1 | 19.09 | 19.09 | 915
2012-11-30 | Plate Compactor - Dry Hire & Damage Waiver | Plate Compactor |  | 1 | 77.63 | 77.63 | 915
| Subtotal for 915 |  |  |  |  | 925.02
Portfolio WBS C20 - 20Mpa
2012-04-13 | N20 Concrete. Inv No - 9652 | N20 |  | 1 | 255.8 | 255.8 | C20 - 20Mpa
2012-06-20 | N20 Concrete. Inv No - 10148 | N20 |  | 1 | 117.01 | 117.01 | C20 - 20Mpa
| Subtotal for C20 - 20Mpa |  |  |  |  | 372.81
Portfolio WBS C25
2011-11-28 | Inv No - 8595 | N25 |  | 3.8 | 168.2 | 639.16 | C25
2011-12-09 | Inv No - 8754 | N25 |  | 1 | 146.95 | 146.95 | C25
2012-01-19 | N25 Concrete . Inv No - 9084 | N25 |  | 1 | 476.78 | 476.78 | C25
2012-01-20 | N25 Concrete Inv No - 9118 | N25 |  | 1 | 236.9 | 236.9 | C25
2012-01-23 | N25 Concrete. Inv No - 9110 | N25 |  | 1 | 236.9 | 236.9 | C25
2012-01-23 | N25 Concrete Inv No 9110 | N25 |  | 1 | 236.9 | 236.9 | C25
2012-04-19 | N32 Concrete. Inv No - QM8327686 | N25 |  | 1 | 659.6 | 659.6 | C25
2012-04-24 | N32 Concrete. Inv No - QM8339014. | N25 |  | 1 | 920.5 | 920.5 | C25
2012-04-24 | N32 Concrete. Inv No - QM8339013 | N32 |  | 1 | 519 | 519 | C25
2012-06-18 | N32 Concrete. Inv No 10119 | N32 |  | 1 | 242.4 | 242.4 | C25
2012-06-29 | N25 Concrete. Inv No - QM8497587 | N25 |  | 1 | 388 | 388 | C25
2012-07-05 | N25 Concrete. Inv No - 67315850 | N25 |  | 1 | 256.8 | 256.8 | C25
2012-07-31 | N25 Concrete. Inv No 67358464 | N25 |  | 1 | 1996 | 1996 | C25
2012-08-03 | N25 Concrete. Inv No - 67368025 | N25 |  | 1 | 770 | 770 | C25
2012-09-06 | N25 Concrete. Dkts No 56368296, 56377226, 56379014. Inv No 67423789 | N25 |  | 1 | 1460.4 | 1460.4 | C25
2012-09-11 | N25 Concrete. Inv No - 67432355 | N25 |  | 1 | 906.8 | 906.8 | C25
2012-09-13 | N25 Concrete. Inv No - 67437073 | N25 |  | 1 | 377.2 | 377.2 | C25
2012-09-13 | N25 Concrete. Inv No - QM8711891 | N25 |  | 1 | 712.31 | 712.31 | C25
2012-09-20 | N25 Concrete. Inv No - QM8729759 | N25 |  | 1 | 562.35 | 562.35 | C25
2012-09-21 | N25 Concrete. Inv No 010701 | N25 |  | 2.4 | 174.3 | 418.32 | C25
2012-10-05 | N32 Concrete. Inv No - 010825 | N32 |  | 1 | 153.32 | 153.32 | C25
2012-10-17 | N25 Concrete | N25 |  | 1 | 460.78 | 460.78 | C25
| Subtotal for C25 |  |  |  |  | 12777.37
Portfolio WBS C32
2011-10-14 | Bulk GP / GB Cement Dock No 3482 Inv - 8098 | N32 |  | 5.2 | 197.6 | 1027.52 | C32
2011-11-01 | Inv - 8280 | N32 |  | 1 | 128.43 | 128.43 | C32
2011-11-30 | N32 Concrete Inv No - 66964187 | N32 |  | 1 | 1256 | 1256 | C32
2011-11-30 | N32 Concrete Inv No 66966602 | N32 |  | 1 | 1316 | 1316 | C32
2011-12-10 | N32 Concrete Inv No - 66983956 | N32 |  | 1 | 1243.8 | 1243.8 | C32
2011-12-20 | N32 Concrete - Inv 8880 | N32 |  | 1 | 184.36 | 184.36 | C32
2012-03-03 | N32 Concrete. Inv No - 67111212 | N32 |  | 1 | 1318.2 | 1318.2 | C32
2012-03-03 | N32 Concrete. Inv No - 67111213 | N32 |  | 1 | 620 | 620 | C32
2012-03-06 | N32 Concrete Inv No - 67114767 | N32 |  | 1 | 1623 | 1623 | C32
2012-03-06 | N32 Concrete. Inv No - 67114768 | N32 |  | 1 | 2601.5 | 2601.5 | C32
2012-03-13 | N32 Concrete. Inv No - 67126435 | N32 |  | 1 | 862.8 | 862.8 | C32
2012-03-17 | N32 Concrete. Inv No - 67133281 | N32 |  | 1 | 207 | 207 | C32
2012-03-20 | N32 Concrete. Inv No - 67122518 | N32 |  | 1 | 801.8 | 801.8 | C32
2012-04-03 | N32 Concrete. Inv No - 9581 | N32 |  | 1 | 170.6 | 170.6 | C32
2012-04-11 | N32 Concrete. Inv No - 9637 | N32 |  | 4 | 175 | 700 | C32
2012-04-12 | N32 Concrete. Inv No - 67181678 | N32 |  | 1 | 425 | 425 | C32
2012-04-12 | N32 Concrete. Inv No - 9647 | N32 |  | 8 | 175 | 1400 | C32
2012-04-13 | N32 Concrete. Inv No - 9654 | N32 |  | 1 | 1387.8 | 1387.8 | C32
2012-04-14 | N32 Concrete. Inv No - 9661 | N32 |  | 8.4 | 175 | 1470 | C32
2012-04-19 | N32 Concrete. Inv No - QM8327685 | N32 |  | 1 | 630 | 630 | C32
2012-04-21 | N32 Concrete. Inv No - 9715 | N32 |  | 1 | 181.8 | 181.8 | C32
2012-04-23 | N32 Concrete. Inv No - 9719 | N32 |  | 1 | 153.6 | 153.6 | C32
2012-04-27 | N32 Concrete. Inv No - QM8345342 | N32 |  | 1 | 141 | 141 | C32
2012-04-27 | N32 Concrete. Inv No - QM8345343 | N32 |  | 1 | 138 | 138 | C32
2012-05-08 | N32 Concrete. Inv No - QM 8369677 | N32 |  | 1 | 1120 | 1120 | C32
2012-05-08 | N32 Concrete. Inv No - QM 8369675 | N32 |  | 1 | 446 | 446 | C32
2012-05-08 | N32 Concrete. Inv No - QM8369676 | N32 |  | 1 | 1120 | 1120 | C32
2012-05-17 | N32 Concrete. Inv No - 9902 | N32 |  | 3 | 41.666 | 124.998 | C32
2012-05-18 | N32 Concrete. Inv No - QM8396538 | N32 |  | 1 | 671.5 | 671.5 | C32
2012-05-18 | N32 Concrete. Inv No - 9915 | N32 |  | 1 | 261 | 261 | C32
2012-05-18 | N32 Concrete. Inv No - QM8396540 | N32 |  | 1 | 1151 | 1151 | C32
2012-05-18 | N32 Concrete. Inv No - QM8396539 | N32 |  | 1 | 671.5 | 671.5 | C32
2012-06-05 | N32 Concrete. Inv No - 67267047 | N32 |  | 1 | 1449.8 | 1449.8 | C32
2012-06-14 | N32 Concrete. Inv No - 67281045 | N32 |  | 1 | 230.6 | 230.6 | C32
2012-06-17 | N32 Concrete. Inv No - 67285270 | N32 |  | 1 | 504.2 | 504.2 | C32
2012-06-17 | N32 Concrete. Inv No - 67285269 | N32 |  | 1 | 230.6 | 230.6 | C32
2012-06-18 | N32 Concrete. Inv No - 10120 | N32 |  | 1 | 242.4 | 242.4 | C32
2012-06-19 | N32 Concrete. Docket No 55916652,55917360,55919089,55919334,55919843. Inv No - 67288419 | N32 |  | 1 | 3825.6 | 3825.6 | C32
2012-06-20 | N32 Concrete. Inv No - 10146 | N32 |  | 1 | 209.28 | 209.28 | C32
2012-06-26 | N32 Concrete. Inv No - 10182 | N32 |  | 1 | 193 | 193 | C32
2012-06-26 | N32 Concrete. Inv No - 10181 | N32 |  | 1 | 209.28 | 209.28 | C32
2012-06-26 | N32 Concrete. Inv No - QM8486119 | N32 |  | 1 | 766 | 766 | C32
2012-06-27 | N32 Concrete. Inv No - 10197 | N32 |  | 1 | 278.16 | 278.16 | C32
2012-06-28 | N32 Concrete. Inv No - 67303997 | N32 |  | 1 | 436.4 | 436.4 | C32
2012-06-30 | N32 Concrete. Inv No - 67307055 | N32 |  | 1 | 632.8 | 632.8 | C32
2012-06-30 | N32 Concrete. Inv No - QM8502675 | N32 |  | 3 | 192.5 | 577.5 | C32
2012-07-03 | N32 Concrete. Inv No - 10246 | N32 |  | 1 | 193 | 193 | C32
2012-07-08 | N32 Concrete. Inv No - 67320305 | N32 |  | 1 | 426 | 426 | C32
2012-07-19 | N32 Concrete. Inv No - 67338804 | N32 |  | 4 | 182 | 728 | C32
2012-07-20 | N32 Concrete. Inv No 67342989 | N32 |  | 1 | 440 | 440 | C32
2012-07-24 | N32 Concrete. Dkt No 56112194, 56107731,56100682. Inv No - 67346359 | N32 |  | 1 | 3197.6 | 3197.6 | C32
2012-07-26 | N32 Concrete. Inv No - 67350772 | N32 |  | 1 | 303 | 303 | C32
2012-07-26 | N32 Concrete. Inv No - 67350773 | N32 |  | 1 | 324.8 | 324.8 | C32
2012-07-28 | N32 Concrete. Inv No - 10387 | N32 |  | 3 | 183.75 | 551.25 | C32
2012-07-31 | N32 Concrete. Inv No QM8572686 | N32 |  | 1 | 1340.46 | 1340.46 | C32
2012-08-04 | N32 Concrete. Inv No - 67368026 | N32 |  | 1 | 517.6 | 517.6 | C32
2012-08-07 | N32 Concrete. Inv No - 67372050 | N32 | m³ | 1 | 641.6 | 641.6 | C32
2012-08-08 | N32 Concrete. Inv No - 67375234 | N32 |  | 1 | 945 | 945 | C32
2012-08-09 | N32 Concrete. Inv No - 67375235 | N32 |  | 1 | 1001 | 1001 | C32
2012-08-26 | N32 Concrete Dkt No 56301648,56302168,56303086,56303438,56303998,56304448,56305035. Inv No - 67402751 | N32 |  | 1 | 6132 | 6132 | C32
2012-08-29 | N32 Concrete. Inv No - QM8672778 | N32 |  | 1 | 386.9 | 386.9 | C32
2012-08-30 | N32 Concrete. Inv No - QM8677374 | N32 |  | 1 | 464.28 | 464.28 | C32
2012-08-31 | N32 Concrete. Inv No - 67412756 | N32 |  | 1 | 446 | 446 | C32
2012-08-31 | N32 Concrete. Inv No - Qm8686902 | N32 |  | 1 | 502.97 | 502.97 | C32
2012-08-31 | N32 Concrete. Inv No - 10601 | N32 |  | 1 | 353.55 | 353.55 | C32
2012-09-13 | N32 Concrete. Inv No - 010675 | N32 |  | 1 | 155.85 | 155.85 | C32
2012-09-13 | N32 Concrete. Inv No - 010674 | N32 |  | 1 | 485.35 | 485.35 | C32
2012-09-18 | N32 Concrete. Dockts No 56443021 56443535 56444147 56445045. Inv No 67444581 | N32 |  | 1 | 3215 | 3215 | C32
2012-09-19 | N32 Concrete. Inv No - 010709 | N32 |  | 2.4 | 189 | 453.6 | C32
2012-09-21 | N32 Concrete. Inv No - 010702 | N32 |  | 1 | 91.83 | 91.83 | C32
2012-10-02 | N32 Concrete. Inv No - 010794 | N32 |  | 1 | 155.85 | 155.85 | C32
2012-10-09 | N32 Concrete. Inv No - QM8774229 | N32 |  | 1 | 183.45 | 183.45 | C32
2012-10-09 | N32 Concrete. Inv No - 67481762 | N32 |  | 1 | 465.6 | 465.6 | C32
2012-10-09 | N32 Concrete. Inv No - 010841 | N32 |  | 1 | 159 | 159 | C32
| Subtotal for C32 |  |  |  |  | 59600.368
Portfolio WBS C40
2011-11-26 | 40 Mpa Inv - 66955610 | C40 |  | 1 | 514.4 | 514.4 | C40
2012-07-02 | N40 Concrete. Inv No - 10234 | N40 |  | 1 | 521.31 | 521.31 | C40
2012-07-04 | N40 Concrete. Inv No - 10256 | N40 |  | 1 | 482.91 | 482.91 | C40
| Subtotal for C40 |  |  |  |  | 1518.62
Portfolio WBS CKM
2011-11-19 | Inv - 66943287 | Kerb Adaptors |  | 1 | 4036.36 | 4036.36 | CKM
2012-02-29 | N32 Concrete. Dock No - 55307253,7692,8437,8754,9588,9774,10387,10496,10832. Inv No - 67105440 | N32 |  | 1 | 7948.8 | 7948.8 | CKM
2012-02-29 | Inv No - 21267827 | Cement |  | 1 | 362.72 | 362.72 | CKM
2012-04-10 | N32 Concrete. Inv No - 67475077 | N32 |  | 1 | 1663.2 | 1663.2 | CKM
2012-04-10 | N32 Concrete. Inv No - 67475076 | N32 |  | 1 | 3652.8 | 3652.8 | CKM
2012-04-23 | Cement QCL GP 20kg Bag. Inv No - 21269636 | Cement |  | 1 | 272.04 | 272.04 | CKM
2012-04-24 | N32 Concrete. Plus Dkts 55600528, 55600969 Inv No - 67196025 | N32 |  | 1 | 3029.1 | 3029.1 | CKM
2012-05-01 | 20Kg bag. Inv No - 21269902 | Cement - GP Bulk |  | 1 | 18.13 | 18.13 | CKM
2012-06-04 | 20Kg Bag Cement. Inv No -21271058 | Cement |  | 1 | 272.045 | 272.045 | CKM
2012-09-04 | Bulk GP / GB Cement. Inv No - 21274111 | Cement |  | 1 | 226.72 | 226.72 | CKM
2012-09-17 | Bulk GP / GB Cement. Inv No - 21274512 | Cement |  | 1 | 272.04 | 272.04 | CKM
| Subtotal for CKM |  |  |  |  | 21753.955
Portfolio WBS CSA
2012-04-21 | Inv No - 94695054 | Cement Powder |  | 1 | 6089.32 | 6089.32 | CSA
2012-05-31 | Inv No - 94736310 | Cement Powder |  | 22.15 | 240.21 | 5320.6515 | CSA
2012-06-19 | Cement 20kg Bag. Inv No - 21271573 | Cement - GP Bulk |  | 1 | 90.68 | 90.68 | CSA
2012-06-19 | Inv No - 21271537 | Cement - GP Bulk |  | 1 | 272.045 | 272.045 | CSA
2012-08-22 | Cement 20 Kg Bags. Inv No - 21273752 | Cement |  | 1 | 634.77 | 634.77 | CSA
2012-10-09 | 50 Mpa Terracotta Concrete Speed Bump. Inv No - 67481763 | N40 |  | 1 | 1991 | 1991 | CSA
| Subtotal for CSA |  |  |  |  | 14398.4665
Portfolio WBS CSS
2011-11-18 | Docket No 3826/3828 Inv 8484 | Stabilised Sand |  | 7 | 170 | 1190 | CSS
2011-11-19 | Docket No 3841 Inv - 8485 | Cement Powder |  | 5 | 170 | 850 | CSS
2011-11-21 | Docket No 3852 Inv - 8511 | Cement Powder |  | 1 | 1209 | 1209 | CSS
2012-02-16 | Stabilised Sand. Inv No - 9304 | Stabilised Sand |  | 1 | 172.9 | 172.9 | CSS
2012-02-17 | Stabilised Sand. Inv No - 9311 | Stabilised Sand |  | 1 | 265.61 | 265.61 | CSS
2012-02-20 | Stabilised Sand. Inv No - 9336 | Stabilised Sand |  | 1 | 242.43 | 242.43 | CSS
2012-03-12 | Stabilised Sand. Inv No - 9483 | Stabilised Sand |  | 1 | 181 | 181 | CSS
| Subtotal for CSS |  |  |  |  | 4110.94
Portfolio WBS QMR
2012-04-24 | Inv No - 7689 | Rock |  | 521.51 | 30 | 15645.3 | QMR
2012-04-24 | Inv No - Inv No - 7687 | Rock |  | 296.97 | 30 | 8909.1 | QMR
2012-04-30 | Gabion Rock. Inv No - 20416 | Gabion Rock |  | 737.8 | 31.9 | 23535.82 | QMR
2012-04-30 | Inv No - 7690. With a credit, Inv No - 7762 | Rock |  | 147.22 | 30 | 4416.6 | QMR
2012-04-30 | Inv No - 7763 | Rock |  | 29.37 | 30 | 881.1 | QMR
2012-05-17 | Inv No - 7869 | Rock |  | 87.97 | 30 | 2639.1 | QMR
2012-05-17 | Inv No - 7868 | Rock |  | 147.59 | 30 | 4427.7 | QMR
2012-05-18 | Inv No - 7870 | Rock |  | 25.16 | 30 | 754.8 | QMR
2012-05-21 | Inv No - 6051 | Rock |  | 107.64 | 19.4 | 2088.216 | QMR
2012-05-31 | 75/100mm Rock. Inv No 124545 | Rock |  | 11.64 | 30 | 349.2 | QMR
2012-06-14 | Inv No- 124561 | Rock |  | 50 | 30 | 1500 | QMR
2012-07-04 | Medium Fine Sand. Inv No - 4935 | Sand |  | 11.84 | 13.64 | 161.4976 | QMR
2012-09-20 | Inv No - 7291 | Rock |  | 1 | 1768.89 | 1768.89 | QMR
2012-09-20 | Inv No - 7290 | Rock |  | 1 | 1106.57 | 1106.57 | QMR
| Subtotal for QMR |  |  |  |  | 68183.8936
Portfolio WBS QMS
2011-10-19 | Bedding Sand Dock No 3524 Inv - 8135 | Sand |  | 3.2 | 134.9 | 431.68 | QMS
2011-11-30 | Sand | Sand |  | 1 | 1468.82 | 1468.82 | QMS
2012-01-19 | Bedding Sand. Inv No - 4474 | Sand |  | 1 | 70.38 | 70.38 | QMS
2012-01-20 | Bedding Sand. Inv No - 4474 | Sand |  | 4.3 | 13.639 | 58.6477 | QMS
2012-01-27 | Bedding Sand. Inv No - 4474 | Sand |  | 16.42 | 39.7 | 651.874 | QMS
2012-02-08 | Medium/Fine Sand. Inv No - 4518 | Sand |  | 18.2 | 17.082 | 310.8924 | QMS
2012-02-09 | Bedding Sand. Inv No - 4518 | Sand |  | 17.52 | 17.082 | 299.2766 | QMS
2012-02-13 | Bedding Sand. Inv No - 4518 | Sand |  | 12.24 | 13.64 | 166.9536 | QMS
2012-02-14 | Bedding Sand.Inv No - 4518 | Sand |  | 22.58 | 13.64 | 307.9912 | QMS
2012-02-23 | Bedding Sand. Inv No - 4518 | Sand |  | 1 | 136.95 | 136.95 | QMS
2012-02-29 | Bedding Sand. Inv No - 4518 | Sand |  | 2.6 | 36.369 | 94.5594 | QMS
2012-03-02 | Bedding Sand. Inv No - 4603 | Sand |  | 12.02 | 13.64 | 163.9528 | QMS
2012-03-02 | Bedding Sand. Inv No - 4603 | Sand |  | 11.52 | 13.64 | 157.1328 | QMS
2012-03-05 | Bedding Sand. Inv No 4603 | Sand |  | 1.34 | 36.373 | 48.7398 | QMS
2012-03-06 | Bedding Sand. Inv No - 4603 | Sand |  | 11.8 | 13.64 | 160.952 | QMS
2012-03-09 | Bedding Sand. Inv No - 4603 | Sand |  | 18.56 | 13.64 | 253.1584 | QMS
2012-03-09 | Bedding Sand. Inv No - 4603 | Sand |  | 18.5 | 13.64 | 252.34 | QMS
2012-03-23 | Bedding Sand. Inv No - 4603 | Sand |  | 3.2 | 26.562 | 84.9984 | QMS
2012-03-27 | Bedding Sand. Inv No - 4603 | Sand |  | 14 | 17.082 | 239.148 | QMS
2012-03-28 | Bedding Sand. Inv No - 4603 | Sand |  | 13.98 | 17.082 | 238.8064 | QMS
2012-03-29 | Bedding Sand. Inv No - 4603 | Sand |  | 12.46 | 13.64 | 169.9544 | QMS
2012-04-02 | Bedding Sand. Inv No - 4647 | Sand |  | 11.94 | 13.64 | 162.8616 | QMS
2012-04-02 | Bedding Sand. Inv No - 4647 | Sand |  | 11.94 | 13.64 | 0.0016 | QMS
2012-04-04 | Bedding Sand. Inv No - 4647 | Sand |  | 10 | 13.64 | 136.4 | QMS
2012-04-10 | Bedding Sand. Inv No- 4647 | Sand |  | 12.12 | 13.64 | 165.3168 | QMS
2012-04-10 | Bedding Sand. Inv No - 4647 | Sand |  | 2.7 | 36.37 | 98.199 | QMS
2012-04-11 | Bedding Sand. Inv No - 4647 | Sand |  | 10.8 | 13.64 | 147.312 | QMS
2012-04-12 | Bedding Sand. Inv No - 4647 | Sand |  | 12.02 | 13.64 | 163.9528 | QMS
2012-04-13 | Bedding Sand. Inv No - 4647 | Sand |  | 12.4 | 13.64 | 169.136 | QMS
2012-04-14 | Bedding Sand. Inv No - 4647 | Sand |  | 11.7 | 30.807 | 360.4419 | QMS
2012-04-16 | Bedding Sand. Inv No - 4647 | Sand |  | 11.64 | 17.082 | 198.8345 | QMS
2012-04-18 | Bedding Sand. Inv No - 4647 | Sand |  | 1 | 39.83 | 39.83 | QMS
2012-04-19 | Bedding Sand. Inv No - 4647 | Sand |  | 1 | 222.07 | 222.07 | QMS
2012-04-23 | Bedding Sand.Inv No - 4647 | Sand |  | 1 | 70.56 | 70.56 | QMS
2012-05-01 | Bedding Sand. Inv No - 4735 | Sand |  | 20.14 | 13.64 | 274.7096 | QMS
2012-05-01 | Medium Fine Sand. Inv No - 4735 | Sand |  | 17.9 | 13.64 | 244.156 | QMS
2012-05-08 | Bedding Sand. Inv No - 4735 | Sand |  | 16.94 | 17.042 | 288.6915 | QMS
2012-05-09 | Fine Sand. Inv No -4735 | Sand |  | 3 | 36.37 | 109.11 | QMS
2012-05-15 | Bedding Sand. Inv No - 4735 | Sand |  | 13.252 | 17.04 | 225.8141 | QMS
2012-05-19 | Bedding Sand. Inv No - 4735 | Sand |  | 12.56 | 13.64 | 171.3184 | QMS
2012-05-29 | Bedding Sand. Inv No - 4735 | Sand |  | 12.28 | 13.64 | 167.4992 | QMS
2012-06-04 | Medium Fine Sand. Inv No 4842 | Sand |  | 2.42 | 13.64 | 33.0088 | QMS
2012-06-05 | MediumFine Sand. Inv No - 4842 | Sand |  | 9.24 | 13.64 | 126.0336 | QMS
2012-06-05 | Medium Fine Sand. Inv No - 4842 | Sand |  | 12 | 13.64 | 163.68 | QMS
2012-06-08 | Medium Fine Sand. Inv No 4842 | Sand |  | 11.32 | 17.291 | 195.7341 | QMS
2012-06-14 | Medium Fine Sand. Inv No - 4842 | Sand |  | 12.08 | 13.64 | 164.7712 | QMS
2012-06-14 | Medium Fine Sand. Inv No - 4842 | Sand |  | 12.86 | 13.64 | 175.4104 | QMS
2012-06-18 | Medium Fine Sand. Inv No - 4842 | Sand |  | 11.46 | 13.64 | 156.3144 | QMS
2012-06-19 | Medium Fine Sand. Inv No - 4842 | Sand |  | 2.2 | 13.64 | 30.008 | QMS
2012-06-20 | Inv No - 8227936 | Signs Complete |  | 1 | 651.83 | 651.83 | QMS
2012-06-28 | Medium Fine Sand. Inv No- 4842 | Sand |  | 11.9 | 13.64 | 162.316 | QMS
2012-06-29 | Medium Fine Sand. Inv No - 4842 | Sand |  | 12.3 | 17.082 | 210.1086 | QMS
2012-07-12 | Weight - Order Inv No - 4935 | Weight - Order |  | 1 | 31.82 | 31.82 | QMS
2012-07-12 | Weight - Order . Inv No - 4935 | Weight - Order |  | 1 | 31.82 | 31.82 | QMS
2012-07-23 | Medium Fine Sand. Inv No - 4935 | Sand |  | 7.08 | 13.64 | 96.5712 | QMS
2012-07-24 | Medium Fine Sand. Inv No - 4935 | Sand |  | 1.48 | 13.64 | 20.1872 | QMS
2012-07-30 | Medium Fine Sand. Inv No - 4935 | Sand |  | 6.82 | 20.035 | 136.6387 | QMS
2012-08-15 | Stabilised Sand. Inv No - 10492 | Sand |  | 5 | 137.55 | 687.75 | QMS
2012-08-16 | Medium Fine Sand. Inv No - 5015 | Sand |  | 12.68 | 17.082 | 216.5998 | QMS
2012-08-16 | Medium Fine Sand. Inv No - 5015 | Sand |  | 12.58 | 17.082 | 214.8916 | QMS
2012-08-17 | Medium Fine Sand. Inv No - 5015 | Sand |  | 12.54 | 13.64 | 171.0456 | QMS
2012-08-21 | Medium Fine Sand. Inv No - 5015 | Sand |  | 11.62 | 13.64 | 158.4968 | QMS
2012-08-21 | Medium Fine Sand. Inv No - | Sand |  | 12.58 | 17.081 | 214.879 | QMS
2012-08-24 | Medium Fine Sand. Inv No - 5015 | Sand |  | 2.26 | 13.64 | 30.8264 | QMS
2012-09-04 | Medium Fine Sand. Inv No - 5103 | Sand |  | 2.38 | 13.64 | 32.4632 | QMS
2012-09-17 | Medium Fine Sand. Inv No - 5103 | Sand |  | 2 | 13.64 | 27.28 | QMS
| Subtotal for QMS |  |  |  |  | 13323.9074
Portfolio WBS RFS
2011-10-20 | Galv Med Pipe Inv 1586224 | Signs - General |  | 6 | 74.2 | 445.2 | RFS
2011-11-11 | fabricate 2PL sign boards * 5 Inv- 10198 | Signs Complete |  | 1 | 133.75 | 133.75 | RFS
2011-12-05 | Inv No IN - 8204925 | Signs Complete |  | 1 | 291.48 | 291.48 | RFS
2012-03-14 | Inv No - 8215971 | Signs Complete |  | 1 | 88.64 | 88.64 | RFS
| Subtotal for RFS |  |  |  |  | 959.07
Portfolio WBS RSM
2011-10-25 | Dock No 14866 Inv - 19736 | Cement |  | 1 | 4350 | 4350 | RSM
2011-11-16 | Bidim A34 6.00 M - 150M Inv =- CD201209301 | A34 |  | 1 | 2728 | 2728 | RSM
2011-11-16 | NF82 Square Ribmesh Docket No 15024 Inv - 19910 | Mesh |  | 1 | 832.5 | 832.5 | RSM
2011-11-28 | Bar Chairs Inv No - 8603 | Bar Chairs |  | 1 | 22.2 | 22.2 | RSM
2011-11-30 | NF82 Square Ribmesh Inv No 20005 | Mesh |  | 3 | 82.5 | 247.5 | RSM
2011-12-06 | NF 72 Ribmesh Inv No 20041 | Mesh |  | 1 | 65.2 | 65.2 | RSM
2011-12-07 | NF 82 & NF 72 Inv No 20054 | Mesh |  | 1 | 312.7 | 312.7 | RSM
2012-04-11 | Inv No - 20649 | Mesh |  | 1 | 2443.5 | 2443.5 | RSM
2012-07-05 | Inv No - 21157 | Mesh |  | 17 | 73.994 | 1257.898 | RSM
2012-07-30 | Mesh, Circular Saw. Inv No - 21272973 | Small Tools |  | 1 | 554.86 | 554.86 | RSM
2012-08-29 | Mesh SL 6M x 2.4M. Inv No - 21273961 | Mesh |  | 1 | 786 | 786 | RSM
2012-09-10 | 6M x 2.4M Sheet Ribbed Mesh. Inv No - 21274314 | Mesh |  | 1 | 336 | 336 | RSM
2012-09-13 | Steel Plastic Bar Chairs & Mesh. Inv No - 21274437 | Mesh |  | 1 | 437.59 | 437.59 | RSM
| Subtotal for RSM |  |  |  |  | 14373.948
Portfolio WBS SWC
2012-02-15 | 750MM X 1.2M RCBC Crowns. ( 30 ) . Inv No - 20391 | HW- 750 x 300 RCBC |  | 30 | 370 | 11100 | SWC
2012-03-05 | Inv No - 20473 | RCBC - 1200 x 300 |  | 8 | 438 | 3504 | SWC
2012-07-02 | HW - 1200 x 450 x 2400. RCBC . Inv No -21118 | HW - 1200 x 450 RCBC |  | 11 | 920 | 10120 | SWC
2012-07-02 | HW - 1200 x 450 x 1200 RCBC . Inv No - 21118 | HW - 1200 x 450 RCBC |  | 31 | 460 | 14260 | SWC
2012-07-20 | RCBC Crown Unit- 900 x 450. Inv No - 21230 | RCBC- 900 x 450 |  | 36 | 400 | 14400 | SWC
2012-07-30 | Inv No - 21295 | HW 1200 x 600 RCBC |  | 8 | 480 | 3840 | SWC
2012-07-30 | Inv No - 21295 | HW - 1200 x 450 RCBC |  | 10 | 460 | 4600 | SWC
2012-07-30 | Inv No - 21295 | HW - 3/1200 x 300 RCBC |  | 3 | 440 | 1320 | SWC
2012-07-30 | HW - 900 x 450 RCBC. Inv No 21295 | HW - 900 x 450 RCBC |  | 1 | 400 | 400 | SWC
2012-07-30 | HW - 1800 x 600 RCBC. Inv No - 21295 | HW - 1800 x 600 RCBC |  | 1 | 660 | 660 | SWC
2012-09-04 | Inv No 21598 | HW - 3/1200 x 300 RCBC |  | 7 | 438 | 3066 | SWC
| Subtotal for SWC |  |  |  |  | 67270
Portfolio WBS SWL
2012-04-11 | Inv No - 20648 | Kerb Adaptors |  | 40 | 58 | 2320 | SWL
2012-05-11 | Inv No 20837 | Grate & Frame |  | 6 | 466 | 2796 | SWL
2012-05-31 | Inv No 20962 | Plumbers Mates |  | 5 | 27.5 | 137.5 | SWL
2012-07-13 | Inv No - 21184 | Grate & Frame |  | 2 | 298 | 596 | SWL
2012-08-06 | 600 X 600 Medium Duty Galvanised Grate & Frame. Inv No - 21367 | Grate & Frame |  | 1 | 279 | 279 | SWL
2012-10-04 | Inv No - 021834 | Grate & Frame |  | 2 | 1227.27 | 2454.54 | SWL
| Subtotal for SWL |  |  |  |  | 8583.04
Portfolio WBS SWP
2011-12-12 | 8- 3 FJ RC pipes, 3- 2FJ RC PIPES Inv No - 20095 | 375 RCP FJ CL3 |  | 1 | 1778 | 1778 | SWP
2012-03-13 | Inv No - 20515 | 450 RCP FJ CL2 |  | 6 | 265 | 1590 | SWP
2012-03-13 | Plus Delivery. Inv No - 20515 | Sand Bands |  | 16 | 264 | 4224 | SWP
2012-07-05 | Inv No 21147 | 300 RCP |  | 7 | 162.857 | 1139.999 | SWP
2012-08-08 | Inv No - 16323 | 450 RCP FJ CL2 |  | 6 | 206 | 1236 | SWP
2012-08-10 | Cartage Chard on Kerb Entry Pits. Inv No - 072408 | Float |  | 1 | 430 | 430 | SWP
2012-08-10 | Inv No - 072408 | Kerb Entry Pit |  | 2 | 76.75 | 153.5 | SWP
| Subtotal for SWP |  |  |  |  | 10551.499
Portfolio WBS SWPC
2011-12-06 | Inv No 070739 | Pre-cast Kerb Unit |  | 1 | 511.67 | 511.67 | SWPC
2012-02-17 | Inv No - 171070. | Kerb Entry Pit |  | 9 | 511.67 | 4605.03 | SWPC
2012-02-17 | Inv No 071070 | Pre-cast Pits |  | 5 | 1377 | 6885 | SWPC
2012-09-01 | Inv No - 072596 | Kerb Entry Pit |  | 1 | 1458.3 | 1458.3 | SWPC
| Subtotal for SWPC |  |  |  |  | 13460
Portfolio WBS WMF
2012-09-04 | Pvc S/W Pipes & Pvc Fittings. Inv No - 21274108 | Pvc S/W Pipe |  | 1 | 134.4 | 134.4 | WMF
| Subtotal for WMF |  |  |  |  | 134.4
| Grand Total |  |  |  |  | 3156786.2267