## Estimate
[9 empty] | 1953141.4285 |  |  | 221063.275 | 354662.8055 | 437028.89 | 940386.458 | 1953141.4285
WBS | Line No. | Resource Name | Unit | Type | No | Prodn | Quantity | Rate | Cost | Usage | Duration | Labour | Material | Plant | Subcontract | Total | Portfolio WBS
3 |  | PRELIMINARIES
4 | Line No 21 Item No 1.1 | Site establishment & disestablishment including but not limited to, mandatory permits and fees | Item |  |  |  | 1 | 36340 | 36340 |  | 5 | 10400 | 0 | 10100 | 15840 | 36340
| 1 | CAR | Item | S | 1 |  | 15840 | 1 | 15840 |  |  | 0 | 0 | 0 | 15840 | 15840 | 904
| 2 | Float | LS | P | 1 |  | 750 | 1 | 750 |  |  | 0 | 0 | 750 | 0 | 750 | 907
| 3 | Float | LS | P | 1 |  | 1800 | 1 | 1800 |  |  | 0 | 0 | 1800 | 0 | 1800 | 907
| 4 | Float | LS | P | 1 |  | 750 | 1 | 750 |  |  | 0 | 0 | 750 | 0 | 750 | 907
| 5 | Float | LS | P | 1 |  | 500 | 1 | 500 |  |  | 0 | 0 | 500 | 0 | 500 | 907
| 6 | Float | LS | P | 1 |  | 900 | 1 | 900 |  |  | 0 | 0 | 900 | 0 | 900 | 907
| 7 | Float | LS | P | 1 |  | 4600 | 1 | 4600 |  |  | 0 | 0 | 4600 | 0 | 4600 | 907
| 8 | Float | LS | P | 1 |  | 800 | 1 | 800 |  |  | 0 | 0 | 800 | 0 | 800 | 907
| 9 | Labour | hr | L | 1 | 1 | 100 | 38 | 3800 | 100 | 100 | 3800 | 0 | 0 | 0 | 3800 | 907
| 10 | Project Supervisor | week | L | 1 | 1 | 1 | 3350 | 3350 | 1 | 1 | 3350 | 0 | 0 | 0 | 3350 | 902
| 11 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 | 1 | 1 | 3250 | 0 | 0 | 0 | 3250 | 901
5 | Line No 22 Item No 1.2 | Establishment and maintenance of Provision for Traffic in accordance with AS 1742 Manual of uniform traffic control devices and as directed by the Superintendent | Item |  |  |  | 1 | 25694.4 | 25694.4 |  | 0 | 0 | 0 | 0 | 25694.4 | 25694.4
5.1 | 1 | Water Barriers | m | S | 1 | 1 | 200 | 82.5 | 16500 | 200 | 200 | 0 | 0 | 0 | 16500 | 16500 | 142
5.2 | 2 | Traffic Control Crew | hr | S | 1 | 1 | 90 | 102.16 | 9194.4 | 90 | 90 | 0 | 0 | 0 | 9194.4 | 9194.4 | 141
6 | Line No 23 Item No 1.3 | Construction Survey Set out | Item |  |  |  | 1 | 16650 | 16650 |  | 0 | 16650 | 0 | 0 | 0 | 16650
6.1 | 1 | Surveyor | hr | L | 1 | 1 | 12 | 185 | 2220 | 0 |  | 2220 | 0 | 0 | 0 | 2220 | 11
6.2 | 2 | Surveyor | hr | L | 1 | 1 | 18 | 185 | 3330 | 0 |  | 3330 | 0 | 0 | 0 | 3330 | 11
6.3 | 3 | Surveyor | hr | L | 1 | 1 | 60 | 185 | 11100 | 0 |  | 11100 | 0 | 0 | 0 | 11100 | 11
7 | Line No 24 Item No 1.4 | As constructed drawings and data, including surveying & drafting in accordance with Council Standards | Item |  |  |  | 1 | 7030 | 7030 |  | 5 | 7030 | 0 | 0 | 0 | 7030
7.1 | 1 | Surveyor | hr | L |  |  | 12 | 185 | 2220 | 0 |  | 2220 | 0 | 0 | 0 | 2220 | 11
7.2 | 2 | Surveyor | hr | L |  |  | 26 | 185 | 4810 | 0 |  | 4810 | 0 | 0 | 0 | 4810 | 11
8 | Line No 25 Item No 1.5 | Preparation & implementation of project quality & OHS&R plans | Item |  |  |  | 1 | 3250 | 3250 |  | 5 | 3250 | 0 | 0 | 0 | 3250
| 1 | Project Engineer | week | L |  |  | 1 | 3250 | 3250 | 0 |  | 3250 | 0 | 0 | 0 | 3250 | 901
9 | Line No 26 Item No 1.6 | Geotechnical Testing | Item |  |  |  | 1 | 14950 | 14950 |  | 0 | 0 | 0 | 0 | 14950 | 14950
| 1 | Geotech Level One | hr | S | 1 | 1 | 1 | 14950 | 14950 | 1 | 1 | 0 | 0 | 0 | 14950 | 14950 | 13
10 | Line No 27 Item No 1.7 | Portable Long Service Levy | Item |  |  |  | 1 | 10220 | 10220 |  | 0 | 0 | 0 | 0 | 10220 | 10220
| 1 | PLSL | Item | S |  |  | 10220 | 1 | 10220 | 0 |  | 0 | 0 | 0 | 10220 | 10220 | 904
11 | Line No 28 Item No 1.8 | Enviromental Management (including ASS management) | Item |  |  |  | 1 | 3250 | 3250 |  | 0 | 3250 | 0 | 0 | 0 | 3250
| 1 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 | 1 | 1 | 3250 | 0 | 0 | 0 | 3250 | 901
12 | Line No 29 Item No 1.9 | Provision for Water | Item |  |  |  | 1 | 12700.8 | 12700.8 |  |  | 0 | 12700.8 | 0 | 0 | 12700.8
| 1 | Water Charge | kL | M | 1 | 1 | 5184 | 2.45 | 12700.8 |  | 5184 | 0 | 12700.8 | 0 | 0 | 12700.8 | 903
13 |  | SEDIMENT & EROSION CONTROL
14 | Line No 33 Item No 2.1 | Establishment and maintenance of interim site drainage as required, sediment and erosion control devices as nominated on drawings and as directed by the Superintendent complete in place | Item |  |  |  | 1 | 9126.0308 | 9126.0308 |  | 3 | 5016.0137 | 2400 | 1710.0171 | 0 | 9126.0308
| 1 | Initial Set-up
14.1 | 2 | Silt Fence | m | M | 1 | 1 | 600 | 2 | 1200 |  |  | 0 | 1200 | 0 | 0 | 1200 | 151
| 3 | Pickets | each | M | 1 | 1 | 200 | 6 | 1200 |  |  | 0 | 1200 | 0 | 0 | 1200 | 151
14.2 | 4 | Bobcat | hr | P | 1 | 33.333 | 600 | 95 | 1710.0171 | 18.0002 | 18.0002 | 0 | 0 | 1710.0171 | 0 | 1710.0171 | 151
| 5 | Labour | hr | L | 2 | 33.333 | 600 | 38 | 1368.0137 | 36.0004 | 18.0002 | 1368.0137 | 0 | 0 | 0 | 1368.0137 | 151
| 6 | Ongoing Maintenance
| 7 | Labour | hr | L | 2 | 1 | 48 | 38 | 3648 | 96 | 48 | 3648 | 0 | 0 | 0 | 3648 | 151
15 |  | EARTHWORKS
16 |  | Tree Protection
17 | Line No 38 Item No | Tree protection including installation, maintenance and removal at the completion of works (Provisional Quantity) | Item |  |  |  | 1 | 514 | 514 |  | 1 | 304 | 210 | 0 | 0 | 514
1
| 2 | Palings | each | M | 60 | 1 | 1 | 3.5 | 210 |  |  | 0 | 210 | 0 | 0 | 210 | 151
| 3 | Labour | hr | L | 2 | 1 | 4 | 38 | 304 | 8 | 4 | 304 | 0 | 0 | 0 | 304 | 151
18 |  | Clearing, Grubbing & Demolition
19 | Line No 41 Item No 3.2.1 | Clearing, grubbing vegetation and disposal off site of cleared vegetation, including but not limited to loading, transportation and dumping fees as nominated on the project drawings | m2 |  |  |  | 12233 | 1.0555 | 12912 |  | 4 | 2052 | 0 | 4860 | 6000 | 12912
1
19.1 | 2 | Excavator - 25T | hr | P | 1 | 1 | 36 | 135 | 4860 | 36 | 36 | 0 | 0 | 4860 | 0 | 4860 | 22
| 3 | Labour | hr | L | 3 | 1 | 18 | 38 | 2052 | 54 | 18 | 2052 | 0 | 0 | 0 | 2052 | 22
| 4 | Mulcher | Item | S | 1 | 12233 | 12233 | 6000 | 6000 | 1 | 1 | 0 | 0 | 0 | 6000 | 6000 | 23
20 | Line No 43 Item No 3.2.2.1 | Existing Bitumen Seal | m2 |  |  |  | 7813 | 1.0097 | 7888.6786 |  | 5 | 1670.0267 | 0 | 6218.6519 | 0 | 7888.6786
1
20.1 | 2 | CAT297 | hr | P | 1 | 177.778 | 7813 | 46.5 | 2043.5853 | 43.9481 | 43.9481 | 0 | 0 | 2043.5853 | 0 | 2043.5853 | 41
| 3 | Labour | hr | L | 1 | 177.778 | 7813 | 38 | 1670.0267 | 43.9481 | 43.9481 | 1670.0267 | 0 | 0 | 0 | 1670.0267 | 41
| 4 | Water Cart - Hire | hr | P | 1 | 177.778 | 7813 | 95 | 4175.0667 | 43.9481 | 43.9481 | 0 | 0 | 4175.0667 | 0 | 4175.0667 | 41
21 | Line No 44 Item No 3.2.2.2 | Existing Concrete Kerb / Kerb & Channel | m |  |  |  | 445 | 28.4741 | 12670.9651 |  | 2 | 608.7551 | 0 | 6247.75 | 5814.4599 | 12670.9651
| 1 | Tip Fees | tonne | S | 1 | 1 | 129.2102 | 45 | 5814.4599 |  |  | 0 | 0 | 0 | 5814.4599 | 5814.4599 | 41
21.1 | 2 | Excavator - 30T | hr | P | 1 | 27.778 | 445 | 135 | 2162.6827 | 16.0199 | 16.0199 | 0 | 0 | 2162.6827 | 0 | 2162.6827 | 41
| 3 | Tipper | hr | P | 3 | 27.778 | 445 | 85 | 4085.0673 | 48.0596 | 16.0199 | 0 | 0 | 4085.0673 | 0 | 4085.0673 | 41
| 4 | Labour | hr | L | 1 | 27.778 | 445 | 38 | 608.7551 | 16.0199 | 16.0199 | 608.7551 | 0 | 0 | 0 | 608.7551 | 41
22 | Line No 45 Item No 3.2.3 | Remove existing structures, slabs, tanks etc. | Item |  |  |  | 1 | 3429 | 3429 |  | 1 | 684 | 0 | 2745 | 0 | 3429
22.1 | 1 | Excavator - 25T | hr | P |  | 1 | 9 | 135 | 1215 | 0 | 9 | 0 | 0 | 1215 | 0 | 1215 | 41
| 2 | Tipper | hr | P |  | 2 | 18 | 85 | 1530 | 0 | 9 | 0 | 0 | 1530 | 0 | 1530 | 41
| 3 | Labour | hr | L |  | 2 | 18 | 38 | 684 | 0 | 9 | 684 | 0 | 0 | 0 | 684 | 41
23 | Line No 46 Item No 3.2.4 | Backfill and compact existing well to WRC requirements | Item |  |  |  | 1 | 3172 | 3172 |  | 1 | 228 | 2944 | 0 | 0 | 3172
23.1 | 1 | Stabilised Sand | m³ | M |  |  | 10 | 258.5 | 2585 |  |  | 0 | 2585 | 0 | 0 | 2585 | 41
| 2 | Sand | tonne | M |  |  | 20 | 17.95 | 359 |  |  | 0 | 359 | 0 | 0 | 359 | 41
| 3 | Labour | hr | L |  | 1 | 6 | 38 | 228 | 0 | 6 | 228 | 0 | 0 | 0 | 228 | 41
24 | Line No 47 Item No 3.2.5 | Relocate existing hazard marker and street sign | Item |  |  |  | 1 | 750 | 750 |  | 1 | 0 | 750 | 0 | 0 | 750
| 1 | Signs - General | Item | M |  |  | 750 | 1 | 750 |  |  | 0 | 750 | 0 | 0 | 750 | 67
25 | Line No 48 Item No 3.2.6 | Remove and stack existing unused signage as directed | item |  |  |  | 1 | 750 | 750 |  | 1 | 0 | 750 | 0 | 0 | 750
| 1 | Signs - General | Item | M |  |  | 750 | 1 | 750 |  |  | 0 | 750 | 0 | 0 | 750 | 67
26 | Line No 49 Item No 3.2.7 | Reinstate existing island and landscaping upon completion of stormwater drainage | m2 |  |  |  | 480 | 1.4253 | 684.1354 |  | 1 | 304 | 0 | 380 | 0.13536 | 684.1354
| 1 | Grass Seeding | m² | S | 1 | 10000 | 576 | 2.35 | 0.13536 |  | 0.0576 | 0 | 0 | 0 | 0.13536 | 0.13536 | 111
26.1 | 2 | Bobcat | hr | P | 1 | 120 | 480 | 95 | 380 | 4 | 4 | 0 | 0 | 380 | 0 | 380 | 111
| 3 | Labour | hr | L | 2 | 120 | 480 | 38 | 304 | 8 | 4 | 304 | 0 | 0 | 0 | 304 | 111
27 | Line No 50 Item No 3.2.8 | Remove abandoned Storm Water Lines and headwalls and dispose off site | m |  |  |  | 83 | 22.8769 | 1898.7814 |  | 1 | 75.3644 | 0 | 1373.417 | 450 | 1898.7814
27.1 | 1 | Excavator - 25T | hr | P | 1 | 9.3 | 83 | 135 | 1204.8387 | 8.9247 | 8.9247 | 0 | 0 | 1204.8387 | 0 | 1204.8387 | 41
| 2 | Tipper | hr | P | 2 | 83.7 | 83 | 85 | 168.5783 | 1.9833 | 0.99164 | 0 | 0 | 168.5783 | 0 | 168.5783 | 41
| 3 | Labour | hr | L | 2 | 83.7 | 83 | 38 | 75.3644 | 1.9833 | 0.99164 | 75.3644 | 0 | 0 | 0 | 75.3644 | 41
| 4 | Tip Fees | tonne | S | 1 | 1 | 10 | 45 | 450 |  |  | 0 | 0 | 0 | 450 | 450 | 41
28 |  | Earthworks
29 | Line No 53 Item No 3.3.1 | Strip and stockpile topsoil from areas of excavation and filling in accordance with the specification (measured as a solid volume, calculated based on an average 100mm natural topsoil depth) | m3 |  |  |  | 916 | 8.575 | 7854.7 |  | 3 | 870.2 | 0 | 6984.5 | 0 | 7854.7
29.1 | 1 | Excavator - 25T | hr | P | 1 | 40 | 916 | 135 | 3091.5 | 22.9 | 22.9 | 0 | 0 | 3091.5 | 0 | 3091.5 | 31
| 2 | Tipper | hr | P | 2 | 40 | 916 | 85 | 3893 | 45.8 | 22.9 | 0 | 0 | 3893 | 0 | 3893 | 31
| 3 | Labour | hr | L | 1 | 40 | 916 | 38 | 870.2 | 22.9 | 22.9 | 870.2 | 0 | 0 | 0 | 870.2 | 31
30 | Line No 54 Item No 3.3.2 | Respread topsoil in accordance with the specification (measured as a solid volume, calculated based on an average 100mm natural topsoil depth) | m3 |  |  |  | 341 | 14.24 | 4855.84 |  | 2 | 1036.64 | 0 | 3819.2 | 0 | 4855.84
30.1 | 1 | Backhoe | hr | P | 1 | 250 | 3410 | 100 | 1364 | 13.64 | 13.64 | 0 | 0 | 1364 | 0 | 1364 | 33
| 2 | Tipper | hr | P | 1 | 250 | 3410 | 85 | 1159.4 | 13.64 | 13.64 | 0 | 0 | 1159.4 | 0 | 1159.4 | 33
| 3 | Bobcat | hr | P | 1 | 250 | 3410 | 95 | 1295.8 | 13.64 | 13.64 | 0 | 0 | 1295.8 | 0 | 1295.8 | 33
| 4 | Labour | hr | L | 2 | 250 | 3410 | 38 | 1036.64 | 27.28 | 13.64 | 1036.64 | 0 | 0 | 0 | 1036.64 | 33
31 | Line No 55 Item No 3.3.3 | Remove from site unused grip material as directed (Provisional) |  |  |  |  | 575 | 13.075 | 7518.125 |  | 2 | 546.25 | 0 | 6971.875 | 0 | 7518.125
31.1 | 1 | Excavator - 25T | hr | P | 1 | 40 | 575 | 135 | 1940.625 | 14.375 | 14.375 | 0 | 0 | 1940.625 | 0 | 1940.625 | 53
| 2 | Tipper | hr | P | 3 | 40 | 575 | 85 | 3665.625 | 43.125 | 14.375 | 0 | 0 | 3665.625 | 0 | 3665.625 | 53
| 3 | Water Cart - Hire | hr | P | 1 | 40 | 575 | 95 | 1365.625 | 14.375 | 14.375 | 0 | 0 | 1365.625 | 0 | 1365.625 | 53
| 4 | Labour | hr | L | 1 | 40 | 575 | 38 | 546.25 | 14.375 | 14.375 | 546.25 | 0 | 0 | 0 | 546.25 | 53
32 | Line No 56 Item No 3.3.4 | Cut to fill including but not limited to, moisture control and compaction as specified (in-place compacted volume of filling) | m3 |  |  |  | 2388 | 7.1168 | 16994.988 |  | 3 | 1633.3936 | 0 | 15361.5944 | 0 | 16994.988
32.1 | 1 | Excavator - 25T | hr | P | 1 | 111.111 | 2388 | 135 | 2901.4229 | 21.492 | 21.492 | 0 | 0 | 2901.4229 | 0 | 2901.4229 | 51
| 2 | Tipper | hr | P | 3 | 111.111 | 2388 | 85 | 5480.4655 | 64.4761 | 21.492 | 0 | 0 | 5480.4655 | 0 | 5480.4655 | 51
| 3 | Labour | hr | L | 2 | 111.111 | 2388 | 38 | 1633.3936 | 42.984 | 21.492 | 1633.3936 | 0 | 0 | 0 | 1633.3936 | 51
| 4 | Grader | hr | P | 1 | 111.111 | 2388 | 145 | 3116.3431 | 21.492 | 21.492 | 0 | 0 | 3116.3431 | 0 | 3116.3431 | 51
| 5 | PF Roller | day | P | 1 | 999.999 | 2388 | 365 | 871.6209 | 2.388 | 2.388 | 0 | 0 | 871.6209 | 0 | 871.6209 | 51
| 6 | Water Cart - Hire | hr | P | 1 | 111.111 | 2388 | 95 | 2041.742 | 21.492 | 21.492 | 0 | 0 | 2041.742 | 0 | 2041.742 | 51
| 7 | Add day with Bobcat to cut Kerb Pads
| 8 | Bobcat | hr | P | 1 | 1 | 10 | 95 | 950 | 10 | 10 | 0 | 0 | 950 | 0 | 950 | 51
33 | Line No 57 Item No 3.3.5 | Imported Fill material including but not limited to, moisture control and compaction as specified (in-place compacted volume of filling) | m3 |  |  |  | 4030 | 13.5037 | 54420.0654 |  | 6 | 5168.4685 | 0 | 49251.5969 | 0 | 54420.0654
| 1 | Win Material From Local Pit
33.1 | 2 | D6 | hr | P | 1 | 133.333 | 4030 | 185 | 5591.639 | 30.2251 | 30.2251 | 0 | 0 | 5591.639 | 0 | 5591.639 | 52
| 3 | Load & Cart
33.2 | 4 | Excavator - 25T | hr | P | 1 | 88.889 | 4030 | 135 | 6120.5548 | 45.3374 | 45.3374 | 0 | 0 | 6120.5548 | 0 | 6120.5548 | 52
| 5 | Truck & Dog | hr | P | 3 | 88.889 | 4030 | 145 | 19721.7878 | 136.0123 | 45.3374 | 0 | 0 | 19721.7878 | 0 | 19721.7878 | 52
| 6 | Place & Compact
| 7 | Grader | hr | P | 1 | 88.889 | 4030 | 145 | 6573.9293 | 45.3374 | 45.3374 | 0 | 0 | 6573.9293 | 0 | 6573.9293 | 52
| 8 | Water Cart - Hire | hr | P | 1 | 88.889 | 4030 | 95 | 4307.0571 | 45.3374 | 45.3374 | 0 | 0 | 4307.0571 | 0 | 4307.0571 | 52
| 9 | PF Roller Wet - No OP | hr | P | 1 | 88.889 | 4030 | 58 | 2629.5717 | 45.3374 | 45.3374 | 0 | 0 | 2629.5717 | 0 | 2629.5717 | 52
| 10 | Labour | hr | L | 3 | 88.889 | 4030 | 38 | 5168.4685 | 136.0123 | 45.3374 | 5168.4685 | 0 | 0 | 0 | 5168.4685 | 52
| 11 | Bobcat | hr | P | 1 | 88.889 | 4030 | 95 | 4307.0571 | 45.3374 | 45.3374 | 0 | 0 | 4307.0571 | 0 | 4307.0571 | 52
34 | Line No 58 Item No 3.3.6 | Cut to spoil including but not limited to loading, transportation and tip fees (Provisional) | m2 |  |  |  | 100 | 17.4333 | 1743.3333 |  | 1 | 126.6667 | 0 | 1616.6667 | 0 | 1743.3333
34.1 | 1 | Excavator - 25T | hr | P | 1 | 30 | 100 | 135 | 450 | 3.3333 | 3.3333 | 0 | 0 | 450 | 0 | 450 | 53
| 2 | Tipper | hr | P | 3 | 30 | 100 | 85 | 850 | 10 | 3.3333 | 0 | 0 | 850 | 0 | 850 | 53
| 3 | Water Cart - Hire | hr | P | 1 | 30 | 100 | 95 | 316.6667 | 3.3333 | 3.3333 | 0 | 0 | 316.6667 | 0 | 316.6667 | 53
| 4 | Labour | hr | L | 1 | 30 | 100 | 38 | 126.6667 | 3.3333 | 3.3333 | 126.6667 | 0 | 0 | 0 | 126.6667 | 53
35 | Line No 59 Item No 3.3.7 | Removal of unsuitable material including excavation, filling and spoiling material (provisional) |  |  |  |  | 150 | 51.1312 | 7669.674 |  | 1 | 703.0051 | 0 | 6966.6689 | 0 | 7669.674
| 1 | Excavatio to spoil
35.1 | 2 | Excavator - 25T | hr | P | 1 | 30 | 150 | 135 | 675 | 5 | 5 | 0 | 0 | 675 | 0 | 675 | 57
| 3 | Tipper | hr | P | 3 | 30 | 150 | 85 | 1275 | 15 | 5 | 0 | 0 | 1275 | 0 | 1275 | 57
| 4 | Water Cart - Hire | hr | P | 1 | 30 | 150 | 95 | 475 | 5 | 5 | 0 | 0 | 475 | 0 | 475 | 57
| 5 | Labour | hr | L | 1 | 30 | 150 | 38 | 190 | 5 | 5 | 190 | 0 | 0 | 0 | 190 | 57
| 6 | Placement of Gravel
| 7 | Win material from local pit
| 8 | D6 | hr | P | 1 | 133.333 | 150 | 185 | 208.1255 | 1.125 | 1.125 | 0 | 0 | 208.1255 | 0 | 208.1255 | 57
| 9 | Load & Cart
35.2 | 10 | Excavator - 25T | hr | P | 1 | 33.333 | 150 | 135 | 607.5061 | 4.5 | 4.5 | 0 | 0 | 607.5061 | 0 | 607.5061 | 57
| 11 | Truck & Dog | hr | P | 3 | 33.333 | 150 | 145 | 1957.5196 | 13.5001 | 4.5 | 0 | 0 | 1957.5196 | 0 | 1957.5196 | 57
| 12 | Place & Compact
| 13 | Grader | hr | P | 1 | 33.333 | 150 | 145 | 652.5065 | 4.5 | 4.5 | 0 | 0 | 652.5065 | 0 | 652.5065 | 57
| 14 | Water Cart - Hire | hr | P | 1 | 33.333 | 150 | 95 | 427.5043 | 4.5 | 4.5 | 0 | 0 | 427.5043 | 0 | 427.5043 | 57
| 15 | PF Roller Wet - No OP | hr | P | 1 | 33.333 | 150 | 58 | 261.0026 | 4.5 | 4.5 | 0 | 0 | 261.0026 | 0 | 261.0026 | 57
| 16 | Labour | hr | L | 3 | 33.333 | 150 | 38 | 513.0051 | 13.5001 | 4.5 | 513.0051 | 0 | 0 | 0 | 513.0051 | 57
| 17 | Bobcat | hr | P | 1 | 33.333 | 150 | 95 | 427.5043 | 4.5 | 4.5 | 0 | 0 | 427.5043 | 0 | 427.5043 | 57
36 | Line No 60 Item No 3.3.8 | Grass seeding to disturbed areas as directed by the Superintendent. | m2 |  |  |  | 2791 | 2.82 | 7870.62 |  | 1 | 0 | 0 | 0 | 7870.62 | 7870.62
| 1 | Grass Seeding | m² | S | 1 | 1 | 3349.2 | 2.35 | 7870.62 |  | 3349.2 | 0 | 0 | 0 | 7870.62 | 7870.62 | 111
37 |  | ROAD WORKS
38 | Line No 64 Item No 4.1 | Sub grade preparation as specified including, but not limited to scarifying, moisture control, blending, spreading, compaction and trimming | m2 |  |  |  | 19963 | 2.0375 | 40673.8203 |  | 13 | 8669.6457 | 0 | 32004.1746 | 0 | 40673.8203
38.1 | 1 | Grader | hr | P | 1 | 175 | 19963 | 145 | 16540.7714 | 114.0743 | 114.0743 | 0 | 0 | 16540.7714 | 0 | 16540.7714 | 61
| 2 | SD Roller | day | P | 1 | 1575 | 19963 | 365 | 4626.346 | 12.6749 | 12.6749 | 0 | 0 | 4626.346 | 0 | 4626.346 | 61
| 3 | Water Cart - Hire | hr | P | 1 | 175 | 19963 | 95 | 10837.0571 | 114.0743 | 114.0743 | 0 | 0 | 10837.0571 | 0 | 10837.0571 | 61
| 4 | Labour | hr | L | 2 | 175 | 19963 | 38 | 8669.6457 | 228.1486 | 114.0743 | 8669.6457 | 0 | 0 | 0 | 8669.6457 | 61
39 |  | Pavement A1
40 | Line No 69 Item No 4.2.1.1 | Base Course - 125mm Type 2.1 | m3 |  |  |  | 555 | 62.9162 | 34918.48 |  | 2 | 1911.6524 | 28302.225 | 4704.6026 | 0 | 34918.48
| 1 | CBR80 | tonne | M | 1 | 1 | 1304.25 | 21.7 | 28302.225 |  |  | 0 | 28302.225 | 0 | 0 | 28302.225 | QM2.1
40.1 | 2 | Grader | hr | P | 1 | 77.778 | 1304.25 | 145 | 2431.4877 | 16.7689 | 16.7689 | 0 | 0 | 2431.4877 | 0 | 2431.4877 | 62
| 3 | Water Cart - Hire | hr | P | 1 | 77.778 | 1304.25 | 95 | 1593.0437 | 16.7689 | 16.7689 | 0 | 0 | 1593.0437 | 0 | 1593.0437 | 62
| 4 | SD Roller | day | P | 1 | 700.002 | 1304.25 | 365 | 680.0713 | 1.8632 | 1.8632 | 0 | 0 | 680.0713 | 0 | 680.0713 | 62
| 5 | Labour | hr | L | 3 | 77.778 | 1304.25 | 38 | 1911.6524 | 50.3066 | 16.7689 | 1911.6524 | 0 | 0 | 0 | 1911.6524 | 62
41 | Line No 70 Item No 4.2.1.2 | Sub-base Course - 100mm Type 2.3 | m3 |  |  |  | 444 | 61.1537 | 27152.234 |  | 2 | 1529.3219 | 21859.23 | 3763.6821 | 0 | 27152.234
| 1 | CBR45 | tonne | M | 1 | 1 | 1043.4 | 20.95 | 21859.23 |  |  | 0 | 21859.23 | 0 | 0 | 21859.23 | QM2.1
41.1 | 2 | Grader | hr | P | 1 | 77.778 | 1043.4 | 145 | 1945.1902 | 13.4151 | 13.4151 | 0 | 0 | 1945.1902 | 0 | 1945.1902 | 62
| 3 | Water Cart - Hire | hr | P | 1 | 77.778 | 1043.4 | 95 | 1274.4349 | 13.4151 | 13.4151 | 0 | 0 | 1274.4349 | 0 | 1274.4349 | 62
| 4 | SD Roller | day | P | 1 | 700.002 | 1043.4 | 365 | 544.057 | 1.4906 | 1.4906 | 0 | 0 | 544.057 | 0 | 544.057 | 62
| 5 | Labour | hr | L | 3 | 77.778 | 1043.4 | 38 | 1529.3219 | 40.2453 | 13.4151 | 1529.3219 | 0 | 0 | 0 | 1529.3219 | 62
42 |  | Pavement A2 - Roadways
43 | Line No 72 Item No 4.2.3.1 | Base Course - 125mm Type 2.1 | m3 |  |  |  | 38 | 62.9162 | 2390.8148 |  | 1 | 130.8879 | 1937.81 | 322.1169 | 0 | 2390.8148
| 1 | CBR80 | tonne | M | 1 | 1 | 89.3 | 21.7 | 1937.81 |  |  | 0 | 1937.81 | 0 | 0 | 1937.81 | QM2.1
43.1 | 2 | Grader | hr | P | 1 | 77.778 | 89.3 | 145 | 166.4802 | 1.1481 | 1.1481 | 0 | 0 | 166.4802 | 0 | 166.4802 | 62
| 3 | Water Cart - Hire | hr | P | 1 | 77.778 | 89.3 | 95 | 109.0733 | 1.1481 | 1.1481 | 0 | 0 | 109.0733 | 0 | 109.0733 | 62
| 4 | SD Roller | day | P | 1 | 700.002 | 89.3 | 365 | 46.5634 | 0.12757 | 0.12757 | 0 | 0 | 46.5634 | 0 | 46.5634 | 62
| 5 | Labour | hr | L | 3 | 77.778 | 89.3 | 38 | 130.8879 | 3.4444 | 1.1481 | 130.8879 | 0 | 0 | 0 | 130.8879 | 62
44 | Line No 73 Item No 4.2.3.2 | Sub-base Course - 100mm Type 2.3 | m3 |  |  |  | 31 | 61.1537 | 1895.7641 |  | 1 | 106.777 | 1526.2075 | 262.7796 | 0 | 1895.7641
| 1 | CBR45 | tonne | M | 1 | 1 | 72.85 | 20.95 | 1526.2075 |  |  | 0 | 1526.2075 | 0 | 0 | 1526.2075 | QM2.1
44.1 | 2 | Grader | hr | P | 1 | 77.778 | 72.85 | 145 | 135.8128 | 0.93664 | 0.93664 | 0 | 0 | 135.8128 | 0 | 135.8128 | 62
| 3 | Water Cart - Hire | hr | P | 1 | 77.778 | 72.85 | 95 | 88.9808 | 0.93664 | 0.93664 | 0 | 0 | 88.9808 | 0 | 88.9808 | 62
| 4 | SD Roller | day | P | 1 | 700.002 | 72.85 | 365 | 37.986 | 0.10407 | 0.10407 | 0 | 0 | 37.986 | 0 | 37.986 | 62
| 5 | Labour | hr | L | 3 | 77.778 | 72.85 | 38 | 106.777 | 2.8099 | 0.93664 | 106.777 | 0 | 0 | 0 | 106.777 | 62
45 |  | Pavement A2 - Rental Car Park
46 | Line No 75 Item No 4.2.4.1 | Base Course - 125mm Type 2.1 | m3 |  |  |  | 344 | 62.9162 | 21643.166 |  | 2 | 1184.88 | 17542.28 | 2916.006 | 0 | 21643.166
| 1 | CBR80 | tonne | M | 1 | 1 | 808.4 | 21.7 | 17542.28 |  |  | 0 | 17542.28 | 0 | 0 | 17542.28 | QM2.1
46.1 | 2 | Grader | hr | P | 1 | 77.778 | 808.4 | 145 | 1507.0843 | 10.3937 | 10.3937 | 0 | 0 | 1507.0843 | 0 | 1507.0843 | 62
| 3 | Water Cart - Hire | hr | P | 1 | 77.778 | 808.4 | 95 | 987.4 | 10.3937 | 10.3937 | 0 | 0 | 987.4 | 0 | 987.4 | 62
| 4 | SD Roller | day | P | 1 | 700.002 | 808.4 | 365 | 421.5217 | 1.1549 | 1.1549 | 0 | 0 | 421.5217 | 0 | 421.5217 | 62
| 5 | Labour | hr | L | 3 | 77.778 | 808.4 | 38 | 1184.88 | 31.1811 | 10.3937 | 1184.88 | 0 | 0 | 0 | 1184.88 | 62
47 | Line No 76 Item No 4.2.4.2 | Sub-Base Course - 100mm Type 2.3 | m3 |  |  |  | 275 | 61.1537 | 16817.2621 |  | 1 | 947.2152 | 13538.9375 | 2331.1094 | 0 | 16817.2621
| 1 | CBR45 | tonne | M | 1 | 1 | 646.25 | 20.95 | 13538.9375 |  |  | 0 | 13538.9375 | 0 | 0 | 13538.9375 | QM2.1
47.1 | 2 | Grader | hr | P | 1 | 77.778 | 646.25 | 145 | 1204.7912 | 8.3089 | 8.3089 | 0 | 0 | 1204.7912 | 0 | 1204.7912 | 62
| 3 | Water Cart - Hire | hr | P | 1 | 77.778 | 646.25 | 95 | 789.346 | 8.3089 | 8.3089 | 0 | 0 | 789.346 | 0 | 789.346 | 62
| 4 | SD Roller | day | P | 1 | 700.002 | 646.25 | 365 | 336.9723 | 0.92321 | 0.92321 | 0 | 0 | 336.9723 | 0 | 336.9723 | 62
| 5 | Labour | hr | L | 3 | 77.778 | 646.25 | 38 | 947.2152 | 24.9267 | 8.3089 | 947.2152 | 0 | 0 | 0 | 947.2152 | 62
48 |  | Pavement B - Roadway
49 | Line No 78 Item No 4.2.5.1 | Base Course - 150mm Type 2.1 | m3 |  |  |  | 77 | 62.9162 | 4844.5459 |  | 1 | 265.2202 | 3926.615 | 652.7106 | 0 | 4844.5459
| 1 | CBR80 | tonne | M | 1 | 1 | 180.95 | 21.7 | 3926.615 |  |  | 0 | 3926.615 | 0 | 0 | 3926.615 | QM2.1
49.1 | 2 | Grader | hr | P | 1 | 77.778 | 180.95 | 145 | 337.3415 | 2.3265 | 2.3265 | 0 | 0 | 337.3415 | 0 | 337.3415 | 62
| 3 | Water Cart - Hire | hr | P | 1 | 77.778 | 180.95 | 95 | 221.0169 | 2.3265 | 2.3265 | 0 | 0 | 221.0169 | 0 | 221.0169 | 62
| 4 | SD Roller | day | P | 1 | 700.002 | 180.95 | 365 | 94.3522 | 0.2585 | 0.2585 | 0 | 0 | 94.3522 | 0 | 94.3522 | 62
| 5 | Labour | hr | L | 3 | 77.778 | 180.95 | 38 | 265.2202 | 6.9795 | 2.3265 | 265.2202 | 0 | 0 | 0 | 265.2202 | 62
50 | Line No 79 Item No 4.2.5.2 | Upper Sub-Base Course - 150mm Type 2.3 | m3 |  |  |  | 77 | 61.1537 | 4708.8334 |  | 1 | 265.2202 | 3790.9025 | 652.7106 | 0 | 4708.8334
| 1 | CBR45 | tonne | M | 1 | 1 | 180.95 | 20.95 | 3790.9025 |  |  | 0 | 3790.9025 | 0 | 0 | 3790.9025 | QM2.1
50.1 | 2 | Grader | hr | P | 1 | 77.778 | 180.95 | 145 | 337.3415 | 2.3265 | 2.3265 | 0 | 0 | 337.3415 | 0 | 337.3415 | 62
| 3 | Water Cart - Hire | hr | P | 1 | 77.778 | 180.95 | 95 | 221.0169 | 2.3265 | 2.3265 | 0 | 0 | 221.0169 | 0 | 221.0169 | 62
| 4 | SD Roller | day | P | 1 | 700.002 | 180.95 | 365 | 94.3522 | 0.2585 | 0.2585 | 0 | 0 | 94.3522 | 0 | 94.3522 | 62
| 5 | Labour | hr | L | 3 | 77.778 | 180.95 | 38 | 265.2202 | 6.9795 | 2.3265 | 265.2202 | 0 | 0 | 0 | 265.2202 | 62
51 | Line No 80 Item No 4.2.5.3 | Lower Sub-Base Course - 150mm Type 2.3 | m3 |  |  |  | 77 | 61.1537 | 4708.8334 |  | 1 | 265.2202 | 3790.9025 | 652.7106 | 0 | 4708.8334
| 1 | CBR45 | tonne | M | 1 | 1 | 180.95 | 20.95 | 3790.9025 |  |  | 0 | 3790.9025 | 0 | 0 | 3790.9025 | QM2.1
51.1 | 2 | Grader | hr | P | 1 | 77.778 | 180.95 | 145 | 337.3415 | 2.3265 | 2.3265 | 0 | 0 | 337.3415 | 0 | 337.3415 | 62
| 3 | Water Cart - Hire | hr | P | 1 | 77.778 | 180.95 | 95 | 221.0169 | 2.3265 | 2.3265 | 0 | 0 | 221.0169 | 0 | 221.0169 | 62
| 4 | SD Roller | day | P | 1 | 700.002 | 180.95 | 365 | 94.3522 | 0.2585 | 0.2585 | 0 | 0 | 94.3522 | 0 | 94.3522 | 62
| 5 | Labour | hr | L | 3 | 77.778 | 180.95 | 38 | 265.2202 | 6.9795 | 2.3265 | 265.2202 | 0 | 0 | 0 | 265.2202 | 62
52 |  | Pavement B - Public Car Park including Road 3
53 | Line No 82 Item No 4.2.6.1 | Base Course - 150mm Type 2.1 | m3 |  |  |  | 336 | 62.9162 | 21139.8366 |  | 2 | 1157.3247 | 17134.32 | 2848.1919 | 0 | 21139.8366
| 1 | CBR80 | tonne | M | 1 | 1 | 789.6 | 21.7 | 17134.32 |  |  | 0 | 17134.32 | 0 | 0 | 17134.32 | QM2.1
53.1 | 2 | Grader | hr | P | 1 | 77.778 | 789.6 | 145 | 1472.0358 | 10.152 | 10.152 | 0 | 0 | 1472.0358 | 0 | 1472.0358 | 62
| 3 | Water Cart - Hire | hr | P | 1 | 77.778 | 789.6 | 95 | 964.4372 | 10.152 | 10.152 | 0 | 0 | 964.4372 | 0 | 964.4372 | 62
| 4 | SD Roller | day | P | 1 | 700.002 | 789.6 | 365 | 411.7188 | 1.128 | 1.128 | 0 | 0 | 411.7188 | 0 | 411.7188 | 62
| 5 | Labour | hr | L | 3 | 77.778 | 789.6 | 38 | 1157.3247 | 30.4559 | 10.152 | 1157.3247 | 0 | 0 | 0 | 1157.3247 | 62
54 | Line No 83 Item No 4.2.6.2 | Upper Sub Base Course - 150mm Type 2.3 | m3 |  |  |  | 336 | 61.1537 | 20547.6366 |  | 2 | 1157.3247 | 16542.12 | 2848.1919 | 0 | 20547.6366
| 1 | CBR45 | tonne | M | 1 | 1 | 789.6 | 20.95 | 16542.12 |  |  | 0 | 16542.12 | 0 | 0 | 16542.12 | QM2.1
54.1 | 2 | Grader | hr | P | 1 | 77.778 | 789.6 | 145 | 1472.0358 | 10.152 | 10.152 | 0 | 0 | 1472.0358 | 0 | 1472.0358 | 62
| 3 | Water Cart - Hire | hr | P | 1 | 77.778 | 789.6 | 95 | 964.4372 | 10.152 | 10.152 | 0 | 0 | 964.4372 | 0 | 964.4372 | 62
| 4 | SD Roller | day | P | 1 | 700.002 | 789.6 | 365 | 411.7188 | 1.128 | 1.128 | 0 | 0 | 411.7188 | 0 | 411.7188 | 62
| 5 | Labour | hr | L | 3 | 77.778 | 789.6 | 38 | 1157.3247 | 30.4559 | 10.152 | 1157.3247 | 0 | 0 | 0 | 1157.3247 | 62
55 | Line No 84 Item No 4.2.6.3 | Lower Base Course - 150mm Type 2.3 | m3 |  |  |  | 336 | 61.1537 | 20547.6366 |  | 2 | 1157.3247 | 16542.12 | 2848.1919 | 0 | 20547.6366
| 1 | CBR45 | tonne | M | 1 | 1 | 789.6 | 20.95 | 16542.12 |  |  | 0 | 16542.12 | 0 | 0 | 16542.12 | QM2.1
55.1 | 2 | Grader | hr | P | 1 | 77.778 | 789.6 | 145 | 1472.0358 | 10.152 | 10.152 | 0 | 0 | 1472.0358 | 0 | 1472.0358 | 62
| 3 | Water Cart - Hire | hr | P | 1 | 77.778 | 789.6 | 95 | 964.4372 | 10.152 | 10.152 | 0 | 0 | 964.4372 | 0 | 964.4372 | 62
| 4 | SD Roller | day | P | 1 | 700.002 | 789.6 | 365 | 411.7188 | 1.128 | 1.128 | 0 | 0 | 411.7188 | 0 | 411.7188 | 62
| 5 | Labour | hr | L | 3 | 77.778 | 789.6 | 38 | 1157.3247 | 30.4559 | 10.152 | 1157.3247 | 0 | 0 | 0 | 1157.3247 | 62
56 | Line No 85 Item No 4.3 | Final Trim to Pavement | m2 |  |  |  | 16547 | 2.4622 | 40742.3911 |  | 13 | 8383.8133 | 0 | 32358.5778 | 0 | 40742.3911
56.1 | 1 | Grader | hr | P | 1 | 150 | 16547 | 145 | 15995.4333 | 110.3133 | 110.3133 | 0 | 0 | 15995.4333 | 0 | 15995.4333 | 63
| 2 | MW Roller | day | P | 1 | 1350 | 16547 | 480 | 5883.3778 | 12.257 | 12.257 | 0 | 0 | 5883.3778 | 0 | 5883.3778 | 63
| 3 | Water Cart - Hire | hr | P | 1 | 150 | 16547 | 95 | 10479.7667 | 110.3133 | 110.3133 | 0 | 0 | 10479.7667 | 0 | 10479.7667 | 63
| 4 | Labour | hr | L | 2 | 150 | 16547 | 38 | 8383.8133 | 220.6267 | 110.3133 | 8383.8133 | 0 | 0 | 0 | 8383.8133 | 63
57 |  | Concrete Works
58 |  | Concrete Kerb & Channel as specified in place, including but not limited to transitions, ramps & gullies
59 | Line No 90 Item No 4.4.1.1 | Barrier Kerb & Channel Type B1 600mm wide | m |  |  |  | 670 | 41.0082 | 27475.5126 |  | 6.7 | 0 | 13908.0126 | 0 | 13567.5 | 27475.5126
| 1 | S32 - Kerb Mix | m³ | M | 1 | 1 | 77.916 | 178.5 | 13908.0126 |  |  | 0 | 13908.0126 | 0 | 0 | 13908.0126 | CKM
| 2 | Kerb Subbie | m | S | 1 | 1 | 670 | 20.25 | 13567.5 | 670 | 670 | 0 | 0 | 0 | 13567.5 | 13567.5 | 71
60 | Line No 91 Item No 4.4.1.2 | Barrier Kerb Type B2 | m |  |  |  | 372 | 29.0871 | 10820.3905 |  | 3.72 | 0 | 3287.3905 | 0 | 7533 | 10820.3905
| 1 | S32 - Kerb Mix | m³ | M | 1 | 1 | 18.4168 | 178.5 | 3287.3905 |  |  | 0 | 3287.3905 | 0 | 0 | 3287.3905 | CKM
| 2 | Kerb Subbie | m | S | 1 | 1 | 372 | 20.25 | 7533 | 372 | 372 | 0 | 0 | 0 | 7533 | 7533 | 71
61 | Line No 92 Item No 4.4.1.3 | Semi Mountable Kerb Type SM4 | m |  |  |  | 207 | 4.1469 | 858.4031 |  | 1 | 0 | 850.0196 | 0 | 8.3835 | 858.4031
| 1 | S32 - Kerb Mix | m³ | M | 1 | 1 | 4.762 | 178.5 | 850.0196 |  |  | 0 | 850.0196 | 0 | 0 | 850.0196 | CKM
| 2 | Kerb Subbie | m | S | 1 | 500 | 207 | 20.25 | 8.3835 | 0.414 | 0.414 | 0 | 0 | 0 | 8.3835 | 8.3835 | 71
62 | Line No 93 Item No 4.4.2 | Kerb Ramp | No. |  |  |  | 5 | 458.2 | 2291 |  | 5 | 0 | 791 | 0 | 1500 | 2291
| 1 | N25 | m³ | M | 1 | 1 | 5 | 158.2 | 791 |  |  | 0 | 791 | 0 | 0 | 791 | C25
| 2 | Kerb Ramp Subbie | each | S | 1 | 1 | 5 | 300 | 1500 | 5 | 5 | 0 | 0 | 0 | 1500 | 1500 | 73
63 | Line No 94 Item No 4.4.3 | Raised Threshold Pedestrian Crossing | m2 |  |  |  | 161 | 70.0401 | 11276.4621 |  | 4.025 | 224.3491 | 6746.6766 | 280.4364 | 4025 | 11276.4621
| 1 | Material Supply
| 2 | N32 | m³ | M | 1 | 1 | 30.9913 | 167.2 | 5181.7517 |  |  | 0 | 5181.7517 | 0 | 0 | 5181.7517 | C32
| 3 | SL72 | m² | M | 1 | 1 | 193.2 | 5.76 | 1112.832 |  |  | 0 | 1112.832 | 0 | 0 | 1112.832 | RSM
| 4 | Sand | tonne | M | 1 | 1 | 17.7118 | 17.95 | 317.9263 |  |  | 0 | 317.9263 | 0 | 0 | 317.9263 | QMS
| 5 | Dowels | each | M | 1 | 1 | 67.0833 | 2 | 134.1667 |  |  | 0 | 134.1667 | 0 | 0 | 134.1667 | RSB
| 6 | Place Sand
63.1 | 7 | Bobcat | hr | P | 1 | 6 | 17.7118 | 95 | 280.4364 | 2.952 | 2.952 | 0 | 0 | 280.4364 | 0 | 280.4364 | 73
| 8 | Labour | hr | L | 2 | 6 | 17.7118 | 38 | 224.3491 | 5.9039 | 2.952 | 224.3491 | 0 | 0 | 0 | 224.3491 | 73
| 9 | Form & Place
| 10 | Concrete Subbie | m² | S | 1 | 1 | 161 | 25 | 4025 | 161 | 161 | 0 | 0 | 0 | 4025 | 4025 | 73
64 |  | Additional Concrete Works
65 | Line No 97 Item No 4.4.4.1 | Concrete Footpaths 2.45m wide | m2 |  |  |  | 195 | 55.2566 | 10775.0386 |  | 5 | 271.6973 | 5288.7197 | 339.6216 | 4875 | 10775.0386
| 1 | Material Supply
| 2 | N25 | m³ | M | 1 | 1 | 21.4498 | 158.2 | 3393.3561 |  |  | 0 | 3393.3561 | 0 | 0 | 3393.3561 | C25
| 3 | SL72 | m² | M | 1 | 1 | 234 | 5.76 | 1347.84 |  |  | 0 | 1347.84 | 0 | 0 | 1347.84 | RSM
| 4 | Sand | tonne | M | 1 | 1 | 21.4498 | 17.95 | 385.0236 |  |  | 0 | 385.0236 | 0 | 0 | 385.0236 | QMS
| 5 | Dowels | each | M | 1 | 1 | 81.25 | 2 | 162.5 |  |  | 0 | 162.5 | 0 | 0 | 162.5 | RSB
| 6 | Place Sand
65.1 | 7 | Bobcat | hr | P | 1 | 6 | 21.4498 | 95 | 339.6216 | 3.575 | 3.575 | 0 | 0 | 339.6216 | 0 | 339.6216 | 73
| 8 | Labour | hr | L | 2 | 6 | 21.4498 | 38 | 271.6973 | 7.1499 | 3.575 | 271.6973 | 0 | 0 | 0 | 271.6973 | 73
Form & Supply
| 10 | Concrete Subbie | m² | S | 1 | 1 | 195 | 25 | 4875 |  | 195 | 0 | 0 | 0 | 4875 | 4875 | 73
66 | Line No 98 Item No 4.4.4.2 | Concrete Footpaths 2.5m wide | m2 |  |  |  | 23 | 55.2566 | 1270.902 |  | 1 | 32.0463 | 623.7977 | 40.0579 | 575 | 1270.902
| 1 | Material Supply
| 2 | N25 | m³ | M | 1 | 1 | 2.53 | 158.2 | 400.242 |  |  | 0 | 400.242 | 0 | 0 | 400.242 | C25
| 3 | SL72 | m² | M | 1 | 1 | 27.6 | 5.76 | 158.976 |  |  | 0 | 158.976 | 0 | 0 | 158.976 | RSM
| 4 | Sand | tonne | M | 1 | 1 | 2.53 | 17.95 | 45.413 |  |  | 0 | 45.413 | 0 | 0 | 45.413 | QMS
| 5 | Dowels | each | M | 1 | 1 | 9.5833 | 2 | 19.1667 |  |  | 0 | 19.1667 | 0 | 0 | 19.1667 | RSB
| 6 | Place Sand
66.1 | 7 | Bobcat | hr | P | 1 | 6 | 2.53 | 95 | 40.0579 | 0.42166 | 0.42166 | 0 | 0 | 40.0579 | 0 | 40.0579 | 73
| 8 | Labour | hr | L | 2 | 6 | 2.53 | 38 | 32.0463 | 0.84332 | 0.42166 | 32.0463 | 0 | 0 | 0 | 32.0463 | 73
| 9 | Form & Place
| 10 | Concrete Subbie | m² | S | 1 | 1 | 23 | 25 | 575 |  | 23 | 0 | 0 | 0 | 575 | 575 | 73
67 | Line No 99 Item No 4.4.4.3 | Concrete Footpaths 3m wide | m2 |  |  |  | 439 | 37.7566 | 16575.151 |  | 8 | 611.6672 | 11906.3998 | 764.584 | 3292.5 | 16575.151
| 1 | Material Supply
| 2 | N25 | m³ | M | 1 | 1 | 48.2895 | 158.2 | 7639.4016 |  |  | 0 | 7639.4016 | 0 | 0 | 7639.4016 | C25
| 3 | SL72 | m² | M | 1 | 1 | 526.8 | 5.76 | 3034.368 |  |  | 0 | 3034.368 | 0 | 0 | 3034.368 | RSM
| 4 | Sand | tonne | M | 1 | 1 | 48.2895 | 17.95 | 866.7968 |  |  | 0 | 866.7968 | 0 | 0 | 866.7968 | QMS
| 5 | Dowels | each | M | 1 | 1 | 182.9167 | 2 | 365.8333 |  |  | 0 | 365.8333 | 0 | 0 | 365.8333 | RSB
| 6 | Place Sand
67.1 | 7 | Bobcat | hr | P | 1 | 6 | 48.2895 | 95 | 764.584 | 8.0483 | 8.0483 | 0 | 0 | 764.584 | 0 | 764.584 | 73
| 8 | Labour | hr | L | 2 | 6 | 48.2895 | 38 | 611.6672 | 16.0965 | 8.0483 | 611.6672 | 0 | 0 | 0 | 611.6672 | 73
| 9 | Form & Place
| 10 | Concrete Subbie | m² | S | 1 | 3.3333 | 439 | 25 | 3292.5 |  | 131.7 | 0 | 0 | 0 | 3292.5 | 3292.5 | 73
68 | Line No 100 Item No 4.4.4.4 | Concrete Infill to Median Islands to carparks and round about island, complete in place | m2 |  |  |  | 102 | 36.9233 | 3766.174 |  | 4 | 142.1186 | 2681.4072 | 177.6482 | 765 | 3766.174
| 1 | Material Supply
| 2 | N25 | m³ | M | 1 | 1 | 11.2199 | 158.2 | 1774.9863 |  |  | 0 | 1774.9863 | 0 | 0 | 1774.9863 | C25
| 3 | SL72 | m² | M | 1 | 1 | 122.4 | 5.76 | 705.024 |  |  | 0 | 705.024 | 0 | 0 | 705.024 | RSM
| 4 | Sand | tonne | M | 1 | 1 | 11.2199 | 17.95 | 201.397 |  |  | 0 | 201.397 | 0 | 0 | 201.397 | QMS
| 5 | Place Sand
| 6 | Bobcat | hr | P | 1 | 6 | 11.2199 | 95 | 177.6482 | 1.87 | 1.87 | 0 | 0 | 177.6482 | 0 | 177.6482 | 73
| 7 | Labour | hr | L | 2 | 6 | 11.2199 | 38 | 142.1186 | 3.74 | 1.87 | 142.1186 | 0 | 0 | 0 | 142.1186 | 73
| 8 | Form & Place
| 9 | Concrete Subbie | m² | S | 1 | 3.3333 | 102 | 25 | 765 |  | 30.6 | 0 | 0 | 0 | 765 | 765 | 73
69 | Line No 101 Item No 4.4.4.5 | Wheelstops, complete in place (in accordance with AS2890.1) | No. |  |  |  | 86 | 154.6667 | 13301.3333 |  | 1 | 3268 | 7310 | 2723.3333 | 0 | 13301.3333
| 1 | Wheelstops | each | M | 1 | 1 | 86 | 85 | 7310 |  |  | 0 | 7310 | 0 | 0 | 7310 | 67
| 2 | Labour | hr | L | 3 | 3 | 86 | 38 | 3268 | 86 | 28.6667 | 3268 | 0 | 0 | 0 | 3268 | 67
| 3 | Bobcat | hr | P | 1 | 3 | 86 | 95 | 2723.3333 | 28.6667 | 28.6667 | 0 | 0 | 2723.3333 | 0 | 2723.3333 | 67
70 |  | Surfacing Works
71 |  | Existing Public Carpark
72 | Line No 105 Item No 4.5.1.1 | First Seal: 7mm CRS60 | m2 |  |  |  | 2490 | 4.7145 | 11739.105 |  | 1 | 0 | 0 | 0 | 11739.105 | 11739.105
| 1 | Primer Seal | m² | S | 1 | 1 | 2614.5 | 4.49 | 11739.105 |  | 1 | 0 | 0 | 0 | 11739.105 | 11739.105 | 64
73 | Line No 106 Item No 4.5.1.2 | Second Seal: 40mm AC Surfacing, (DG10) complete in place, including but not limited to supply, compaction and prime coat) | tonne |  |  |  | 249 | 287 | 71463 |  | 1 | 0 | 0 | 0 | 71463 | 71463
| 1 | DG10 | tonne | S | 1 | 1 | 249 | 287 | 71463 |  | 1 | 0 | 0 | 0 | 71463 | 71463 | 65
74 |  | Roadways and New Carpark
75 | Line No 108 Item No 4.6.2.1 | First Seal: 7mm CRS60 Primerseal | m2 |  |  |  | 10261 | 4.7145 | 48375.4845 |  | 1 | 0 | 0 | 0 | 48375.4845 | 48375.4845
| 1 | Primer Seal | m² | S | 1 | 1 | 10774.05 | 4.49 | 48375.4845 |  | 1 | 0 | 0 | 0 | 48375.4845 | 48375.4845 | 64
76 | Line No 109 Item No 4.6.2.2 | Second Seal: 40mm AC Surfacing, (DG10) complete in place, including but not limited to supply, compaction and prime coat) | tonne |  |  |  | 1026 | 287 | 294462 |  | 3 | 0 | 0 | 0 | 294462 | 294462
| 1 | DG10 | tonne | S | 1 | 1 | 1026 | 287 | 294462 |  | 3 | 0 | 0 | 0 | 294462 | 294462 | 65
77 |  | Signage and Pavement Marking
78 | Line No 112 Item No 4.7.1 | Signage and pavement marking, complete in place. All work to be in accordance with the requirements of AS 1742 Manual of Uniform Traffic Control Devices (Provisional Sum) | Item |  |  |  | 1 | 7660 | 7660 |  | 1 | 0 | 0 | 0 | 7660 | 7660
| 1 | Line Marking | m² | S | 1 | 1 | 1 | 7660 | 7660 |  | 1 | 0 | 0 | 0 | 7660 | 7660 | 66
79 | Line No 113 Item No 4.7.2 | Signage complete in place including supply and installation. All work to be in accordance with the requirements of AS 1742 Manual of Uniform Traffic Control Devices(Provisional Sum) | Item |  |  |  | 1 | 1682.1 | 1682.1 |  | 1 | 228 | 1314.6 | 139.5 | 0 | 1682.1
| 1 | Signs Complete | each | M |  | 1 | 6 | 140 | 840 |  |  | 0 | 840 | 0 | 0 | 840 | RFS
| 2 | N25 | m³ | M |  | 1 | 3 | 158.2 | 474.6 |  |  | 0 | 474.6 | 0 | 0 | 474.6 | C25
| 3 | CAT297 | hr | P |  | 1 | 3 | 46.5 | 139.5 | 0 | 3 | 0 | 0 | 139.5 | 0 | 139.5 | 67
| 4 | Labour | hr | L |  | 1 | 6 | 38 | 228 | 0 | 6 | 228 | 0 | 0 | 0 | 228 | 67
80 |  | STORMWATER DRAINAGE
81 |  | Pipework
82 | Line No 119 Item No 5.1.1 | 375mm dia Class 2 RRJ | m |  |  |  | 82.8 | 123.278 | 10207.4201 |  | 2 | 1415.8092 | 6928.704 | 1862.9069 | 0 | 10207.4201
| 1 | Material Supply
| 2 | 375 RCP | m | M | 1 | 1 | 82.8 | 58.55 | 4847.94 |  |  | 0 | 4847.94 | 0 | 0 | 4847.94 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 115.92 | 17.95 | 2080.764 |  |  | 0 | 2080.764 | 0 | 0 | 2080.764 | QMS
| 4 | Excavation & Laying
82.1 | 5 | Excavator - 25T | hr | P | 1 | 6.667 | 82.8 | 135 | 1676.6162 | 12.4194 | 12.4194 | 0 | 0 | 1676.6162 | 0 | 1676.6162 | 81
| 6 | Labour | hr | L | 3 | 6.667 | 82.8 | 38 | 1415.8092 | 37.2581 | 12.4194 | 1415.8092 | 0 | 0 | 0 | 1415.8092 | 81
| 7 | Trench Roller | hr | P | 1 | 6.667 | 82.8 | 15 | 186.2907 | 12.4194 | 12.4194 | 0 | 0 | 186.2907 | 0 | 186.2907 | 81
83 | Line No 120 Item No 5.1.2 | 375mm dia Class 3 RRJ | m |  |  |  | 46.8 | 136.648 | 6395.1273 |  | 1 | 800.24 | 4541.94 | 1052.9474 | 0 | 6395.1273
| 1 | Material Supply
| 2 | 375 RCP FJ CL3 | m | M | 1 | 1 | 46.8 | 71.92 | 3365.856 |  |  | 0 | 3365.856 | 0 | 0 | 3365.856 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 65.52 | 17.95 | 1176.084 |  |  | 0 | 1176.084 | 0 | 0 | 1176.084 | QMS
| 4 | Excavation & Laying
83.1 | 5 | Excavator - 25T | hr | P | 1 | 6.667 | 46.8 | 135 | 947.6526 | 7.0196 | 7.0196 | 0 | 0 | 947.6526 | 0 | 947.6526 | 81
| 6 | Labour | hr | L | 3 | 6.667 | 46.8 | 38 | 800.24 | 21.0589 | 7.0196 | 800.24 | 0 | 0 | 0 | 800.24 | 81
| 7 | Trench Roller | hr | P | 1 | 6.667 | 46.8 | 15 | 105.2947 | 7.0196 | 7.0196 | 0 | 0 | 105.2947 | 0 | 105.2947 | 81
84 | Line No 121 Item No 5.1.3 | 450mm dia Class 2 RRJ | m |  |  |  | 20.4 | 141.658 | 2889.8236 |  | 1 | 348.8226 | 2082.024 | 458.9771 | 0 | 2889.8236
| 1 | Material Supply
| 2 | 450 RCP FJ CL2 | m | M | 1 | 1 | 20.4 | 76.93 | 1569.372 |  |  | 0 | 1569.372 | 0 | 0 | 1569.372 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 28.56 | 17.95 | 512.652 |  |  | 0 | 512.652 | 0 | 0 | 512.652 | QMS
| 4 | Excavation & Laying
84.1 | 5 | Excavator - 25T | hr | P | 1 | 6.667 | 20.4 | 135 | 413.0793 | 3.0598 | 3.0598 | 0 | 0 | 413.0793 | 0 | 413.0793 | 81
| 6 | Labour | hr | L | 3 | 6.667 | 20.4 | 38 | 348.8226 | 9.1795 | 3.0598 | 348.8226 | 0 | 0 | 0 | 348.8226 | 81
| 7 | Trench Roller | hr | P | 1 | 6.667 | 20.4 | 15 | 45.8977 | 3.0598 | 3.0598 | 0 | 0 | 45.8977 | 0 | 45.8977 | 81
85 | Line No 122 Item No 5.1.4 | 450mm dia Class 3 RRJ | m |  |  |  | 21.6 | 179.788 | 3883.4212 |  | 1 | 369.3415 | 3028.104 | 485.9757 | 0 | 3883.4212
| 1 | Material Supply
| 2 | 450 RCP FJ CL4 | m | M | 1 | 1 | 21.6 | 115.06 | 2485.296 |  |  | 0 | 2485.296 | 0 | 0 | 2485.296 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 30.24 | 17.95 | 542.808 |  |  | 0 | 542.808 | 0 | 0 | 542.808 | QMS
| 4 | Excavation & Laying
85.1 | 5 | Excavator - 25T | hr | P | 1 | 6.667 | 21.6 | 135 | 437.3781 | 3.2398 | 3.2398 | 0 | 0 | 437.3781 | 0 | 437.3781 | 81
| 6 | Labour | hr | L | 3 | 6.667 | 21.6 | 38 | 369.3415 | 9.7195 | 3.2398 | 369.3415 | 0 | 0 | 0 | 369.3415 | 81
| 7 | Trench Roller | hr | P | 1 | 6.667 | 21.6 | 15 | 48.5976 | 3.2398 | 3.2398 | 0 | 0 | 48.5976 | 0 | 48.5976 | 81
86 |  | Drainage Structures
87 |  | Manholes as per IPWEA STD Drawings:
88 | Line No 127 Item No 5.2.1.1 | 1050mm dia Access Chamber | No. |  |  |  | 4 | 2954.2 | 11816.8 |  | 19 | 6384 | 3452.8 | 1980 | 0 | 11816.8
| 1 | N32 | m³ | M | 4 | 1 | 1 | 167.2 | 668.8 |  |  | 0 | 668.8 | 0 | 0 | 668.8 | C32
| 2 | Manhole Forms (1050) | day | P | 4 | 1 | 3 | 75 | 900 |  | 3 | 0 | 0 | 900 | 0 | 900 | 85
| 3 | 1050 Surround & Lid | each | M | 4 | 1 | 1 | 696 | 2784 |  |  | 0 | 2784 | 0 | 0 | 2784 | SWL
| 4 | Labour | hr | L | 4 | 1 | 12 | 38 | 1824 | 48 | 12 | 1824 | 0 | 0 | 0 | 1824 | 85
| 5 | Labour | hr | L | 4 | 1 | 6 | 38 | 912 | 24 | 6 | 912 | 0 | 0 | 0 | 912 | 85
| 6 | Labour | hr | L | 4 | 1 | 6 | 38 | 912 | 24 | 6 | 912 | 0 | 0 | 0 | 912 | 85
| 7 | Labour | hr | L | 4 | 1 | 18 | 38 | 2736 | 72 | 18 | 2736 | 0 | 0 | 0 | 2736 | 85
| 8 | Excavator - 25T | hr | P | 4 | 1 | 2 | 135 | 1080 | 8 | 2 | 0 | 0 | 1080 | 0 | 1080 | 85
89 | Line No 128 Item No 5.2.1.2 | 900x900 mm Access Chamber | No. |  |  |  | 9 | 1086.076 | 9774.684 |  | 18 | 6156 | 3618.684 | 0 | 0 | 9774.684
| 1 | N32 | m³ | M | 9 | 1 | 1.23 | 167.2 | 1850.904 |  |  | 0 | 1850.904 | 0 | 0 | 1850.904 | C32
| 2 | SL72 | m² | M | 9 | 1 | 7 | 5.76 | 362.88 |  |  | 0 | 362.88 | 0 | 0 | 362.88 | RSM
| 3 | Y12 | m | M | 9 | 1 | 30 | 1.87 | 504.9 |  |  | 0 | 504.9 | 0 | 0 | 504.9 | RSB
| 4 | Form Ply | m² | M | 9 | 1 | 10 | 10 | 900 |  |  | 0 | 900 | 0 | 0 | 900 | 905
| 5 | Labour | hr | L | 9 | 1 | 12 | 38 | 4104 | 108 | 12 | 4104 | 0 | 0 | 0 | 4104 | 85
| 6 | Labour | hr | L | 9 | 1 | 4 | 38 | 1368 | 36 | 4 | 1368 | 0 | 0 | 0 | 1368 | 85
| 7 | Labour | hr | L | 9 | 1 | 2 | 38 | 684 | 18 | 2 | 684 | 0 | 0 | 0 | 684 | 85
90 | Line No 129 Item No 5.2.1.3 | 4/10 - 900x900 Manhole | Item |  |  |  | 1 | 2920.76 | 2920.76 |  | 5 | 1596 | 829.76 | 495 | 0 | 2920.76
| 1 | N32 | m³ | M | 1 | 1 | 0.8 | 167.2 | 133.76 |  |  | 0 | 133.76 | 0 | 0 | 133.76 | C32
| 2 | Manhole Forms (1050) | day | P | 1 | 1 | 3 | 75 | 225 |  | 3 | 0 | 0 | 225 | 0 | 225 | 85
| 3 | 1050 Surround & Lid | each | M | 1 | 1 | 1 | 696 | 696 |  |  | 0 | 696 | 0 | 0 | 696 | 85
| 4 | Labour | hr | L | 1 | 1 | 12 | 38 | 456 | 12 | 12 | 456 | 0 | 0 | 0 | 456 | 85
| 5 | Labour | hr | L | 1 | 1 | 6 | 38 | 228 | 6 | 6 | 228 | 0 | 0 | 0 | 228 | 85
| 6 | Labour | hr | L | 1 | 1 | 6 | 38 | 228 | 6 | 6 | 228 | 0 | 0 | 0 | 228 | 85
| 7 | Labour | hr | L | 1 | 1 | 18 | 38 | 684 | 18 | 18 | 684 | 0 | 0 | 0 | 684 | 85
| 8 | Excavator - 25T | hr | P | 1 | 1 | 2 | 135 | 270 | 2 | 2 | 0 | 0 | 270 | 0 | 270 | 85
91 |  | Kerb Inlets
92 |  | On Grade (L)
93 | Line No 133 Item No | 2.4m Lintel | No. |  |  |  | 4 | 2107.2 | 8428.8 |  | 6 | 1824 | 6604.8 | 0 | 0 | 8428.8
| 1 | 2.4 Lintel Complete | Item | M | 4 | 1 | 1 | 1484 | 5936 |  |  | 0 | 5936 | 0 | 0 | 5936 | SWL
| 2 | N32 | m³ | M | 4 | 1 | 1 | 167.2 | 668.8 |  |  | 0 | 668.8 | 0 | 0 | 668.8 | C32
| 3 | Labour | hr | L | 4 | 1 | 12 | 38 | 1824 | 48 | 12 | 1824 | 0 | 0 | 0 | 1824 | 85
94 |  | On Grade(RH)
95 | Line No 135 Item No | 2.4m Lintel | No. |  |  |  | 5 | 2107.2 | 10536 |  | 7 | 2280 | 8256 | 0 | 0 | 10536
| 1 | 2.4 Lintel Complete | Item | M | 5 | 1 | 1 | 1484 | 7420 |  |  | 0 | 7420 | 0 | 0 | 7420 | SWL
| 2 | N32 | m³ | M | 5 | 1 | 1 | 167.2 | 836 |  |  | 0 | 836 | 0 | 0 | 836 | C32
| 3 | Labour | hr | L | 5 | 1 | 12 | 38 | 2280 | 60 | 12 | 2280 | 0 | 0 | 0 | 2280 | 85
96 |  | Pre-Cast Headwalls
97 | Line No 138 Item No 5.2.3.1 | Humes Precast Headwall or equivalent for 375mm pipe | No. |  |  |  | 2 | 847 | 1694 |  | 2 | 608 | 546 | 540 | 0 | 1694
| 1 | HW - 375 | each | M | 1 | 1 | 2 | 273 | 546 |  |  | 0 | 546 | 0 | 0 | 546 | SWH
97.1 | 2 | Excavator - 25T | hr | P | 1 | 1 | 4 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 81
| 3 | Labour | hr | L | 2 | 1 | 8 | 38 | 608 | 16 | 8 | 608 | 0 | 0 | 0 | 608 | 81
98 | Line No 139 Item No 5.2.3.2 | Humes Precast Headwall or equivalent for 450mm pipe | No. |  |  |  | 2 | 990 | 1980 |  | 2 | 608 | 832 | 540 | 0 | 1980
| 1 | HW - 450 | each | M | 1 | 1 | 2 | 416 | 832 |  |  | 0 | 832 | 0 | 0 | 832 | SWH
98.1 | 2 | Excavator - 25T | hr | P | 1 | 1 | 4 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 81
| 3 | Labour | hr | L | 2 | 1 | 8 | 38 | 608 | 16 | 8 | 608 | 0 | 0 | 0 | 608 | 81
99 | Line No 140 Item No 5.2.4 | Rock Protection at Outlet Drains (300 Deep) | m3 |  |  |  | 4.7 | 151.2 | 710.64 |  | 1 | 71.44 | 385.4 | 253.8 | 0 | 710.64
| 1 | Gabion Rock | tonne | M | 1 | 1 | 9.4 | 41 | 385.4 |  |  | 0 | 385.4 | 0 | 0 | 385.4 | QMR
99.1 | 2 | Excavator - 25T | hr | P | 1 | 5 | 9.4 | 135 | 253.8 | 1.88 | 1.88 | 0 | 0 | 253.8 | 0 | 253.8 | 221
| 3 | Labour | hr | L | 1 | 5 | 9.4 | 38 | 71.44 | 1.88 | 1.88 | 71.44 | 0 | 0 | 0 | 71.44 | 221
100 |  | ELECTRICAL AND LIGHTING
101 | Line No 144 Item No 6.1 | Trenching for electrical, lighting and communications service Conduits, complete in place, including trenching, backfilling, reinstatment of surface and maintence of trench while open. (trench configuration not specified) | m |  |  |  | 940 | 34.6714 | 32591.0822 |  | 7 | 10715.7857 | 2699.68 | 19175.6165 | 0 | 32591.0822
| 1 | Excavate Trench
101.1 | 2 | Excavator - 25T | hr | P | 1 | 16.667 | 940 | 135 | 7613.8477 | 56.3989 | 56.3989 | 0 | 0 | 7613.8477 | 0 | 7613.8477 | 111
| 3 | Labour | hr | L | 3 | 16.667 | 940 | 38 | 6429.4714 | 169.1966 | 56.3989 | 6429.4714 | 0 | 0 | 0 | 6429.4714 | 111
| 4 | Sand | tonne | M | 1 | 1 | 150.4 | 17.95 | 2699.68 |  |  | 0 | 2699.68 | 0 | 0 | 2699.68 | QMS
| 5 | Backfill & Compact
| 6 | Bobcat | hr | P | 1 | 16.667 | 940 | 95 | 5357.8928 | 56.3989 | 56.3989 | 0 | 0 | 5357.8928 | 0 | 5357.8928 | 111
| 7 | Water Cart - Hire | hr | P | 1 | 16.667 | 940 | 95 | 5357.8928 | 56.3989 | 56.3989 | 0 | 0 | 5357.8928 | 0 | 5357.8928 | 111
| 8 | Trench Roller | hr | P | 1 | 16.667 | 940 | 15 | 845.9831 | 56.3989 | 56.3989 | 0 | 0 | 845.9831 | 0 | 845.9831 | 111
| 9 | Labour | hr | L | 2 | 16.667 | 940 | 38 | 4286.3143 | 112.7977 | 56.3989 | 4286.3143 | 0 | 0 | 0 | 4286.3143 | 111
102 | Line No 145 Item No 6.2 | Supply only of electrical conduits (100 diameter), conuits and marker tape | m |  |  |  | 613 | 5.4535 | 3342.9955 |  | 5 | 0 | 3342.9955 | 0 | 0 | 3342.9955
| 1 | 100 LD uPVC Electrical | m | M | 1 | 1 | 643.65 | 4.45 | 2864.2425 |  |  | 0 | 2864.2425 | 0 | 0 | 2864.2425 | ETC
| 2 | Draw Rope - Conduits | m | M | 1 | 1 | 674.3 | 0.11 | 74.173 |  |  | 0 | 74.173 | 0 | 0 | 74.173 | ETM
| 3 | Warning Tape | m | M | 1 | 1 | 1226 | 0.33 | 404.58 |  |  | 0 | 404.58 | 0 | 0 | 404.58 | ETM
103 | Line No 146 Item No 6.3 | Supply only of electrical conduits (40 diameter), conuits and marker tape |  |  |  |  | 500 | 2.923 | 1461.5 |  | 5 | 0 | 1461.5 | 0 | 0 | 1461.5
| 1 | 40 HD uPVC Electrical | m | M | 1 | 1 | 525 | 2.04 | 1071 |  |  | 0 | 1071 | 0 | 0 | 1071 | ETC
| 2 | Draw Rope - Conduits | m | M | 1 | 1 | 550 | 0.11 | 60.5 |  |  | 0 | 60.5 | 0 | 0 | 60.5 | ETM
| 3 | Warning Tape | m | M | 1 | 1 | 1000 | 0.33 | 330 |  |  | 0 | 330 | 0 | 0 | 330 | ETM
104 | Line No 147 Item No 6.4 | Supply only, conduits and marker tape | m |  |  |  | 270 | 6.199 | 1673.73 |  | 5 | 0 | 1673.73 | 0 | 0 | 1673.73
| 1 | 100 Communication Conduit | m | M | 1 | 1 | 283.5 | 5.16 | 1462.86 |  |  | 0 | 1462.86 | 0 | 0 | 1462.86 | ETC
| 2 | Draw Rope - Conduits | m | M | 1 | 1 | 297 | 0.11 | 32.67 |  |  | 0 | 32.67 | 0 | 0 | 32.67 | ETM
| 3 | Warning Tape | m | M | 1 | 1 | 540 | 0.33 | 178.2 |  |  | 0 | 178.2 | 0 | 0 | 178.2 | ETM
105 | Line No 148 Item No 6.5 | Installation of electrical pit, complete in place, including trenching, bedding, supplying, laying, marker tape/hard cover and backfill. (trench configuration not specified) | No. |  |  |  | 13 | 1249.75 | 16246.75 |  | 6 | 3952 | 9824.75 | 2470 | 0 | 16246.75
| 1 | Electrical Pit - Type 66 | each | M | 1 | 1 | 13 | 737.8 | 9591.4 |  |  | 0 | 9591.4 | 0 | 0 | 9591.4 | ETP
| 2 | Sand | tonne | M | 1 | 1 | 13 | 17.95 | 233.35 |  |  | 0 | 233.35 | 0 | 0 | 233.35 | QMS
| 3 | Bobcat | hr | P | 1 | 1 | 26 | 95 | 2470 | 26 | 26 | 0 | 0 | 2470 | 0 | 2470 | 111
| 4 | Labour | hr | L | 2 | 1 | 52 | 38 | 3952 | 104 | 52 | 3952 | 0 | 0 | 0 | 3952 | 111
106 | Line No 149 Item No 6.6 | Installation of communications pit, complete in place, including trenching, bedding, supplying, laying, marker tape/hard cover and backfill. (trench configuration not specified) | No. |  |  |  | 8 | 1538.5 | 12308 |  | 4 | 2432 | 8356 | 1520 | 0 | 12308
| 1 | Comms Pit - J8 | each | M | 1 | 1 | 8 | 1026.55 | 8212.4 |  |  | 0 | 8212.4 | 0 | 0 | 8212.4 | ETP
| 2 | Sand | tonne | M | 1 | 1 | 8 | 17.95 | 143.6 |  |  | 0 | 143.6 | 0 | 0 | 143.6 | QMS
| 3 | Bobcat | hr | P | 1 | 1 | 16 | 95 | 1520 | 16 | 16 | 0 | 0 | 1520 | 0 | 1520 | 111
| 4 | Labour | hr | L | 2 | 1 | 32 | 38 | 2432 | 64 | 32 | 2432 | 0 | 0 | 0 | 2432 | 111
107 | Line No 150 Item No 6.7 | Supply and installation of distribution board complete in place including all ground works, plinth and circuit breakers | No. |  |  |  | 1 | 12010 | 12010 |  | 3 | 0 | 0 | 0 | 12010 | 12010
| 1 | Distribution Board | each | S |  | 1 | 1 | 10810 | 10810 |  | 1 | 0 | 0 | 0 | 10810 | 10810 | 113
| 2 | Electrician | Item | S |  | 1 | 20 | 60 | 1200 |  | 20 | 0 | 0 | 0 | 1200 | 1200 | 113
108 | Line No 151 Item No 6.8 | Supply and installation of electrical and communication conduits to gate controllers from nearest pits including all trenching and coordination with gate installer | No. |  |  |  | 5 | 937.93 | 4689.65 |  | 1 | 1520 | 1819.65 | 1350 | 0 | 4689.65
| 1 | Excavator - 25T | hr | P | 5 | 1 | 2 | 135 | 1350 | 10 | 2 | 0 | 0 | 1350 | 0 | 1350 | 111
| 2 | 100 Communication Conduit | m | M | 5 | 1 | 30 | 5.16 | 774 |  |  | 0 | 774 | 0 | 0 | 774 | ETC
| 3 | 40 HD uPVC Electrical | m | M | 5 | 1 | 60 | 2.04 | 612 |  |  | 0 | 612 | 0 | 0 | 612 | ETC
| 4 | 100 Comms Bend Cl9 584R | each | M | 5 | 1 | 3 | 25 | 375 |  |  | 0 | 375 | 0 | 0 | 375 | ETC
| 5 | 40 HD 90 Degree Bend 304R | each | M | 5 | 1 | 3 | 3.91 | 58.65 |  |  | 0 | 58.65 | 0 | 0 | 58.65 | ETC
| 6 | Labour | hr | L | 5 | 1 | 8 | 38 | 1520 | 40 | 8 | 1520 | 0 | 0 | 0 | 1520 | 111
109 | Line No 152 Item No 6.9 | Supply and installation of electrical and communication conduits to ticket machines from nearest pits including all trenching and coordination with ticket machine installer | No. |  |  |  | 2 | 556.91 | 1113.82 |  | 2 | 912 | 201.82 | 0 | 0 | 1113.82
| 1 | 40 HD uPVC Electrical | m | M | 2 | 1 | 10 | 2.04 | 40.8 |  |  | 0 | 40.8 | 0 | 0 | 40.8 | ETC
| 2 | 40 HD 90 Degree Bend 304R | each | M | 2 | 1 | 1 | 3.91 | 7.82 |  |  | 0 | 7.82 | 0 | 0 | 7.82 | ETC
| 3 | 100 Communication Conduit | m | M | 2 | 1 | 10 | 5.16 | 103.2 |  |  | 0 | 103.2 | 0 | 0 | 103.2 | ETC
| 4 | 100 Comms Bend Cl9 584R | each | M | 2 | 1 | 1 | 25 | 50 |  |  | 0 | 50 | 0 | 0 | 50 | ETC
| 5 | Labour | hr | L | 2 | 1 | 12 | 38 | 912 | 24 | 12 | 912 | 0 | 0 | 0 | 912 | 111
110 | Line No 153 Item No 6.10 | Supply and installation of new car park lights and poles to match existing including footing installation, pole and all cabling from distribution board | No. |  |  |  | 4 | 5804.65 | 23218.6 |  | 2 | 1216 | 10205.6 | 5780 | 6017 | 23218.6
| 1 | Materials
| 2 | Rag Bolt | each | M | 1 | 1 | 4 | 375 | 1500 |  |  | 0 | 1500 | 0 | 0 | 1500 | ETM
| 3 | N32 | m³ | M | 1 | 1 | 3 | 167.2 | 501.6 |  |  | 0 | 501.6 | 0 | 0 | 501.6 | ETM
| 4 | Light Pole - 10.5m | each | M | 1 | 1 | 4 | 1391 | 5564 |  |  | 0 | 5564 | 0 | 0 | 5564 | ETM
| 5 | Luminaires | each | M | 1 | 1 | 8 | 330 | 2640 |  |  | 0 | 2640 | 0 | 0 | 2640 | ETM
| 6 | Installation of Footing Cages
110.1 | 7 | Backhoe | hr | P | 1 | 0.5 | 4 | 100 | 800 | 8 | 8 | 0 | 0 | 800 | 0 | 800 | 111
| 8 | Labour | hr | L | 2 | 0.5 | 4 | 38 | 608 | 16 | 8 | 608 | 0 | 0 | 0 | 608 | 111
| 9 | Installation of Poles & Lights
| 10 | Electrician | Item | S | 40 | 1 | 1 | 60 | 2400 |  | 1 | 0 | 0 | 0 | 2400 | 2400 | 113
| 11 | Crane - 30Ton | hr | P | 3 | 1 | 4 | 165 | 1980 | 12 | 4 | 0 | 0 | 1980 | 0 | 1980 | 111
| 12 | Labour | hr | L | 2 | 0.5 | 4 | 38 | 608 | 16 | 8 | 608 | 0 | 0 | 0 | 608 | 111
| 13 | EWP | day | P | 1 | 1 | 4 | 750 | 3000 | 4 | 4 | 0 | 0 | 3000 | 0 | 3000 | 111
| 14 | Light Cables | each | S | 1 | 1 | 1 | 3617 | 3617 | 1 | 1 | 0 | 0 | 0 | 3617 | 3617 | 113
111 | Line No 154 Item No 6.11 | Supply and installation of services pillar at car wash bays P1, P2,P3 incl socket outlets (IP56), Safety Switch and Hose Cock and all cabling back to distribution board including all cabling back to distribution board | No. |  |  |  | 3 | 1543.3333 | 4630 |  | 3 | 0 | 0 | 0 | 4630 | 4630
| 1 | GPO | each | S |  | 1 | 1 | 3430 | 3430 |  | 1 | 0 | 0 | 0 | 3430 | 3430 | ETM
| 2 | Electrician | Item | S |  | 1 | 20 | 60 | 1200 |  | 20 | 0 | 0 | 0 | 1200 | 1200 | 113
112 |  | MISCELLANEOUS
113 |  | Existing Services
114 |  | Service Conduit Crossings and Alterations to existing services, as required
115 | Line No 162 Item No 7.1.3 | Existing above ground services to be raised to compliment proposed earthworks level (50mm) | Item |  |  |  | 1 | 2499 | 2499 |  | 1 | 0 | 0 | 0 | 2499 | 2499
| 1 | Plumber | hr | S | 1 | 1 | 29.4 | 85 | 2499 |  | 29.4 | 0 | 0 | 0 | 2499 | 2499 | 103
116 |  | Fencing & Vehicle Barriers
117 |  | Vehicle Barriers - CCA Treated Logs
118 | Line No 166 Item No 7.2.1.1 | Trafficked roadways and busbays within the extents of stage 1 boundary | m |  |  |  | 624 | 26.985 | 16838.64 |  | 10 | 0 | 0 | 0 | 16838.64 | 16838.64
| 1 | Log Fence | m | S | 1 | 1 | 655.2 | 25.7 | 16838.64 |  | 655.2 | 0 | 0 | 0 | 16838.64 | 16838.64 | 131
119 | Line No 167 Item No 7.2.1.2 | Extension of Trafficked roadways beyond stage 1 boundary. (prevent vehicles leaving roadway and parking outside formal carpark) | m |  |  |  | 710 | 26.985 | 19159.35 |  | 11 | 0 | 0 | 0 | 19159.35 | 19159.35
| 1 | Log Fence | m | S | 1 | 1 | 745.5 | 25.7 | 19159.35 |  | 745.5 | 0 | 0 | 0 | 19159.35 | 19159.35 | 131
120 | Line No 168 Item No 7.2.1.3 | Public Carpark | m |  |  |  | 220 | 26.985 | 5936.7 |  | 4 | 0 | 0 | 0 | 5936.7 | 5936.7
| 1 | Log Fence | m | S | 1 | 1 | 231 | 25.7 | 5936.7 |  | 231 | 0 | 0 | 0 | 5936.7 | 5936.7 | 131
121 | Line No 169 Item No 7.2.3.1 | Pedestrian Safety Fence | m |  |  |  | 15 | 100 | 1500 |  | 1 | 0 | 0 | 0 | 1500 | 1500
| 1 | Pedestrian Safety Fence | m | S | 1 | 1 | 15 | 100 | 1500 |  | 15 | 0 | 0 | 0 | 1500 | 1500 | 131
122 | Line No 170 Item No 7.2.3.2 | Supply & Installation of Fixed Bollards | No. |  |  |  | 4 | 52.5 | 210 |  | 1 | 0 | 0 | 0 | 210 | 210
| 1 | Bollards | each | S | 1 | 1 | 4.2 | 50 | 210 |  | 4.2 | 0 | 0 | 0 | 210 | 210 | 131
Construction Management & Mitigation Works
123 | Line No 173 Item No 7.3.1 | Temporary Fencing & Signage | Item |  |  |  | 1 | 12768 | 12768 |  | 2 | 1368 | 5000 | 0 | 6400 | 12768
| 1 | Temporary Fencing | m | S | 1 | 1 | 400 | 16 | 6400 |  | 400 | 0 | 0 | 0 | 6400 | 6400 | 152
| 2 | Signs - General | Item | M | 1 | 1 | 5000 | 1 | 5000 |  |  | 0 | 5000 | 0 | 0 | 5000 | 152
| 3 | Labour | hr | L | 3 | 1 | 12 | 38 | 1368 | 36 | 12 | 1368 | 0 | 0 | 0 | 1368 | 152
124 |  | SCHEDULE B - SEWER WORKS
125 |  | EARTHWORKS
126 | Line No 179 Item No 1.1 | Clearing & Grubbing | m2 |  |  |  | 550 | 8.1491 | 4482 |  | 2 | 2052 | 0 | 2430 | 0 | 4482
1
| 2 | Excavator - 25T | hr | P | 1 | 1 | 18 | 135 | 2430 | 18 | 18 | 0 | 0 | 2430 | 0 | 2430 | 21
| 3 | Labour | hr | L | 3 | 1 | 18 | 38 | 2052 | 54 | 18 | 2052 | 0 | 0 | 0 | 2052 | 21
127 | Line No 180 Item No 1.2 | Strip & Stockpile Topsoil | m3 |  |  |  | 55 | 8.575 | 471.625 |  | 1 | 52.25 | 0 | 419.375 | 0 | 471.625
127.1 | 1 | Excavator - 25T | hr | P | 1 | 40 | 55 | 135 | 185.625 | 1.375 | 1.375 | 0 | 0 | 185.625 | 0 | 185.625 | 31
| 2 | Tipper | hr | P | 2 | 40 | 55 | 85 | 233.75 | 2.75 | 1.375 | 0 | 0 | 233.75 | 0 | 233.75 | 31
| 3 | Labour | hr | L | 1 | 40 | 55 | 38 | 52.25 | 1.375 | 1.375 | 52.25 | 0 | 0 | 0 | 52.25 | 31
128 | Line No 181 Item No 1.3 | Placement of Topsoil | m2 |  |  |  | 28 | 14.24 | 398.72 |  | 1 | 85.12 | 0 | 313.6 | 0 | 398.72
128.1 | 1 | Backhoe | hr | P | 1 | 250 | 280 | 100 | 112 | 1.12 | 1.12 | 0 | 0 | 112 | 0 | 112 | 33
| 2 | Tipper | hr | P | 1 | 250 | 280 | 85 | 95.2 | 1.12 | 1.12 | 0 | 0 | 95.2 | 0 | 95.2 | 33
| 3 | Bobcat | hr | P | 1 | 250 | 280 | 95 | 106.4 | 1.12 | 1.12 | 0 | 0 | 106.4 | 0 | 106.4 | 33
| 4 | Labour | hr | L | 2 | 250 | 280 | 38 | 85.12 | 2.24 | 1.12 | 85.12 | 0 | 0 | 0 | 85.12 | 33
129 | Line No 182 Item No 1.4 | Disposal of excess topsoil as directed | m3 |  |  |  | 27 | 13.075 | 353.025 |  | 1 | 25.65 | 0 | 327.375 | 0 | 353.025
129.1 | 1 | Excavator - 25T | hr | P | 1 | 40 | 27 | 135 | 91.125 | 0.675 | 0.675 | 0 | 0 | 91.125 | 0 | 91.125 | 32
| 2 | Tipper | hr | P | 3 | 40 | 27 | 85 | 172.125 | 2.025 | 0.675 | 0 | 0 | 172.125 | 0 | 172.125 | 32
| 3 | Water Cart - Hire | hr | P | 1 | 40 | 27 | 95 | 64.125 | 0.675 | 0.675 | 0 | 0 | 64.125 | 0 | 64.125 | 32
| 4 | Labour | hr | L | 1 | 40 | 27 | 38 | 25.65 | 0.675 | 0.675 | 25.65 | 0 | 0 | 0 | 25.65 | 32
130 | Line No 183 Item No 1.5 | Gravel access and hardstand from airport pit min CBR10 300 thick(Provisional) | m3 |  |  |  | 165 | 18.178 | 2999.374 |  | 1 | 426.5837 | 0 | 2572.7903 | 0 | 2999.374
| 1 | Win Material from Local Pit
| 2 | D6 | hr | P | 1 | 133.333 | 165 | 185 | 228.9381 | 1.2375 | 1.2375 | 0 | 0 | 228.9381 | 0 | 228.9381 | 52
| 3 | Load & Cart
130.1 | 4 | Excavator - 25T | hr | P | 1 | 88.889 | 165 | 135 | 250.5934 | 1.8562 | 1.8562 | 0 | 0 | 250.5934 | 0 | 250.5934 | 52
| 5 | Truck & Dog | hr | P | 3 | 88.889 | 165 | 145 | 807.4677 | 5.5687 | 1.8562 | 0 | 0 | 807.4677 | 0 | 807.4677 | 52
| 6 | Place & Compact
| 7 | Grader | hr | P | 1 | 88.889 | 165 | 145 | 269.1559 | 1.8562 | 1.8562 | 0 | 0 | 269.1559 | 0 | 269.1559 | 52
| 8 | Water Cart - Hire | hr | P | 1 | 88.889 | 165 | 95 | 176.3435 | 1.8562 | 1.8562 | 0 | 0 | 176.3435 | 0 | 176.3435 | 52
| 9 | PF Roller Wet - No OP | hr | P | 1 | 88.889 | 165 | 58 | 107.6624 | 1.8562 | 1.8562 | 0 | 0 | 107.6624 | 0 | 107.6624 | 52
| 10 | Labour | hr | L | 3 | 88.889 | 165 | 38 | 211.6122 | 5.5687 | 1.8562 | 211.6122 | 0 | 0 | 0 | 211.6122 | 52
| 11 | Bobcat | hr | P | 1 | 88.889 | 165 | 95 | 176.3435 | 1.8562 | 1.8562 | 0 | 0 | 176.3435 | 0 | 176.3435 | 52
| 12 | Final Trim
130.2 | 13 | Grader | hr | P | 1 | 250 | 471.4286 | 145 | 273.4286 | 1.8857 | 1.8857 | 0 | 0 | 273.4286 | 0 | 273.4286 | 52
| 14 | Water Cart - Hire | hr | P | 1 | 250 | 471.4286 | 95 | 179.1429 | 1.8857 | 1.8857 | 0 | 0 | 179.1429 | 0 | 179.1429 | 52
| 15 | SD Roller - Wet (No Op) | hr | P | 1 | 250 | 471.4286 | 55 | 103.7143 | 1.8857 | 1.8857 | 0 | 0 | 103.7143 | 0 | 103.7143 | 52
| 16 | Labour | hr | L | 3 | 250 | 471.4286 | 38 | 214.9714 | 5.6571 | 1.8857 | 214.9714 | 0 | 0 | 0 | 214.9714 | 52
131 |  | SEWER WORKS
132 |  | Gravity Sewer
133 | Line No 188 Item No 2.1.3 | Connection of existing DN100 AC gravity sewers to new ssanitary drain | No. |  |  |  | 2 | 2400 | 4800 |  | 2 | 0 | 0 | 0 | 4800 | 4800
| 1 | Sewer Subbie | LS | S | 2400 | 1 | 2 | 1 | 4800 |  | 2 | 0 | 0 | 0 | 4800 | 4800 | 95
134 | Line No 189 Item No 2.1.4 | Decommision existing Septic Tanks and associated pipework (excluding demolition of tanks - refer schedule A) | Item |  |  |  | 2 | 2000 | 4000 |  | 2 | 0 | 0 | 0 | 4000 | 4000
| 1 | Sewer Subbie | LS | S | 1 | 1 | 4000 | 1 | 4000 |  | 4000 | 0 | 0 | 0 | 4000 | 4000 | 95
135 |  | Sewerage Pump Station
136 | Line No 191 Item No 2.2.1 | Supply & delivery of Proprietry PE Pump Station (incl pumps, pipework, electrical controls etc) | No. |  |  |  | 1 | 23520 | 23520 |  | 15 | 0 | 0 | 0 | 23520 | 23520
| 1 | Sewer Subbie | LS | S | 23520 | 1 | 1 | 1 | 23520 |  | 1 | 0 | 0 | 0 | 23520 | 23520 | 95
137 | Line No 192 Item No 2.2.2 | Installation of Sewerage Pump Station (including concrete ballast) | Item |  |  |  | 1 | 4100 | 4100 |  | 2 | 0 | 0 | 0 | 4100 | 4100
| 1 | Sewer Subbie | LS | S | 4100 | 0.5 | 1 | 1 | 4100 |  | 2 | 0 | 0 | 0 | 4100 | 4100 | 95
138 | Line No 193 Item No 2.2.3 | Connection of gravity sewer pipe | Item |  |  |  | 1 | 2400 | 2400 |  | 1 | 0 | 0 | 0 | 2400 | 2400
| 1 | Sewer Subbie | LS | S | 2400 | 1 | 1 | 1 | 2400 |  | 1 | 0 | 0 | 0 | 2400 | 2400 | 95
139 | Line No 194 Item No 2.2.4 | Supply and construction of DN50 vent | No. |  |  |  | 1 | 1800 | 1800 |  | 1 | 0 | 0 | 0 | 1800 | 1800
| 1 | Sewer Subbie | LS | S | 1800 | 1 | 1 | 1 | 1800 |  | 1 | 0 | 0 | 0 | 1800 | 1800 | 95
140 | Line No 195 Item No 2.2.5 | Electrical connections from mains supply | Item |  |  |  | 1 | 3600 | 3600 |  | 7 | 0 | 0 | 0 | 3600 | 3600
| 1 | Electrician | Item | S | 1 | 1 | 60 | 60 | 3600 |  | 60 | 0 | 0 | 0 | 3600 | 3600 | 113
141 | Line No 196 Item No 2.2.6 | Commisioning Pump Station and electrical controls | Item |  |  |  | 1 | 2000 | 2000 |  | 1 | 0 | 0 | 0 | 2000 | 2000
| 1 | Sewer Subbie | LS | S | 2000 | 1 | 1 | 1 | 2000 |  | 1 | 0 | 0 | 0 | 2000 | 2000 | 95
142 |  | Rising Main
143 | Line No 198 Item No 2.3.1 | Supply and construction of DN32 PE rising main (40OD PE100 PN16) incl 3 No. tees, ball vavles, pits for future STP connection | m |  |  |  | 215 | 66.6344 | 14326.4 |  | 2 | 0 | 1826.4 | 0 | 12500 | 14326.4
| 1 | Sewer Subbie | LS | S | 12500 | 1 | 1 | 1 | 12500 |  | 1 | 0 | 0 | 0 | 12500 | 12500 | 95
| 2 | Valve Box & Surround | each | M | 3 | 1 | 1 | 150 | 450 |  |  | 0 | 450 | 0 | 0 | 450 | 95
| 3 | 150 x 150 Tee | each | M | 3 | 1 | 1 | 318.8 | 956.4 |  |  | 0 | 956.4 | 0 | 0 | 956.4 | 95
| 4 | 150 SV So-So | each | M | 1 | 1 | 1 | 420 | 420 |  |  | 0 | 420 | 0 | 0 | 420 | 95
144 | Line No 199 Item No 2.3.2 | Connection to new wet weather storage tanks | Item |  |  |  | 1 | 1500 | 1500 |  | 1 | 0 | 0 | 0 | 1500 | 1500
| 1 | Sewer Subbie | LS | S | 1500 | 1 | 1 | 1 | 1500 |  | 1 | 0 | 0 | 0 | 1500 | 1500 | 95
145 |  | Water Supply
146 | Line No 201 Item No 2.4.1 | Supply and construction of DN32 PE water supply main (40OD PE100 PN16) to carpark hosecocks. | m |  |  |  | 210 | 66.6314 | 13992.5949 |  | 1 | 0 | 1783.8449 | 0 | 12208.75 | 13992.5949
| 1 | Sewer Subbie | LS | S | 12500 | 1 | 0.9767 | 1 | 12208.75 |  | 0.9767 | 0 | 0 | 0 | 12208.75 | 12208.75 | 103
| 2 | Valve Box & Surround | each | M | 3 | 1 | 0.9767 | 150 | 439.515 |  |  | 0 | 439.515 | 0 | 0 | 439.515 | 103
| 3 | 150 x 150 Tee | each | M | 3 | 1 | 0.9767 | 318.8 | 934.1159 |  |  | 0 | 934.1159 | 0 | 0 | 934.1159 | 103
| 4 | 150 SV So-So | each | M | 1 | 1 | 0.9767 | 420 | 410.214 |  |  | 0 | 410.214 | 0 | 0 | 410.214 | 103
147 | Line No 202 Item No 2.4.2 | Supply and installation of DN32 RPZD in enclosure complete | No. |  |  |  | 1 | 2074.4 | 2074.4 |  | 1 | 0 | 1074.8 | 0 | 999.6 | 2074.4
| 1 | 150 SV So-So | each | M | 1 | 1 | 1 | 420 | 420 |  |  | 0 | 420 | 0 | 0 | 420 | 103
| 2 | 150 Vari-Gib | each | M | 3 | 1 | 1 | 112 | 336 |  |  | 0 | 336 | 0 | 0 | 336 | 103
| 3 | 150 x 150 Tee | each | M | 1 | 1 | 1 | 318.8 | 318.8 |  |  | 0 | 318.8 | 0 | 0 | 318.8 | 103
| 4 | Plumber | hr | S | 11.76 | 1 | 1 | 85 | 999.6 |  | 1 | 0 | 0 | 0 | 999.6 | 999.6 | 103
148 | Line No 203 Item No 2.4.3 | Supply, installation & connection of hosecocks to carwash Service Pillars complete (excluding pillars, refer Schedule A, 6.11) | No. |  |  |  | 3 | 245 | 735 |  | 1 | 0 | 225 | 0 | 510 | 735
| 1 | Hose Cock | each | M | 1 | 1 | 3 | 75 | 225 |  |  | 0 | 225 | 0 | 0 | 225 | 103
| 2 | Plumber | hr | S | 1 | 1 | 6 | 85 | 510 |  | 6 | 0 | 0 | 0 | 510 | 510 | 103
149 | Line No 204 Item No 2.4.4 | Supply and construct DN25 water supply main (32OD PE100 PN16) to STP | m |  |  |  | 75 | 64.302 | 4822.6483 |  | 2 | 0 | 637.0483 | 0 | 4185.6 | 4822.6483
| 1 | Sewer Subbie | LS | S | 12000 | 1 | 0.3488 | 1 | 4185.6 |  | 0.3488 | 0 | 0 | 0 | 4185.6 | 4185.6 | 103
| 2 | Valve Box & Surround | each | M | 3 | 1 | 0.3488 | 150 | 156.96 |  |  | 0 | 156.96 | 0 | 0 | 156.96 | 103
| 3 | 150 x 150 Tee | each | M | 3 | 1 | 0.3488 | 318.8 | 333.5923 |  |  | 0 | 333.5923 | 0 | 0 | 333.5923 | 103
| 4 | 150 SV So-So | each | M | 1 | 1 | 0.3488 | 420 | 146.496 |  |  | 0 | 146.496 | 0 | 0 | 146.496 | 103
150 |  | Miscellaneous
151 | Line No 206 Item No 2.5.1 | Gate to STP Access | item |  |  |  | 1 | 1500.109 | 1500.109 |  | 10.5066 | 0 | 0 | 0 | 1500.109 | 1500.109
| 1 | Log Fence | m | S | 1 | 1 | 58.37 | 25.7 | 1500.109 |  | 58.37 | 0 | 0 | 0 | 1500.109 | 1500.109 | 131
1426642.6385
152 |  | PROJECT OVERHEADS (TO BE SPREAD ACROSS ABOVE ITEMS)
| Line No. | Resource Name | Unit |  | No | Production | Quantity | Rate |  |  |  | Labour | Material | Plant | Subcontract | Total
153 | Line No OH 1 Item No | Project Supervision | Item |  |  |  | 1 | 33500 | 33500 |  |  | 33500 | 0 | 0 | 0 | 33500
153.1 | 1 | Project Supervisor | week | L |  | 1 | 10 | 3350 | 33500 |  | 10 | 33500 | 0 | 0 | 0 | 33500 | 902
154 | Line No OH 2 Item No | Project Engineer | Item |  |  |  | 1 | 19500 | 19500 |  |  | 19500 | 0 | 0 | 0 | 19500
154.1 | 1 | Project Engineer | week | L |  | 1 | 6 | 3250 | 19500 |  | 6 | 19500 | 0 | 0 | 0 | 19500 | 901
155 | Line No OH 3 Item No | Resource Balance | Item |  |  |  | 1 | 26240 | 26240 |  |  | 0 | 0 | 26240 | 0 | 26240
155.1 | 1 | Water Cart - Hire | hr | P |  | 1 | 100 | 95 | 9500 |  | 100 | 0 | 0 | 9500 | 0 | 9500 | 151
155.2 | 2 | CAT297 | hr | P |  | 1 | 360 | 46.5 | 16740 |  | 360 | 0 | 0 | 16740 | 0 | 16740 | 910
156 | Line No OH 4 Item No | Dual Grade Laser | Item |  |  |  | 1 | 3324 | 3324 |  |  | 0 | 0 | 3324 | 0 | 3324
156.1 | 1 | Dual Grade Laser | week | P |  | 1 | 12 | 277 | 3324 |  | 12 | 0 | 0 | 3324 | 0 | 3324 | 905
157 | Line No OH 5 Item No | Site Facilities | Item |  |  |  | 1 | 17936 | 17936 |  |  | 0 | 0 | 17936 | 0 | 17936
157.1 | 1 | Crib Facilities | week | P | 1 | 1 | 16 | 1121 | 17936 |  | 16 | 0 | 0 | 17936 | 0 | 17936 | 903
158 | Line No OH 6 Item No | Wet Weather | Item |  |  |  | 1 | 380 | 380 |  |  | 380 | 0 | 0 | 0 | 380
158.1 | 1 | Labour | hr | L | 4 | 4 | 160 | 38 | 380 |  | 40 | 380 | 0 | 0 | 0 | 380 | WW | 0
| Variation No. | Resource Name | Unit | Type | No | Prodn | Quantity | Rate | Cost | Usage | Duration | Labour | Material | Plant | Subcontract | Total | Portfolio WBS
159 | PV02 | Additional Clearing & Grubbing - Moving rental car park 10m to the north to avoid fibre optic cable. | item |  |  |  | 1 |  | 2728 |  | 1 | 513 | 0 | 1215 | 1000 | 2728
1
159.1 | 2 | Excavator - 25T | hr | P | 1 | 1 | 9 | 135 | 1215 | 9 | 9 | 0 | 0 | 1215 | 0 | 1215 | 22
| 3 | Labour | hr | L | 3 | 1 | 4.5 | 38 | 513 | 13.5 | 4.5 | 513 | 0 | 0 | 0 | 513 | 22
| 4 | Mulcher | Item | S | 1 | 11082 | 1847 | 6000 | 1000 | 0.16667 | 0.16667 | 0 | 0 | 0 | 1000 | 1000 | 23
160 | PV03 a | Additional Material for Revised Levels (Main Pad) |  |  |  |  | 1
161 | PV03 a.1 | Additional Imported General Fill (BOQ Item 3.3.5) | m³ |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Win Material From Local Pit
161.1 | 2 | D6 | hr | P | 1 | 133.333 | 0 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52
| 3 | Load & Cart
161.2 | 4 | Excavator - 25T | hr | P | 1 | 88.889 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52
| 5 | Truck & Dog | hr | P | 3 | 88.889 | 0 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52
| 6 | Place & Compact
| 7 | Grader | hr | P | 1 | 88.889 | 0 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52
| 8 | Water Cart - Hire | hr | P | 1 | 88.889 | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52
| 9 | PF Roller Wet - No OP | hr | P | 1 | 88.889 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52
| 10 | Labour | hr | L | 3 | 88.889 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52
| 11 | Bobcat | hr | P | 1 | 88.889 | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52
162 | PV03 b | Additional Fill, road base gravel, spray seal & AC to elongated access ramp |  |  |  |  | 1 |  | 4551.3452 |  | 0.23638 | 207.4184 | 840.0663 | 1164.8455 | 2339.015 | 4551.3452
163 | PV03 b.1 | Imported General Fill (BOQ Item 3.3.5) | m³ |  |  |  | 62 |  | 837.2318 |  | 0.0775 | 79.5149 | 0 | 757.7169 | 0 | 837.2318
| 1 | Win Material From Local Pit
163.1 | 2 | D6 | hr | P | 1 | 133.333 | 62 | 185 | 86.0252 | 0.465 | 0.465 | 0 | 0 | 86.0252 | 0 | 86.0252 | 52
| 3 | Load & Cart
163.2 | 4 | Excavator - 25T | hr | P | 1 | 88.889 | 62 | 135 | 94.1624 | 0.6975 | 0.6975 | 0 | 0 | 94.1624 | 0 | 94.1624 | 52
| 5 | Truck & Dog | hr | P | 3 | 88.889 | 62 | 145 | 303.4121 | 2.0925 | 0.6975 | 0 | 0 | 303.4121 | 0 | 303.4121 | 52
| 6 | Place & Compact
| 7 | Grader | hr | P | 1 | 88.889 | 62 | 145 | 101.1374 | 0.6975 | 0.6975 | 0 | 0 | 101.1374 | 0 | 101.1374 | 52
| 8 | Water Cart - Hire | hr | P | 1 | 88.889 | 62 | 95 | 66.2624 | 0.6975 | 0.6975 | 0 | 0 | 66.2624 | 0 | 66.2624 | 52
| 9 | PF Roller Wet - No OP | hr | P | 1 | 88.889 | 62 | 58 | 40.4549 | 0.6975 | 0.6975 | 0 | 0 | 40.4549 | 0 | 40.4549 | 52
| 10 | Labour | hr | L | 3 | 88.889 | 62 | 38 | 79.5149 | 2.0925 | 0.6975 | 79.5149 | 0 | 0 | 0 | 79.5149 | 52
| 11 | Bobcat | hr | P | 1 | 88.889 | 62 | 95 | 66.2624 | 0.6975 | 0.6975 | 0 | 0 | 66.2624 | 0 | 66.2624 | 52
164 | PV03 b.2 | Additional sub-grade preparation (BOQ item 4.1) | m² |  |  |  | 80 |  | 162.9968 |  | 0.050794 | 34.7429 | 0 | 128.254 | 0 | 162.9968
164.1 | 1 | Grader | hr | P | 1 | 175 | 80 | 145 | 66.2857 | 0.45714 | 0.45714 | 0 | 0 | 66.2857 | 0 | 66.2857 | 61
| 2 | SD Roller | day | P | 1 | 1575 | 80 | 365 | 18.5397 | 0.050794 | 0.050794 | 0 | 0 | 18.5397 | 0 | 18.5397 | 61
| 3 | Water Cart - Hire | hr | P | 1 | 175 | 80 | 95 | 43.4286 | 0.45714 | 0.45714 | 0 | 0 | 43.4286 | 0 | 43.4286 | 61
| 4 | Labour | hr | L | 2 | 175 | 80 | 38 | 34.7429 | 0.91429 | 0.45714 | 34.7429 | 0 | 0 | 0 | 34.7429 | 61
165 | PV03 b.3 | Additional 2.3 Material (BOQ Item 4.2.3.2) | m³ |  |  |  | 8 |  | 489.2294 |  | 0.026857 | 27.5553 | 393.86 | 67.8141 | 0 | 489.2294
| 1 | CBR45 | tonne | M | 1 | 1 | 18.8 | 20.95 | 393.86 |  |  | 0 | 393.86 | 0 | 0 | 393.86 | QM2.1
165.1 | 2 | Grader | hr | P | 1 | 77.778 | 18.8 | 145 | 35.0485 | 0.24171 | 0.24171 | 0 | 0 | 35.0485 | 0 | 35.0485 | 62
| 3 | Water Cart - Hire | hr | P | 1 | 77.778 | 18.8 | 95 | 22.9628 | 0.24171 | 0.24171 | 0 | 0 | 22.9628 | 0 | 22.9628 | 62
| 4 | SD Roller | day | P | 1 | 700.002 | 18.8 | 365 | 9.8028 | 0.026857 | 0.026857 | 0 | 0 | 9.8028 | 0 | 9.8028 | 62
| 5 | Labour | hr | L | 3 | 77.778 | 18.8 | 38 | 27.5553 | 0.72514 | 0.24171 | 27.5553 | 0 | 0 | 0 | 27.5553 | 62
166 | PV03 b.4 | Additional 2.1 Material (BOQ Item 4.2.3.1) | m³ |  |  |  | 8.75 |  | 550.5166 |  | 0.029375 | 30.1387 | 446.2063 | 74.1717 | 0 | 550.5166
| 1 | CBR80 | tonne | M | 1 | 1 | 20.5625 | 21.7 | 446.2063 |  |  | 0 | 446.2063 | 0 | 0 | 446.2063 | QM2.1
166.1 | 2 | Grader | hr | P | 1 | 77.778 | 20.5625 | 145 | 38.3343 | 0.26437 | 0.26437 | 0 | 0 | 38.3343 | 0 | 38.3343 | 62
| 3 | Water Cart - Hire | hr | P | 1 | 77.778 | 20.5625 | 95 | 25.1156 | 0.26437 | 0.26437 | 0 | 0 | 25.1156 | 0 | 25.1156 | 62
| 4 | SD Roller | day | P | 1 | 700.002 | 20.5625 | 365 | 10.7218 | 0.029375 | 0.029375 | 0 | 0 | 10.7218 | 0 | 10.7218 | 62
| 5 | Labour | hr | L | 3 | 77.778 | 20.5625 | 38 | 30.1387 | 0.79312 | 0.26437 | 30.1387 | 0 | 0 | 0 | 30.1387 | 62
167 | PV03 b.5 | Additional final trim (BOQ Item 4.3) | m³ |  |  |  | 70 |  | 172.3556 |  | 0.051852 | 35.4667 | 0 | 136.8889 | 0 | 172.3556
167.1 | 1 | Grader | hr | P | 1 | 150 | 70 | 145 | 67.6667 | 0.46667 | 0.46667 | 0 | 0 | 67.6667 | 0 | 67.6667 | 63
| 2 | MW Roller | day | P | 1 | 1350 | 70 | 480 | 24.8889 | 0.051852 | 0.051852 | 0 | 0 | 24.8889 | 0 | 24.8889 | 63
| 3 | Water Cart - Hire | hr | P | 1 | 150 | 70 | 95 | 44.3333 | 0.46667 | 0.46667 | 0 | 0 | 44.3333 | 0 | 44.3333 | 63
| 4 | Labour | hr | L | 2 | 150 | 70 | 38 | 35.4667 | 0.93333 | 0.46667 | 35.4667 | 0 | 0 | 0 | 35.4667 | 63
168 | PV03 b.6 | Additional Spray Seal (BOQ Item 4.5.1.1) | m² |  |  |  | 70 |  | 330.015 |  | 1 | 0 | 0 | 0 | 330.015 | 330.015
| 1 | Primer Seal | m² | S | 1 | 1 | 73.5 | 4.49 | 330.015 |  | 1 | 0 | 0 | 0 | 330.015 | 330.015 | 64
169 | PV03 b.7 | Additional AC (BOQ Item 4.5.1.2) | tonne |  |  |  | 7 |  | 2009 |  | 1 | 0 | 0 | 0 | 2009 | 2009
| 1 | DG10 | tonne | S | 1 | 1 | 7 | 287 | 2009 |  | 1 | 0 | 0 | 0 | 2009 | 2009 | 65
170 | PV03 c | Additional Kerb & Channel (Type B1) |  |  |  |  | 1
171 | PV03 c.1 | B1 Barrier Kerb & Channel (BOQ Item 4.4.1.1) | m |  |  |  | 20 |  | 820.1646 |  | 0.4 | 0 | 415.1646 | 0 | 405 | 820.1646
| 1 | S32 - Kerb Mix | m³ | M | 1 | 1 | 2.3259 | 178.5 | 415.1646 |  |  | 0 | 415.1646 | 0 | 0 | 415.1646 | CKM
| 2 | Kerb Subbie | m | S | 1 | 1 | 20 | 20.25 | 405 | 20 | 20 | 0 | 0 | 0 | 405 | 405 | 71
172 | PV03 d | Additional Footpath |  |  |  |  | 1
173 | PV03 d.1 | Additional Concrete Footpath 2.45m Wide (BOQ Item 4.4.4.1) | m² |  |  |  | 24.5 |  | 1353.7869 |  | 0.49 | 34.1363 | 664.4802 | 42.6704 | 612.5 | 1353.7869
| 1 | Material Supply
| 2 | N25 | m³ | M | 1 | 1 | 2.695 | 158.2 | 426.3447 |  |  | 0 | 426.3447 | 0 | 0 | 426.3447 | C25
| 3 | SL72 | m² | M | 1 | 1 | 29.4 | 5.76 | 169.344 |  |  | 0 | 169.344 | 0 | 0 | 169.344 | RSM
| 4 | Sand | tonne | M | 1 | 1 | 2.695 | 17.95 | 48.3748 |  |  | 0 | 48.3748 | 0 | 0 | 48.3748 | QMS
| 5 | Dowels | each | M | 1 | 1 | 10.2083 | 2 | 20.4167 |  |  | 0 | 20.4167 | 0 | 0 | 20.4167 | RSB
| 6 | Place Sand
173.1 | 7 | Bobcat | hr | P | 1 | 6 | 2.695 | 95 | 42.6704 | 0.44916 | 0.44916 | 0 | 0 | 42.6704 | 0 | 42.6704 | 73
| 8 | Labour | hr | L | 2 | 6 | 2.695 | 38 | 34.1363 | 0.89832 | 0.44916 | 34.1363 | 0 | 0 | 0 | 34.1363 | 73
Form & Supply
| 10 | Concrete Subbie | m² | S | 1 | 1 | 24.5 | 25 | 612.5 |  | 24.5 | 0 | 0 | 0 | 612.5 | 612.5 | 73
174 | PV03 e | Additional Storm Water |  |  |  |  | 1
175 | PV03 e.1 | Additional 450 mm Diameter Class 2 RRJ (BOQ Item 5.1.3) | m |  |  |  | 4.88 |  | 691.2911 |  | 0.081329 | 83.4438 | 498.0528 | 109.7945 | 0 | 691.2911
| 1 | Material Supply
| 2 | 450 RCP FJ CL2 | m | M | 1 | 1 | 4.88 | 76.93 | 375.4184 |  |  | 0 | 375.4184 | 0 | 0 | 375.4184 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 6.832 | 17.95 | 122.6344 |  |  | 0 | 122.6344 | 0 | 0 | 122.6344 | QMS
| 4 | Excavation & Laying
175.1 | 5 | Excavator - 25T | hr | P | 1 | 6.667 | 4.88 | 135 | 98.8151 | 0.73196 | 0.73196 | 0 | 0 | 98.8151 | 0 | 98.8151 | 81
| 6 | Labour | hr | L | 3 | 6.667 | 4.88 | 38 | 83.4438 | 2.1959 | 0.73196 | 83.4438 | 0 | 0 | 0 | 83.4438 | 81
| 7 | Trench Roller | hr | P | 1 | 6.667 | 4.88 | 15 | 10.9795 | 0.73196 | 0.73196 | 0 | 0 | 10.9795 | 0 | 10.9795 | 81
176 | PV03 f | Additional General Fill between rental car aprk and batter of new road one |  |  |  |  | 1
177 | PV03 f.1 | Cut to Fill (BOQ Item 3.3.4) | m³ |  |  |  | 460 |  | 3090.7431 |  | 0.46 | 314.6403 | 0 | 2776.1028 | 0 | 3090.7431
177.1 | 1 | Excavator - 25T | hr | P | 1 | 111.111 | 460 | 135 | 558.9006 | 4.14 | 4.14 | 0 | 0 | 558.9006 | 0 | 558.9006 | 51
| 2 | Tipper | hr | P | 3 | 111.111 | 460 | 85 | 1055.7011 | 12.42 | 4.14 | 0 | 0 | 1055.7011 | 0 | 1055.7011 | 51
| 3 | Labour | hr | L | 2 | 111.111 | 460 | 38 | 314.6403 | 8.28 | 4.14 | 314.6403 | 0 | 0 | 0 | 314.6403 | 51
| 4 | Grader | hr | P | 1 | 111.111 | 460 | 145 | 600.3006 | 4.14 | 4.14 | 0 | 0 | 600.3006 | 0 | 600.3006 | 51
| 5 | PF Roller | day | P | 1 | 999.999 | 460 | 365 | 167.9002 | 0.46 | 0.46 | 0 | 0 | 167.9002 | 0 | 167.9002 | 51
| 6 | Water Cart - Hire | hr | P | 1 | 111.111 | 460 | 95 | 393.3004 | 4.14 | 4.14 | 0 | 0 | 393.3004 | 0 | 393.3004 | 51
178 | PV03 g | Additional Conduit & Trenching |  |  |  |  | 1 |  | 502.5086 |  |  | 113.9977 | 184.515 | 203.9959 | 0 | 502.5086
179 | PV03 g.1 | Additional Trenching (BOQ Item 6.1) | m |  |  |  | 10 |  | 346.7136 |  | 0.22222 | 113.9977 | 28.72 | 203.9959 | 0 | 346.7136
| 1 | Excavate Trench
179.1 | 2 | Excavator - 25T | hr | P | 1 | 16.667 | 10 | 135 | 80.9984 | 0.59999 | 0.59999 | 0 | 0 | 80.9984 | 0 | 80.9984 | 111
| 3 | Labour | hr | L | 3 | 16.667 | 10 | 38 | 68.3986 | 1.8 | 0.59999 | 68.3986 | 0 | 0 | 0 | 68.3986 | 111
| 4 | Sand | tonne | M | 1 | 1 | 1.6 | 17.95 | 28.72 |  |  | 0 | 28.72 | 0 | 0 | 28.72 | QMS
| 5 | Backfill & Compact
| 6 | Bobcat | hr | P | 1 | 16.667 | 10 | 95 | 56.9989 | 0.59999 | 0.59999 | 0 | 0 | 56.9989 | 0 | 56.9989 | 111
| 7 | Water Cart - Hire | hr | P | 1 | 16.667 | 10 | 95 | 56.9989 | 0.59999 | 0.59999 | 0 | 0 | 56.9989 | 0 | 56.9989 | 111
| 8 | Trench Roller | hr | P | 1 | 16.667 | 10 | 15 | 8.9998 | 0.59999 | 0.59999 | 0 | 0 | 8.9998 | 0 | 8.9998 | 111
| 9 | Labour | hr | L | 2 | 16.667 | 10 | 38 | 45.5991 | 1.2 | 0.59999 | 45.5991 | 0 | 0 | 0 | 45.5991 | 111
180 | PV03 g.2 | Additional 100 diameter communications conduit | m |  |  |  | 10 |  | 46.725 |  | 0.22222 | 0 | 46.725 | 0 | 0 | 46.725
| 1 | 100 LD uPVC Electrical | m | M | 1 | 1 | 10.5 | 4.45 | 46.725 |  |  | 0 | 46.725 | 0 | 0 | 46.725 | ETC
181 | PV03 g.3 | Additional 100 diameter electrical conduit (BOQ Item 6.2) | m |  |  |  | 20 |  | 109.07 |  | 0.22222 | 0 | 109.07 | 0 | 0 | 109.07
| 1 | 100 LD uPVC Electrical | m | M | 1 | 1 | 21 | 4.45 | 93.45 |  |  | 0 | 93.45 | 0 | 0 | 93.45 | ETC
| 2 | Draw Rope - Conduits | m | M | 1 | 1 | 22 | 0.11 | 2.42 |  |  | 0 | 2.42 | 0 | 0 | 2.42 | ETM
| 3 | Warning Tape | m | M | 1 | 1 | 40 | 0.33 | 13.2 |  |  | 0 | 13.2 | 0 | 0 | 13.2 | ETM
182 | PV04 | Remove & Replace Unsuitable (Extra Over BOQ Item 3.3.7) | m³ |  |  |  | 100 |  | 5113.116 |  | 3.6667 | 468.6701 | 0 | 4644.4459 | 0 | 5113.116
| 1 | Excavatio to spoil
182.1 | 2 | Excavator - 25T | hr | P | 1 | 30 | 100 | 135 | 450 | 3.3333 | 3.3333 | 0 | 0 | 450 | 0 | 450 | 57
| 3 | Tipper | hr | P | 3 | 30 | 100 | 85 | 850 | 10 | 3.3333 | 0 | 0 | 850 | 0 | 850 | 57
| 4 | Water Cart - Hire | hr | P | 1 | 30 | 100 | 95 | 316.6667 | 3.3333 | 3.3333 | 0 | 0 | 316.6667 | 0 | 316.6667 | 57
| 5 | Labour | hr | L | 1 | 30 | 100 | 38 | 126.6667 | 3.3333 | 3.3333 | 126.6667 | 0 | 0 | 0 | 126.6667 | 57
| 6 | Placement of Gravel
| 7 | Win material from local pit
| 8 | D6 | hr | P | 1 | 133.333 | 100 | 185 | 138.7503 | 0.75 | 0.75 | 0 | 0 | 138.7503 | 0 | 138.7503 | 57
| 9 | Load & Cart
182.2 | 10 | Excavator - 25T | hr | P | 1 | 33.333 | 100 | 135 | 405.0041 | 3 | 3 | 0 | 0 | 405.0041 | 0 | 405.0041 | 57
| 11 | Truck & Dog | hr | P | 3 | 33.333 | 100 | 145 | 1305.0131 | 9.0001 | 3 | 0 | 0 | 1305.0131 | 0 | 1305.0131 | 57
| 12 | Place & Compact
| 13 | Grader | hr | P | 1 | 33.333 | 100 | 145 | 435.0044 | 3 | 3 | 0 | 0 | 435.0044 | 0 | 435.0044 | 57
| 14 | Water Cart - Hire | hr | P | 1 | 33.333 | 100 | 95 | 285.0029 | 3 | 3 | 0 | 0 | 285.0029 | 0 | 285.0029 | 57
| 15 | PF Roller Wet - No OP | hr | P | 1 | 33.333 | 100 | 58 | 174.0017 | 3 | 3 | 0 | 0 | 174.0017 | 0 | 174.0017 | 57
| 16 | Labour | hr | L | 3 | 33.333 | 100 | 38 | 342.0034 | 9.0001 | 3 | 342.0034 | 0 | 0 | 0 | 342.0034 | 57
| 17 | Bobcat | hr | P | 1 | 33.333 | 100 | 95 | 285.0029 | 3 | 3 | 0 | 0 | 285.0029 | 0 | 285.0029 | 57
183 | PV05 | Remove & Replace Soft Spots - Rental Car Park | item |  |  |  | 75 |  | 3834.837 |  | 2.75 | 351.5026 | 0 | 3483.3344 | 0 | 3834.837
| 1 | Excavatio to spoil
183.1 | 2 | Excavator - 25T | hr | P | 1 | 30 | 75 | 135 | 337.5 | 2.5 | 2.5 | 0 | 0 | 337.5 | 0 | 337.5 | 57
| 3 | Tipper | hr | P | 3 | 30 | 75 | 85 | 637.5 | 7.5 | 2.5 | 0 | 0 | 637.5 | 0 | 637.5 | 57
| 4 | Water Cart - Hire | hr | P | 1 | 30 | 75 | 95 | 237.5 | 2.5 | 2.5 | 0 | 0 | 237.5 | 0 | 237.5 | 57
| 5 | Labour | hr | L | 1 | 30 | 75 | 38 | 95 | 2.5 | 2.5 | 95 | 0 | 0 | 0 | 95 | 57
| 6 | Placement of Gravel
| 7 | Win material from local pit
| 8 | D6 | hr | P | 1 | 133.333 | 75 | 185 | 104.0628 | 0.5625 | 0.5625 | 0 | 0 | 104.0628 | 0 | 104.0628 | 57
| 9 | Load & Cart
183.2 | 10 | Excavator - 25T | hr | P | 1 | 33.333 | 75 | 135 | 303.753 | 2.25 | 2.25 | 0 | 0 | 303.753 | 0 | 303.753 | 57
| 11 | Truck & Dog | hr | P | 3 | 33.333 | 75 | 145 | 978.7598 | 6.7501 | 2.25 | 0 | 0 | 978.7598 | 0 | 978.7598 | 57
| 12 | Place & Compact
| 13 | Grader | hr | P | 1 | 33.333 | 75 | 145 | 326.2533 | 2.25 | 2.25 | 0 | 0 | 326.2533 | 0 | 326.2533 | 57
| 14 | Water Cart - Hire | hr | P | 1 | 33.333 | 75 | 95 | 213.7521 | 2.25 | 2.25 | 0 | 0 | 213.7521 | 0 | 213.7521 | 57
| 15 | PF Roller Wet - No OP | hr | P | 1 | 33.333 | 75 | 58 | 130.5013 | 2.25 | 2.25 | 0 | 0 | 130.5013 | 0 | 130.5013 | 57
| 16 | Labour | hr | L | 3 | 33.333 | 75 | 38 | 256.5026 | 6.7501 | 2.25 | 256.5026 | 0 | 0 | 0 | 256.5026 | 57
| 17 | Bobcat | hr | P | 1 | 33.333 | 75 | 95 | 213.7521 | 2.25 | 2.25 | 0 | 0 | 213.7521 | 0 | 213.7521 | 57
184 | PV06 | Extension To Commercial Car Park | item |  |  |  | 1 |  | 75658.3253 |  |  | 6617.4757 | 28505.5038 | 26665.4934 | 13869.8524 | 75658.3253
185 | PV06.a | Clear & Grubbing (BOQ Item 3.2.1) | m² |  |  |  | 1800 |  | 192 |  | 0.11111 | 57 | 0 | 135 | 0 | 192
1
185.1 | 2 | Excavator - 25T | hr | P | 1 | 1 | 1 | 135 | 135 | 1 | 1 | 0 | 0 | 135 | 0 | 135 | 22
| 3 | Labour | hr | L | 3 | 1 | 0.5 | 38 | 57 | 1.5 | 0.5 | 57 | 0 | 0 | 0 | 57 | 22
186 | PV06.b | Stripping Topsoil (BOQ item 3.3.1) | m³ |  |  |  | 180 |  | 1543.5 |  | 0.5 | 171 | 0 | 1372.5 | 0 | 1543.5
186.1 | 1 | Excavator - 25T | hr | P | 1 | 40 | 180 | 135 | 607.5 | 4.5 | 4.5 | 0 | 0 | 607.5 | 0 | 607.5 | 31
| 2 | Tipper | hr | P | 2 | 40 | 180 | 85 | 765 | 9 | 4.5 | 0 | 0 | 765 | 0 | 765 | 31
| 3 | Labour | hr | L | 1 | 40 | 180 | 38 | 171 | 4.5 | 4.5 | 171 | 0 | 0 | 0 | 171 | 31
187 | PV06.c | Import General Fill (BOQ Item 3.3.5) | m³ |  |  |  | 1080 |  | 14584.0374 |  | 1.35 | 1385.0983 | 0 | 13198.9391 | 0 | 14584.0374
| 1 | Win Material From Local Pit
187.1 | 2 | D6 | hr | P | 1 | 133.333 | 1080 | 185 | 1498.5037 | 8.1 | 8.1 | 0 | 0 | 1498.5037 | 0 | 1498.5037 | 52
| 3 | Load & Cart
187.2 | 4 | Excavator - 25T | hr | P | 1 | 88.889 | 1080 | 135 | 1640.2479 | 12.15 | 12.15 | 0 | 0 | 1640.2479 | 0 | 1640.2479 | 52
| 5 | Truck & Dog | hr | P | 3 | 88.889 | 1080 | 145 | 5285.2434 | 36.45 | 12.15 | 0 | 0 | 5285.2434 | 0 | 5285.2434 | 52
| 6 | Place & Compact
| 7 | Grader | hr | P | 1 | 88.889 | 1080 | 145 | 1761.7478 | 12.15 | 12.15 | 0 | 0 | 1761.7478 | 0 | 1761.7478 | 52
| 8 | Water Cart - Hire | hr | P | 1 | 88.889 | 1080 | 95 | 1154.2486 | 12.15 | 12.15 | 0 | 0 | 1154.2486 | 0 | 1154.2486 | 52
| 9 | PF Roller Wet - No OP | hr | P | 1 | 88.889 | 1080 | 58 | 704.6991 | 12.15 | 12.15 | 0 | 0 | 704.6991 | 0 | 704.6991 | 52
| 10 | Labour | hr | L | 3 | 88.889 | 1080 | 38 | 1385.0983 | 36.45 | 12.15 | 1385.0983 | 0 | 0 | 0 | 1385.0983 | 52
| 11 | Bobcat | hr | P | 1 | 88.889 | 1080 | 95 | 1154.2486 | 12.15 | 12.15 | 0 | 0 | 1154.2486 | 0 | 1154.2486 | 52
188 | PV06.d | Prepare Sub-grade (BOQ Item 4.1) | m² |  |  |  | 1800 |  | 3667.4286 |  | 1.1429 | 781.7143 | 0 | 2885.7143 | 0 | 3667.4286
188.1 | 1 | Grader | hr | P | 1 | 175 | 1800 | 145 | 1491.4286 | 10.2857 | 10.2857 | 0 | 0 | 1491.4286 | 0 | 1491.4286 | 61
| 2 | SD Roller | day | P | 1 | 1575 | 1800 | 365 | 417.1429 | 1.1429 | 1.1429 | 0 | 0 | 417.1429 | 0 | 417.1429 | 61
| 3 | Water Cart - Hire | hr | P | 1 | 175 | 1800 | 95 | 977.1429 | 10.2857 | 10.2857 | 0 | 0 | 977.1429 | 0 | 977.1429 | 61
| 4 | Labour | hr | L | 2 | 175 | 1800 | 38 | 781.7143 | 20.5714 | 10.2857 | 781.7143 | 0 | 0 | 0 | 781.7143 | 61
189 | PV06.e | Import 2.1 (BOQ Item 4.2.3.1) | m³ |  |  |  | 225 |  | 14156.1406 |  | 0.75535 | 774.9942 | 11473.875 | 1907.2713 | 0 | 14156.1406
| 1 | CBR80 | tonne | M | 1 | 1 | 528.75 | 21.7 | 11473.875 |  |  | 0 | 11473.875 | 0 | 0 | 11473.875 | QM2.1
189.1 | 2 | Grader | hr | P | 1 | 77.778 | 528.75 | 145 | 985.7383 | 6.7982 | 6.7982 | 0 | 0 | 985.7383 | 0 | 985.7383 | 62
| 3 | Water Cart - Hire | hr | P | 1 | 77.778 | 528.75 | 95 | 645.8285 | 6.7982 | 6.7982 | 0 | 0 | 645.8285 | 0 | 645.8285 | 62
| 4 | SD Roller | day | P | 1 | 700.002 | 528.75 | 365 | 275.7046 | 0.75535 | 0.75535 | 0 | 0 | 275.7046 | 0 | 275.7046 | 62
| 5 | Labour | hr | L | 3 | 77.778 | 528.75 | 38 | 774.9942 | 20.3946 | 6.7982 | 774.9942 | 0 | 0 | 0 | 774.9942 | 62
190 | PV06.f | Import 2.3 (BOQ Item 4.2.3.2) |  |  |  |  | 180 |  | 11007.6624 |  | 0.60428 | 619.9954 | 8861.85 | 1525.8171 | 0 | 11007.6624
| 1 | CBR45 | tonne | M | 1 | 1 | 423 | 20.95 | 8861.85 |  |  | 0 | 8861.85 | 0 | 0 | 8861.85 | QM2.1
190.1 | 2 | Grader | hr | P | 1 | 77.778 | 423 | 145 | 788.5906 | 5.4386 | 5.4386 | 0 | 0 | 788.5906 | 0 | 788.5906 | 62
| 3 | Water Cart - Hire | hr | P | 1 | 77.778 | 423 | 95 | 516.6628 | 5.4386 | 5.4386 | 0 | 0 | 516.6628 | 0 | 516.6628 | 62
| 4 | SD Roller | day | P | 1 | 700.002 | 423 | 365 | 220.5637 | 0.60428 | 0.60428 | 0 | 0 | 220.5637 | 0 | 220.5637 | 62
| 5 | Labour | hr | L | 3 | 77.778 | 423 | 38 | 619.9954 | 16.3157 | 5.4386 | 619.9954 | 0 | 0 | 0 | 619.9954 | 62
191 | PV06.g | Primer Seal (7mm) (BOQ Item 4.5.1.1) | m² |  |  |  | 1800 |  | 8486.1 |  | 1 | 0 | 0 | 0 | 8486.1 | 8486.1
| 1 | Primer Seal | m² | S | 1 | 1 | 1890 | 4.49 | 8486.1 |  | 1 | 0 | 0 | 0 | 8486.1 | 8486.1 | 64
192 | PV06.h | SM4 Kerb (BOQ Item 4.4.1.3) | m |  |  |  | 44 |  | 1071.6805 |  | 1 | 0 | 180.6805 | 0 | 891 | 1071.6805
| 1 | S32 - Kerb Mix | m³ | M | 1 | 1 | 1.0122 | 178.5 | 180.6805 |  |  | 0 | 180.6805 | 0 | 0 | 180.6805 | CKM
| 2 | Kerb Subbie | m | S | 1 | 1 | 44 | 20.25 | 891 | 44 | 44 | 0 | 0 | 0 | 891 | 891 | 71
193 | PV06.i | B1 Kerb (BOQ Item 4.4.1.1) | m |  |  |  | 44 |  | 2431.2908 |  | 1 | 61.3061 | 1193.3521 | 76.6326 | 1100 | 2431.2908
| 1 | Material Supply
| 2 | N25 | m³ | M | 1 | 1 | 4.84 | 158.2 | 765.6803 |  |  | 0 | 765.6803 | 0 | 0 | 765.6803 | C25
| 3 | SL72 | m² | M | 1 | 1 | 52.8 | 5.76 | 304.128 |  |  | 0 | 304.128 | 0 | 0 | 304.128 | RSM
| 4 | Sand | tonne | M | 1 | 1 | 4.84 | 17.95 | 86.8771 |  |  | 0 | 86.8771 | 0 | 0 | 86.8771 | QMS
| 5 | Dowels | each | M | 1 | 1 | 18.3333 | 2 | 36.6667 |  |  | 0 | 36.6667 | 0 | 0 | 36.6667 | RSB
| 6 | Place Sand
193.1 | 7 | Bobcat | hr | P | 1 | 6 | 4.84 | 95 | 76.6326 | 0.80666 | 0.80666 | 0 | 0 | 76.6326 | 0 | 76.6326 | 71
| 8 | Labour | hr | L | 2 | 6 | 4.84 | 38 | 61.3061 | 1.6133 | 0.80666 | 61.3061 | 0 | 0 | 0 | 61.3061 | 71
Form & Supply
| 10 | Concrete Subbie | m² | S | 1 | 1 | 44 | 25 | 1100 |  | 44 | 0 | 0 | 0 | 1100 | 1100 | 71
194 | PV06.j | B2 Kerb (BOQ Item 4.4.1.2) | m |  |  |  | 44 |  | 1279.8311 |  | 1 | 0 | 388.8311 | 0 | 891 | 1279.8311
| 1 | S32 - Kerb Mix | m³ | M | 1 | 1 | 2.1783 | 178.5 | 388.8311 |  |  | 0 | 388.8311 | 0 | 0 | 388.8311 | CKM
| 2 | Kerb Subbie | m | S | 1 | 1 | 44 | 20.25 | 891 | 44 | 44 | 0 | 0 | 0 | 891 | 891 | 71
195 | PV06.k | Topsoil to Back of Kerb (BOQ Item 3.3.2) | m³ |  |  |  | 20 |  | 284.8 |  | 0.088889 | 60.8 | 0 | 224 | 0 | 284.8
195.1 | 1 | Backhoe | hr | P | 1 | 250 | 200 | 100 | 80 | 0.8 | 0.8 | 0 | 0 | 80 | 0 | 80 | 33
| 2 | Tipper | hr | P | 1 | 250 | 200 | 85 | 68 | 0.8 | 0.8 | 0 | 0 | 68 | 0 | 68 | 33
| 3 | Bobcat | hr | P | 1 | 250 | 200 | 95 | 76 | 0.8 | 0.8 | 0 | 0 | 76 | 0 | 76 | 33
| 4 | Labour | hr | L | 2 | 250 | 200 | 38 | 60.8 | 1.6 | 0.8 | 60.8 | 0 | 0 | 0 | 60.8 | 33
196 | PV06.l | Additional 450 RCP (BOQ Item 5.1.4) | m |  |  |  | 26 |  | 4674.4885 |  | 0.43331 | 444.5778 | 3644.94 | 584.9708 | 0 | 4674.4885
| 1 | Material Supply
| 2 | 450 RCP FJ CL4 | m | M | 1 | 1 | 26 | 115.06 | 2991.56 |  |  | 0 | 2991.56 | 0 | 0 | 2991.56 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 36.4 | 17.95 | 653.38 |  |  | 0 | 653.38 | 0 | 0 | 653.38 | QMS
| 4 | Excavation & Laying
196.1 | 5 | Excavator - 25T | hr | P | 1 | 6.667 | 26 | 135 | 526.4737 | 3.8998 | 3.8998 | 0 | 0 | 526.4737 | 0 | 526.4737 | 81
| 6 | Labour | hr | L | 3 | 6.667 | 26 | 38 | 444.5778 | 11.6994 | 3.8998 | 444.5778 | 0 | 0 | 0 | 444.5778 | 81
| 7 | Trench Roller | hr | P | 1 | 6.667 | 26 | 15 | 58.4971 | 3.8998 | 3.8998 | 0 | 0 | 58.4971 | 0 | 58.4971 | 81
197 | PV06.m | Final Trim (BOQ Item 4.3) | m² |  |  |  | 1800 |  | 4432 |  | 1.3333 | 912 | 0 | 3520 | 0 | 4432
197.1 | 1 | Grader | hr | P | 1 | 150 | 1800 | 145 | 1740 | 12 | 12 | 0 | 0 | 1740 | 0 | 1740 | 63
| 2 | MW Roller | day | P | 1 | 1350 | 1800 | 480 | 640 | 1.3333 | 1.3333 | 0 | 0 | 640 | 0 | 640 | 63
| 3 | Water Cart - Hire | hr | P | 1 | 150 | 1800 | 95 | 1140 | 12 | 12 | 0 | 0 | 1140 | 0 | 1140 | 63
| 4 | Labour | hr | L | 2 | 150 | 1800 | 38 | 912 | 24 | 12 | 912 | 0 | 0 | 0 | 912 | 63
198 | PV06.n | Additional Conduit Trenching (BOQ Item 6.1) | m |  |  |  | 45 |  | 1560.2114 |  | 0.29999 | 512.9897 | 129.24 | 917.9816 | 0 | 1560.2114
| 1 | Excavate Trench
198.1 | 2 | Excavator - 25T | hr | P | 1 | 16.667 | 45 | 135 | 364.4927 | 2.6999 | 2.6999 | 0 | 0 | 364.4927 | 0 | 364.4927 | 111
| 3 | Labour | hr | L | 3 | 16.667 | 45 | 38 | 307.7938 | 8.0998 | 2.6999 | 307.7938 | 0 | 0 | 0 | 307.7938 | 111
| 4 | Sand | tonne | M | 1 | 1 | 7.2 | 17.95 | 129.24 |  |  | 0 | 129.24 | 0 | 0 | 129.24 | QMS
| 5 | Backfill & Compact
| 6 | Bobcat | hr | P | 1 | 16.667 | 45 | 95 | 256.4949 | 2.6999 | 2.6999 | 0 | 0 | 256.4949 | 0 | 256.4949 | 111
| 7 | Water Cart - Hire | hr | P | 1 | 16.667 | 45 | 95 | 256.4949 | 2.6999 | 2.6999 | 0 | 0 | 256.4949 | 0 | 256.4949 | 111
| 8 | Trench Roller | hr | P | 1 | 16.667 | 45 | 15 | 40.4992 | 2.6999 | 2.6999 | 0 | 0 | 40.4992 | 0 | 40.4992 | 111
| 9 | Labour | hr | L | 2 | 16.667 | 45 | 38 | 205.1959 | 5.3999 | 2.6999 | 205.1959 | 0 | 0 | 0 | 205.1959 | 111
199 | PV06.o | Additional Conduit (BOQ Item 6.3) | m |  |  |  | 45 |  | 131.535 |  | 1 | 0 | 131.535 | 0 | 0 | 131.535
| 1 | 40 HD uPVC Electrical | m | M | 1 | 1 | 47.25 | 2.04 | 96.39 |  |  | 0 | 96.39 | 0 | 0 | 96.39 | ETC
| 2 | Draw Rope - Conduits | m | M | 1 | 1 | 49.5 | 0.11 | 5.445 |  |  | 0 | 5.445 | 0 | 0 | 5.445 | ETM
| 3 | Warning Tape | m | M | 1 | 1 | 90 | 0.33 | 29.7 |  |  | 0 | 29.7 | 0 | 0 | 29.7 | ETM
200 | PV06.p | Additional Wheel Stops (BOQ Item 4.4.4.5) | ea |  |  |  | 10 |  | 1546.6667 |  | 0.11111 | 380 | 850 | 316.6667 | 0 | 1546.6667
| 1 | Wheelstops | each | M | 1 | 1 | 10 | 85 | 850 |  |  | 0 | 850 | 0 | 0 | 850 | 67
| 2 | Labour | hr | L | 3 | 3 | 10 | 38 | 380 | 10 | 3.3333 | 380 | 0 | 0 | 0 | 380 | 67
| 3 | Bobcat | hr | P | 1 | 3 | 10 | 95 | 316.6667 | 3.3333 | 3.3333 | 0 | 0 | 316.6667 | 0 | 316.6667 | 67
201 | PV06.q | Additional Log Barrier Fence (BOQ Item 7.2.1.1) | m |  |  |  | 31 |  | 836.535 |  | 2 | 0 | 0 | 0 | 836.535 | 836.535
| 1 | Log Fence | m | S | 1 | 1 | 32.55 | 25.7 | 836.535 |  | 32.55 | 0 | 0 | 0 | 836.535 | 836.535 | 131
202 | PV06.r | New 2.4m Kerb Lintel | item |  |  |  | 1 |  | 2107.2 |  | 1.3333 | 456 | 1651.2 | 0 | 0 | 2107.2
| 1 | 2.4 Lintel Complete | Item | M | 1 | 1 | 1 | 1484 | 1484 |  |  | 0 | 1484 | 0 | 0 | 1484 | SWL
| 2 | N32 | m³ | M | 1 | 1 | 1 | 167.2 | 167.2 |  |  | 0 | 167.2 | 0 | 0 | 167.2 | C32
| 3 | Labour | hr | L | 1 | 1 | 12 | 38 | 456 | 12 | 12 | 456 | 0 | 0 | 0 | 456 | 85
203 | PV06.s | Additional Line Marking (BOQ Item 4.7.1) | item |  |  |  | 0.21739 |  | 1665.2174 |  | 0.33333 | 0 | 0 | 0 | 1665.2174 | 1665.2174
| 1 | Line Marking | m² | S | 1 | 1 | 0.21739 | 7660 | 1665.2174 |  | 0.21739 | 0 | 0 | 0 | 1665.2174 | 1665.2174 | 66
204 | PV07 | Additional Box Out & General Fill |  |  |  |  | 1 |  | 41486.6131 |  | 4.9667 | 3418.4304 | 0 | 38068.1827 | 0 | 41486.6131
205 | PV07.a | Cut To Spoil (BOQ Item 3.3.6) | m³ |  |  |  | 1341 |  | 23378.1 |  | 4.9667 | 1698.6 | 0 | 21679.5 | 0 | 23378.1
205.1 | 1 | Excavator - 25T | hr | P | 1 | 30 | 1341 | 135 | 6034.5 | 44.7 | 44.7 | 0 | 0 | 6034.5 | 0 | 6034.5 | 53
| 2 | Tipper | hr | P | 3 | 30 | 1341 | 85 | 11398.5 | 134.1 | 44.7 | 0 | 0 | 11398.5 | 0 | 11398.5 | 53
| 3 | Water Cart - Hire | hr | P | 1 | 30 | 1341 | 95 | 4246.5 | 44.7 | 44.7 | 0 | 0 | 4246.5 | 0 | 4246.5 | 53
| 4 | Labour | hr | L | 1 | 30 | 1341 | 38 | 1698.6 | 44.7 | 44.7 | 1698.6 | 0 | 0 | 0 | 1698.6 | 53
206 | PV07.b | Import General Fill (BOQ Item 3.3.5) | m³ |  |  |  | 1341 |  | 18108.5131 |  | 1.6762 | 1719.8304 | 0 | 16388.6827 | 0 | 18108.5131
| 1 | Win Material From Local Pit
206.1 | 2 | D6 | hr | P | 1 | 133.333 | 1341 | 185 | 1860.6422 | 10.0575 | 10.0575 | 0 | 0 | 1860.6422 | 0 | 1860.6422 | 52
| 3 | Load & Cart
206.2 | 4 | Excavator - 25T | hr | P | 1 | 88.889 | 1341 | 135 | 2036.6412 | 15.0862 | 15.0862 | 0 | 0 | 2036.6412 | 0 | 2036.6412 | 52
| 5 | Truck & Dog | hr | P | 3 | 88.889 | 1341 | 145 | 6562.5105 | 45.2587 | 15.0862 | 0 | 0 | 6562.5105 | 0 | 6562.5105 | 52
| 6 | Place & Compact
| 7 | Grader | hr | P | 1 | 88.889 | 1341 | 145 | 2187.5035 | 15.0862 | 15.0862 | 0 | 0 | 2187.5035 | 0 | 2187.5035 | 52
| 8 | Water Cart - Hire | hr | P | 1 | 88.889 | 1341 | 95 | 1433.192 | 15.0862 | 15.0862 | 0 | 0 | 1433.192 | 0 | 1433.192 | 52
| 9 | PF Roller Wet - No OP | hr | P | 1 | 88.889 | 1341 | 58 | 875.0014 | 15.0862 | 15.0862 | 0 | 0 | 875.0014 | 0 | 875.0014 | 52
| 10 | Labour | hr | L | 3 | 88.889 | 1341 | 38 | 1719.8304 | 45.2587 | 15.0862 | 1719.8304 | 0 | 0 | 0 | 1719.8304 | 52
| 11 | Bobcat | hr | P | 1 | 88.889 | 1341 | 95 | 1433.192 | 15.0862 | 15.0862 | 0 | 0 | 1433.192 | 0 | 1433.192 | 52
207 | PV08 | Remove & Replace Unsuitable - Bus Bay & Round-a-bout | item |  |  |  | 1 |  | 14387.7283 |  | 1.1027 | 1328.7438 | 0 | 13058.9846 | 0 | 14387.7283
208 | PV08.a | Remove Soft Spots (BOQ Item 3.3.7) | m³ |  |  |  | 222.6 |  | 11381.7962 |  | 0.82444 | 1043.2596 | 0 | 10338.5366 | 0 | 11381.7962
| 1 | Excavatio to spoil
208.1 | 2 | Excavator - 25T | hr | P | 1 | 30 | 222.6 | 135 | 1001.7 | 7.42 | 7.42 | 0 | 0 | 1001.7 | 0 | 1001.7 | 57
| 3 | Tipper | hr | P | 3 | 30 | 222.6 | 85 | 1892.1 | 22.26 | 7.42 | 0 | 0 | 1892.1 | 0 | 1892.1 | 57
| 4 | Water Cart - Hire | hr | P | 1 | 30 | 222.6 | 95 | 704.9 | 7.42 | 7.42 | 0 | 0 | 704.9 | 0 | 704.9 | 57
| 5 | Labour | hr | L | 1 | 30 | 222.6 | 38 | 281.96 | 7.42 | 7.42 | 281.96 | 0 | 0 | 0 | 281.96 | 57
| 6 | Placement of Gravel
| 7 | Win material from local pit
| 8 | D6 | hr | P | 1 | 133.333 | 222.6 | 185 | 308.8583 | 1.6695 | 1.6695 | 0 | 0 | 308.8583 | 0 | 308.8583 | 57
| 9 | Load & Cart
208.2 | 10 | Excavator - 25T | hr | P | 1 | 33.333 | 222.6 | 135 | 901.539 | 6.6781 | 6.6781 | 0 | 0 | 901.539 | 0 | 901.539 | 57
| 11 | Truck & Dog | hr | P | 3 | 33.333 | 222.6 | 145 | 2904.959 | 20.0342 | 6.6781 | 0 | 0 | 2904.959 | 0 | 2904.959 | 57
| 12 | Place & Compact
| 13 | Grader | hr | P | 1 | 33.333 | 222.6 | 145 | 968.3197 | 6.6781 | 6.6781 | 0 | 0 | 968.3197 | 0 | 968.3197 | 57
| 14 | Water Cart - Hire | hr | P | 1 | 33.333 | 222.6 | 95 | 634.4163 | 6.6781 | 6.6781 | 0 | 0 | 634.4163 | 0 | 634.4163 | 57
| 15 | PF Roller Wet - No OP | hr | P | 1 | 33.333 | 222.6 | 58 | 387.3279 | 6.6781 | 6.6781 | 0 | 0 | 387.3279 | 0 | 387.3279 | 57
| 16 | Labour | hr | L | 3 | 33.333 | 222.6 | 38 | 761.2996 | 20.0342 | 6.6781 | 761.2996 | 0 | 0 | 0 | 761.2996 | 57
| 17 | Bobcat | hr | P | 1 | 33.333 | 222.6 | 95 | 634.4163 | 6.6781 | 6.6781 | 0 | 0 | 634.4163 | 0 | 634.4163 | 57
209 | PV08.b | Import General Fill (BOQ Item 3.3.5) | m³ |  |  |  | 222.6 |  | 3005.9322 |  | 0.27825 | 285.4841 | 0 | 2720.448 | 0 | 3005.9322
| 1 | Win Material From Local Pit
209.1 | 2 | D6 | hr | P | 1 | 133.333 | 222.6 | 185 | 308.8583 | 1.6695 | 1.6695 | 0 | 0 | 308.8583 | 0 | 308.8583 | 52
| 3 | Load & Cart
209.2 | 4 | Excavator - 25T | hr | P | 1 | 88.889 | 222.6 | 135 | 338.0733 | 2.5042 | 2.5042 | 0 | 0 | 338.0733 | 0 | 338.0733 | 52
| 5 | Truck & Dog | hr | P | 3 | 88.889 | 222.6 | 145 | 1089.3474 | 7.5127 | 2.5042 | 0 | 0 | 1089.3474 | 0 | 1089.3474 | 52
| 6 | Place & Compact
| 7 | Grader | hr | P | 1 | 88.889 | 222.6 | 145 | 363.1158 | 2.5042 | 2.5042 | 0 | 0 | 363.1158 | 0 | 363.1158 | 52
| 8 | Water Cart - Hire | hr | P | 1 | 88.889 | 222.6 | 95 | 237.9035 | 2.5042 | 2.5042 | 0 | 0 | 237.9035 | 0 | 237.9035 | 52
| 9 | PF Roller Wet - No OP | hr | P | 1 | 88.889 | 222.6 | 58 | 145.2463 | 2.5042 | 2.5042 | 0 | 0 | 145.2463 | 0 | 145.2463 | 52
| 10 | Labour | hr | L | 3 | 88.889 | 222.6 | 38 | 285.4841 | 7.5127 | 2.5042 | 285.4841 | 0 | 0 | 0 | 285.4841 | 52
| 11 | Bobcat | hr | P | 1 | 88.889 | 222.6 | 95 | 237.9035 | 2.5042 | 2.5042 | 0 | 0 | 237.9035 | 0 | 237.9035 | 52
210 | PV09 | Stabilise Sub-Grade | m² |  |  |  | 1 |  | 43119.1214 |  | 7.78 | 10643.04 | 332 | 32144.0814 | 0 | 43119.1214
211 | PV09.a | Supply GB Cement Stabilising Agent | tonne |  |  |  | 36 |  | 332 |  |  | 0 | 332 | 0 | 0 | 332
| 1 | Supply GB Cement Stabilising Agent
211.1 | 2 | Cement | tonne | M | 1 | 1 | 1 | 332 | 332 |  |  | 0 | 332 | 0 | 0 | 332 | CSA
212 | PV09.b | In-situ Stabilising Sub-grade | m² |  |  |  | 3890 |  | 42787.1214 |  | 7.78 | 10643.04 | 0 | 32144.0814 | 0 | 42787.1214
| 6 | Stabilising Sub-Grade
212.1 | 7 | CAT297 Stabiliser | hr | P | 1 | 55.5556 | 3890 | 66.07 | 4626.2214 | 70.02 | 70.02 | 0 | 0 | 4626.2214 | 0 | 4626.2214 | 68
| 7 | Grader | hr | P | 1 | 55.5556 | 3890 | 145 | 10152.9 | 70.02 | 70.02 | 0 | 0 | 10152.9 | 0 | 10152.9 | 68
| 8 | Water Cart - Hire | hr | P | 1 | 55.5556 | 3890 | 95 | 6651.9 | 70.02 | 70.02 | 0 | 0 | 6651.9 | 0 | 6651.9 | 68
| 9 | PF Roller Wet - No OP | hr | P | 1 | 55.5556 | 3890 | 58 | 4061.16 | 70.02 | 70.02 | 0 | 0 | 4061.16 | 0 | 4061.16 | 68
| 10 | Labour | hr | L | 4 | 55.5556 | 3890 | 38 | 10643.04 | 280.08 | 70.02 | 10643.04 | 0 | 0 | 0 | 10643.04 | 68
| 11 | Bobcat | hr | P | 1 | 55.5556 | 3890 | 95 | 6651.9 | 70.02 | 70.02 | 0 | 0 | 6651.9 | 0 | 6651.9 | 68
213 | PV10 | Supply & Install Visi-ball Tank Level Indicator | item |  |  |  | 1 |  | 700 |  | 1 | 0 | 0 | 0 | 700 | 700
| 1 | Sewer Subbie | LS | S | 700 | 1 | 1 | 1 | 700 |  | 1 | 0 | 0 | 0 | 700 | 700 | 95
214 | PV11 | Centre Median Footpath Beam Thickening | m³ |  |  |  | 1 |  | 2275.2128 |  | 1.5467 | 11.1466 | 916.7997 | 13.9332 | 1333.3333 | 2275.2128
215 | PV11.a | Excavate for, Supply, Place and Finish Additional N25 Concrete | m³ |  |  |  | 8 |  | 1497.6277 |  | 1.0667 | 11.1466 | 139.2146 | 13.9332 | 1333.3333 | 1497.6277
| 1 | Material Supply
| 2 | N25 | m³ | M | 1 | 1 | 0.87999 | 158.2 | 139.2146 |  |  | 0 | 139.2146 | 0 | 0 | 139.2146 | C25
| 6 | Place Sand
215.1 | 7 | Bobcat | hr | P | 1 | 6 | 0.87999 | 95 | 13.9332 | 0.14667 | 0.14667 | 0 | 0 | 13.9332 | 0 | 13.9332 | 73
| 8 | Labour | hr | L | 2 | 6 | 0.87999 | 38 | 11.1466 | 0.29333 | 0.14667 | 11.1466 | 0 | 0 | 0 | 11.1466 | 73
Form & Supply
| 10 | Concrete Subbie | m² | S | 1 | 1 | 53.3333 | 25 | 1333.3333 |  | 53.3333 | 0 | 0 | 0 | 1333.3333 | 1333.3333 | 73
216 | PV11.b | Supply, cut, tie and place SL72 Reinforcing Mesh | m² |  |  |  | 80 |  | 777.5851 |  | 0.48 | 0 | 777.5851 | 0 | 0 | 777.5851
| 1 | Material Supply
| 3 | SL72 | m² | M | 1 | 1 | 96 | 5.76 | 552.96 |  |  | 0 | 552.96 | 0 | 0 | 552.96 | RSM
| 4 | Sand | tonne | M | 1 | 1 | 8.7999 | 17.95 | 157.9584 |  |  | 0 | 157.9584 | 0 | 0 | 157.9584 | QMS
| 5 | Dowels | each | M | 1 | 1 | 33.3333 | 2 | 66.6667 |  |  | 0 | 66.6667 | 0 | 0 | 66.6667 | RSM
217 | PV12 | Install 150mm & 225mm Roof water drainage lines from terminal building, including road crossings and stubs to existing stormwater pits | item |  |  |  | 1 |  | 6250 |  | 3 | 0 | 0 | 0 | 6250 | 6250
| 1 | Sewer Subbie | LS | S | 6250 | 1 | 1 | 1 | 6250 |  | 1 | 0 | 0 | 0 | 6250 | 6250 | 95
218 | PV13 | Installation of STP Irrigation System |  |  |  |  | 1
219 | PV13.a | Installation only of Pump No. 01 & Pump Well | item |  |  |  | 1 |  | 3850 |  | 25 | 0 | 0 | 0 | 3850 | 3850
| 1 | Sewer Subbie | LS | S | 3850 | 1 | 1 | 1 | 3850 |  | 1 | 0 | 0 | 0 | 3850 | 3850 | 95
220 | PV13.b | Supply & Install Pump & Well No. 02 | item |  |  |  | 1 |  | 17000 |  | 25 | 0 | 0 | 0 | 17000 | 17000
| 1 | Sewer Subbie | LS | S | 17000 | 1 | 1 | 1 | 17000 |  | 1 | 0 | 0 | 0 | 17000 | 17000 | 95
221 | PV13.c | Supply & Installation of Electrical as Per E002 & Clarification Letter | item |  |  |  | 1 |  | 33700 |  | 25 | 0 | 0 | 0 | 33700 | 33700
| 1 | Electrical Subbie | each | S | 33700 | 1 | 1 | 1 | 33700 |  | 1 | 0 | 0 | 0 | 33700 | 33700 | 113
222 | PV13.d | Raise STP pad height 500mm and provide 100mm reinforced concrete slab | item |  |  |  | 1 |  | 3800 |  | 1 | 0 | 0 | 0 | 3800 | 3800
| 1 | Sewer Subbie | LS | S | 3800 | 1 | 1 | 1 | 3800 |  | 1 | 0 | 0 | 0 | 3800 | 3800 | 95
223 | PV13.e | Supply & Install light to roof of container | item |  |  |  | 1 |  | 700 |  | 1 | 0 | 0 | 0 | 700 | 700
| 1 | Electrical Subbie | each | S | 700 | 1 | 1 | 1 | 700 |  | 1 | 0 | 0 | 0 | 700 | 700 | 113
224 | PV13.f | Supply & Installation of rising main from Pump well No. 02 to irrigation area as per H101 in existing cleared areas | item |  |  |  | 1 |  | 39000 |  | 5 | 0 | 0 | 0 | 39000 | 39000
| 1 | Sewer Subbie | LS | S | 39000 | 1 | 1 | 1 | 39000 |  | 1 | 0 | 0 | 0 | 39000 | 39000 | 95
225 | PV13.g | Supply & installation of irrigation area (3,000 sqm) as per H103 including air & flush valves | item |  |  |  | 1 |  | 39600 |  | 5 | 0 | 0 | 0 | 39600 | 39600
| 1 | Sewer Subbie | LS | S | 39600 | 1 | 1 | 1 | 39600 |  | 1 | 0 | 0 | 0 | 39600 | 39600 | 95
226 | PV13.h | Supply & installation of signal cable as per clarification email | item |  |  |  | 1 |  | 12600 |  | 3 | 0 | 0 | 0 | 12600 | 12600
| 1 | Electrical Subbie | each | S | 12600 | 1 | 1 | 1 | 12600 |  | 1 | 0 | 0 | 0 | 12600 | 12600 | 113
227 | PV14 | Installation of Edge Restraint | m |  |  |  | 105 |  | 4305.8639 |  | 1 | 0 | 2179.6139 | 0 | 2126.25 | 4305.8639
| 1 | S32 - Kerb Mix | m³ | M | 1 | 1 | 12.2107 | 178.5 | 2179.6139 |  |  | 0 | 2179.6139 | 0 | 0 | 2179.6139 | CKM
| 2 | Kerb Subbie | m | S | 1 | 1 | 105 | 20.25 | 2126.25 | 105 | 105 | 0 | 0 | 0 | 2126.25 | 2126.25 | 71
228 | PV15 | Fie Lay Away | item |  |  |  | 1 |  | 5017.9083 |  | 3.3727 | 250.6657 | 2769.9402 | 1086.0523 | 911.25 | 5017.9083
229 | PV15.a | Cut To Spoil | m³ |  |  |  | 36 |  | 513.6 |  | 0.13333 | 45.6 | 0 | 468 | 0 | 513.6
229.1 | 1 | Excavator - 25T | hr | P | 1 | 30 | 36 | 135 | 162 | 1.2 | 1.2 | 0 | 0 | 162 | 0 | 162 | 53
| 2 | Tipper | hr | P | 3 | 30 | 36 | 85 | 306 | 3.6 | 1.2 | 0 | 0 | 306 | 0 | 306 | 53
| 4 | Labour | hr | L | 1 | 30 | 36 | 38 | 45.6 | 1.2 | 1.2 | 45.6 | 0 | 0 | 0 | 45.6 | 53
230 | PV15.b | Prepare & Trim Sub-grade | m² |  |  |  | 160 |  | 393.9556 |  | 0.11852 | 81.0667 | 0 | 312.8889 | 0 | 393.9556
230.1 | 1 | Grader | hr | P | 1 | 150 | 160 | 145 | 154.6667 | 1.0667 | 1.0667 | 0 | 0 | 154.6667 | 0 | 154.6667 | 61
| 2 | MW Roller | day | P | 1 | 1350 | 160 | 480 | 56.8889 | 0.11852 | 0.11852 | 0 | 0 | 56.8889 | 0 | 56.8889 | 61
| 3 | Water Cart - Hire | hr | P | 1 | 150 | 160 | 95 | 101.3333 | 1.0667 | 1.0667 | 0 | 0 | 101.3333 | 0 | 101.3333 | 61
| 4 | Labour | hr | L | 2 | 150 | 160 | 38 | 81.0667 | 2.1333 | 1.0667 | 81.0667 | 0 | 0 | 0 | 81.0667 | 61
231 | PV15.c | Edge Restraint | m |  |  |  | 45 |  | 1845.3702 |  | 1 | 0 | 934.1202 | 0 | 911.25 | 1845.3702
| 1 | S32 - Kerb Mix | m³ | M | 1 | 1 | 5.2332 | 178.5 | 934.1202 |  |  | 0 | 934.1202 | 0 | 0 | 934.1202 | CKM
| 2 | Kerb Subbie | m | S | 1 | 1 | 45 | 20.25 | 911.25 | 45 | 45 | 0 | 0 | 0 | 911.25 | 911.25 | 71
232 | PV15.d | Supply & Place 2.1 Gravel | m³ |  |  |  | 36 |  | 2264.9825 |  | 0.12086 | 123.9991 | 1835.82 | 305.1634 | 0 | 2264.9825
| 1 | CBR80 | tonne | M | 1 | 1 | 84.6 | 21.7 | 1835.82 |  |  | 0 | 1835.82 | 0 | 0 | 1835.82 | QM2.1
232.1 | 2 | Grader | hr | P | 1 | 77.778 | 84.6 | 145 | 157.7181 | 1.0877 | 1.0877 | 0 | 0 | 157.7181 | 0 | 157.7181 | 62
| 3 | Water Cart - Hire | hr | P | 1 | 77.778 | 84.6 | 95 | 103.3326 | 1.0877 | 1.0877 | 0 | 0 | 103.3326 | 0 | 103.3326 | 62
| 4 | SD Roller | day | P | 1 | 700.002 | 84.6 | 365 | 44.1127 | 0.12086 | 0.12086 | 0 | 0 | 44.1127 | 0 | 44.1127 | 62
| 5 | Labour | hr | L | 3 | 77.778 | 84.6 | 38 | 123.9991 | 3.2631 | 1.0877 | 123.9991 | 0 | 0 | 0 | 123.9991 | 62
233 | PV15.e | Primer Seal | m² |  |  |  | 160 |  | 718.4 |  | 1 | 0 | 0 | 0 | 718.4 | 718.4
| 1 | Primer Seal | m² | S | 1 | 1 | 160 | 4.49 | 718.4 |  | 1 | 0 | 0 | 0 | 718.4 | 718.4 | 64
234 | PV15.f | DG10 Asphalt (40mm) | tonne |  |  |  | 16 |  | 4592 |  | 1 | 0 | 0 | 0 | 4592 | 4592
| 1 | DG10 | tonne | S | 1 | 1 | 16 | 287 | 4592 |  | 1 | 0 | 0 | 0 | 4592 | 4592 | 65
235 | PV16 | Bin Area | item |  |  |  | 1 |  |  |  | 3.1789
236 | PV16.a | General Fill | m³ |  |  |  | 76 |  | 1026.2841 |  | 0.095 | 97.4699 | 0 | 928.8142 | 0 | 1026.2841
| 1 | Win Material From Local Pit
236.1 | 2 | D6 | hr | P | 1 | 133.333 | 76 | 185 | 105.4503 | 0.57 | 0.57 | 0 | 0 | 105.4503 | 0 | 105.4503 | 52
| 3 | Load & Cart
236.2 | 4 | Excavator - 25T | hr | P | 1 | 88.889 | 76 | 135 | 115.4249 | 0.855 | 0.855 | 0 | 0 | 115.4249 | 0 | 115.4249 | 52
| 5 | Truck & Dog | hr | P | 3 | 88.889 | 76 | 145 | 371.9245 | 2.565 | 0.855 | 0 | 0 | 371.9245 | 0 | 371.9245 | 52
| 6 | Place & Compact
| 7 | Grader | hr | P | 1 | 88.889 | 76 | 145 | 123.9748 | 0.855 | 0.855 | 0 | 0 | 123.9748 | 0 | 123.9748 | 52
| 8 | Water Cart - Hire | hr | P | 1 | 88.889 | 76 | 95 | 81.2249 | 0.855 | 0.855 | 0 | 0 | 81.2249 | 0 | 81.2249 | 52
| 9 | PF Roller Wet - No OP | hr | P | 1 | 88.889 | 76 | 58 | 49.5899 | 0.855 | 0.855 | 0 | 0 | 49.5899 | 0 | 49.5899 | 52
| 10 | Labour | hr | L | 3 | 88.889 | 76 | 38 | 97.4699 | 2.565 | 0.855 | 97.4699 | 0 | 0 | 0 | 97.4699 | 52
| 11 | Bobcat | hr | P | 1 | 88.889 | 76 | 95 | 81.2249 | 0.855 | 0.855 | 0 | 0 | 81.2249 | 0 | 81.2249 | 52
237 | PV16.b | Supply & Place Type 2.1 Gravel | m³ |  |  |  | 25 |  | 1572.9045 |  | 0.083928 | 86.1105 | 1274.875 | 211.919 | 0 | 1572.9045
| 1 | CBR80 | tonne | M | 1 | 1 | 58.75 | 21.7 | 1274.875 |  |  | 0 | 1274.875 | 0 | 0 | 1274.875 | QM2.1
237.1 | 2 | Grader | hr | P | 1 | 77.778 | 58.75 | 145 | 109.5265 | 0.75535 | 0.75535 | 0 | 0 | 109.5265 | 0 | 109.5265 | 62
| 3 | Water Cart - Hire | hr | P | 1 | 77.778 | 58.75 | 95 | 71.7587 | 0.75535 | 0.75535 | 0 | 0 | 71.7587 | 0 | 71.7587 | 62
| 4 | SD Roller | day | P | 1 | 700.002 | 58.75 | 365 | 30.6338 | 0.083928 | 0.083928 | 0 | 0 | 30.6338 | 0 | 30.6338 | 62
| 5 | Labour | hr | L | 3 | 77.778 | 58.75 | 38 | 86.1105 | 2.2661 | 0.75535 | 86.1105 | 0 | 0 | 0 | 86.1105 | 62
238 | PV16.c | Colourbonfd Fence (1800 High - 20m) | item |  |  |  | 1 |  | 2323 |  | 3 |  |  |  |  | 2323
| 1 | Fencing Subbie | LS | S | 2323 | 1 | 1 | 1 | 2323 |  | 1 | 0 | 0 | 0 | 2323 | 2323 | 131
239 | PV17 | Additional Edge Restraint | m |  |  |  | 71 |  | 2911.5842 |  | 1 | 0 | 1473.8342 | 0 | 1437.75 | 2911.5842
| 1 | S32 - Kerb Mix | m³ | M | 1 | 1 | 8.2568 | 178.5 | 1473.8342 |  |  | 0 | 1473.8342 | 0 | 0 | 1473.8342 | CKM
| 2 | Kerb Subbie | m | S | 1 | 1 | 71 | 20.25 | 1437.75 | 71 | 71 | 0 | 0 | 0 | 1437.75 | 1437.75 | 71
240 | PV18 | Supply & Install Additional Electrical Pit | each |  |  |  | 1 |  | 1210 |  | 1 | 0 | 0 | 0 | 1210 | 1210
| 1 | Electrical Subbie | each | S | 1210 | 1 | 1 | 1 | 1210 |  | 1 | 0 | 0 | 0 | 1210 | 1210 | 111
241 | PV19 | Extra Over Log Barrier Fenec - Monowills Pedestrian Safety Fence | m |  |  |  | 58 |  | 2146 |  | 0 | 0 | 0 | 0 | 2146 | 2146
| 1 | Fencing Subbie | LS | S | 37 | 1 | 58 | 1 | 2146 |  | 1 | 0 | 0 | 0 | 2146 | 2146 | 131
242 | PV20 | Additional AC | tonne |  |  |  | 70.7 |  | 20290.9 |  | 1 | 0 | 0 | 0 | 20290.9 | 20290.9
| 1 | DG10 | tonne | S | 1 | 1 | 70.7 | 287 | 20290.9 |  | 1 | 0 | 0 | 0 | 20290.9 | 20290.9 | 65
243 | PV21 | Miscellaneous Additional Works | item |  |  |  | 1 |  | 22691.1516 |  | 3 | 2407.85 | 2472.4316 | 1445 | 16365.87 | 22691.1516
Additional Kerb - 95m
| 1 | S32 - Kerb Mix | m³ | M | 1 | 1 | 11.0478 | 178.5 | 1972.0316 |  |  | 0 | 1972.0316 | 0 | 0 | 1972.0316 | CKM
| 2 | Kerb Subbie | m | S | 1 | 1 | 95 | 20.25 | 1923.75 | 95 | 95 | 0 | 0 | 0 | 1923.75 | 1923.75 | 71
Additional Line Marking (Lump Sum)
| 1 | Line Marking | m² | S | 0.432 | 1 | 1 | 7660 | 3309.12 |  | 1 | 0 | 0 | 0 | 3309.12 | 3309.12 | 66
Additional Fencing (Lump Sum)
| 1 | Fencing Subbie | LS | S | 4507 | 1 | 1 | 1 | 4507 |  | 1 | 0 | 0 | 0 | 4507 | 4507 | 131
Additional Work at STP
| 1 | Sewer Subbie | LS | S | 6026 | 1 | 1 | 1 | 6026 |  | 1 | 0 | 0 | 0 | 6026 | 6026 | 95
Additional Rag Bolt
| 1 | Materials
| 2 | Rag Bolt | each | M | 1 | 1 | 1 | 375 | 375 |  |  | 0 | 375 | 0 | 0 | 375 | 111
| 3 | N32 | m³ | M | 1 | 1 | 0.75 | 167.2 | 125.4 |  |  | 0 | 125.4 | 0 | 0 | 125.4 | 111
| 6 | Installation of Footing Cages
| 7 | Backhoe | hr | P | 1 | 0.5 | 1 | 100 | 200 | 2 | 2 | 0 | 0 | 200 | 0 | 200 | 111
| 8 | Labour | hr | L | 2 | 0.5 | 1 | 38 | 152 | 4 | 2 | 152 | 0 | 0 | 0 | 152 | 111
| 9 | Installation of Poles & Lights
| 10 | Electrician | Item | S | 10 | 1 | 1 | 60 | 600 |  | 1 | 0 | 0 | 0 | 600 | 600 | 111
| 11 | Crane - 30Ton | hr | P | 3 | 1 | 1 | 165 | 495 | 3 | 1 | 0 | 0 | 495 | 0 | 495 | 111
| 12 | Labour | hr | L | 2 | 0.5 | 1 | 38 | 152 | 4 | 2 | 152 | 0 | 0 | 0 | 152 | 111
| 13 | EWP | day | P | 1 | 1 | 1 | 750 | 750 | 1 | 1 | 0 | 0 | 750 | 0 | 750 | 111
Additional Engineering
| 1 | Project Engineer | week | L |  | 1 | 0.167 | 3250 | 542.75 |  | 0.167 | 542.75 | 0 | 0 | 0 | 542.75 | 901
Additional Supervision
| 1 | Project Supervisor | week | L |  | 1 | 0.466 | 3350 | 1561.1 |  | 0.466 | 1561.1 | 0 | 0 | 0 | 1561.1 | 902
425618.79

## Resources
| Resource Name | Description | Type | Unit | Currency | Base Rate
LABOUR RESOURCES | Concretor | Concretor | L | hr | AUD | 50
| Concretor - Labour |  | L | hr | AUD | 85
| Engineer / CQR |  | L | hr | AUD | 135
| Foreman - Hourly |  | L | hr | AUD | 125
| Labour | Labour | L | hr | AUD | 38
| Labour - RATE ONLY |  | L | hr | AUD | 58
| Operator | Plant Operator | L |  | AUD | 48
| PM |  | L | hr | AUD | 145
| Pipe Layer | Pipe Layer | L | hr | AUD | 65
| Pipelayer |  | L | hr | AUD | 75
| Project Engineer | Project Engineer - Weekly Rate | L | week | AUD | 3250
| Project Manager | Weekly Rate - Project Manager | L | week | AUD | 4250
| Project Supervisor | Project Supervisor | L | week | AUD | 3350
| Surveyor | Survey Team | L | hr | AUD | 185
| Traffic Controller | Traffic Controller with Vehicle | L | hr | AUD | 38
| WHSO | Work Place Health & Safety Officer | L | week | AUD | 3200
MATERIAL RESOURCES | 100 Bend - 11.25 deg |  | M | each | AUD | 58
| 100 Bend - 22.5 deg |  | M | each | AUD | 58
| 100 Bend - 45 deg |  | M | each | AUD | 58
| 100 Comms Bend Cl9 584R | 100 diameter Comms Bend | M | each | AUD | 25
| 100 Communication Conduit | 6m 100 dia communications conduit | M | m | AUD | 5.16
| 100 End Cap |  | M | each | AUD | 39
| 100 Gasket Set |  | M | each | AUD | 18.5
| 100 LD uPVC Electrical |  | M | m | AUD | 4.45
| 100 SV So-So |  | M | each | AUD | 248
| 100 x 100 Tee |  | M | each | AUD | 108.88
| 1050 Manhole per metre | 1050 pre-cast man hole rings (sewer / storm water) | M | m | AUD | 434.16
| 1050 Reducer Slab | 1050 Reducer Slab for 1050 Manhole | M | each | AUD | 218.86
| 1050 Surround & Lid | 1050 Concrete Surround with CI Class D Lid | M | each | AUD | 696
| 1200 RCP FJ CL2 |  | M | m | AUD | 429.14
| 125 LD uPVC Electrical |  | M | m | AUD | 8
| 150 Bend - 11.25 deg |  | M | each | AUD | 89
| 150 Bend - 22.5 deg |  | M | each | AUD | 89
| 150 Bend - 45 deg |  | M | each | AUD | 89
| 150 Bend - 90 deg |  | M | each | AUD | 122
| 150 End Cap |  | M | each | AUD | 51
| 150 Gasket Set |  | M | m | AUD | 34
| 150 SN8 Sewer Pipe |  | M | m | AUD | 25
| 150 SV So-So |  | M | each | AUD | 420
| 150 Vari-Gib |  | M | each | AUD | 112
| 150 Water Meter - Helix |  | M | each | AUD | 1449.3
| 150 x 100 Tee |  | M | each | AUD | 257.32
| 150 x 150 Tee |  | M | each | AUD | 318.8
| 2.4 Lintel Complete | 2.4m Pre-cats Lintel with IPWEAQ grate. | M | Item | AUD | 1484
| 20mm Drainage Agg |  | M | ton | AUD | 33.5
| 300 RCP |  | M | m | AUD | 55
| 300 RCP FJ CL3 |  | M | m | AUD | 48.72
| 375 RCP |  | M | m | AUD | 58.55
| 375 RCP FJ CL3 |  | M | m | AUD | 71.92
| 375 Sloping Headwall |  | M | each | AUD | 609.68
| 40 HD 90 Degree Bend 304R |  | M | each | AUD | 3.91
| 40 HD uPVC Electrical |  | M | m | AUD | 2.04
| 40mm Drainage Agg |  | M | ton | AUD | 27.5
| 450 RCP FJ CL2 |  | M | m | AUD | 76.93
| 450 RCP FJ CL4 |  | M | m | AUD | 115.06
| 50 HD uPVC Electrical |  | M | m | AUD | 3
| 50 uPVC Communications |  | M | m | AUD | 2.32
| 525 RCP FJ CL2 |  | M | m | AUD | 105.79
| 63 HD VX Electrical |  | M | m | AUD | 3.85
| 675 RCP FJ CL3 |  | M | m | AUD | 203.21
| 750 HW |  | M | each | AUD | 873.47
| 750 RCP |  | M | m | AUD | 305.54
| 80 uPVC Communications |  | M | m | AUD | 4.62
| 900 RCP FJ CL2 |  | M | m | AUD | 259.81
| A24 | A24 - Bidum | M | m² | AUD | 1.03
| A34 |  | M | m² | AUD | 2.5
| A64 | A64 Bidum | M | m² | AUD | 2.49
| Abel Flex |  | M | m | AUD | 3
| Bar Chairs |  | M | each | AUD | 0.8
| Bollard - Plain |  | M | each | AUD | 250
| Bolts |  | M | each | AUD | 7.5
| Bro Pit - 1C1T | Bro Pit 1 Chamber, 1 Trough | M | each | AUD | 1346.26
| Bro Pit - 1C2T | Bro Pit - 1 Chamber, 2 Trough | M | each | AUD | 1709.44
| CBR15 | CBR15 Road Base | M | tonne | AUD | 33.63
| CBR45 | CBR45 Road Base | M | tonne | AUD | 20.95
| CBR80 | CBR80 Road Base - Delivered | M | tonne | AUD | 21.7
| Cast Iron Lid & Surround | Cast Iron Lid (Class D) & Surround for Man Holes | M | each | AUD | 419.97
| Cement | Bulk GP / GB Cement | M | tonne | AUD | 332
| Cement - 2 Tonne Bag | Cement Powder - 2 Tonne Bag | M | tonne | AUD | 240
| Cement - GP Bulk |  | M | tonne | AUD | 293
| Cold Mix AC |  | M | tonne | AUD | 180
| Comms Pit - J8 | Communications Pit with steel lid | M | each | AUD | 1026.55
| Crusher Dust - Delivered |  | M | tonne | AUD | 21.8
| DN100 uPVC PN18 |  | M | m | AUD | 13.67
| DN100 uPVC SN10 |  | M | m | AUD | 4.35
| DN100 uPVC SN8 |  | M | m | AUD | 9.09
| DN150 uPVC PN16 |  | M | m | AUD | 19.17
| DN150 uPVC PN18 |  | M | m | AUD | 26.67
| DN150 uPVC SN8 |  | M | m | AUD | 9.09
| DN25 PE100 PN12.5 | 50m Roll | M | Item | AUD | 30
| DN32 PE100 PN12.5 | 50m Roll | M | m | AUD | 50
| DN40 PE100 ON12.5 | 50m Roll | M | Item | AUD | 71.74
| DN50 PE100 PN12.5 | 50m Roll | M | Item | AUD | 120.5
| DN63 PE100 PN12.5 | 50m roll | M | Item | AUD | 184.29
| DN63 PE80B SDR11 (Gas) | 110m Roll | M | Item | AUD | 518.45
| DN90 PE100 PN12.5 | 90 PE - 100m roll | M | Item | AUD | 633.14
| Daneley Joints |  | M | each | AUD | 65
| Delineation |  | M | Item | AUD | 12000
| Denso Tape | Denso Tape | M | m | AUD | 5
| Dowels |  | M | each | AUD | 2
| Drainage Agg | Drainage Aggregate | M | tonne | AUD | 37.5
| Draw Rope - Conduits |  | M | m | AUD | 0.11
| Electrical Pit - Precast |  | M | each | AUD | 1800
| Electrical Pit - Type 66 | Electrical Pit with Steel Lid | M | each | AUD | 737.8
| Ferrule & Bonnet - 25mm |  | M | each | AUD | 73.97
| Ferrule & Bonnet - 40mm |  | M | each | AUD | 164.31
| Ferrule & Bonnet - 50mm |  | M | each | AUD | 220.46
| Fire Booster Assembly |  | M | each | AUD | 3640.84
| Fire Booster Cabinet |  | M | each | AUD | 1597.57
| Form Boards |  | M | m | AUD | 5
| Form Ply |  | M | m² | AUD | 10
| GCL |  | M | m² | AUD | 7.2
| Gabion Rock | Gabion Rock (150 - 300) | M | tonne | AUD | 41
| Gates |  | M | each | AUD | 900
| General Fill | General Fill | M | tonne | AUD | 13.97
| General Fill (CBR15) | CBR 15 General Fill | M | tonne | AUD | 13.97
| Grate & Frame |  | M | each | AUD | 1000
| Guide Post |  | M | each | AUD | 50
| HW - 1200 x 450 RCBC |  | M | each | AUD | 2342.34
| HW - 1800 x 600 RCBC |  | M | Item | AUD | 1918.8
| HW - 2400 x 900 RCBC |  | M | each | AUD | 5347.16
| HW - 3/1200 x 300 RCBC |  | M | each | AUD | 2484.3
| HW - 300 |  | M | each | AUD | 320
| HW - 375 | Head Wall 375 RCP | M | each | AUD | 273
| HW - 450 |  | M | each | AUD | 416
| HW - 450 Sloping |  | M | each | AUD | 1088.36
| HW - 600 x 375 RCBC |  | M | each | AUD | 804.44
| HW - 675 |  | M | each | AUD | 396.31
| HW - 750 x 450 RCBC |  | M | each | AUD | 946.4
| HW 1200 x 600 RCBC |  | M | each | AUD | 2277.6
| Hard Cover - Electrical |  | M | m | AUD | 2.7
| Hay Bale |  | M | each | AUD | 20
| Hazard Board |  | M | each | AUD | 750
| Hose Cock |  | M | each | AUD | 75
| Hydrant Riser |  | M | each | AUD | 230
| Hydrant Riser - 100 Dual |  | M | each | AUD | 614.3
| Hydrant Riser 150 Dual |  | M | each | AUD | 1046.6
| Kerb Adaptors |  | M | each | AUD | 75
| Light Pole - 10.5m | Light POle 10.5m 1200 cross arm | M | each | AUD | 1391
| Luminaires | Luminaires to suit | M | each | AUD | 330
| MDPE Junctions |  | M | each | AUD | 391.4
| Marker Post |  | M | each | AUD | 35
| N20 | N20 Concrete | M |  | AUD | 180
| N25 | N25 Concrete | M | m³ | AUD | 158.2
| N32 | N32 Concrete | M | m³ | AUD | 167.2
| PN10 : 200 DiaPE100 | DN200 - PE100 MDPE Pipe | M | m | AUD | 22.9
| Palings |  | M | each | AUD | 3.5
| Pickets | Star Pickets | M | each | AUD | 6
| Pugmill |  | M | tonne | AUD | 2.5
| RCBC - 1200 x 300 |  | M | m | AUD | 250
| RCBC - 1200 x 450 |  | M | m | AUD | 287.72
| RCBC - 1200 x 600 |  | M | m | AUD | 311.3
| RCBC - 1800 x 600 |  | M | m | AUD | 835.5
| RCBC - 2100 x 600 |  | M | m | AUD | 1008
| RCBC - 2400 x 900 |  | M | m | AUD | 1176.34
| RCBC - 3600 x 900 | RCBC Crown Unit - 3600 x 900 | M | each | AUD | 1755.6
| RCBC - 750 x 450 |  | M | m | AUD | 159.43
| RCBC 600 x 375 |  | M | m | AUD | 152.82
| RCBC Base Slab 1800 x 600 |  | M | m | AUD | 546
| RCBC Base Slab 2100 x 600 |  | M | m | AUD | 698
| Rag Bolt |  | M | each | AUD | 375
| Rag Bolt - Small |  | M | each | AUD | 300
| Reinforcing Steel |  | M | tonne | AUD | 2200
| S32 - Exposed Aggregate |  | M | m³ | AUD | 260
| S32 - Kerb Mix | S32 - Kerb Mix | M | m³ | AUD | 178.5
| SL72 | SL72 - Reinforcing Mesh | M | m² | AUD | 5.76
| SL82 | SL82 Reinforcing Mesh | M | m² | AUD | 7.5
| Sand | Bedding Sand | M | tonne | AUD | 17.95
| Sand Bags |  | M | each | AUD | 1
| Signs - General | General signs & delineation for traffic control. | M | Item | AUD | 1
| Signs Complete |  | M | each | AUD | 140
| Silt Fence | Silt Fence | M | m | AUD | 2
| Single Check Detector |  | M | each | AUD | 3630.96
| Small Signs |  | M | each | AUD | 350
| Small Tools |  | M | Item | AUD | 1
| Stabilised Sand | Stabilised Sand | M | m³ | AUD | 258.5
| Sub Soil Drain |  | M | m | AUD | 2.08
| Tack Coat |  | M | m² | AUD | 1.5
| Tapping Band - 100 x 25 |  | M | each | AUD | 36.3
| Tapping Band - 100 x 50 |  | M | each | AUD | 57.62
| Tapping Band 100 x 40 |  | M | each | AUD | 57.62
| Type 5 Elec Pit |  | M | each | AUD | 625
| Type 7 Elec Pit |  | M | each | AUD | 780
| Type A Sewer Junction |  | M | each | AUD | 110
| Valve Box & Surround |  | M | each | AUD | 150
| Warning Tape | Warning Tape - Detectable (200m Roll) | M | m | AUD | 0.33
| Water Charge | Water Rate per kL. | M | kL | AUD | 2.45
| Water Meter Interface |  | M | each | AUD | 378.47
| Wheel Stops | Pre-cast wheel stops | M | each | AUD | 68.83
| Wheelstops | Wheel Stop with 2 x Galv pins | M | each | AUD | 85
| Y12 | Y12 - Reinforcing Bar | M | m | AUD | 1.87
PLANT RESOURCES | A25 |  | P | hr | AUD | 185
| Back Hoe | Backhoe - Wet Hire | P | hr | AUD | 110
| Backhoe |  | P | hr | AUD | 100
| Bobcat | Bobcat - Wet Hire | P | hr | AUD | 95
| Bobcat - RATE ONLY |  | P | hr | AUD | 115
| Bomag 124DH | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | P | hr | AUD | 26.46
| Bomag 124DH (Stand Down) | Stand Down SD Roller | P | hr | AUD | 10.75
| CAT297 | CAT297C MTL - No Operator | P | hr | AUD | 46.5
| CAT297 Stabiliser | CAT297 Stabiliser - No operator | P | hr | AUD | 66.07
| CAT311 | CAT311D - 12T Excavator (No Operator) | P | hr | AUD | 48
| Container |  | P | week | AUD | 40
| Crane - 30Ton |  | P | hr | AUD | 165
| Crane Truck |  | P | day | AUD | 360
| Crib Facilities | Site Office & Tiolet, 1 Pump out during project. | P | week | AUD | 1121
| D6 | D6 Dozer | P | hr | AUD | 185
| Dual Grade Laser |  | P | week | AUD | 277
| EWP |  | P | day | AUD | 750
| Excavator - 15T | 15T Excavator - Wet Hire | P | hr | AUD | 115
| Excavator - 25T | 25T Excavator - Wet Hire | P | hr | AUD | 135
| Excavator - 30T | 30T Excavator - Wet Hire | P | hr | AUD | 135
| Excavator - 8T | 8T Excavator - Wet Hire | P | hr | AUD | 100
| Excavator 25T - RATE ONLY |  | P | hr | AUD | 162.5
| Excavator < 24 RATE ONLY |  | P | hr | AUD | 143.75
| FAE Mixer | FAE Mixer with Tractor | P | day | AUD | 2800
| Float |  | P | LS | AUD | 1
| Ford Utility | Ford Ranger 4WD Utility | P | hr | AUD | 11.67
| Generator |  | P | week | AUD | 350
| Grader | Grader - Wet Hire | P | hr | AUD | 145
| Grader - RATE ONLY |  | P | hr | AUD | 168.75
| Hammer | Rock Hammer | P | hr | AUD | 275
| MW Roller | Multi Wheel Roller - Day rate including fuel | P | day | AUD | 480
| Manhole Forms (1050) | Manhole Formwork Hire | P | day | AUD | 75
| NH Grader | New Holland Compact Grader - No Operator | P | hr | AUD | 25.78
| PF Roller | Pad Foot Roller - Dry | P | day | AUD | 365
| PF Roller Wet - No OP |  | P | hr | AUD | 58
| Plant Float - Allciv |  | P | hr | AUD | 7
| Plate Compactor | Plate Compactor - Dry Hire | P | hr | AUD | 3.5
| Rock Breaker | Excavator - Wet Hire with Rock Breaker | P | hr | AUD | 195
| SD Roller | SD Roller - Dry | P | day | AUD | 365
| SD Roller - RATE ONLY |  | P | hr | AUD | 95
| SD Roller - Wet (No Op) | SD Roller Wet Hire - No Operator | P | hr | AUD | 55
| Scraper - RATE ONLY |  | P | hr | AUD | 406.25
| Shake-down | Shake-down grid complete | P | Item | AUD | 1000
| Spreader Truck - 30T | Spreader Truck - 30T | P | day | AUD | 1250
| T&D - RATE ONLY |  | P | hr | AUD | 181.25
| Tipper | Tipper (Wet Hire) | P | hr | AUD | 85
| Tipper - Allciv | Tipper - Allciv (No Driver) | P | hr | AUD | 42.79
| Toyota Utility | Toyota Landcruiser 100 Utility | P | hr | AUD | 17
| Trench Roller |  | P | hr | AUD | 15
| Truck & Dog | Truck & Dog - Wet Hire | P | hr | AUD | 145
| Truck - RATE ONLY |  | P | hr | AUD | 106.25
| UD Spreader | UD Spreader Truck - No Driver | P | hr | AUD | 21.61
| UD Spreader - Daily |  | P | day | AUD | 198
| Variable Message Board | Variable Message Board | P | day | AUD | 100
| WC - Allciv | Water Cart Allciv - No Operator | P | hr | AUD | 42.79
| Water Cart - Hire | Water Cart Hire | P | hr | AUD | 95
| Water Cart - RATE ONLY |  | P | hr | AUD | 118.75
SUBCONTRACT RESOURCES | 10mm Seal | 10mm Spary Seal | S | m² | AUD | 3.19
| 14mm Primerseal | 14mm Primerseal | S | m² | AUD | 6.78
| 16mm Primer Seal |  | S | m² | AUD | 20.35
| 7mm Primer Seal | 7mm Primer Seal | S | m² | AUD | 4.3
| AMC0 Prime |  | S | m² | AUD | 1.5
| Accommodation | Accommodation & 3 meals Rate | S | day | AUD | 125
| Bollards |  | S | each | AUD | 50
| Broons - Day One | Broons Impact Roller First day hire | S | day | AUD | 15400
| Broons - Day Two + | Broons Impact Roller - Daily hire after day one | S | day | AUD | 5240
| CAR | CAR Insurance | S | Item | AUD | 1
| CBR Test |  | S | each | AUD | 400
| CCTV |  | S | Item | AUD | 1
| Concrete Cylinders | Cylinders - Set of Three | S | each | AUD | 200
| Concrete Sub-contract | Concrete Sub-contractor (Slab on Ground) | S | m² | AUD | 35
| Concrete Subbie | Slab on Ground | S | m² | AUD | 25
| Conduit Subbie |  | S | LS | AUD | 1
| Council Fee |  | S | Item | AUD | 1
| Distribution Board |  | S | each | AUD | 10810
| Electrical Subbie |  | S | each | AUD | 1
| Electrician |  | S | Item | AUD | 60
| Fencing Subbie |  | S | LS | AUD | 1
| Field Density |  | S | each | AUD | 125
| Final Seal |  | S | m² | AUD | 2.91
| GPO |  | S | each | AUD | 3430
| Geotech Level One |  | S | hr | AUD | 14950
| Geotech Travel | Travel rate per km. | S | km | AUD | 2
| Grass Seeding |  | S | m² | AUD | 2.35
| Gravel Properties Testing |  | S | each | AUD | 390
| Grinder |  | S | day | AUD | 8500
| Guard Rail | Guard Rail Subbie, including bull nose | S | m | AUD | 320
| HDPE Liner |  | S | Item | AUD | 26553
| Hydromulch - Establish | Establish Hydromulch / seeding contractor | S | Item | AUD | 1
| Kerb Ramp Subbie | Place & Finish Kerb Ramp | S | each | AUD | 300
| Kerb Subbie |  | S | m | AUD | 20.25
| Lab Compaction |  | S | each | AUD | 120
| Light Cables |  | S | each | AUD | 3617
| Log Fence | Log Barrier Fence | S | m | AUD | 25.7
| Manhole Builder (1-2m) |  | S | LS | AUD | 1
| Manhole Builder (2-3m) |  | S | each | AUD | 5500
| Mulcher |  | S | Item | AUD | 6000
| PE Welder |  | S | each | AUD | 50
| PL | PL Insurance | S | Item | AUD | 6250
| PLSL |  | S | Item | AUD | 1
| Pavement Subbie |  | S | Item | AUD | 1
| Pavement Test |  | S | each | AUD | 180
| Pedestrian Safety Fence |  | S | m | AUD | 100
| Pit Builder | Contract Rate per pit | S | each | AUD | 3750
| Pit Builder - Modify | Modify Manholes | S | each | AUD | 2500
| Plumber |  | S | hr | AUD | 85
| Pot Holes R Us |  | S | tonne | AUD | 600
| Power |  | S | Item | AUD | 5000
| Pram Ramps |  | S | each | AUD | 700
| Primer Seal | Primer Seal - Subcontract Rate sqm | S | m² | AUD | 4.49
| Profiling Subbie |  | S | Item | AUD | 2100
| RPM Enviro | 2 x 25kL Sewer Tanks | S | Item | AUD | 73745
| Retention Costs |  | S | Item | AUD | 1
| SAMI Seal |  | S | m² | AUD | 7.81
| Safety Rails |  | S | m | AUD | 195
| Sand Replacements | Field Density via Sand Replacement Method | S | each | AUD | 145
| Seal Visit Eight |  | S | m² | AUD | 5.56
| Seal Visit Five |  | S | m² | AUD | 4.89
| Seal Visit Four |  | S | m² | AUD | 6.67
| Seal Visit One |  | S | m² | AUD | 5.99
| Seal Visit Seven |  | S | m² | AUD | 4.27
| Seal Visit Six |  | S | m² | AUD | 4.54
| Seal Visit Three |  | S | m² | AUD | 4.37
| Seal Visit Two |  | S | m² | AUD | 5.34
| Security Fence | Security Fence - Three Strand Barb & Crank | S | m | AUD | 66
| Service Locator |  | S | hr | AUD | 200
| Sewer Subbie |  | S | LS | AUD | 1
| Soil Tests |  | S | Item | AUD | 1650
| Steel Fixing |  | S | tonne | AUD | 2200
| Stone Pitching |  | S | m² | AUD | 75
| Sub Soil Clean Out - Inst |  | S | each | AUD | 143.68
| Survey - Boundary Pegs |  | S | each | AUD | 45
| Temporary Fencing |  | S | m | AUD | 16
| Tip Fees | Tip fees per ton of waste | S | tonne | AUD | 45
| Traffic Control Crew | 2 x TC's + Ute, Signs & Comms | S | hr | AUD | 102.16
| Traffic Ute |  | S | hr | AUD | 25
| Turf Subbie |  | S | m² | AUD | 7
| WHS | WHS Insurance / Levy | S | Item | AUD | 1
| Water Barriers | Water Barriers Hire per m. | S | m | AUD | 82.5
| Water Subbie |  | S | LS | AUD | 1
| DG10 |  | S | tonne | AUD | 287
| DG14 |  | S | tonne | AUD | 262
| Line Marking |  | S | m² | AUD | 7660

## Model Inputs
WBS | DESCRIPTION | TYPE | MODEL INPUT | UOM
3 | PRELIMINARIES | Q | 0
4 | Site establishment & disestablishment including but not limited to, mandatory permits and fees | Q | 1 | Item
5 | Establishment and maintenance of Provision for Traffic in accordance with AS 1742 Manual of uniform traffic control devices and as directed by the Superintendent | Q | 1 | Item
5.1 | Water Barriers | Q | 200 | m
5.2 | Traffic Control Crew | Q | 90 | hr
6 | Construction Survey Set out | Q | 1 | Item
6.1 | Surveyor | Q | 12 | hr
6.2 | Surveyor | Q | 18 | hr
6.3 | Surveyor | Q | 60 | hr
7 | As constructed drawings and data, including surveying & drafting in accordance with Council Standards | Q | 1 | Item
7.1 | Surveyor | Q | 12 | hr
7.2 | Surveyor | Q | 26 | hr
8 | Preparation & implementation of project quality & OHS&R plans | Q | 1 | Item
9 | Geotechnical Testing | Q | 1 | Item
10 | Portable Long Service Levy | Q | 1 | Item
11 | Enviromental Management (including ASS management) | Q | 1 | Item
12 | Provision for Water | Q | 1 | Item
13 | SEDIMENT & EROSION CONTROL | Q | 0
14 | Establishment and maintenance of interim site drainage as required, sediment and erosion control devices as nominated on drawings and as directed by the Superintendent complete in place | Q | 1 | Item
14.1 | Silt Fence | Q | 600 | m
14.2 | Bobcat | P | 33.333 | hr
15 | EARTHWORKS | Q | 0 | 0
16 | Tree Protection | Q | 0 | 0
17 | Tree protection including installation, maintenance and removal at the completion of works (Provisional Quantity) | Q | 1 | Item
18 | Clearing, Grubbing & Demolition | Q | 0
19 | Clearing, grubbing vegetation and disposal off site of cleared vegetation, including but not limited to loading, transportation and dumping fees as nominated on the project drawings | Q | 12233 | m2
19.1 | Excavator - 25T | Q | 36 | hr
20 | Existing Bitumen Seal | Q | 7813 | m2
20.1 | CAT297 | P | 177.778 | hr
21 | Existing Concrete Kerb / Kerb & Channel | Q | 445 | m
21.1 | Excavator - 30T | P | 27.778 | hr
22 | Remove existing structures, slabs, tanks etc. | Q | 1 | Item
22.1 | Excavator - 25T | Q | 9 | hr
23 | Backfill and compact existing well to WRC requirements | Q | 1 | Item
23.1 | Stabilised Sand | Q | 10 | m³
24 | Relocate existing hazard marker and street sign | Q | 1 | Item
25 | Remove and stack existing unused signage as directed | Q | 1 | item
26 | Reinstate existing island and landscaping upon completion of stormwater drainage | Q | 480 | m2
26.1 | Bobcat | P | 120 | hr
27 | Remove abandoned Storm Water Lines and headwalls and dispose off site | Q | 83 | m
27.1 | Excavator - 25T | P | 9.3 | hr
28 | Earthworks | Q | 0
29 | Strip and stockpile topsoil from areas of excavation and filling in accordance with the specification (measured as a solid volume, calculated based on an average 100mm natural topsoil depth) | Q | 916 | m3
29.1 | Excavator - 25T | P | 40 | hr
30 | Respread topsoil in accordance with the specification (measured as a solid volume, calculated based on an average 100mm natural topsoil depth) | Q | 341 | m3
30.1 | Backhoe | P | 250 | hr
31 | Remove from site unused grip material as directed (Provisional) | Q | 575
31.1 | Excavator - 25T | P | 40 | hr
32 | Cut to fill including but not limited to, moisture control and compaction as specified (in-place compacted volume of filling) | Q | 2388 | m3
32.1 | Excavator - 25T | P | 111.111 | hr
33 | Imported Fill material including but not limited to, moisture control and compaction as specified (in-place compacted volume of filling) | Q | 4030 | m3
33.1 | D6 | P | 133.333 | hr
33.2 | Excavator - 25T | P | 88.889 | hr
34 | Cut to spoil including but not limited to loading, transportation and tip fees (Provisional) | Q | 100 | m2
34.1 | Excavator - 25T | P | 30 | hr
35 | Removal of unsuitable material including excavation, filling and spoiling material (provisional) | Q | 150 | 0
35.1 | Excavator - 25T | P | 30 | hr
35.2 | Excavator - 25T | P | 33.333 | hr
36 | Grass seeding to disturbed areas as directed by the Superintendent. | Q | 2791 | m2
37 | ROAD WORKS
38 | Sub grade preparation as specified including, but not limited to scarifying, moisture control, blending, spreading, compaction and trimming | Q | 19963 | m2
38.1 | Grader | P | 175 | hr
39 | Pavement A1 | Q
40 | Base Course - 125mm Type 2.1 | Q | 555 | m3
40.1 | Grader | P | 77.778 | hr
41 | Sub-base Course - 100mm Type 2.3 | Q | 444 | m3
41.1 | Grader | P | 77.778 | hr
42 | Pavement A2 - Roadways | Q | 0 | 0
43 | Base Course - 125mm Type 2.1 | Q | 38 | m3
43.1 | Grader | P | 77.778 | hr
44 | Sub-base Course - 100mm Type 2.3 | Q | 31 | m3
44.1 | Grader | P | 77.778 | hr
45 | Pavement A2 - Rental Car Park | Q | 0 | 0
46 | Base Course - 125mm Type 2.1 | Q | 344 | m3
46.1 | Grader | P | 77.778 | hr
47 | Sub-Base Course - 100mm Type 2.3 | Q | 275 | m3
47.1 | Grader | P | 77.778 | hr
48 | Pavement B - Roadway | Q | 0 | 0
49 | Base Course - 150mm Type 2.1 | Q | 77 | m3
49.1 | Grader | P | 77.778 | hr
50 | Upper Sub-Base Course - 150mm Type 2.3 | Q | 77 | m3
50.1 | Grader | P | 77.778 | hr
51 | Lower Sub-Base Course - 150mm Type 2.3 | Q | 77 | m3
51.1 | Grader | P | 77.778 | hr
52 | Pavement B - Public Car Park including Road 3 | Q | 0 | 0
53 | Base Course - 150mm Type 2.1 | Q | 336 | m3
53.1 | Grader | P | 77.778 | hr
54 | Upper Sub Base Course - 150mm Type 2.3 | Q | 336 | m3
54.1 | Grader | P | 77.778 | hr
55 | Lower Base Course - 150mm Type 2.3 | Q | 336 | m3
55.1 | Grader | P | 77.778 | hr
56 | Final Trim to Pavement | Q | 16547 | m2
56.1 | Grader | P | 150 | hr
57 | Concrete Works | Q | 0 | 0
58 | Concrete Kerb & Channel as specified in place, including but not limited to transitions, ramps & gullies | Q | 0 | 0
59 | Barrier Kerb & Channel Type B1 600mm wide | Q | 670 | m
60 | Barrier Kerb Type B2 | Q | 372 | m
61 | Semi Mountable Kerb Type SM4 | Q | 207 | m
62 | Kerb Ramp | Q | 5 | No.
63 | Raised Threshold Pedestrian Crossing | Q | 161 | m2
63.1 | Bobcat | P | 6 | hr
64 | Additional Concrete Works | Q | 0 | 0
65 | Concrete Footpaths 2.45m wide | Q | 195 | m2
65.1 | Bobcat | P | 6 | hr
66 | Concrete Footpaths 2.5m wide | Q | 23 | m2
66.1 | Bobcat | P | 6 | hr
67 | Concrete Footpaths 3m wide | Q | 439 | m2
67.1 | Bobcat | P | 6 | hr
68 | Concrete Infill to Median Islands to carparks and round about island, complete in place | Q | 102 | m2
69 | Wheelstops, complete in place (in accordance with AS2890.1) | Q | 86 | No.
70 | Surfacing Works | Q | 0 | 0
71 | Existing Public Carpark | Q | 0 | 0
72 | First Seal: 7mm CRS60 | Q | 2490 | m2
73 | Second Seal: 40mm AC Surfacing, (DG10) complete in place, including but not limited to supply, compaction and prime coat) | Q | 249 | tonne
74 | Roadways and New Carpark | Q | 0 | 0
75 | First Seal: 7mm CRS60 Primerseal | Q | 10261 | m2
76 | Second Seal: 40mm AC Surfacing, (DG10) complete in place, including but not limited to supply, compaction and prime coat) | Q | 1026 | tonne
77 | Signage and Pavement Marking | Q | 0 | 0
78 | Signage and pavement marking, complete in place. All work to be in accordance with the requirements of AS 1742 Manual of Uniform Traffic Control Devices (Provisional Sum) | Q | 1 | Item
79 | Signage complete in place including supply and installation. All work to be in accordance with the requirements of AS 1742 Manual of Uniform Traffic Control Devices(Provisional Sum) | Q | 1 | Item
80 | STORMWATER DRAINAGE | Q | 0 | 0
81 | Pipework | Q | 0 | 0
82 | 375mm dia Class 2 RRJ | Q | 82.8 | m
82.1 | Excavator - 25T | P | 6.667 | hr
83 | 375mm dia Class 3 RRJ | Q | 46.8 | m
83.1 | Excavator - 25T | P | 6.667 | hr
84 | 450mm dia Class 2 RRJ | Q | 20.4 | m
84.1 | Excavator - 25T | P | 6.667 | hr
85 | 450mm dia Class 3 RRJ | Q | 21.6 | m
85.1 | Excavator - 25T | P | 6.667 | hr
86 | Drainage Structures | Q | 0 | 0
87 | Manholes as per IPWEA STD Drawings: | Q | 0 | 0
88 | 1050mm dia Access Chamber | Q | 4 | No.
89 | 900x900 mm Access Chamber | Q | 9 | No.
90 | 4/10 - 900x900 Manhole | Q | 1 | Item
91 | Kerb Inlets | Q | 0 | 0
92 | On Grade (L) | Q | 0 | 0
93 | 2.4m Lintel | Q | 4 | No.
94 | On Grade(RH) | Q | 0 | 0
95 | 2.4m Lintel | Q | 5 | No.
96 | Pre-Cast Headwalls | Q | 0 | 0
97 | Humes Precast Headwall or equivalent for 375mm pipe | Q | 2 | No.
97.1 | Excavator - 25T | P | 1 | hr
98 | Humes Precast Headwall or equivalent for 450mm pipe | Q | 2 | No.
98.1 | Excavator - 25T | P | 1 | hr
99 | Rock Protection at Outlet Drains (300 Deep) | Q | 4.7 | m3
99.1 | Excavator - 25T | P | 5 | hr
100 | ELECTRICAL AND LIGHTING | Q | 0 | 0
101 | Trenching for electrical, lighting and communications service Conduits, complete in place, including trenching, backfilling, reinstatment of surface and maintence of trench while open. (trench configuration not specified) | Q | 940 | m
101.1 | Excavator - 25T | P | 16.667 | hr
102 | Supply only of electrical conduits (100 diameter), conuits and marker tape | Q | 613 | m
103 | Supply only of electrical conduits (40 diameter), conuits and marker tape | Q | 500 | 0
104 | Supply only, conduits and marker tape | Q | 270 | m
105 | Installation of electrical pit, complete in place, including trenching, bedding, supplying, laying, marker tape/hard cover and backfill. (trench configuration not specified) | Q | 13 | No.
106 | Installation of communications pit, complete in place, including trenching, bedding, supplying, laying, marker tape/hard cover and backfill. (trench configuration not specified) | Q | 8 | No.
107 | Supply and installation of distribution board complete in place including all ground works, plinth and circuit breakers | Q | 1 | No.
108 | Supply and installation of electrical and communication conduits to gate controllers from nearest pits including all trenching and coordination with gate installer | Q | 5 | No.
109 | Supply and installation of electrical and communication conduits to ticket machines from nearest pits including all trenching and coordination with ticket machine installer | Q | 2 | No.
110 | Supply and installation of new car park lights and poles to match existing including footing installation, pole and all cabling from distribution board | Q | 4 | No.
110.1 | Backhoe | P | 0.5 | hr
111 | Supply and installation of services pillar at car wash bays P1, P2,P3 incl socket outlets (IP56), Safety Switch and Hose Cock and all cabling back to distribution board including all cabling back to distribution board | Q | 3 | No.
112 | MISCELLANEOUS | Q | 0 | 0
113 | Existing Services | Q | 0 | 0
114 | Service Conduit Crossings and Alterations to existing services, as required | Q | 0 | 0
115 | Existing above ground services to be raised to compliment proposed earthworks level (50mm) | Q | 1 | Item
116 | Fencing & Vehicle Barriers | Q | 0 | 0
117 | Vehicle Barriers - CCA Treated Logs | Q | 0 | 0
118 | Trafficked roadways and busbays within the extents of stage 1 boundary | Q | 624 | m
119 | Extension of Trafficked roadways beyond stage 1 boundary. (prevent vehicles leaving roadway and parking outside formal carpark) | Q | 710 | m
120 | Public Carpark | Q | 220 | m
121 | Pedestrian Safety Fence | Q | 15 | m
122 | Supply & Installation of Fixed Bollards | Q | 4 | No.
123 | Temporary Fencing & Signage | Q | 1 | Item
124 | SCHEDULE B - SEWER WORKS | Q | 0 | 0
125 | EARTHWORKS | Q | 0 | 0
126 | Clearing & Grubbing | Q | 550 | m2
127 | Strip & Stockpile Topsoil | Q | 55 | m3
127.1 | Excavator - 25T | P | 40 | hr
128 | Placement of Topsoil | Q | 28 | m2
128.1 | Backhoe | P | 250 | hr
129 | Disposal of excess topsoil as directed | Q | 27 | m3
129.1 | Excavator - 25T | P | 40 | hr
130 | Gravel access and hardstand from airport pit min CBR10 300 thick(Provisional) | Q | 165 | m3
130.1 | Excavator - 25T | P | 88.889 | hr
130.2 | Grader | P | 250 | hr
131 | SEWER WORKS | Q | 0 | 0
132 | Gravity Sewer | Q | 0 | 0
133 | Connection of existing DN100 AC gravity sewers to new ssanitary drain | Q | 2 | No.
134 | Decommision existing Septic Tanks and associated pipework (excluding demolition of tanks - refer schedule A) | Q | 2 | Item
135 | Sewerage Pump Station | Q | 0 | 0
136 | Supply & delivery of Proprietry PE Pump Station (incl pumps, pipework, electrical controls etc) | Q | 1 | No.
137 | Installation of Sewerage Pump Station (including concrete ballast) | Q | 1 | Item
138 | Connection of gravity sewer pipe | Q | 1 | Item
139 | Supply and construction of DN50 vent | Q | 1 | No.
140 | Electrical connections from mains supply | Q | 1 | Item
141 | Commisioning Pump Station and electrical controls | Q | 1 | Item
142 | Rising Main | Q | 0 | 0
143 | Supply and construction of DN32 PE rising main (40OD PE100 PN16) incl 3 No. tees, ball vavles, pits for future STP connection | Q | 215 | m
144 | Connection to new wet weather storage tanks | Q | 1 | Item
145 | Water Supply | Q | 0 | 0
146 | Supply and construction of DN32 PE water supply main (40OD PE100 PN16) to carpark hosecocks. | Q | 210 | m
147 | Supply and installation of DN32 RPZD in enclosure complete | Q | 1 | No.
148 | Supply, installation & connection of hosecocks to carwash Service Pillars complete (excluding pillars, refer Schedule A, 6.11) | Q | 3 | No.
149 | Supply and construct DN25 water supply main (32OD PE100 PN16) to STP | Q | 75 | m
150 | Miscellaneous | Q | 0 | 0
151 | Gate to STP Access | Q | 1 | item
152 | PROJECT OVERHEADS (TO BE SPREAD ACROSS ABOVE ITEMS) | Q | 0 | 0
153 | Project Supervision | Q | 1 | Item
153.1 | Project Supervisor | Q | 10 | week
154 | Project Engineer | Q | 1 | Item
154.1 | Project Engineer | Q | 6 | week
155 | Resource Balance | Q | 1 | Item
155.1 | Water Cart - Hire | Q | 100 | hr
155.2 | CAT297 | Q | 360 | hr
156 | Dual Grade Laser | Q | 1 | Item
156.1 | Dual Grade Laser | Q | 12 | week
157 | Site Facilities | Q | 1 | Item
157.1 | Crib Facilities | Q | 16 | week
158 | Wet Weather | Q | 1 | Item
158.1 | Labour | Q | 160 | hr
159 | Additional Clearing & Grubbing - Moving rental car park 10m to the north to avoid fibre optic cable. | Q | 1 | item
159.1 | Excavator - 25T | Q | 9 | hr
160 | Additional Material for Revised Levels (Main Pad) | Q | 1
161 | Additional Imported General Fill (BOQ Item 3.3.5) | Q | 0 | m³
161.1 | D6 | P | 133.333 | hr
161.2 | Excavator - 25T | P | 88.889 | hr
162 | Additional Fill, road base gravel, spray seal & AC to elongated access ramp | Q | 1 | 0
163 | Imported General Fill (BOQ Item 3.3.5) | Q | 62 | m³
163.1 | D6 | P | 133.333 | hr
163.2 | Excavator - 25T | P | 88.889 | hr
164 | Additional sub-grade preparation (BOQ item 4.1) | Q | 80 | m²
164.1 | Grader | P | 175 | hr
165 | Additional 2.3 Material (BOQ Item 4.2.3.2) | Q | 8 | m³
165.1 | Grader | P | 77.778 | hr
166 | Additional 2.1 Material (BOQ Item 4.2.3.1) | Q | 8.75 | m³
166.1 | Grader | P | 77.778 | hr
167 | Additional final trim (BOQ Item 4.3) | Q | 70 | m³
167.1 | Grader | P | 150 | hr
168 | Additional Spray Seal (BOQ Item 4.5.1.1) | Q | 70 | m²
169 | DG10 | Q | 7 | tonne
170 | Additional Kerb & Channel (Type B1) | Q | 1
171 | B1 Barrier Kerb & Channel (BOQ Item 4.4.1.1) | Q | 20 | m
172 | Additional Footpath | Q | 1
173 | Additional Concrete Footpath 2.45m Wide (BOQ Item 4.4.4.1) | Q | 24.5 | m²
173.1 | Bobcat | P | 6 | hr
174 | Additional Storm Water | Q | 1
175 | Additional 450 mm Diameter Class 2 RRJ (BOQ Item 5.1.3) | Q | 4.88 | m
175.1 | Excavator - 25T | P | 6.667 | hr
176 | Additional General Fill between rental car aprk and batter of new road one | Q | 1
177 | Cut to Fill (BOQ Item 3.3.4) | Q | 460 | m³
177.1 | Excavator - 25T | P | 111.111 | hr
178 | Additional Conduit & Trenching | Q | 1
179 | Additional Trenching (BOQ Item 6.1) | Q | 10 | m
179.1 | Excavator - 25T | P | 16.667 | hr
180 | Additional 100 diameter communications conduit | Q | 10 | m
181 | Additional 100 diameter electrical conduit (BOQ Item 6.2) | Q | 20 | m
182 | Remove & Replace Unsuitable (Extra Over BOQ Item 3.3.7) | Q | 100 | m³
182.1 | Excavator - 25T | P | 30 | hr
182.2 | Excavator - 25T | P | 33.333 | hr
183 | Remove & Replace Soft Spots - Rental Car Park | Q | 75 | item
183.1 | Excavator - 25T | P | 30 | hr
183.2 | Excavator - 25T | P | 33.333 | hr
184 | Extension To Commercial Car Park | Q | 1 | item
185 | Clear & Grubbing (BOQ Item 3.2.1) | Q | 1800 | m²
185.1 | Excavator - 25T | P | 1 | hr
186 | Stripping Topsoil (BOQ item 3.3.1) | Q | 180 | m³
186.1 | Excavator - 25T | P | 40 | hr
187 | Import General Fill (BOQ Item 3.3.5) | Q | 1080 | m³
187.1 | D6 | P | 133.333 | hr
187.2 | Excavator - 25T | P | 88.889 | hr
188 | Prepare Sub-grade (BOQ Item 4.1) | Q | 1800 | m²
188.1 | Grader | P | 175 | hr
189 | Import 2.1 (BOQ Item 4.2.3.1) | Q | 225 | m³
189.1 | Grader | P | 77.778 | hr
190 | Import 2.3 (BOQ Item 4.2.3.2) | Q | 180
190.1 | Grader | P | 77.778 | hr
191 | Primer Seal (7mm) (BOQ Item 4.5.1.1) | Q | 1800 | m²
192 | SM4 Kerb (BOQ Item 4.4.1.3) | Q | 44 | m
193 | B1 Kerb (BOQ Item 4.4.1.1) | Q | 44 | m
193.1 | Bobcat | P | 6 | hr
194 | B2 Kerb (BOQ Item 4.4.1.2) | Q | 44 | m
195 | Topsoil to Back of Kerb (BOQ Item 3.3.2) | Q | 20 | m³
195.1 | Backhoe | P | 250 | hr
196 | Additional 450 RCP (BOQ Item 5.1.4) | Q | 26 | m
196.1 | Excavator - 25T | P | 6.667 | hr
197 | Final Trim (BOQ Item 4.3) | Q | 1800 | m²
197.1 | Grader | P | 150 | hr
198 | Additional Conduit Trenching (BOQ Item 6.1) | Q | 45 | m
198.1 | Excavator - 25T | P | 16.667 | hr
199 | Additional Conduit (BOQ Item 6.3) | Q | 45 | m
200 | Additional Wheel Stops (BOQ Item 4.4.4.5) | Q | 10 | ea
201 | Additional Log Barrier Fence (BOQ Item 7.2.1.1) | Q | 31 | m
202 | New 2.4m Kerb Lintel | Q | 1 | item
203 | Additional Line Marking (BOQ Item 4.7.1) | Q | 0.21739 | item
204 | Additional Box Out & General Fill | Q | 1
205 | Cut To Spoil (BOQ Item 3.3.6) | Q | 1341 | m³
205.1 | Excavator - 25T | P | 30 | hr
206 | Import General Fill (BOQ Item 3.3.5) | Q | 1341 | m³
206.1 | D6 | P | 133.333 | hr
206.2 | Excavator - 25T | P | 88.889 | hr
207 | Remove & Replace Unsuitable - Bus Bay & Round-a-bout | Q | 1 | item
208 | Remove Soft Spots (BOQ Item 3.3.7) | Q | 222.6 | m³
208.1 | Excavator - 25T | P | 30 | hr
208.2 | Excavator - 25T | P | 33.333 | hr
209 | Import General Fill (BOQ Item 3.3.5) | Q | 222.6 | m³
209.1 | D6 | P | 133.333 | hr
209.2 | Excavator - 25T | P | 88.889 | hr
210 | Stabilise Sub-Grade | Q | 1 | m²
211 | Supply GB Cement Stabilising Agent | Q | 36 | tonne
211.1 | Cement | P | 1 | tonne
212 | In-situ Stabilising Sub-grade | Q | 3890 | m²
212.1 | CAT297 Stabiliser | P | 55.5556 | hr
213 | Supply & Install Visi-ball Tank Level Indicator | Q | 1 | item
214 | Centre Median Footpath Beam Thickening | Q | 1 | m³
215 | Excavate for, Supply, Place and Finish Additional N25 Concrete | Q | 8 | m³
215.1 | Bobcat | P | 6 | hr
216 | Supply, cut, tie and place SL72 Reinforcing Mesh | Q | 80 | m²
217 | Install 150mm & 225mm Roof water drainage lines from terminal building, including road crossings and stubs to existing stormwater pits | Q | 1 | item
218 | Installation of STP Irrigation System | Q | 1
219 | Installation only of Pump No. 01 & Pump Well | Q | 1 | item
220 | Supply & Install Pump & Well No. 02 | Q | 1 | item
221 | Supply & Installation of Electrical as Per E002 & Clarification Letter | Q | 1 | item
222 | Raise STP pad height 500mm and provide 100mm reinforced concrete slab | Q | 1 | item
223 | Supply & Install light to roof of container | Q | 1 | item
224 | Supply & Installation of rising main from Pump well No. 02 to irrigation area as per H101 in existing cleared areas | Q | 1 | item
225 | Supply & installation of irrigation area (3,000 sqm) as per H103 including air & flush valves | Q | 1 | item
226 | Supply & installation of signal cable as per clarification email | Q | 1 | item
227 | Installation of Edge Restraint | Q | 105 | m
228 | Fie Lay Away | Q | 1 | item
229 | Cut To Spoil | Q | 36 | m³
229.1 | Excavator - 25T | P | 30 | hr
230 | Prepare & Trim Sub-grade | Q | 160 | m²
230.1 | Grader | P | 150 | hr
231 | Edge Restraint | Q | 45 | m
232 | Supply & Place 2.1 Gravel | Q | 36 | m³
232.1 | Grader | P | 77.778 | hr
233 | Primer Seal | Q | 160 | m²
234 | DG10 Asphalt (40mm) | Q | 16 | tonne
235 | Bin Area | Q | 1 | item
236 | General Fill | Q | 76 | m³
236.1 | D6 | P | 133.333 | hr
236.2 | Excavator - 25T | P | 88.889 | hr
237 | Supply & Place Type 2.1 Gravel | Q | 25 | m³
237.1 | Grader | P | 77.778 | hr
238 | Colourbonfd Fence (1800 High - 20m) | Q | 1 | item
239 | Additional Edge Restraint | Q | 71 | m
240 | Supply & Install Additional Electrical Pit | Q | 1 | each
241 | Extra Over Log Barrier Fenec - Monowills Pedestrian Safety Fence | Q | 58 | m
242 | Additional AC | Q | 70.7 | tonne
243 | Miscellaneous Additional Works | Q | 1 | item

## Non-Work Days
Non-Working Calendar 2011 - 2015 (Queensland - Australia)
| 2011-01-01 |  | 2012-01-01 |  | 2013-01-01 |  | 2014-01-01 |  | 2015-01-01
| 2011-01-08 | 2011-01-09 | 2012-01-14 | 2012-01-15 | 2013-01-19 | 2013-01-20 | 2014-01-18 | 2014-01-19 | 2015-01-17 | 2015-01-18
| 2011-01-01 | 2011-01-02 |  | 2012-01-01 | 2013-01-05 | 2013-01-06 | 2014-01-04 | 2014-01-05 | 2015-01-03 | 2015-01-04
| 2011-01-08 | 2011-01-09 | 2012-01-07 | 2012-01-08 | 2013-01-12 | 2013-01-13 | 2014-01-11 | 2014-01-12 | 2015-01-10 | 2015-01-11
| 2011-01-15 | 2011-01-16 | 2012-01-14 | 2012-01-15 | 2013-01-19 | 2013-01-20 | 2014-01-18 | 2014-01-19 | 2015-01-17 | 2015-01-18
| 2011-01-22 | 2011-01-23 | 2012-01-21 | 2012-01-22 | 2013-01-26 | 2013-01-27 | 2014-01-25 | 2014-01-26 | 2015-01-24 | 2015-01-25
| 2011-01-29 | 2011-01-30 | 2012-01-28 | 2012-01-29 | 2013-02-02 | 2013-02-03 | 2014-02-01 | 2014-02-02 | 2015-01-31 | 2015-02-01
| 2011-02-05 | 2011-02-06 | 2012-02-04 | 2012-02-05 | 2013-02-09 | 2013-02-10 | 2014-02-08 | 2014-02-09 | 2015-02-07 | 2015-02-08
| 2011-02-12 | 2011-02-13 | 2012-02-11 | 2012-02-12 | 2013-02-16 | 2013-02-17 | 2014-02-15 | 2014-02-16 | 2015-02-14 | 2015-02-15
| 2011-02-19 | 2011-02-20 | 2012-02-18 | 2012-02-19 | 2013-02-23 | 2013-02-24 | 2014-02-22 | 2014-02-23 | 2015-02-21 | 2015-02-22
| 2011-02-26 | 2011-02-27 | 2012-02-25 | 2012-02-26 | 2013-03-02 | 2013-03-03 | 2014-03-01 | 2014-03-02 | 2015-02-28 | 2015-03-01
| 2011-03-05 | 2011-03-06 | 2012-03-03 | 2012-03-04 | 2013-03-09 | 2013-03-10 | 2014-03-08 | 2014-03-09 | 2015-03-07 | 2015-03-08
| 2011-03-12 | 2011-03-13 | 2012-03-10 | 2012-03-11 | 2013-03-16 | 2013-03-17 | 2014-03-15 | 2014-03-16 | 2015-03-14 | 2015-03-15
| 2011-03-19 | 2011-03-20 | 2012-03-17 | 2012-03-18 | 2013-03-23 | 2013-03-24 | 2014-03-22 | 2014-03-23 | 2015-03-21 | 2015-03-22
| 2011-03-26 | 2011-03-27 | 2012-03-24 | 2012-03-25 | 2013-03-30 | 2013-03-31 | 2014-03-29 | 2014-03-30 | 2015-03-28 | 2015-03-29
| 2011-04-02 | 2011-04-03 | 2012-03-31 | 2012-04-01 | 2013-04-06 | 2013-04-07 | 2014-04-05 | 2014-04-06 | 2015-04-04 | 2015-04-05
| 2011-04-09 | 2011-04-10 | 2012-04-07 | 2012-04-08 | 2013-04-13 | 2013-04-14 | 2014-04-12 | 2014-04-13 | 2015-04-11 | 2015-04-12
| 2011-04-16 | 2011-04-17 | 2012-04-14 | 2012-04-15 | 2013-04-20 | 2013-04-21 | 2014-04-19 | 2014-04-20 | 2015-04-18 | 2015-04-19
| 2011-04-23 | 2011-04-24 | 2012-04-21 | 2012-04-22 | 2013-04-27 | 2013-04-28 | 2014-04-26 | 2014-04-27 | 2015-04-25 | 2015-04-26
| 2011-04-30 | 2011-05-01 | 2012-04-28 | 2012-04-29 | 2013-05-04 | 2013-05-05 | 2014-05-03 | 2014-05-04 | 2015-05-02 | 2015-05-03
| 2011-05-07 | 2011-05-08 | 2012-05-05 | 2012-05-06 | 2013-05-11 | 2013-05-12 | 2014-05-10 | 2014-05-11 | 2015-05-09 | 2015-05-10
| 2011-05-14 | 2011-05-15 | 2012-05-12 | 2012-05-13 | 2013-05-18 | 2013-05-19 | 2014-05-17 | 2014-05-18 | 2015-05-16 | 2015-05-17
| 2011-05-21 | 2011-05-22 | 2012-05-19 | 2012-05-20 | 2013-05-25 | 2013-05-26 | 2014-05-24 | 2014-05-25 | 2015-05-23 | 2015-05-24
| 2011-05-28 | 2011-05-29 | 2012-05-26 | 2012-05-27 | 2013-06-01 | 2013-06-02 | 2014-05-31 | 2014-06-01 | 2015-05-30 | 2015-05-31
| 2011-06-04 | 2011-06-05 | 2012-06-02 | 2012-06-03 | 2013-06-08 | 2013-06-09 | 2014-06-07 | 2014-06-08 | 2015-06-06 | 2015-06-07
| 2011-06-11 | 2011-06-12 | 2012-06-09 | 2012-06-10 | 2013-06-15 | 2013-06-16 | 2014-06-14 | 2014-06-15 | 2015-06-13 | 2015-06-14
| 2011-06-18 | 2011-06-19 | 2012-06-16 | 2012-06-17 | 2013-06-22 | 2013-06-23 | 2014-06-21 | 2014-06-22 | 2015-06-20 | 2015-06-21
| 2011-06-25 | 2011-06-26 | 2012-06-23 | 2012-06-24 | 2013-06-29 | 2013-06-30 | 2014-06-28 | 2014-06-29 | 2015-06-27 | 2015-06-28
| 2011-07-02 | 2011-07-03 | 2012-06-30 | 2012-07-01 | 2013-07-06 | 2013-07-07 | 2014-07-05 | 2014-07-06 | 2015-07-04 | 2015-07-05
| 2011-07-09 | 2011-07-10 | 2012-07-07 | 2012-07-08 | 2013-07-13 | 2013-07-14 | 2014-07-12 | 2014-07-13 | 2015-07-11 | 2015-07-12
| 2011-07-16 | 2011-07-17 | 2012-07-14 | 2012-07-15 | 2013-07-20 | 2013-07-21 | 2014-07-19 | 2014-07-20 | 2015-07-18 | 2015-07-19
| 2011-07-23 | 2011-07-24 | 2012-07-21 | 2012-07-22 | 2013-07-27 | 2013-07-28 | 2014-07-26 | 2014-07-27 | 2015-07-25 | 2015-07-26
| 2011-07-30 | 2011-07-31 | 2012-07-28 | 2012-07-29 | 2013-08-03 | 2013-08-04 | 2014-08-02 | 2014-08-03 | 2015-08-01 | 2015-08-02
| 2011-08-06 | 2011-08-07 | 2012-08-04 | 2012-08-05 | 2013-08-10 | 2013-08-11 | 2014-08-09 | 2014-08-10 | 2015-08-08 | 2015-08-09
| 2011-08-13 | 2011-08-14 | 2012-08-11 | 2012-08-12 | 2013-08-17 | 2013-08-18 | 2014-08-16 | 2014-08-17 | 2015-08-15 | 2015-08-16
| 2011-08-20 | 2011-08-21 | 2012-08-18 | 2012-08-19 | 2013-08-24 | 2013-08-25 | 2014-08-23 | 2014-08-24 | 2015-08-22 | 2015-08-23
| 2011-08-27 | 2011-08-28 | 2012-08-25 | 2012-08-26 | 2013-08-31 | 2013-09-01 | 2014-08-30 | 2014-08-31 | 2015-08-29 | 2015-08-30
| 2011-09-03 | 2011-09-04 | 2012-09-01 | 2012-09-02 | 2013-09-07 | 2013-09-08 | 2014-09-06 | 2014-09-07 | 2015-09-05 | 2015-09-06
| 2011-09-10 | 2011-09-11 | 2012-09-08 | 2012-09-09 | 2013-09-14 | 2013-09-15 | 2014-09-13 | 2014-09-14 | 2015-09-12 | 2015-09-13
| 2011-09-17 | 2011-09-18 | 2012-09-15 | 2012-09-16 | 2013-09-21 | 2013-09-22 | 2014-09-20 | 2014-09-21 | 2015-09-19 | 2015-09-20
| 2011-09-24 | 2011-09-25 | 2012-09-22 | 2012-09-23 | 2013-09-28 | 2013-09-29 | 2014-09-27 | 2014-09-28 | 2015-09-26 | 2015-09-27
| 2011-10-01 | 2011-10-02 | 2012-09-29 | 2012-09-30 | 2013-10-05 | 2013-10-06 | 2014-10-04 | 2014-10-05 | 2015-10-03 | 2015-10-04
| 2011-10-08 | 2011-10-09 | 2012-10-06 | 2012-10-07 | 2013-10-12 | 2013-10-13 | 2014-10-11 | 2014-10-12 | 2015-10-10 | 2015-10-11
| 2011-10-15 | 2011-10-16 | 2012-10-13 | 2012-10-14 | 2013-10-19 | 2013-10-20 | 2014-10-18 | 2014-10-19 | 2015-10-17 | 2015-10-18
| 2011-10-22 | 2011-10-23 | 2012-10-20 | 2012-10-21 | 2013-10-26 | 2013-10-27 | 2014-10-25 | 2014-10-26 | 2015-10-24 | 2015-10-25
| 2011-10-29 | 2011-10-30 | 2012-10-27 | 2012-10-28 | 2013-11-02 | 2013-11-03 | 2014-11-01 | 2014-11-02 | 2015-10-31 | 2015-11-01
| 2011-11-05 | 2011-11-06 | 2012-11-03 | 2012-11-04 | 2013-11-09 | 2013-11-10 | 2014-11-08 | 2014-11-09 | 2015-11-07 | 2015-11-08
| 2011-11-12 | 2011-11-13 | 2012-11-10 | 2012-11-11 | 2013-11-16 | 2013-11-17 | 2014-11-15 | 2014-11-16 | 2015-11-14 | 2015-11-15
| 2011-11-19 | 2011-11-20 | 2012-11-17 | 2012-11-18 | 2013-11-23 | 2013-11-24 | 2014-11-22 | 2014-11-23 | 2015-11-21 | 2015-11-22
| 2011-11-26 | 2011-11-27 | 2012-11-24 | 2012-11-25 | 2013-11-30 | 2013-12-01 | 2014-11-29 | 2014-11-30 | 2015-11-28 | 2015-11-29
| 2011-12-03 | 2011-12-04 | 2012-12-01 | 2012-12-02 | 2013-12-07 | 2013-12-08 | 2014-12-06 | 2014-12-07 | 2015-12-05 | 2015-12-06
| 2011-12-10 | 2011-12-11 | 2012-12-08 | 2012-12-09 | 2013-12-14 | 2013-12-15 | 2014-12-13 | 2014-12-14 | 2015-12-12 | 2015-12-13
| 2011-12-17 | 2011-12-18 | 2012-12-15 | 2012-12-16 | 2013-12-21 | 2013-12-22 | 2014-12-20 | 2014-12-21 | 2015-12-19 | 2015-12-20
| 2011-12-24 | 2011-12-25 | 2012-12-22 | 2012-12-23 | 2013-12-28 | 2013-12-29 | 2014-12-27 | 2014-12-28 | 2015-12-26 | 2015-12-27
| 2011-12-31 |  | 2012-12-29 | 2012-12-30
Christmas Day | 2011-12-25 | 2011-12-23 | 2012-12-25 | 2012-01-02 | 2013-12-25 | 2013-01-02 | 2014-12-25 | 2014-01-02 | 2015-12-25 | 2015-01-02
Boxing Day | 2011-12-27 | 2011-12-24 | 2012-12-26 | 2012-01-03 | 2013-12-26 | 2013-01-03 | 2014-12-26 | 2014-01-03 | 2015-12-26 | 2015-01-05
New Years Day | 2011-01-01 | 2011-12-28 | 2012-01-01 | 2012-01-04 | 2013-01-01 | 2013-01-04 | 2014-01-01 | 2014-12-22 | 2015-01-01 | 2015-01-06
Australia Day | 2011-01-26 | 2011-12-29 | Australia Day | 2012-01-05 | 2013-01-28 | 2013-12-23 | 2014-01-27 | 2014-12-23 | 2015-01-26 | 2015-01-07
Good Friday | 2011-04-22 | 2011-12-30 | 2012-04-06 | 2012-01-06 | 2013-03-29 | 2013-12-24 | 2014-04-18 | 2014-12-24 | 2015-04-03 | 2015-01-08
Easter Monday | 2011-04-25 |  | 2012-04-09 | 2012-12-24 | 2013-04-01 | 2013-12-27 | 2014-04-21 | 2014-12-29 | 2015-04-06 | 2015-01-09
ANZAC Day | 2011-04-26 |  | 2012-04-25 | 2012-12-27 | 2013-04-25 | 2013-12-30 | 2014-04-25 | 2014-12-30 | 2015-04-27 | 2015-12-24
Labour Day | 2011-05-02 |  | 2012-05-07 | 2012-12-28 | 2013-06-10 | 2013-12-31 | 2014-10-06 | 2014-12-31 | 2015-10-05 | 2015-12-27
Queen's Birthday | 2011-06-13 |  | 2012-06-11 | 2012-12-31 | 2013-10-07 |  | 2014-06-09 |  | 2015-06-08 | 2015-12-28
2015-12-29
2015-12-30
2015-12-31
|  | Xmas S/D | 2012-12-28: Xmas S/D; 2013-12-31: Xmas S/D; 2014-12-31: Xmas S/D; 2015-12-27: Xmas S/D
Work Hours Per Day |  | 9
Start Date |  | 2011-04-01
Note on C71: Brett Thiele: This allows the durations of each task to be turned into days, Durations in hours are rounded up to the nearest full day based on this number.

## Program Links
WBS | Task | Duration | Predecessors | Successors | Budget | %C Claim 01 | %C Claim 02 | %C Claim 03 | %C Claim 04 | %C Claim 05 | %C Claim 06 | %C Claim 07 | %C Claim 08
1 | CONTRACT AWARD | 0 |  | 4,8,10,136,11 | 0
2 | PRACTICAL COMPLETION | 0 | 36,7,31,69,9,111,123,148,223,226,240,238,243,213,6,12 |  | 0
3 | PRELIMINARIES | 0 |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4 | Site establishment & disestablishment including but not limited to, mandatory permits and fees | 5 | 1,10,8,11 | 5,12,14,102,103,104,107,7 | 36340 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
5 | Establishment and maintenance of Provision for Traffic in accordance with AS 1742 Manual of uniform traffic control devices and as directed by the Superintendent | 0 | 4,8 | 6 | 25694.4 | 20% | 60% | 80% | 90% | 95% | 100% | 100% | 100%
6 | Construction Survey Set out | 0 | 5,8 | 2 | 16650 | 15% | 30% | 60% | 80% | 100% | 100% | 100% | 100%
7 | As constructed drawings and data, including surveying & drafting in accordance with Council Standards | 5 | 4,30 | 2 | 7030 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
8 | Preparation & implementation of project quality & OHS&R plans | 5 | 1 | 4,5,6 | 3250 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9 | Geotechnical Testing | 0 | 32 | 2 | 14950 | 5% | 15% | 50% | 75% | 100% | 100% | 100% | 100%
10 | Portable Long Service Levy | 0 | 1 | 4 | 10220 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
11 | Enviromental Management (including ASS management) | 0 | 1 | 4 | 3250 | 15% | 30% | 60% | 80% | 95% | 100% | 100% | 100%
12 | Provision for Water | 0 | 4 | 2 | 12700.8 | 20% | 40% | 70% | 85% | 95% | 100% | 100% | 100%
13 | SEDIMENT & EROSION CONTROL | 0 |  |  | 0
14 | Establishment and maintenance of interim site drainage as required, sediment and erosion control devices as nominated on drawings and as directed by the Superintendent complete in place | 3 | 4 | 17 | 9126.0308 | 20% | 40% | 70% | 85% | 100% | 100% | 100% | 100%
15 | EARTHWORKS |  |  |  | 0
16 | Tree Protection |  |  |  | 0
17 | Tree protection including installation, maintenance and removal at the completion of works (Provisional Quantity) | 1 | 14 | 19 | 514 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
18 | Clearing, Grubbing & Demolition | 0 |  |  | 0
19 | Clearing, grubbing vegetation and disposal off site of cleared vegetation, including but not limited to loading, transportation and dumping fees as nominated on the project drawings | 4 | 17 | 20,29,126,159,185 | 12912 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
20 | Existing Bitumen Seal | 5 | 19159 | 21 | 7888.6786 | 0% | 0% | 28.54% | 74.4% | 100% | 100% | 100% | 100%
21 | Existing Concrete Kerb / Kerb & Channel | 2 | 20 | 22,27 | 12670.9651 | 0% | 0% | 67.42% | 100% | 100% | 100% | 100% | 100%
22 | Remove existing structures, slabs, tanks etc. | 1 | 21 | 23 | 3429 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
23 | Backfill and compact existing well to WRC requirements | 1 | 22 | 24 | 3172 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
24 | Relocate existing hazard marker and street sign | 1 | 23 | 25 | 750 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
25 | Remove and stack existing unused signage as directed | 1 | 24 |  | 750 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
26 | Reinstate existing island and landscaping upon completion of stormwater drainage | 1 | 98 | 36 | 684.1354 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
27 | Remove abandoned Storm Water Lines and headwalls and dispose off site | 1 | 21 | 32 | 1898.7814 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
28 | Earthworks | 0 |  |  | 0
29 | Strip and stockpile topsoil from areas of excavation and filling in accordance with the specification (measured as a solid volume, calculated based on an average 100mm natural topsoil depth) | 3 | 19 | 32186 | 7854.7 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
30 | Respread topsoil in accordance with the specification (measured as a solid volume, calculated based on an average 100mm natural topsoil depth) | 2 | 79,67,68,115,215,173 | 7,31,36,195FF | 4855.84 | 0% | 0% | 8.798% | 26.39% | 100% | 100% | 100% | 100%
31 | Remove from site unused grip material as directed (Provisional) | 2 | 30 | 2 | 7518.125 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
32 | Cut to fill including but not limited to, moisture control and compaction as specified (in-place compacted volume of filling) | 3 | 27,29 | 9,33,187,177FF | 16994.988 | 0% | 0% | 25.13% | 100% | 100% | 100% | 100% | 100%
33 | Imported Fill material including but not limited to, moisture control and compaction as specified (in-place compacted volume of filling) | 6 | 32 | 34,38,187FF,161,163FF,206FF | 54420.0654 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
34 | Cut to spoil including but not limited to loading, transportation and tip fees (Provisional) | 1 | 33 | 35205 | 1743.3333 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
35 | Removal of unsuitable material including excavation, filling and spoiling material (provisional) | 1 | 34 | 38 | 7669.674 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
36 | Grass seeding to disturbed areas as directed by the Superintendent. | 1 | 26,30,99,134,129 | 2 | 7870.62 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
37 | ROAD WORKS | 0 |  |  | 0
38 | Sub grade preparation as specified including, but not limited to scarifying, moisture control, blending, spreading, compaction and trimming | 13 | 33,35,206,161 | 82,101,146,183FF,164FF,212,208 | 40673.8203 | 0% | 11.77% | 34.11% | 39.82% | 100% | 100% | 100% | 100%
39 | Pavement A1 | 0 |  |  | 0
40 | Base Course - 125mm Type 2.1 | 2 | 41,47,59 | 43 | 34918.48 | 0% | 0% | 0% | 71.89% | 100% | 100% | 100% | 100%
41 | Sub-base Course - 100mm Type 2.3 | 2 | 85101149183 | 40,44 | 27152.234 | 0% | 0% | 43.47% | 71.85% | 100% | 100% | 100% | 100%
42 | Pavement A2 - Roadways | 0 |  |  | 0
43 | Base Course - 125mm Type 2.1 | 1 | 40,44 | 46 | 2390.8148 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
44 | Sub-base Course - 100mm Type 2.3 | 1 | 41 | 43,47 | 1895.7641 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
45 | Pavement A2 - Rental Car Park | 0 |  |  | 0
46 | Base Course - 125mm Type 2.1 | 2 | 43,47 | 72,53 | 21643.166 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
47 | Sub-Base Course - 100mm Type 2.3 | 1 | 44 | 40,46,59,55 | 16817.2621 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
48 | Pavement B - Roadway | 0 |  |  | 0
49 | Base Course - 150mm Type 2.1 | 1 | 53 | 56229 | 4844.5459 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
50 | Upper Sub-Base Course - 150mm Type 2.3 | 1 | 54,63 | 60 | 4708.8334 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
51 | Lower Sub-Base Course - 150mm Type 2.3 | 1 | 55212211 | 54,63 | 4708.8334 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
52 | Pavement B - Public Car Park including Road 3 | 0 |  |  | 0
53 | Base Course - 150mm Type 2.1 | 2 | 46,60,239 | 49,189,166FF | 21139.8366 | 0% | 0% | 0% | 46.43% | 100% | 100% | 100% | 100%
54 | Upper Sub Base Course - 150mm Type 2.3 | 2 | 51 | 50,190,165FF | 20547.6366 | 0% | 0% | 0% | 37.2% | 100% | 100% | 100% | 100%
55 | Lower Base Course - 150mm Type 2.3 | 2 | 47 | 51 | 20547.6366 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
56 | Final Trim to Pavement | 13 | 49 | 75,197FF,167FF | 40742.3911 | 0% | 0% | 19.34% | 48.04% | 100% | 100% | 100% | 100%
57 | Concrete Works | 0 |  |  | 0
58 | Concrete Kerb & Channel as specified in place, including but not limited to transitions, ramps & gullies | 0 |  |  | 0
59 | Barrier Kerb & Channel Type B1 600mm wide | 6.7 | 47 | 40,93,193FF | 27475.5126 | 0% | 0% | 46.27% | 47.46% | 100% | 100% | 100% | 100%
60 | Barrier Kerb Type B2 | 3.72 | 50 | 53,61,115,194FF | 10820.3905 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
61 | Semi Mountable Kerb Type SM4 | 1 | 60 | 62,227,231FF,192FF | 858.4031 | 0% | 0% | 43.48% | 43.48% | 79.71% | 95.17% | 95.17% | 100%
62 | Kerb Ramp | 5 | 61 | 65 | 2291 | 0% | 0% | 0% | 60% | 100% | 100% | 100% | 100%
63 | Raised Threshold Pedestrian Crossing | 4.025 | 51 | 50 | 11276.4621 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
64 | Additional Concrete Works | 0 |  |  | 0
65 | Concrete Footpaths 2.45m wide | 5 | 62 | 66,173FF | 10775.0386 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
66 | Concrete Footpaths 2.5m wide | 1 | 65 | 67 | 1270.902 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
67 | Concrete Footpaths 3m wide | 8 | 66 | 30,68,216 | 16575.151 | 0% | 0% | 0% | 91.91% | 91.91% | 100% | 100% | 100%
68 | Concrete Infill to Median Islands to carparks and round about island, complete in place | 4 | 67 | 30 | 3766.174 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
69 | Wheelstops, complete in place (in accordance with AS2890.1) | 1 | 79 | 2,200FF | 13301.3333 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
70 | Surfacing Works | 0 |  |  | 0
71 | Existing Public Carpark | 0 |  |  | 0
72 | First Seal: 7mm CRS60 | 1 | 46 | 73 | 11739.105 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
73 | Second Seal: 40mm AC Surfacing, (DG10) complete in place, including but not limited to supply, compaction and prime coat) | 1 | 72 | 110 | 71463 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
74 | Roadways and New Carpark | 0 |  |  | 0
75 | First Seal: 7mm CRS60 Primerseal | 1 | 56,95 | 76,233FF,168FF | 48375.4845 | 0% | 0% | 31.19% | 77.48% | 100% | 100% | 100% | 100%
76 | Second Seal: 40mm AC Surfacing, (DG10) complete in place, including but not limited to supply, compaction and prime coat) | 3 | 75 | 78,118,147,242,234FF,191FF,169FF | 294462 | 0% | 0% | 0% | 0% | 19.01% | 100% | 100% | 100%
77 | Signage and Pavement Marking | 0 |  |  | 0
78 | Signage and pavement marking, complete in place. All work to be in accordance with the requirements of AS 1742 Manual of Uniform Traffic Control Devices (Provisional Sum) | 1 | 76 | 79,203FF | 7660 | 0% | 0% | 0% | 0% | 25% | 25% | 100% | 100%
79 | Signage complete in place including supply and installation. All work to be in accordance with the requirements of AS 1742 Manual of Uniform Traffic Control Devices(Provisional Sum) | 1 | 78203 | 30,69 | 1682.1 | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100%
80 | STORMWATER DRAINAGE | 0 |  |  | 0
81 | Pipework | 0 |  |  | 0
82 | 375mm dia Class 2 RRJ | 2 | 38 | 83 | 10207.4201 | 0% | 58.97% | 80.59% | 80.59% | 100% | 100% | 100% | 100%
83 | 375mm dia Class 3 RRJ | 1 | 82 | 84,88,97,217 | 6395.1273 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
84 | 450mm dia Class 2 RRJ | 1 | 83,88,217 | 85,89,175FF | 2889.8236 | 0% | 97.75% | 100% | 100% | 100% | 100% | 100% | 100%
85 | 450mm dia Class 3 RRJ | 1 | 84,89 | 41,90,98,196FF | 3883.4212 | 0% | 0% | 67.59% | 67.59% | 100% | 100% | 100% | 100%
86 | Drainage Structures | 0 |  |  | 0
87 | Manholes as per IPWEA STD Drawings: | 0 |  |  | 0
88 | 1050mm dia Access Chamber | 19 | 83 | 84,89 | 11816.8 | 0% | 0% | 0% | 25% | 25% | 25% | 25% | 25%
89 | 900x900 mm Access Chamber | 18 | 84,88 | 85,90 | 9774.684 | 0% | 0% | 77.78% | 100% | 100% | 100% | 100% | 100%
90 | 4/10 - 900x900 Manhole | 5 | 85,89 | 93 | 2920.76 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
91 | Kerb Inlets | 0 |  |  | 0
92 | On Grade (L) | 0 |  |  | 0
93 | 2.4m Lintel | 6 | 59,90 | 95202 | 8428.8 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
94 | On Grade(RH) | 0 |  |  | 0
95 | 2.4m Lintel | 7 | 93202 | 75 | 10536 | 0% | 0% | 0% | 40% | 100% | 100% | 100% | 100%
96 | Pre-Cast Headwalls | 0 |  |  | 0
97 | Humes Precast Headwall or equivalent for 375mm pipe | 2 | 83 | 98 | 1694 | 0% | 25% | 25% | 50% | 50% | 50% | 50% | 50%
98 | Humes Precast Headwall or equivalent for 450mm pipe | 2 | 85,97 | 26,99 | 1980 | 0% | 32.5% | 32.5% | 100% | 100% | 100% | 100% | 100%
99 | Rock Protection at Outlet Drains (300 Deep) | 1 | 98 | 36 | 710.64 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
100 | ELECTRICAL AND LIGHTING | 0 |  |  | 0
101 | Trenching for electrical, lighting and communications service Conduits, complete in place, including trenching, backfilling, reinstatment of surface and maintence of trench while open. (trench configuration not specified) | 7 | 38 | 41,102FF,103FF,104FF,105,240,198FF,179FF | 32591.0822 | 0% | 28.72% | 79.26% | 100% | 100% | 100% | 100% | 100%
102 | Supply only of electrical conduits (100 diameter), conuits and marker tape | 5 | 4,101FF | 105,181FF | 3342.9955 | 0% | 27.73% | 95.92% | 100% | 100% | 100% | 100% | 100%
103 | Supply only of electrical conduits (40 diameter), conuits and marker tape | 5 | 4,101FF | 105 | 1461.5 | 0% | 44% | 66% | 100% | 100% | 100% | 100% | 100%
104 | Supply only, conduits and marker tape | 5 | 4,101FF | 105 | 1673.73 | 0% | 11.11% | 100% | 100% | 100% | 100% | 100% | 100%
105 | Installation of electrical pit, complete in place, including trenching, bedding, supplying, laying, marker tape/hard cover and backfill. (trench configuration not specified) | 6 | 101102103104 | 106,240FF | 16246.75 | 0% | 0% | 0% | 61.54% | 100% | 100% | 100% | 100%
106 | Installation of communications pit, complete in place, including trenching, bedding, supplying, laying, marker tape/hard cover and backfill. (trench configuration not specified) | 4 | 105 | 107 | 12308 | 0% | 0% | 0% | 62.5% | 100% | 100% | 100% | 100%
107 | Supply and installation of distribution board complete in place including all ground works, plinth and circuit breakers | 3 | 4106 | 108 | 12010 | 0% | 0% | 0% | 0% | 75% | 100% | 100% | 100%
108 | Supply and installation of electrical and communication conduits to gate controllers from nearest pits including all trenching and coordination with gate installer | 1 | 107 | 109 | 4689.65 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
109 | Supply and installation of electrical and communication conduits to ticket machines from nearest pits including all trenching and coordination with ticket machine installer | 2 | 108 | 111 | 1113.82 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
110 | Supply and installation of new car park lights and poles to match existing including footing installation, pole and all cabling from distribution board | 2 | 73 | 111 | 23218.6 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
111 | Supply and installation of services pillar at car wash bays P1, P2,P3 incl socket outlets (IP56), Safety Switch and Hose Cock and all cabling back to distribution board including all cabling back to distribution board | 3 | 109110 | 2 | 4630 | 0% | 0% | 0% | 33.33% | 100% | 100% | 100% | 100%
112 | MISCELLANEOUS | 0 |  |  | 0
113 | Existing Services | 0 |  |  | 0
114 | Service Conduit Crossings and Alterations to existing services, as required | 0 |  |  | 0
115 | Existing above ground services to be raised to compliment proposed earthworks level (50mm) | 1 | 60 | 30 | 2499 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
116 | Fencing & Vehicle Barriers | 0 |  |  | 0
117 | Vehicle Barriers - CCA Treated Logs | 0 |  |  | 0
118 | Trafficked roadways and busbays within the extents of stage 1 boundary | 10 | 76242 | 119201 | 16838.64 | 0% | 0% | 0% | 0% | 48.88% | 100% | 100% | 100%
119 | Extension of Trafficked roadways beyond stage 1 boundary. (prevent vehicles leaving roadway and parking outside formal carpark) | 11 | 118201 | 120 | 19159.35 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
120 | Public Carpark | 4 | 119 | 121 | 5936.7 | 0% | 0% | 0% | 0% | 0% | 73.64% | 100% | 100%
121 | Pedestrian Safety Fence | 1 | 120 | 122241 | 1500 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
122 | Supply & Installation of Fixed Bollards | 1 | 121241 | 123243 | 210 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
123 | Temporary Fencing & Signage | 2 | 122 | 2 | 12768 | 10% | 30% | 60% | 80% | 100% | 100% | 100% | 100%
124 | SCHEDULE B - SEWER WORKS | 0 |  |  | 0
125 | EARTHWORKS | 0 |  |  | 0
126 | Clearing & Grubbing | 2 | 19 | 127 | 4482 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
127 | Strip & Stockpile Topsoil | 1 | 126 | 130143 | 471.625 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
128 | Placement of Topsoil | 1 | 141 | 129 | 398.72 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
129 | Disposal of excess topsoil as directed | 1 | 128 | 36 | 353.025 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
130 | Gravel access and hardstand from airport pit min CBR10 300 thick(Provisional) | 1 | 127 | 133222 | 2999.374 | 48.48% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
131 | SEWER WORKS | 0 |  |  | 0
132 | Gravity Sewer | 0 |  |  | 0
133 | Connection of existing DN100 AC gravity sewers to new ssanitary drain | 2 | 130141144222 | 134 | 4800 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
134 | Decommision existing Septic Tanks and associated pipework (excluding demolition of tanks - refer schedule A) | 2 | 133 | 36 | 4000 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
135 | Sewerage Pump Station | 0 |  |  | 0
136 | Supply & delivery of Proprietry PE Pump Station (incl pumps, pipework, electrical controls etc) | 15 | 1,143FF | 137 | 23520 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
137 | Installation of Sewerage Pump Station (including concrete ballast) | 2 | 136 | 138 | 4100 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
138 | Connection of gravity sewer pipe | 1 | 137 | 139 | 2400 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
139 | Supply and construction of DN50 vent | 1 | 138 | 140 | 1800 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
140 | Electrical connections from mains supply | 7 | 139 | 141 | 3600 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
141 | Commisioning Pump Station and electrical controls | 1 | 140 | 128133151219 | 2000 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
142 | Rising Main | 0 |  |  | 0
143 | Supply and construction of DN32 PE rising main (40OD PE100 PN16) incl 3 No. tees, ball vavles, pits for future STP connection | 2 | 127 | 136FF,144 | 14326.4 | 44.19% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
144 | Connection to new wet weather storage tanks | 1 | 143 | 133213 | 1500 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
145 | Water Supply | 0 |  |  | 0
146 | Supply and construction of DN32 PE water supply main (40OD PE100 PN16) to carpark hosecocks. | 1 | 38 | 149 | 13992.5949 | 61.9% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
147 | Supply and installation of DN32 RPZD in enclosure complete | 1 | 76 | 148 | 2074.4 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
148 | Supply, installation & connection of hosecocks to carwash Service Pillars complete (excluding pillars, refer Schedule A, 6.11) | 1 | 147 | 2 | 735 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
149 | Supply and construct DN25 water supply main (32OD PE100 PN16) to STP | 2 | 146 | 41 | 4822.6483 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
150 | Miscellaneous | 0 |  |  | 0
151 | Gate to STP Access | 10.5066 | 141 |  | 1500.109 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
152 | PROJECT OVERHEADS (TO BE SPREAD ACROSS ABOVE ITEMS) | 0 |  |  | 0
153 | Project Supervision | 0 |  |  | 33500
154 | Project Engineer | 0 |  |  | 19500
155 | Resource Balance | 0 |  |  | 26240
156 | Dual Grade Laser | 0 |  |  | 3324
157 | Site Facilities | 0 |  |  | 17936
158 | Wet Weather | 0 |  |  | 380
159 | Additional Clearing & Grubbing - Moving rental car park 10m to the north to avoid fibre optic cable. | 1 | 19 | 20 | 2728 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
160 | Additional Material for Revised Levels (Main Pad) | 0 |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
161 | Additional Imported General Fill (BOQ Item 3.3.5) | 0 | 33 | 38 | 0 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
162 | Additional Fill, road base gravel, spray seal & AC to elongated access ramp | 0.23638 |  |  | 4551.3452 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
163 | Imported General Fill (BOQ Item 3.3.5) | 0.0775 | 33FF | 164177 | 837.2318 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
164 | Additional sub-grade preparation (BOQ item 4.1) | 0.050794 | 38FF,163,179 | 165175 | 162.9968 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
165 | Additional 2.3 Material (BOQ Item 4.2.3.2) | 0.026857 | 54FF,164,175,181 | 166171 | 489.2294 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
166 | Additional 2.1 Material (BOQ Item 4.2.3.1) | 0.029375 | 53FF,165,171 | 167 | 550.5166 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
167 | Additional final trim (BOQ Item 4.3) | 0.051852 | 56FF,166 | 168 | 172.3556 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
168 | Additional Spray Seal (BOQ Item 4.5.1.1) | 1 | 75FF,167 | 169 | 330.015 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
169 | Additional AC (BOQ Item 4.5.1.2) | 1 | 76FF,168 | 173 | 2009 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
170 | Additional Kerb & Channel (Type B1) | 0 |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
171 | B1 Barrier Kerb & Channel (BOQ Item 4.4.1.1) | 0.4 | 165,193FF | 166 | 820.1646 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
172 | Additional Footpath | 0 |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
173 | Additional Concrete Footpath 2.45m Wide (BOQ Item 4.4.4.1) | 0.49 | 65FF,169 | 30 | 1353.7869 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
174 | Additional Storm Water | 0 |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
175 | Additional 450 mm Diameter Class 2 RRJ (BOQ Item 5.1.3) | 0.081329 | 84FF,164,177 | 165 | 691.2911 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
176 | Additional General Fill between rental car aprk and batter of new road one | 0 |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
177 | Cut to Fill (BOQ Item 3.3.4) | 0.46 | 32FF,163 | 175 | 3090.7431 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
178 | Additional Conduit & Trenching | 0 |  |  | 502.5086 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
179 | Additional Trenching (BOQ Item 6.1) | 0.22222 | 101FF | 164180 | 346.7136 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
180 | Additional 100 diameter communications conduit | 0.22222 | 179 |  | 46.725 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
181 | Additional 100 diameter electrical conduit (BOQ Item 6.2) | 0.22222 | 102FF | 165 | 109.07 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
182 | Remove & Replace Unsuitable (Extra Over BOQ Item 3.3.7) | 3.6667 | 187 | 183 | 5113.116 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
183 | Remove & Replace Soft Spots - Rental Car Park | 2.75 | 38FF,182 | 41 | 3834.837 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
184 | Extension To Commercial Car Park | 0 |  |  | 75658.3253 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
185 | Clear & Grubbing (BOQ Item 3.2.1) | 0.11111 | 19 | 186 | 192 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
186 | Stripping Topsoil (BOQ item 3.3.1) | 0.5 | 29185 | 187 | 1543.5 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
187 | Import General Fill (BOQ Item 3.3.5) | 1.35 | 32,33FF,186 | 188182 | 14584.0374 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
188 | Prepare Sub-grade (BOQ Item 4.1) | 1.1429 | 187 | 189 | 3667.4286 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
189 | Import 2.1 (BOQ Item 4.2.3.1) | 0.75535 | 53188 | 190 | 14156.1406 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
190 | Import 2.3 (BOQ Item 4.2.3.2) | 0.60428 | 54189 | 191 | 11007.6624 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
191 | Primer Seal (7mm) (BOQ Item 4.5.1.1) | 1 | 76FF,190 | 192 | 8486.1 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
192 | SM4 Kerb (BOQ Item 4.4.1.3) | 1 | 61FF,191 | 193 | 1071.6805 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
193 | B1 Kerb (BOQ Item 4.4.1.1) | 1 | 59FF,192 | 171FF,194 | 2431.2908 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
194 | B2 Kerb (BOQ Item 4.4.1.2) | 1 | 60FF,193 | 195 | 1279.8311 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
195 | Topsoil to Back of Kerb (BOQ Item 3.3.2) | 0.088889 | 30FF,194 | 196 | 284.8 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
196 | Additional 450 RCP (BOQ Item 5.1.4) | 0.43331 | 85FF,195 | 197 | 4674.4885 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
197 | Final Trim (BOQ Item 4.3) | 1.3333 | 56FF,196 | 198 | 4432 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
198 | Additional Conduit Trenching (BOQ Item 6.1) | 0.29999 | 101FF,197 | 199FF | 1560.2114 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
199 | Additional Conduit (BOQ Item 6.3) | 1 | 198FF | 200 | 131.535 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
200 | Additional Wheel Stops (BOQ Item 4.4.4.5) | 0.11111 | 69FF,199 | 201 | 1546.6667 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
201 | Additional Log Barrier Fence (BOQ Item 7.2.1.1) | 2 | 118200 | 119 | 836.535 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
202 | New 2.4m Kerb Lintel | 1.3333 | 93 | 95203 | 2107.2 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
203 | Additional Line Marking (BOQ Item 4.7.1) | 0.33333 | 78FF,202 | 79 | 1665.2174 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
204 | Additional Box Out & General Fill | 4.9667 |  |  | 41486.6131 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
205 | Cut To Spoil (BOQ Item 3.3.6) | 4.9667 | 34 | 206 | 23378.1 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
206 | Import General Fill (BOQ Item 3.3.5) | 1.6762 | 33FF,205 | 38 | 18108.5131 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
207 | Remove & Replace Unsuitable - Bus Bay & Round-a-bout | 1.1027 |  |  | 14387.7283 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
208 | Remove Soft Spots (BOQ Item 3.3.7) | 0.82444 | 38 | 209 | 11381.7962 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
209 | Import General Fill (BOQ Item 3.3.5) | 0.27825 | 208 | 212 | 3005.9322 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
210 | Stabilise Sub-Grade | 7.78 |  |  | 43119.1214 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
211 | Supply GB Cement Stabilising Agent | 0 | 212FF | 51 | 332 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
212 | In-situ Stabilising Sub-grade | 7.78 | 38209 | 51,211FF | 42787.1214 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
213 | Supply & Install Visi-ball Tank Level Indicator | 1 | 144 | 2 | 700 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
214 | Centre Median Footpath Beam Thickening | 1.5467 |  |  | 2275.2128 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
215 | Excavate for, Supply, Place and Finish Additional N25 Concrete | 1.0667 | 216SS | 30 | 1497.6277 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
216 | Supply, cut, tie and place SL72 Reinforcing Mesh | 0.48 | 67 | 215SS | 777.5851 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
217 | Install 150mm & 225mm Roof water drainage lines from terminal building, including road crossings and stubs to existing stormwater pits | 3 | 83 | 84 | 6250 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
218 | Installation of STP Irrigation System | 0 |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
219 | Installation only of Pump No. 01 & Pump Well | 25 | 141 | 220FF | 3850 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
220 | Supply & Install Pump & Well No. 02 | 25 | 219FF | 224,221FF | 17000 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
221 | Supply & Installation of Electrical as Per E002 & Clarification Letter | 25 | 220FF | 223 | 33700 | 0% | 0% | 0% | 0% | 85% | 100% | 100% | 100%
222 | Raise STP pad height 500mm and provide 100mm reinforced concrete slab | 1 | 130 | 133223 | 3800 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
223 | Supply & Install light to roof of container | 1 | 221222 | 2 | 700 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
224 | Supply & Installation of rising main from Pump well No. 02 to irrigation area as per H101 in existing cleared areas | 5 | 220 | 225 | 39000 | 0% | 0% | 0% | 44.8% | 100% | 100% | 100% | 100%
225 | Supply & installation of irrigation area (3,000 sqm) as per H103 including air & flush valves | 5 | 224 | 226 | 39600 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
226 | Supply & installation of signal cable as per clarification email | 3 | 225 | 2 | 12600 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
227 | Installation of Edge Restraint | 1 | 61 | 239 | 4305.8639 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
228 | Fie Lay Away | 3.3727 |  |  | 5017.9083 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
229 | Cut To Spoil | 0.13333 | 49 | 230,236FF | 513.6 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
230 | Prepare & Trim Sub-grade | 0.11852 | 229 | 231 | 393.9556 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
231 | Edge Restraint | 1 | 61FF,230 | 232 | 1845.3702 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
232 | Supply & Place 2.1 Gravel | 0.12086 | 231 | 233237 | 2264.9825 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
233 | Primer Seal | 1 | 75FF,232 | 234 | 718.4 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
234 | DG10 Asphalt (40mm) | 1 | 76FF,233 | 238 | 4592 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
235 | Bin Area | 3.1789 |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
236 | General Fill | 0.095 | 229FF | 237 | 1026.2841 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
237 | Supply & Place Type 2.1 Gravel | 0.083928 | 232236 | 238 | 1572.9045 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
238 | Colourbonfd Fence (1800 High - 20m) | 3 | 234237 | 2 | 2323 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
239 | Additional Edge Restraint | 1 | 227 | 53 | 2911.5842 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
240 | Supply & Install Additional Electrical Pit | 1 | 101,105FF | 2 | 1210 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
241 | Extra Over Log Barrier Fenec - Monowills Pedestrian Safety Fence | 0 | 121 | 122 | 2146 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
242 | Additional AC | 1 | 76 | 118 | 20290.9 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
243 | Miscellaneous Additional Works | 3 | 122 | 2 | 22691.1516 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Note on A2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WBS
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Description or Task
Note on C2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Duration of Task, calculated from the estimate based on quantity and productivity.
Note on F2: Brett Thiele: This is the budegt which is calculated from the estimate.
Note on G2: Brett Thiele: %C based on Prgress Claims - Columns G - N
Note on H2: Brett Thiele: Brett Thiele: %C based on Prgress Claims - Columns G - N
Note on I2: Brett Thiele: Brett Thiele: %C based on Prgress Claims - Columns G - N
Note on J2: Brett Thiele: Brett Thiele: %C based on Prgress Claims - Columns G - N
Note on K2: Brett Thiele: Brett Thiele: %C based on Prgress Claims - Columns G - N
Note on L2: Brett Thiele: Brett Thiele: %C based on Prgress Claims - Columns G - N
Note on M2: Brett Thiele: Brett Thiele: %C based on Prgress Claims - Columns G - N
Note on N2: Brett Thiele: Brett Thiele: %C based on Prgress Claims - Columns G - N

## Budget & Revenue
WBS | Item No | Description | Unit | Tender Budget | Tender Quantity | Contract Quantity | Tender Rate | Tender Total | Contract Total |  | Claim 01 | %C - Claim 01 | Claim 02 | %C - Claim 02 | Claim 03 | %C - Claim 03 | Claim 04 | %C - Claim 04 | Claim 05 | %C - Claim 05 | Claim 06 | %C - Claim 06 | Claim 07 | %C - Claim 07 | Claim 08 | %C - Claim 08 | Revenue Claim 01 | Revenue Claim 02 | Revenue Claim 03 | Revenue Claim 04 | Revenue Claim 05 | Revenue Claim 06 | Revenue Claim 07 | Revenue Claim 08
Contract Items
3 | 1 | PRELIMINARIES
4 | 1.1 | Site establishment & disestablishment including but not limited to, mandatory permits and fees | Item | 36340 | 1 | 1 | 46306.14 | 46306.14 | 46306.14 |  | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 23153.07 | 46306.14 | 46306.14 | 46306.14 | 46306.14 | 46306.14 | 46306.14 | 46306.14
5 | 1.2 | Establishment and maintenance of Provision for Traffic in accordance with AS 1742 Manual of uniform traffic control devices and as directed by the Superintendent | Item | 25694.4 | 1 | 1 | 32741.01 | 32741.01 | 32741.01 |  | 0.2 | 20% | 0.6 | 60% | 0.8 | 80% | 0.9 | 90% | 0.95 | 95% | 1 | 100% | 1 | 100% | 1 | 100% | 6548.202 | 19644.606 | 26192.808 | 29466.909 | 31103.9595 | 32741.01 | 32741.01 | 32741.01
6 | 1.3 | Construction Survey Set out | Item | 16650 | 1 | 1 | 21216.21 | 21216.21 | 21216.21 |  | 0.15 | 15% | 0.3 | 30% | 0.6 | 60% | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 3182.4315 | 6364.863 | 12729.726 | 16972.968 | 21216.21 | 21216.21 | 21216.21 | 21216.21
7 | 1.4 | As constructed drawings and data, including surveying & drafting in accordance with Council Standards | Item | 7030 | 1 | 1 | 8957.96 | 8957.96 | 8957.96 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 8957.96 | 8957.96
8 | 1.5 | Preparation & implementation of project quality & OHS&R plans | Item | 3250 | 1 | 1 | 4141.3 | 4141.3 | 4141.3 |  | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 4141.3 | 4141.3 | 4141.3 | 4141.3 | 4141.3 | 4141.3 | 4141.3 | 4141.3
9 | 1.6 | Geotechnical Testing | Item | 14950 | 1 | 1 | 19050 | 19050 | 19050 |  | 0.05 | 5% | 0.15 | 15% | 0.5 | 50% | 0.75 | 75% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 952.5 | 2857.5 | 9525 | 14287.5 | 19050 | 19050 | 19050 | 19050
10 | 1.7 | Portable Long Service Levy | Item | 10220 | 1 | 1 | 13022.81 | 13022.81 | 13022.81 |  | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 13022.81 | 13022.81 | 13022.81 | 13022.81 | 13022.81 | 13022.81 | 13022.81 | 13022.81
11 | 1.8 | Enviromental Management (including ASS management) | Item | 3250 | 1 | 1 | 4141.3 | 4141.3 | 4141.3 |  | 0.15 | 15% | 0.3 | 30% | 0.6 | 60% | 0.8 | 80% | 0.95 | 95% | 1 | 100% | 1 | 100% | 1 | 100% | 621.195 | 1242.39 | 2484.78 | 3313.04 | 3934.235 | 4141.3 | 4141.3 | 4141.3
12 | 1.9 | Provision for Water | Item | 12700.8 | 1 | 1 | 16183.96 | 16183.96 | 16183.96 |  | 0.2 | 20% | 0.4 | 40% | 0.7 | 70% | 0.85 | 85% | 0.95 | 95% | 1 | 100% | 1 | 100% | 1 | 100% | 3236.792 | 6473.584 | 11328.772 | 13756.366 | 15374.762 | 16183.96 | 16183.96 | 16183.96
| 1.1 | Original Tender Difference | Item |  | 1 | 1 | 99682.79 | 99682.79 | 99682.79 |  |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 99682.79 | 99682.79 | 99682.79 | 99682.79 | 99682.79 | 99682.79 | 99682.79
|  | Sub-Total Preliminaries | [5 empty] | 265443.48
13 | 2 | SEDIMENT AND EROSION CONTROL
14 | 2.1 | Establishment and maintenance of interim site drainage as required, sediment and erosion control devices as nominated on drawings and as directed by the Superintendent complete in place | Item | 9126.0308 | 1 | 1 | 11628.78 | 11628.78 | 11628.78 |  | 0.2 | 20% | 0.4 | 40% | 0.7 | 70% | 0.85 | 85% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 2325.756 | 4651.512 | 8140.146 | 9884.463 | 11628.78 | 11628.78 | 11628.78 | 11628.78
|  | Sub-Total Sediment & Erosion Control | [5 empty] | 11628.78
15 | 3 | EARTHWORKS
16 | 3.1 | Tree Protection
17 |  | Tree protection including installation, maintenance and removal at the completion of works (Provisional Quantity) | Item | 514 | 1 | 1 | 654.96 | 654.96 | 654.96 |  |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 654.96 | 654.96 | 654.96 | 654.96 | 654.96 | 654.96
18 | 3.2 | Clearing, Grubbing and Demolition
19 | 3.2.1 | Clearing, grubbing vegetation and disposal off site of cleared vegetation, including but not limited to loading, transportation and dumping fees as nominated on the project drawings | m2 | 12912 | 12233 | 12233 | 1.35 | 16514.55 | 16514.55 |  | 12233 | 100% | 12233 | 100% | 12233 | 100% | 12233 | 100% | 12233 | 100% | 12233 | 100% | 12233 | 100% | 12233 | 100% | 16514.55 | 16514.55 | 16514.55 | 16514.55 | 16514.55 | 16514.55 | 16514.55 | 16514.55
| 3.2.2 | Removal of existing infrastructure and services including but not limited to loading, transportation and dumping fees as nominated on the project
20 | 3.2.2.1 | Existing Bitumen Seal | m2 | 7888.6786 | 7813 | 7813 | 1.29 | 10078.77 | 10078.77 |  |  | 0% |  | 0% | 2230 | 28.54% | 5813 | 74.4% | 7813 | 100% | 7813 | 100% | 7813 | 100% | 7813 | 100% | 0 | 0 | 2876.7 | 7498.77 | 10078.77 | 10078.77 | 10078.77 | 10078.77
21 | 3.2.2.2 | Existing Concrete Kerb / Kerb & Channel | m | 12670.9651 | 445 | 445 | 36.3 | 16153.5 | 16153.5 |  |  | 0% |  | 0% | 300 | 67.42% | 445 | 100% | 445 | 100% | 445 | 100% | 445 | 100% | 445 | 100% | 0 | 0 | 10890 | 16153.5 | 16153.5 | 16153.5 | 16153.5 | 16153.5
22 | 3.2.3 | Remove existing structures, slabs, tanks etc. | Item | 3429 | 1 | 1 | 4369.39 | 4369.39 | 4369.39 |  |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 4369.39 | 4369.39 | 4369.39 | 4369.39 | 4369.39 | 4369.39
23 | 3.2.4 | Backfill and compact existing well to WRC requirements | Item | 3172 | 1 | 1 | 4041.91 | 4041.91 | 4041.91 |  |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 4041.91 | 4041.91 | 4041.91 | 4041.91 | 4041.91 | 4041.91
24 | 3.2.5 | Relocate existing hazard marker and street sign | Item | 750 | 1 | 1 | 955.69 | 955.69 | 955.69 |  |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 955.69 | 955.69 | 955.69 | 955.69
25 | 3.2.6 | Remove and stack existing unused signage as directed | item | 750 | 1 | 1 | 955.69 | 955.69 | 955.69 |  |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 955.69 | 955.69 | 955.69 | 955.69 | 955.69 | 955.69
26 | 3.2.7 | Reinstate existing island and landscaping upon completion of stormwater drainage | m2 | 684.1354 | 480 | 480 | 5.41 | 2596.8 | 2596.8 |  |  | 0% |  | 0% |  | 0% |  | 0% | 480 | 100% | 480 | 100% | 480 | 100% | 480 | 100% | 0 | 0 | 0 | 0 | 2596.8 | 2596.8 | 2596.8 | 2596.8
27 | 3.2.8 | Remove abandoned Storm Water Lines and headwalls and dispose off site | m | 1898.7814 | 83 | 83 | 29.34 | 2435.22 | 2435.22 |  |  | 0% |  | 0% | 83 | 100% | 83 | 100% | 83 | 100% | 83 | 100% | 83 | 100% | 83 | 100% | 0 | 0 | 2435.22 | 2435.22 | 2435.22 | 2435.22 | 2435.22 | 2435.22
28 | 3.3 | Earthworks
29 | 3.3.1 | Strip and stockpile topsoil from areas of excavation and filling in accordance with the specification (measured as a solid volume, calculated based on an average 100mm natural topsoil depth) | m3 | 7854.7 | 916 | 916 | 10.93 | 10011.88 | 10011.88 |  | 916 | 100% | 916 | 100% | 916 | 100% | 916 | 100% | 916 | 100% | 916 | 100% | 916 | 100% | 916 | 100% | 10011.88 | 10011.88 | 10011.88 | 10011.88 | 10011.88 | 10011.88 | 10011.88 | 10011.88
30 | 3.3.2 | Respread topsoil in accordance with the specification (measured as a solid volume, calculated based on an average 100mm natural topsoil depth) | m3 | 4855.84 | 341 | 341 | 18.15 | 6189.15 | 6189.15 |  |  | 0% |  | 0% | 30 | 8.798% | 90 | 26.39% | 341 | 100% | 341 | 100% | 341 | 100% | 341 | 100% | 0 | 0 | 544.5 | 1633.5 | 6189.15 | 6189.15 | 6189.15 | 6189.15
31 | 3.3.3 | Remove from site unused grip material as directed (Provisional) |  | 7518.125 | 575 | 575 | 13.08 | 7521 | 7521 |  | 575 | 100% | 575 | 100% | 575 | 100% | 575 | 100% | 575 | 100% | 575 | 100% | 575 | 100% | 575 | 100% | 7521 | 7521 | 7521 | 7521 | 7521 | 7521 | 7521 | 7521
32 | 3.3.4 | Cut to fill including but not limited to, moisture control and compaction as specified (in-place compacted volume of filling) | m3 | 16994.988 | 2388 | 2388 | 9.09 | 21706.92 | 21706.92 |  |  | 0% |  | 0% | 600 | 25.13% | 2388 | 100% | 2388 | 100% | 2388 | 100% | 2388 | 100% | 2388 | 100% | 0 | 0 | 5454 | 21706.92 | 21706.92 | 21706.92 | 21706.92 | 21706.92
33 | 3.3.5 | Imported Fill material including but not limited to, moisture control and compaction as specified (in-place compacted volume of filling) | m3 | 54420.0654 | 4030 | 4030 | 17.21 | 69356.3 | 69356.3 |  |  | 0% | 4030 | 100% | 4030 | 100% | 4030 | 100% | 4030 | 100% | 4030 | 100% | 4030 | 100% | 4030 | 100% | 0 | 69356.3 | 69356.3 | 69356.3 | 69356.3 | 69356.3 | 69356.3 | 69356.3
34 | 3.3.6 | Cut to spoil including but not limited to loading, transportation and tip fees (Provisional) | m2 | 1743.3333 | 100 | 100 | 17.43 | 1743 | 1743 |  |  | 0% |  | 0% |  | 0% |  | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 0 | 0 | 0 | 0 | 1743 | 1743 | 1743 | 1743
35 | 3.3.7 | Removal of unsuitable material including excavation, filling and spoiling material (provisional) |  | 7669.674 | 150 | 150 | 51.13 | 7669.5 | 7669.5 |  |  | 0% | 150 | 100% | 150 | 100% | 150 | 100% | 150 | 100% | 150 | 100% | 150 | 100% | 150 | 100% | 0 | 7669.5 | 7669.5 | 7669.5 | 7669.5 | 7669.5 | 7669.5 | 7669.5
36 | 3.3.8 | Grass seeding to disturbed areas as directed by the Superintendent. | m2 | 7870.62 | 2791 | 2791 | 3.59 | 10019.69 | 10019.69 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2791 | 100% | 2791 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 10019.69 | 10019.69
|  | Sub-Total Earthworks | [5 empty] | 192973.92
37 | 4 | ROADWORKS
38 | 4.1 | Sub grade preparation as specified including, but not limited to scarifying, moisture control, blending, spreading, compaction and trimming | m2 | 40673.8203 | 19963 | 19963 | 2.6 | 51903.8 | 51903.8 |  |  | 0% | 2350 | 11.77% | 6810 | 34.11% | 7950 | 39.82% | 19963 | 100% | 19963 | 100% | 19963 | 100% | 19963 | 100% | 0 | 6110 | 17706 | 20670 | 51903.8 | 51903.8 | 51903.8 | 51903.8
| 4.2 | New Pavements
Pavement material complete in place including, but not limited to supply, spreading, moisture control, compaction, and trimming as specified (solid measure)
39 | 4.2.1 | Pavement A1
40 | 4.2.1.1 | Base Course - 125mm Type 2.1 | m3 | 34918.48 | 555 | 555 | 80.17 | 44494.35 | 44494.35 |  |  | 0% |  | 0% |  | 0% | 399 | 71.89% | 555 | 100% | 555 | 100% | 555 | 100% | 555 | 100% | 0 | 0 | 0 | 31987.83 | 44494.35 | 44494.35 | 44494.35 | 44494.35
41 | 4.2.1.2 | Sub-base Course - 100mm Type 2.3 | m3 | 27152.234 | 444 | 444 | 77.92 | 34596.48 | 34596.48 |  |  | 0% |  | 0% | 193 | 43.47% | 319 | 71.85% | 444 | 100% | 444 | 100% | 444 | 100% | 444 | 100% | 0 | 0 | 15038.56 | 24856.48 | 34596.48 | 34596.48 | 34596.48 | 34596.48
42 | 4.2.3 | Pavement A2 - Roadways
43 | 4.2.3.1 | Base Course - 125mm Type 2.1 | m3 | 2390.8148 | 38 | 38 | 80.17 | 3046.46 | 3046.46 |  |  | 0% |  | 0% |  | 0% | 38 | 100% | 38 | 100% | 38 | 100% | 38 | 100% | 38 | 100% | 0 | 0 | 0 | 3046.46 | 3046.46 | 3046.46 | 3046.46 | 3046.46
44 | 4.2.3.2 | Sub-base Course - 100mm Type 2.3 | m3 | 1895.7641 | 31 | 31 | 77.92 | 2415.52 | 2415.52 |  |  | 0% |  | 0% |  | 0% | 31 | 100% | 31 | 100% | 31 | 100% | 31 | 100% | 31 | 100% | 0 | 0 | 0 | 2415.52 | 2415.52 | 2415.52 | 2415.52 | 2415.52
45 | 4.2.4 | Pavement A2 - Rental Carpark
46 | 4.2.4.1 | Base Course - 125mm Type 2.1 | m3 | 21643.166 | 344 | 344 | 80.17 | 27578.48 | 27578.48 |  |  | 0% | 344 | 100% | 344 | 100% | 344 | 100% | 344 | 100% | 344 | 100% | 344 | 100% | 344 | 100% | 0 | 27578.48 | 27578.48 | 27578.48 | 27578.48 | 27578.48 | 27578.48 | 27578.48
47 | 4.2.4.2 | Sub-Base Course - 100mm Type 2.3 | m3 | 16817.2621 | 275 | 275 | 77.92 | 21428 | 21428 |  |  | 0% | 275 | 100% | 275 | 100% | 275 | 100% | 275 | 100% | 275 | 100% | 275 | 100% | 275 | 100% | 0 | 21428 | 21428 | 21428 | 21428 | 21428 | 21428 | 21428
48 | 4.2.5 | Pavement B - Roadway
49 | 4.2.5.1 | Base Course - 150mm Type 2.1 | m3 | 4844.5459 | 77 | 77 | 80.17 | 6173.09 | 6173.09 |  |  | 0% |  | 0% |  | 0% |  | 0% | 77 | 100% | 77 | 100% | 77 | 100% | 77 | 100% | 0 | 0 | 0 | 0 | 6173.09 | 6173.09 | 6173.09 | 6173.09
50 | 4.2.5.2 | Upper Sub-Base Course - 150mm Type 2.3 | m3 | 4708.8334 | 77 | 77 | 77.92 | 5999.84 | 5999.84 |  |  | 0% |  | 0% |  | 0% |  | 0% | 77 | 100% | 77 | 100% | 77 | 100% | 77 | 100% | 0 | 0 | 0 | 0 | 5999.84 | 5999.84 | 5999.84 | 5999.84
51 | 4.2.5.3 | Lower Sub-Base Course - 150mm Type 2.3 | m3 | 4708.8334 | 77 | 77 | 77.92 | 5999.84 | 5999.84 |  |  | 0% |  | 0% |  | 0% |  | 0% | 77 | 100% | 77 | 100% | 77 | 100% | 77 | 100% | 0 | 0 | 0 | 0 | 5999.84 | 5999.84 | 5999.84 | 5999.84
52 | 4.2.6 | Pavement B - Public Carpark including Road 3
53 | 4.2.6.1 | Base Course - 150mm Type 2.1 | m3 | 21139.8366 | 336 | 336 | 80.17 | 26937.12 | 26937.12 |  |  | 0% |  | 0% |  | 0% | 156 | 46.43% | 336 | 100% | 336 | 100% | 336 | 100% | 336 | 100% | 0 | 0 | 0 | 12506.52 | 26937.12 | 26937.12 | 26937.12 | 26937.12
54 | 4.2.6.2 | Upper Sub Base Course - 150mm Type 2.3 | m3 | 20547.6366 | 336 | 336 | 77.92 | 26181.12 | 26181.12 |  |  | 0% |  | 0% |  | 0% | 125 | 37.2% | 336 | 100% | 336 | 100% | 336 | 100% | 336 | 100% | 0 | 0 | 0 | 9740 | 26181.12 | 26181.12 | 26181.12 | 26181.12
55 | 4.2.6.3 | Lower Base Course - 150mm Type 2.3 | m3 | 20547.6366 | 336 | 336 | 77.93 | 26184.48 | 26184.48 |  |  | 0% |  | 0% |  | 0% |  | 0% | 336 | 100% | 336 | 100% | 336 | 100% | 336 | 100% | 0 | 0 | 0 | 0 | 26184.48 | 26184.48 | 26184.48 | 26184.48
56 | 4.3 | Final Trim to Pavement | m2 | 40742.3911 | 16547 | 16547 | 3.14 | 51957.58 | 51957.58 |  |  | 0% |  | 0% | 3200 | 19.34% | 7950 | 48.04% | 16547 | 100% | 16547 | 100% | 16547 | 100% | 16547 | 100% | 0 | 0 | 10048 | 24963 | 51957.58 | 51957.58 | 51957.58 | 51957.58
57 | 4.4 | Concrete Works
The following concrete works rates are to include an allowance for compaction, finishing and testing
58 | 4.4.1 | Concrete kerb and kerb and channel as specified complete in place including, but not limited to transitions at kerb ends, ramps and gullies, and testing
59 | 4.4.1.1 | Barrier Kerb & Channel Type B1 600mm wide | m | 27475.5126 | 670 | 670 | 52.25 | 35007.5 | 35007.5 |  |  | 0% |  | 0% | 310 | 46.27% | 318 | 47.46% | 670 | 100% | 670 | 100% | 670 | 100% | 670 | 100% | 0 | 0 | 16197.5 | 16615.5 | 35007.5 | 35007.5 | 35007.5 | 35007.5
60 | 4.4.1.2 | Barrier Kerb Type B2 | m | 10820.3905 | 372 | 372 | 37.06 | 13786.32 | 13786.32 |  |  | 0% |  | 0% |  | 0% |  | 0% | 372 | 100% | 372 | 100% | 372 | 100% | 372 | 100% | 0 | 0 | 0 | 0 | 13786.32 | 13786.32 | 13786.32 | 13786.32
61 | 4.4.1.3 | Semi Mountable Kerb Type SM4 | m | 858.4031 | 207 | 207 | 31 | 6417 | 6417 |  |  | 0% |  | 0% | 90 | 43.48% | 90 | 43.48% | 165 | 79.71% | 197 | 95.17% | 197 | 95.17% | 207 | 100% | 0 | 0 | 2790 | 2790 | 5115 | 6107 | 6107 | 6417
62 | 4.4.2 | Kerb Ramp | No. | 2291 | 5 | 5 | 583.86 | 2919.3 | 2919.3 |  |  | 0% |  | 0% |  | 0% | 3 | 60% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 0 | 0 | 0 | 1751.58 | 2919.3 | 2919.3 | 2919.3 | 2919.3
63 | 4.4.3 | Raised Threshold Pedestrian Crossing | m2 | 11276.4621 | 161 | 161 | 89.25 | 14369.25 | 14369.25 |  |  | 0% |  | 0% |  | 0% |  | 0% | 161 | 100% | 161 | 100% | 161 | 100% | 161 | 100% | 0 | 0 | 0 | 0 | 14369.25 | 14369.25 | 14369.25 | 14369.25
64 | 4.4.4 | Additional concrete works
65 | 4.4.4.1 | Concrete Footpaths 2.45m wide | m2 | 10775.0386 | 195 | 195 | 70.41 | 13729.95 | 13729.95 |  |  | 0% |  | 0% |  | 0% |  | 0% | 195 | 100% | 195 | 100% | 195 | 100% | 195 | 100% | 0 | 0 | 0 | 0 | 13729.95 | 13729.95 | 13729.95 | 13729.95
66 | 4.4.4.2 | Concrete Footpaths 2.5m wide | m2 | 1270.902 | 23 | 23 | 70.41 | 1619.43 | 1619.43 |  |  | 0% |  | 0% |  | 0% | 23 | 100% | 23 | 100% | 23 | 100% | 23 | 100% | 23 | 100% | 0 | 0 | 0 | 1619.43 | 1619.43 | 1619.43 | 1619.43 | 1619.43
67 | 4.4.4.3 | Concrete Footpaths 3m wide | m2 | 16575.151 | 439 | 439 | 70.41 | 30909.99 | 30909.99 |  |  | 0% |  | 0% |  | 0% | 403.5 | 91.91% | 403.5 | 91.91% | 439 | 100% | 439 | 100% | 439 | 100% | 0 | 0 | 0 | 28410.435 | 28410.435 | 30909.99 | 30909.99 | 30909.99
68 | 4.4.4.4 | Concrete Infill to Median Islands to carparks and round about island, complete in place | m2 | 3766.174 | 102 | 102 | 69.35 | 7073.7 | 7073.7 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 102 | 100% | 102 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 7073.7 | 7073.7
69 | 4.4.4.5 | Wheelstops, complete in place (in accordance with AS2890.1) | No. | 13301.3333 | 86 | 86 | 197.08 | 16948.88 | 16948.88 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 86 | 100% | 86 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 16948.88 | 16948.88
70 | 4.5 | Surfacing Works
71 | 4.5.1 | Existing Public Carpark
72 | 4.5.1.1 | First Seal: 7mm CRS60 | m2 | 11739.105 | 2490 | 2490 | 6.01 | 14964.9 | 14964.9 |  |  | 0% |  | 0% |  | 0% | 2490 | 100% | 2490 | 100% | 2490 | 100% | 2490 | 100% | 2490 | 100% | 0 | 0 | 0 | 14964.9 | 14964.9 | 14964.9 | 14964.9 | 14964.9
73 | 4.5.1.2 | Second Seal: 40mm AC Surfacing, (DG10) complete in place, including but not limited to supply, compaction and prime coat) | tonne | 71463 | 249 | 249 | 294.18 | 73250.82 | 73250.82 |  |  | 0% |  | 0% |  | 0% |  | 0% | 249 | 100% | 249 | 100% | 249 | 100% | 249 | 100% | 0 | 0 | 0 | 0 | 73250.82 | 73250.82 | 73250.82 | 73250.82
74 | 4.6.2 | Roadways and New Carpark
75 | 4.6.2.1 | First Seal: 7mm CRS60 Primerseal | m2 | 48375.4845 | 10261 | 10261 | 6.01 | 61668.61 | 61668.61 |  |  | 0% |  | 0% | 3200 | 31.19% | 7950 | 77.48% | 10261 | 100% | 10261 | 100% | 10261 | 100% | 10261 | 100% | 0 | 0 | 19232 | 47779.5 | 61668.61 | 61668.61 | 61668.61 | 61668.61
76 | 4.6.2.2 | Second Seal: 40mm AC Surfacing, (DG10) complete in place, including but not limited to supply, compaction and prime coat) | tonne | 294462 | 1026 | 1026 | 294.2 | 301849.2 | 301849.2 |  |  | 0% |  | 0% |  | 0% |  | 0% | 195 | 19.01% | 1026 | 100% | 1026 | 100% | 1026 | 100% | 0 | 0 | 0 | 0 | 57369 | 301849.2 | 301849.2 | 301849.2
77 | 4.7 | Signage and Pavement Marking
78 | 4.7.1 | Signage and pavement marking, complete in place. All work to be in accordance with the requirements of AS 1742 Manual of Uniform Traffic Control Devices (Provisional Sum) | Item | 7660 | 1 | 1 | 9760.73 | 9760.73 | 9760.73 |  |  | 0% |  | 0% |  | 0% |  | 0% | 0.25 | 25% | 0.25 | 25% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 2440.1825 | 2440.1825 | 9760.73 | 9760.73
79 | 4.7.2 | Signage complete in place including supply and installation. All work to be in accordance with the requirements of AS 1742 Manual of Uniform Traffic Control Devices(Provisional Sum) | Item | 1682.1 | 1 | 1 | 2143.41 | 2143.41 | 2143.41 |  |  | 0% |  | 0% |  | 0% |  | 0% | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 1071.705 | 2143.41 | 2143.41 | 2143.41
|  | Sub-Total Roadworks | [5 empty] | 941315.15
80 | 5 | STORMWATER DRAINAGE
81 | 5.1 | Pipework
Reinforced concrete pipework complete in place and including, but not limited to, supply, transportation, excavation, benching and or shoring as required, bedding, laying, jointing, removal of spoil as specified, backfilling, moisture control and compaction
82 | 5.1.1 | 375mm dia Class 2 RRJ | m | 10207.4201 | 82.8 | 82.8 | 157.09 | 13007.05 | 13007.052 |  |  | 0% | 48.83 | 58.97% | 66.73 | 80.59% | 66.73 | 80.59% | 82.8 | 100% | 82.8 | 100% | 82.8 | 100% | 82.8 | 100% | 0 | 7670.7035 | 10482.6141 | 10482.6141 | 13007.05 | 13007.05 | 13007.05 | 13007.05
83 | 5.1.2 | 375mm dia Class 3 RRJ | m | 6395.1273 | 46.8 | 46.8 | 174.13 | 8149.28 | 8149.284 |  |  | 0% |  | 0% | 46.8 | 100% | 46.8 | 100% | 46.8 | 100% | 46.8 | 100% | 46.8 | 100% | 46.8 | 100% | 0 | 0 | 8149.28 | 8149.28 | 8149.28 | 8149.28 | 8149.28 | 8149.28
84 | 5.1.3 | 450mm dia Class 2 RRJ | m | 2889.8236 | 20.4 | 20.4 | 180.51 | 3682.4 | 3682.404 |  |  | 0% | 19.94 | 97.75% | 20.4 | 100% | 20.4 | 100% | 20.4 | 100% | 20.4 | 100% | 20.4 | 100% | 20.4 | 100% | 0 | 3599.3655 | 3682.4 | 3682.4 | 3682.4 | 3682.4 | 3682.4 | 3682.4
85 | 5.1.4 | 450mm dia Class 3 RRJ | m | 3883.4212 | 21.6 | 21.6 | 229.1 | 4948.56 | 4948.56 |  |  | 0% |  | 0% | 14.6 | 67.59% | 14.6 | 67.59% | 21.6 | 100% | 21.6 | 100% | 21.6 | 100% | 21.6 | 100% | 0 | 0 | 3344.86 | 3344.86 | 4948.56 | 4948.56 | 4948.56 | 4948.56
86 | 5.2 | Drainage Structures
As nominated on the drawings complete in place and including, but not limited to, supply, transportation, excavation, reinforcement, benching, rendering, 100mm dia slotted uPVC weepholes, step irons, covers and grates as detailed, backfilling, moisture control and compaction
87 | 5.2.1 | Manholes as per IPWEA Std Dwg D-0010 and IPWEA Std Dwg D-0011 or WRC Std Dwg
88 | 5.2.1.1 | 1050mm dia Access Chamber | No. | 11816.8 | 4 | 4 | 3764.38 | 15057.52 | 15057.52 |  |  | 0% |  | 0% |  | 0% | 1 | 25% | 1 | 25% | 1 | 25% | 1 | 25% | 1 | 25% | 0 | 0 | 0 | 3764.38 | 3764.38 | 3764.38 | 3764.38 | 3764.38
89 | 5.2.1.2 | 900x900 mm Access Chamber | No. | 9774.684 | 9 | 9 | 1383.93 | 12455.37 | 12455.37 |  |  | 0% |  | 0% | 7 | 77.78% | 9 | 100% | 9 | 100% | 9 | 100% | 9 | 100% | 9 | 100% | 0 | 0 | 9687.51 | 12455.37 | 12455.37 | 12455.37 | 12455.37 | 12455.37
90 | 5.2.1.3 | 4/10 - 900x900 Manhole | Item | 2920.76 | 1 | 1 | 3721.77 | 3721.77 | 3721.77 |  |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 3721.77 | 3721.77 | 3721.77 | 3721.77 | 3721.77
91 | 5.3.1 | Kerb Inlets
92 | 5.3.1.1 | On Grade (L)
93 |  | 2.4m Lintel | No. | 8428.8 | 4 | 4 | 2685.09 | 10740.36 | 10740.36 |  |  | 0% |  | 0% |  | 0% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 0 | 0 | 0 | 10740.36 | 10740.36 | 10740.36 | 10740.36 | 10740.36
94 | 5.3.1.2 | On Grade (R) |  | 0
95 |  | 2.4m Lintel | No. | 10536 | 5 | 5 | 2685.09 | 13425.45 | 13425.45 |  |  | 0% |  | 0% |  | 0% | 2 | 40% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 0 | 0 | 0 | 5370.18 | 13425.45 | 13425.45 | 13425.45 | 13425.45
96 | 5.2.3 | Precast Headwalls
97 | 5.2.3.1 | Humes Precast Headwall or equivalent for 375mm pipe | No. | 1694 | 2 | 2 | 1079.29 | 2158.58 | 2158.58 |  |  | 0% | 0.5 | 25% | 0.5 | 25% | 1 | 50% | 1 | 50% | 1 | 50% | 1 | 50% | 1 | 50% | 0 | 539.645 | 539.645 | 1079.29 | 1079.29 | 1079.29 | 1079.29 | 1079.29
98 | 5.2.3.2 | Humes Precast Headwall or equivalent for 450mm pipe | No. | 1980 | 2 | 2 | 1261.5 | 2523 | 2523 |  |  | 0% | 0.65 | 32.5% | 0.65 | 32.5% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 819.975 | 819.975 | 2523 | 2523 | 2523 | 2523 | 2523
99 | 5.2.4 | Rock Protection at Outlet Drains (300 Deep) | m3 | 710.64 | 4.7 | 4.7 | 192.67 | 905.55 | 905.549 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 4.7 | 100% | 4.7 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 905.55 | 905.55
|  | Sub-Total Stormwater Drainage | [5 empty] | 90774.89
100 | 6 | ELECTRICAL AND LIGHTING
101 | 6.1 | Trenching for electrical, lighting and communications service Conduits, complete in place, including trenching, backfilling, reinstatment of surface and maintence of trench while open. (trench configuration not specified) | m | 32591.0822 | 940 | 940 | 44.18 | 41529.2 | 41529.2 |  |  | 0% | 270 | 28.72% | 745 | 79.26% | 940 | 100% | 940 | 100% | 940 | 100% | 940 | 100% | 940 | 100% | 0 | 11928.6 | 32914.1 | 41529.2 | 41529.2 | 41529.2 | 41529.2 | 41529.2
102 | 6.2 | Supply and installation of electrical conduits (100 diameter) complete in place including bedding, conuits and marker tape | m | 3342.9955 | 613 | 613 | 6.95 | 4260.35 | 4260.35 |  |  | 0% | 170 | 27.73% | 588 | 95.92% | 613 | 100% | 613 | 100% | 613 | 100% | 613 | 100% | 613 | 100% | 0 | 1181.5 | 4086.6 | 4260.35 | 4260.35 | 4260.35 | 4260.35 | 4260.35
103 | 6.3 | Supply and installation of electrical conduits (40 diameter) complete in place including bedding, conuits and marker tape |  | 1461.5 | 500 | 500 | 3.72 | 1860 | 1860 |  |  | 0% | 220 | 44% | 330 | 66% | 500 | 100% | 500 | 100% | 500 | 100% | 500 | 100% | 500 | 100% | 0 | 818.4 | 1227.6 | 1860 | 1860 | 1860 | 1860 | 1860
104 | 6.4 | Supply and installation of communication conduits (100 diameter) complete in place including bedding, conuits and marker tape | m | 1673.73 | 270 | 270 | 7.9 | 2133 | 2133 |  |  | 0% | 30 | 11.11% | 270 | 100% | 270 | 100% | 270 | 100% | 270 | 100% | 270 | 100% | 270 | 100% | 0 | 237 | 2133 | 2133 | 2133 | 2133 | 2133 | 2133
105 | 6.5 | Installation of electrical pit, complete in place, including trenching, bedding, supplying, laying, marker tape/hard cover and backfill. (trench configuration not specified) | No. | 16246.75 | 13 | 13 | 1592.49 | 20702.37 | 20702.37 |  |  | 0% |  | 0% |  | 0% | 8 | 61.54% | 13 | 100% | 13 | 100% | 13 | 100% | 13 | 100% | 0 | 0 | 0 | 12739.92 | 20702.37 | 20702.37 | 20702.37 | 20702.37
106 | 6.6 | Installation of communications pit, complete in place, including trenching, bedding, supplying, laying, marker tape/hard cover and backfill. (trench configuration not specified) | No. | 12308 | 8 | 8 | 1960.43 | 15683.44 | 15683.44 |  |  | 0% |  | 0% |  | 0% | 5 | 62.5% | 8 | 100% | 8 | 100% | 8 | 100% | 8 | 100% | 0 | 0 | 0 | 9802.15 | 15683.44 | 15683.44 | 15683.44 | 15683.44
107 | 6.7 | Supply and installation of distribution board complete in place including all ground works, plinth and circuit breakers | No. | 12010 | 1 | 1 | 15303.71 | 15303.71 | 15303.71 |  |  | 0% |  | 0% |  | 0% |  | 0% | 0.75 | 75% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 11477.7825 | 15303.71 | 15303.71 | 15303.71
108 | 6.8 | Supply and installation of electrical and communication conduits to gate controllers from nearest pits including all trenching and coordination with gate installer | No. | 4689.65 | 5 | 5 | 1195.15 | 5975.75 | 5975.75 |  |  | 0% |  | 0% |  | 0% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 0 | 0 | 0 | 5975.75 | 5975.75 | 5975.75 | 5975.75 | 5975.75
109 | 6.9 | Supply and installation of electrical and communication conduits to ticket machines from nearest pits including all trenching and coordination with ticket machine installer | No. | 1113.82 | 2 | 2 | 709.64 | 1419.28 | 1419.28 |  |  | 0% |  | 0% |  | 0% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 1419.28 | 1419.28 | 1419.28 | 1419.28 | 1419.28
110 | 6.1 | Supply and installation of new car park lights and poles to match existing including footing installation, pole and all cabling from distribution board | No. | 23218.6 | 4 | 4 | 7396.56 | 29586.24 | 29586.24 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 4 | 100% | 4 | 100% | 4 | 100% | 0 | 0 | 0 | 0 | 0 | 29586.24 | 29586.24 | 29586.24
111 | 6.11 | Supply and installation of services pillar at car wash bays P1, P2,P3 incl socket outlets (IP56), Safety Switch and Hose Cock and all cabling back to distribution board including all cabling back to distribution board | No. | 4630 | 3 | 3 | 5899.76 | 17699.28 | 17699.28 |  |  | 0% |  | 0% |  | 0% | 1 | 33.33% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 0 | 0 | 0 | 5899.76 | 17699.28 | 17699.28 | 17699.28 | 17699.28
|  | Sub-Total Electrical & Lighting | [5 empty] | 156152.62
112 | 7 | MISCELLANEOUS
113 | 7.1 | Existing Services
114 |  | Service conduit crossings and alterations to existing services, as required, complete in place.
| 7.1.1 | Water | PS |  | 1 | 1 | 1000 | 1000 | 1000 |  |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000
| 7.1.2 | Sewer | PS |  | 1 | 1 | 5000 | 5000 | 5000 |  |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 5000
115 | 7.1.3 | Existing above ground services to be raised to compliment proposed earthworks level (50mm) | Item | 2499 | 1 | 1 | 3184.34 | 3184.34 | 3184.34 |  |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 3184.34 | 3184.34 | 3184.34 | 3184.34
116 | 7.2 | Fencing & Vehicle Barriers
117 | 7.2.1 | Vehicle Barrier - CCA Treated Log Barrier as per IPWEAQ Standard Drawing SEQ G-042
118 | 7.2.1.1 | Trafficked roadways and busbays within the extents of stage 1 boundary | m | 16838.64 | 624 | 624 | 34.39 | 21459.36 | 21459.36 |  |  | 0% |  | 0% |  | 0% |  | 0% | 305 | 48.88% | 624 | 100% | 624 | 100% | 624 | 100% | 0 | 0 | 0 | 0 | 10488.95 | 21459.36 | 21459.36 | 21459.36
119 | 7.2.1.2 | Extension of Trafficked roadways beyond stage 1 boundary. (prevent vehicles leaving roadway and parking outside formal carpark) | m | 19159.35 | 710 | 710 | 34.39 | 24416.9 | 24416.9 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 710 | 100% | 710 | 100% | 710 | 100% | 0 | 0 | 0 | 0 | 0 | 24416.9 | 24416.9 | 24416.9
120 | 7.2.1.3 | Public Carpark | m | 5936.7 | 220 | 220 | 34.39 | 7565.8 | 7565.8 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 162 | 73.64% | 220 | 100% | 220 | 100% | 0 | 0 | 0 | 0 | 0 | 5571.18 | 7565.8 | 7565.8
121 | 7.2.3.1 | Pedestrian Safety Fence | m | 1500 | 15 | 15 | 127.42 | 1911.3 | 1911.3 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 15 | 100% | 15 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1911.3 | 1911.3
122 | 7.2.3.2 | Supply & Installation of Fixed Bollards | No. | 210 | 4 | 4 | 66.9 | 267.6 | 267.6 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 4 | 100% | 4 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 267.6 | 267.6
| 7.3 | Construction Management & Mitigation of Works
123 | 7.3.1 | Temporary Fencing & Signage | Item | 12768 | 1 | 1 | 16269.59 | 16269.59 | 16269.59 |  | 0.1 | 10% | 0.3 | 30% | 0.6 | 60% | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1626.959 | 4880.877 | 9761.754 | 13015.672 | 16269.59 | 16269.59 | 16269.59 | 16269.59
|  | Sub-Total Miscellaneous | [5 empty] | 81074.89
124 |  | SCHEDULE B - SEWER WORKS
125 | 1 | EARTHWORKS
126 | 1.1 | Clearing & Grubbing | m2 | 4482 | 550 | 550 | 4.57 | 2513.5 | 2513.5 |  | 550 | 100% | 550 | 100% | 550 | 100% | 550 | 100% | 550 | 100% | 550 | 100% | 550 | 100% | 550 | 100% | 2513.5 | 2513.5 | 2513.5 | 2513.5 | 2513.5 | 2513.5 | 2513.5 | 2513.5
127 | 1.2 | Strip & Stockpile Topsoil | m3 | 471.625 | 55 | 55 | 10.93 | 601.15 | 601.15 |  | 55 | 100% | 55 | 100% | 55 | 100% | 55 | 100% | 55 | 100% | 55 | 100% | 55 | 100% | 55 | 100% | 601.15 | 601.15 | 601.15 | 601.15 | 601.15 | 601.15 | 601.15 | 601.15
128 | 1.3 | Placement of Topsoil | m2 | 398.72 | 28 | 28 | 18.15 | 508.2 | 508.2 |  |  | 0% |  | 0% |  | 0% |  | 0% | 28 | 100% | 28 | 100% | 28 | 100% | 28 | 100% | 0 | 0 | 0 | 0 | 508.2 | 508.2 | 508.2 | 508.2
129 | 1.4 | Disposal of excess topsoil as directed | m3 | 353.025 | 27 | 27 | 16.66 | 449.82 | 449.82 |  | 27 | 100% | 27 | 100% | 27 | 100% | 27 | 100% | 27 | 100% | 27 | 100% | 27 | 100% | 27 | 100% | 449.82 | 449.82 | 449.82 | 449.82 | 449.82 | 449.82 | 449.82 | 449.82
130 | 1.5 | Gravel access and hardstand from airport pit min CBR10 300 thick(Provisional) | m3 | 2999.374 | 165 | 165 | 18.18 | 2999.7 | 2999.7 |  | 80 | 48.48% | 165 | 100% | 165 | 100% | 165 | 100% | 165 | 100% | 165 | 100% | 165 | 100% | 165 | 100% | 1454.4 | 2999.7 | 2999.7 | 2999.7 | 2999.7 | 2999.7 | 2999.7 | 2999.7
|  | Sub-Total Earthworks | [5 empty] | 7072.37
131 |  | SEWER WORKS
132 | 2.1 | Gravity Sewerage
133 | 2.1.3 | Connection of existing DN100 AC gravity sewers to new ssanitary drain | No. | 4800 | 2 | 2 | 4317.3 | 8634.6 | 8634.6 |  |  | 0% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 8634.6 | 8634.6 | 8634.6 | 8634.6 | 8634.6 | 8634.6 | 8634.6
134 | 2.1.4 | Decommision existing Septic Tanks and associated pipework (excluding demolition of tanks - refer schedule A) | Item | 4000 | 2 | 2 | 2548.49 | 5096.98 | 5096.98 |  |  | 0% |  | 0% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 5096.98 | 5096.98 | 5096.98 | 5096.98 | 5096.98 | 5096.98
135 | 2.2 | Sewage Pump Station
136 | 2.2.1 | Supply & delivery of Proprietry PE Pump Station (incl pumps, pipework, electrical controls etc) | No. | 23520 | 1 | 1 | 29970.29 | 29970.29 | 29970.29 |  |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 29970.29 | 29970.29 | 29970.29 | 29970.29 | 29970.29 | 29970.29 | 29970.29
137 | 2.2.2 | Installation of Sewerage Pump Station (including concrete ballast) | Item | 4100 | 1 | 1 | 5224.41 | 5224.41 | 5224.41 |  |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 5224.41 | 5224.41 | 5224.41 | 5224.41 | 5224.41 | 5224.41 | 5224.41
138 | 2.2.3 | Connection of gravity sewer pipe | Item | 2400 | 1 | 1 | 3058.19 | 3058.19 | 3058.19 |  |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 3058.19 | 3058.19 | 3058.19 | 3058.19 | 3058.19 | 3058.19 | 3058.19
139 | 2.2.4 | Supply and construction of DN50 vent | No. | 1800 | 1 | 1 | 2293.64 | 2293.64 | 2293.64 |  |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 2293.64 | 2293.64 | 2293.64 | 2293.64 | 2293.64
140 | 2.2.5 | Electrical connections from mains supply | Item | 3600 | 1 | 1 | 4587.29 | 4587.29 | 4587.29 |  |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 4587.29 | 4587.29 | 4587.29 | 4587.29 | 4587.29 | 4587.29 | 4587.29
141 | 2.2.6 | Commisioning Pump Station and electrical controls | Item | 2000 | 1 | 1 | 2548.49 | 2548.49 | 2548.49 |  |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 2548.49 | 2548.49 | 2548.49 | 2548.49 | 2548.49 | 2548.49 | 2548.49
142 | 2.3 | Rising Main
143 | 2.3.1 | Supply and construction of DN32 PE rising main (40OD PE100 PN16) incl 3 No. tees, ball vavles, pits for future STP connection | m | 14326.4 | 215 | 215 | 65.56 | 14095.4 | 14095.4 |  | 95 | 44.19% | 215 | 100% | 215 | 100% | 215 | 100% | 215 | 100% | 215 | 100% | 215 | 100% | 215 | 100% | 6228.2 | 14095.4 | 14095.4 | 14095.4 | 14095.4 | 14095.4 | 14095.4 | 14095.4
144 | 2.3.2 | Connection to new wet weather storage tanks | Item | 1500 | 1 | 1 | 1911.37 | 1911.37 | 1911.37 |  |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 1911.37 | 1911.37 | 1911.37 | 1911.37 | 1911.37 | 1911.37 | 1911.37
145 | 2.4 | Water Supply
146 | 2.4.1 | Supply and construction of DN32 PE water supply main (40OD PE100 PN16) to carpark hosecocks. | m | 13992.5949 | 210 | 210 | 119.86 | 25170.6 | 25170.6 |  | 130 | 61.9% | 210 | 100% | 210 | 100% | 210 | 100% | 210 | 100% | 210 | 100% | 210 | 100% | 210 | 100% | 15581.8 | 25170.6 | 25170.6 | 25170.6 | 25170.6 | 25170.6 | 25170.6 | 25170.6
147 | 2.4.2 | Supply and installation of DN32 RPZD in enclosure complete | No. | 2074.4 | 1 | 1 | 3731.59 | 3731.59 | 3731.59 |  |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 3731.59 | 3731.59 | 3731.59 | 3731.59 | 3731.59
148 | 2.4.3 | Supply, installation & connection of hosecocks to carwash Service Pillars complete (excluding pillars, refer Schedule A, 6.11) | No. | 735 | 3 | 3 | 440.73 | 1322.19 | 1322.19 |  |  | 0% |  | 0% |  | 0% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 0 | 0 | 0 | 1322.19 | 1322.19 | 1322.19 | 1322.19 | 1322.19
149 | 2.4.4 | Supply and construct DN25 water supply main (32OD PE100 PN16) to STP | m | 4822.6483 | 75 | 75 | 115.67 | 8675.25 | 8675.25 |  |  | 0% | 75 | 100% | 75 | 100% | 75 | 100% | 75 | 100% | 75 | 100% | 75 | 100% | 75 | 100% | 0 | 8675.25 | 8675.25 | 8675.25 | 8675.25 | 8675.25 | 8675.25 | 8675.25
150 | 2.5 | Miscellaneous
151 | 2.5.1 | Gate to STP Access | item | 1500.109 | 1 | 1 | 654.96 | 654.96 | 654.96 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 654.96 | 654.96
|  | Sub-Total Sewer Works | [5 empty] | 116975.25
| 3 | SEWERAGE TREATMENT AND DISPOSAL
| 3.3 | Supply and installation on hardstand of 30,000L wet weather storage tanks, including balance pipe, fitting and hold downs complete. (PC Item) | PS |  | 1 | 1 | 39100 | 39100 | 39100 |  | 0.358 | 35.8% | 0.358 | 35.8% | 0.4231 | 42.31% | 0.4231 | 42.31% | 0.4231 | 42.31% | 0.5254 | 52.54% | 0.5254 | 52.54% | 0.5254 | 52.54% | 13997.8 | 13997.8 | 16543.21 | 16543.21 | 16543.21 | 20543.14 | 20543.14 | 20543.14
|  | Sub-Total Sewerage Treatment and Disposal | [5 empty] | 39100
|  | Sub-Total Sewer Works |  | 1426642.6385 |  |  |  | 163147.62 | [25 empty] | 1871582.06
Variations
| PV01 | Changes In Tender Drawings - Nullify Line Item 1.10. | item |  | 1 | 1 | -99682.79 | -99682.79 | -99682.79 |  |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | -99682.79 | -99682.79 | -99682.79 | -99682.79 | -99682.79 | -99682.79 | -99682.79
159 | PV02 | Additional Clearing & Grubbing - Moving rental car park 10m to the north to avoid fibre optic cable. | item | 2728 | 1 | 1 | 3375.9 | 3375.9 | 3375.9 |  | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 3375.9 | 3375.9 | 3375.9 | 3375.9 | 3375.9 | 3375.9 | 3375.9 | 3375.9
162 | PV03 b | Additional Fill, road base gravel, spray seal & AC to elongated access ramp |  |  | 1 | 1 | 1
163 | PV03 b.1 | Imported General Fill (BOQ Item 3.3.5) | m³ | 837.2318 | 62 | 62 | 62 | 1067.02 | 1067.02 | 1067.02 |  | 0% |  | 0% | 62 | 100% | 62 | 100% | 62 | 100% | 62 | 100% | 62 | 100% | 62 | 100% | 0 | 0 | 1067.02 | 1067.02 | 1067.02 | 1067.02 | 1067.02 | 1067.02
164 | PV03 b.2 | Additional sub-grade preparation (BOQ item 4.1) | m² | 162.9968 | 80 | 80 | 80 | 208 | 208 | 208 |  | 0% |  | 0% | 80 | 100% | 80 | 100% | 80 | 100% | 80 | 100% | 80 | 100% | 80 | 100% | 0 | 0 | 208 | 208 | 208 | 208 | 208 | 208
165 | PV03 b.3 | Additional 2.3 Material (BOQ Item 4.2.3.2) | m³ | 489.2294 | 8 | 8 | 8 | 623.36 | 623.36 | 623.36 |  | 0% |  | 0% |  | 0% |  | 0% | 8 | 100% | 8 | 100% | 8 | 100% | 8 | 100% | 0 | 0 | 0 | 0 | 623.36 | 623.36 | 623.36 | 623.36
166 | PV03 b.4 | Additional 2.1 Material (BOQ Item 4.2.3.1) | m³ | 550.5166 | 8.75 | 8.75 | 8.75 | 701.49 | 701.49 | 701.49 |  | 0% |  | 0% |  | 0% |  | 0% | 8.75 | 100% | 8.75 | 100% | 8.75 | 100% | 8.75 | 100% | 0 | 0 | 0 | 0 | 701.49 | 701.49 | 701.49 | 701.49
167 | PV03 b.5 | Additional final trim (BOQ Item 4.3) | m³ | 172.3556 | 70 | 70 | 70 | 219.8 | 219.8 | 219.8 |  | 0% |  | 0% |  | 0% |  | 0% | 70 | 100% | 70 | 100% | 70 | 100% | 70 | 100% | 0 | 0 | 0 | 0 | 219.8 | 219.8 | 219.8 | 219.8
168 | PV03 b.6 | Additional Spray Seal (BOQ Item 4.5.2.1) | m² | 330.015 | 70 | 70 | 70 | 420.7 | 420.7 | 420.7 |  | 0% |  | 0% |  | 0% |  | 0% | 70 | 100% | 70 | 100% | 70 | 100% | 70 | 100% | 0 | 0 | 0 | 0 | 420.7 | 420.7 | 420.7 | 420.7
169 | PV03 b.7 | Additional AC (BOQ Item 4.5.2.2) | tonne | 2009 | 7 | 7 | 7 | 2059.4 | 2059.4 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 7 | 100% | 7 | 100% | 7 | 100% | 0 | 0 | 0 | 0 | 0 | 2059.4 | 2059.4 | 2059.4
160 | PV03 a | Additional Material for Revised Levels (Main Pad) |  | 0 | 1 | 1 | 1
161 | PV03 a.1 | Additional Imported General Fill (BOQ Item 3.3.5) | m³ | 0 | 704 | 704 | 704 | 12115.84 | 12115.84 |  |  | 0% | 704 | 100% | 704 | 100% | 704 | 100% | 704 | 100% | 704 | 100% | 704 | 100% | 704 | 100% | 0 | 12115.84 | 12115.84 | 12115.84 | 12115.84 | 12115.84 | 12115.84 | 12115.84
170 | PV03 c | Additional Kerb & Channel (Type B1) |  | 0 | 1 | 1 | 1
171 | PV03 c.1 | B1 Barrier Kerb & Channel (BOQ Item 4.4.1.1) | m | 820.1646 | 20 | 20 | 20 | 1045 | 1045 |  |  | 0% |  | 0% |  | 0% |  | 0% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 0 | 0 | 0 | 0 | 1045 | 1045 | 1045 | 1045
172 | PV03 d | Additional Footpath |  | 0 | 1 | 1 | 1
173 | PV03 d.1 | Additional Concrete Footpath 2.45m Wide (BOQ Item 4.4.4.1) | m² | 1353.7869 | 24.5 | 24.5 | 24.5 | 1725.05 | 1725.05 |  |  | 0% |  | 0% |  | 0% |  | 0% | 24.5 | 100% | 24.5 | 100% | 24.5 | 100% | 24.5 | 100% | 0 | 0 | 0 | 0 | 1725.05 | 1725.05 | 1725.05 | 1725.05
174 | PV03 e | Additional Storm Water |  | 0 | 1 | 1 | 1
175 | PV03 e.1 | Additional 450 mm Diameter Class 2 RRJ (BOQ Item 5.1.3) | m | 691.2911 | 4.88 | 4.88 | 4.88 | 880.89 | 880.89 |  |  | 0% |  | 0% | 4.88 | 100% | 4.88 | 100% | 4.88 | 100% | 4.88 | 100% | 4.88 | 100% | 4.88 | 100% | 0 | 0 | 880.89 | 880.89 | 880.89 | 880.89 | 880.89 | 880.89
176 | PV03 f | Additional General Fill between rental car aprk and batter of new road one |  | 0 | 1 | 1 | 1
177 | PV03 f.1 | Cut to Fill (BOQ Item 3.3.4) | m³ | 3090.7431 | 460 | 460 | 460 | 4181.4 | 4181.4 |  |  | 0% | 460 | 100% | 460 | 100% | 460 | 100% | 460 | 100% | 460 | 100% | 460 | 100% | 460 | 100% | 0 | 4181.4 | 4181.4 | 4181.4 | 4181.4 | 4181.4 | 4181.4 | 4181.4
178 | PV03 g | Additional Conduit & Trenching |  |  | 1 | 1 | 1
179 | PV03 g.1 | Additional Trenching (BOQ Item 6.1) | m | 346.7136 | 10 | 10 | 10 | 441.8 | 441.8 |  |  | 0% | 10 | 100% | 10 | 100% | 10 | 100% | 10 | 100% | 10 | 100% | 10 | 100% | 10 | 100% | 0 | 441.8 | 441.8 | 441.8 | 441.8 | 441.8 | 441.8 | 441.8
180 | PV03 g.3 | Additional 100 diameter electrical conduit (BOQ Item 6.2) | m | 46.725 | 20 | 20 | 6.95 | 139 | 139 |  |  | 0% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 0 | 139 | 139 | 139 | 139 | 139 | 139 | 139
181 | PV03 g.2 | Additional 100 diameter communications conduit | m | 109.07 | 10 | 10 | 10 | 79 | 79 |  |  | 0% | 10 | 100% | 10 | 100% | 10 | 100% | 10 | 100% | 10 | 100% | 10 | 100% | 10 | 100% | 0 | 79 | 79 | 79 | 79 | 79 | 79 | 79
182 | PV04 | Remove & Replace Unsuitable (Extra Over BOQ Item 3.3.7) | m³ | 5113.116 | 100 | 100 | 51.13 | 5113 | 5113 |  |  | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 0 | 5113 | 5113 | 5113 | 5113 | 5113 | 5113 | 5113
183 | PV05 | Remove & Replace Soft Spots - Rental Car Park | item | 3834.837 | 1 | 1 | 4130.09 | 4130.09 | 4130.09 |  |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 4130.09 | 4130.09 | 4130.09 | 4130.09 | 4130.09 | 4130.09 | 4130.09
184 | PV06 | Extension To Commercial Car Park | item |  | 1 | 1 | 1
185 | PV06.a | Clear & Grubbing (BOQ Item 3.2.1) | m² | 192 | 1800 | 1800 | 1800 | 2430 | 2430 |  |  | 0% |  | 0% | 1800 | 100% | 1800 | 100% | 1800 | 100% | 1800 | 100% | 1800 | 100% | 1800 | 100% | 0 | 0 | 2430 | 2430 | 2430 | 2430 | 2430 | 2430
186 | PV06.b | Stripping Topsoil (BOQ item 3.3.1) | m³ | 1543.5 | 180 | 180 | 180 | 1967.4 | 1967.4 |  |  | 0% |  | 0% | 180 | 100% | 180 | 100% | 180 | 100% | 180 | 100% | 180 | 100% | 180 | 100% | 0 | 0 | 1967.4 | 1967.4 | 1967.4 | 1967.4 | 1967.4 | 1967.4
187 | PV06.c | Import General Fill (BOQ Item 3.3.5) | m³ | 14584.0374 | 1080 | 1080 | 1080 | 18586.8 | 18586.8 |  |  | 0% |  | 0% |  | 0% | 1080 | 100% | 1080 | 100% | 1080 | 100% | 1080 | 100% | 1080 | 100% | 0 | 0 | 0 | 18586.8 | 18586.8 | 18586.8 | 18586.8 | 18586.8
188 | PV06.d | Prepare Sub-grade (BOQ Item 4.1) | m² | 3667.4286 | 1800 | 1800 | 1800 | 4680 | 4680 |  |  | 0% |  | 0% |  | 0% | 1800 | 100% | 1800 | 100% | 1800 | 100% | 1800 | 100% | 1800 | 100% | 0 | 0 | 0 | 4680 | 4680 | 4680 | 4680 | 4680
189 | PV06.e | Import 2.1 (BOQ Item 4.2.3.1) | m³ | 14156.1406 | 225 | 225 | 225 | 18038.25 | 18038.25 |  |  | 0% |  | 0% |  | 0% | 225 | 100% | 225 | 100% | 225 | 100% | 225 | 100% | 225 | 100% | 0 | 0 | 0 | 18038.25 | 18038.25 | 18038.25 | 18038.25 | 18038.25
190 | PV06.f | Import 2.3 (BOQ Item 4.2.3.2) |  | 11007.6624 | 180 | 180 | 180 | 14025.6 | 14025.6 |  |  | 0% |  | 0% |  | 0% | 180 | 100% | 180 | 100% | 180 | 100% | 180 | 100% | 180 | 100% | 0 | 0 | 0 | 14025.6 | 14025.6 | 14025.6 | 14025.6 | 14025.6
191 | PV06.g | Primer Seal (7mm) (BOQ Item 4.5.1.1) | m² | 8486.1 | 1800 | 1800 | 1800 | 10818 | 10818 |  |  | 0% |  | 0% |  | 0% |  | 0% | 1800 | 100% | 1800 | 100% | 1800 | 100% | 1800 | 100% | 0 | 0 | 0 | 0 | 10818 | 10818 | 10818 | 10818
192 | PV06.h | SM4 Kerb (BOQ Item 4.4.1.3) | m | 1071.6805 | 44 | 44 | 44 | 1364 | 1364 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 44 | 100% | 44 | 100% | 44 | 100% | 0 | 0 | 0 | 0 | 0 | 1364 | 1364 | 1364
193 | PV06.i | B1 Kerb (BOQ Item 4.4.1.1) | m | 2431.2908 | 44 | 44 | 44 | 2299 | 2299 |  |  | 0% |  | 0% |  | 0% |  | 0% | 44 | 100% | 44 | 100% | 44 | 100% | 44 | 100% | 0 | 0 | 0 | 0 | 2299 | 2299 | 2299 | 2299
194 | PV06.j | B2 Kerb (BOQ Item 4.4.1.2) | m | 1279.8311 | 44 | 44 | 44 | 1630.64 | 1630.64 |  |  | 0% |  | 0% |  | 0% |  | 0% | 44 | 100% | 44 | 100% | 44 | 100% | 44 | 100% | 0 | 0 | 0 | 0 | 1630.64 | 1630.64 | 1630.64 | 1630.64
195 | PV06.k | Topsoil to Back of Kerb (BOQ Item 3.3.2) | m³ | 284.8 | 20 | 20 | 20 | 363 | 363 |  |  | 0% |  | 0% |  | 0% |  | 0% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 0 | 0 | 0 | 0 | 363 | 363 | 363 | 363
196 | PV06.l | Additional 450 RCP (BOQ Item 5.1.4) | m | 4674.4885 | 26 | 26 | 26 | 5956.6 | 5956.6 |  |  | 0% |  | 0% |  | 0% | 26 | 100% | 26 | 100% | 26 | 100% | 26 | 100% | 26 | 100% | 0 | 0 | 0 | 5956.6 | 5956.6 | 5956.6 | 5956.6 | 5956.6
203 | PV06.s | Additional Line Marking (BOQ Item 4.6.1) | item | 1665.2174 | 1 | 1 | 1 | 2000 | 2000 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000
201 | PV06.q | Additional Log Barrier Fence (BOQ Item 7.2.1.1) | m | 836.535 | 31 | 31 | 31 | 1066.09 | 1066.09 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 31 | 100% | 31 | 100% | 31 | 100% | 0 | 0 | 0 | 0 | 0 | 1066.09 | 1066.09 | 1066.09
202 | PV06.r | New 2.4m Kerb Lintel | item | 2107.2 | 1 | 1 | 1 | 2685.09 | 2685.09 |  |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 2685.09 | 2685.09 | 2685.09 | 2685.09 | 2685.09
197 | PV06.m | Final Trim (BOQ Item 4.3) | m² | 4432 | 1800 | 1800 | 1800 | 5652 | 5652 |  |  | 0% |  | 0% |  | 0% | 1800 | 100% | 1800 | 100% | 1800 | 100% | 1800 | 100% | 1800 | 100% | 0 | 0 | 0 | 5652 | 5652 | 5652 | 5652 | 5652
198 | PV06.n | Additional Conduit Trenching (BOQ Item 6.1) | m | 1560.2114 | 45 | 45 | 45 | 1988.1 | 1988.1 |  |  | 0% |  | 0% |  | 0% | 45 | 100% | 45 | 100% | 45 | 100% | 45 | 100% | 45 | 100% | 0 | 0 | 0 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1
199 | PV06.o | Additional Conduit (BOQ Item 6.3) | m | 131.535 | 45 | 45 | 45 | 167.4 | 167.4 |  |  | 0% |  | 0% |  | 0% | 45 | 100% | 45 | 100% | 45 | 100% | 45 | 100% | 45 | 100% | 0 | 0 | 0 | 167.4 | 167.4 | 167.4 | 167.4 | 167.4
200 | PV06.p | Additional Wheel Stops (BOQ Item 4.4.4.5) | ea | 1546.6667 | 10 | 10 | 10 | 1970.8 | 1970.8 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 10 | 100% | 10 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1970.8 | 1970.8
204 | PV07 | Additional Box Out & General Fill |  |  | 1 | 1 | 1
205 | PV07.a | Cut To Spoil (BOQ Item 3.3.6) | m³ | 23378.1 | 1341 | 1341 | 1341 | 23373.63 | 23373.63 |  |  | 0% |  | 0% | 1341 | 100% | 1341 | 100% | 1341 | 100% | 1341 | 100% | 1341 | 100% | 1341 | 100% | 0 | 0 | 23373.63 | 23373.63 | 23373.63 | 23373.63 | 23373.63 | 23373.63
206 | PV07.b | Import General Fill (BOQ Item 3.3.5) | m³ | 18108.5131 | 1341 | 1341 | 1341 | 23078.61 | 23078.61 |  |  | 0% |  | 0% | 1341 | 100% | 1341 | 100% | 1341 | 100% | 1341 | 100% | 1341 | 100% | 1341 | 100% | 0 | 0 | 23078.61 | 23078.61 | 23078.61 | 23078.61 | 23078.61 | 23078.61
207 | PV08 | Remove & Replace Unsuitable - Bus Bay & Round-a-bout | item |  | 1 | 1 | 1
208 | PV08.a | Remove Soft Spots (BOQ Item 3.3.7) | m³ | 11381.7962 | 222.6 | 222.6 | 222.6 | 11381.54 | 11381.54 |  |  | 0% |  | 0% | 222.6 | 100% | 222.6 | 100% | 222.6 | 100% | 222.6 | 100% | 222.6 | 100% | 222.6 | 100% | 0 | 0 | 11381.54 | 11381.54 | 11381.54 | 11381.54 | 11381.54 | 11381.54
209 | PV08.b | Import General Fill (BOQ Item 3.3.5) | m³ | 3005.9322 | 222.6 | 222.6 | 222.6 | 0
210 | PV09 | Stabilise Sub-Grade |  |  | 1 | 1 | 1
211 | PV09.a | Supply GB Cement Stabilising Agent | tonne | 332 | 36 | 36 | 36 | 16200 | 16200 |  |  | 0% |  | 0% |  | 0% | 36 | 100% | 36 | 100% | 36 | 100% | 36 | 100% | 36 | 100% | 0 | 0 | 0 | 16200 | 16200 | 16200 | 16200 | 16200
212 | PV09.b | In-situ Stabilising Sub-grade | m² | 42787.1214 | 3890 | 3890 | 3890 | 43762.5 | 43762.5 |  |  | 0% |  | 0% |  | 0% | 3890 | 100% | 3890 | 100% | 3890 | 100% | 3890 | 100% | 3890 | 100% | 0 | 0 | 0 | 43762.5 | 43762.5 | 43762.5 | 43762.5 | 43762.5
213 | PV10 | Supply & Install Visi-ball Tank Level Indicator | item | 700 | 1 | 1 | 750 | 750 | 750 |  |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 750 | 750 | 750 | 750 | 750
214 | PV11 | Centre Median Footpath Beam Thickening |  |  | 1 | 1 | 1
215 | PV11.a | Excavate for, Supply, Place and Finish Additional N25 Concrete | m³ | 1497.6277 | 8 | 8 | 8 | 1761.76 | 1761.76 |  |  | 0% |  | 0% |  | 0% | 8 | 100% | 8 | 100% | 8 | 100% | 8 | 100% | 8 | 100% | 0 | 0 | 0 | 1761.76 | 1761.76 | 1761.76 | 1761.76 | 1761.76
216 | PV11.b | Supply, cut, tie and place SL72 Reinforcing Mesh | m² | 777.5851 | 80 | 80 | 80 | 1161.6 | 1161.6 |  |  | 0% |  | 0% |  | 0% | 80 | 100% | 80 | 100% | 80 | 100% | 80 | 100% | 80 | 100% | 0 | 0 | 0 | 1161.6 | 1161.6 | 1161.6 | 1161.6 | 1161.6
217 | PV12 | Install 150mm & 225mm Roof water drainage lines from terminal building, including road crossings and stubs to existing stormwater pits | item | 6250 | 1 | 1 | 7562.5 | 7562.5 | 7562.5 |  |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 7562.5 | 7562.5 | 7562.5 | 7562.5 | 7562.5
218 | PV13 | Installation of STP Irrigation System |  | 0 | 1 | 1 | 1
219 | PV13.a | Installation only of Pump No. 01 & Pump Well | item | 3850 | 1 | 1 | 1 | 4235 | 4235 |  |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 4235 | 4235 | 4235 | 4235
220 | PV13.b | Supply & Install Pump & Well No. 02 | item | 17000 | 1 | 1 | 1 | 18755 | 18755 |  |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 18755 | 18755 | 18755 | 18755
221 | PV13.c | Supply & Installation of Electrical as Per E002 & Clarification Letter | item | 33700 | 1 | 1 | 1 | 37085.29 | 37085.29 |  |  | 0% |  | 0% |  | 0% |  | 0% | 0.85 | 85% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 31522.4965 | 37085.29 | 37085.29 | 37085.29
222 | PV13.d | Raise STP pad height 500mm and provide 100mm reinforced concrete slab | item | 3800 | 1 | 1 | 1 | 4317.28 | 4317.28 |  |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 4317.28 | 4317.28 | 4317.28 | 4317.28
223 | PV13.e | Supply & Install light to roof of container | item | 700 | 1 | 1 | 1 | 1000 | 1000 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000
224 | PV13.f | Supply & Installation of rising main from Pump well No. 02 to irrigation area as per H101 in existing cleared areas | item | 39000 | 1 | 1 | 1 | 42967.1 | 42967.1 |  |  | 0% |  | 0% |  | 0% | 0.448 | 44.8% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 19249.2608 | 42967.1 | 42967.1 | 42967.1 | 42967.1
225 | PV13.g | Supply & installation of irrigation area (3,000 sqm) as per H103 including air & flush valves | item | 39600 | 1 | 1 | 1 | 43560 | 43560 |  |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 43560 | 43560 | 43560 | 43560
226 | PV13.h | Supply & installation of signal cable as per clarification email | item | 12600 | 1 | 1 | 1 | 13906.75 | 13906.75 |  |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 13906.75 | 13906.75 | 13906.75 | 13906.75
227 | PV14 | Installation of Edge Restraint | m | 4305.8639 | 105 | 105 | 52.25 | 5486.25 | 5486.25 |  |  | 0% |  | 0% |  | 0% | 105 | 100% | 105 | 100% | 105 | 100% | 105 | 100% | 105 | 100% | 0 | 0 | 0 | 5486.25 | 5486.25 | 5486.25 | 5486.25 | 5486.25
228 | PV15 | Fie Lay Away | item |  | 1 | 1 | 1
229 | PV15.a | Cut To Spoil | m³ | 513.6 | 36 | 36 | 36 | 627.48 | 627.48 |  |  | 0% |  | 0% |  | 0% |  | 0% | 36 | 100% | 36 | 100% | 36 | 100% | 36 | 100% | 0 | 0 | 0 | 0 | 627.48 | 627.48 | 627.48 | 627.48
230 | PV15.b | Prepare & Trim Sub-grade | m² | 393.9556 | 160 | 160 | 160 | 416 | 416 |  |  | 0% |  | 0% |  | 0% |  | 0% | 160 | 100% | 160 | 100% | 160 | 100% | 160 | 100% | 0 | 0 | 0 | 0 | 416 | 416 | 416 | 416
231 | PV15.c | Edge Restraint | m | 1845.3702 | 45 | 45 | 45 | 2351.25 | 2351.25 |  |  | 0% |  | 0% |  | 0% |  | 0% | 45 | 100% | 45 | 100% | 45 | 100% | 45 | 100% | 0 | 0 | 0 | 0 | 2351.25 | 2351.25 | 2351.25 | 2351.25
232 | PV15.d | Supply & Place 2.1 Gravel | m³ | 2264.9825 | 36 | 36 | 36 | 2886.12 | 2886.12 |  |  | 0% |  | 0% |  | 0% |  | 0% | 36 | 100% | 36 | 100% | 36 | 100% | 36 | 100% | 0 | 0 | 0 | 0 | 2886.12 | 2886.12 | 2886.12 | 2886.12
233 | PV15.e | Primer Seal | m² | 718.4 | 160 | 160 | 160 | 961.6 | 961.6 |  |  | 0% |  | 0% |  | 0% |  | 0% | 160 | 100% | 160 | 100% | 160 | 100% | 160 | 100% | 0 | 0 | 0 | 0 | 961.6 | 961.6 | 961.6 | 961.6
234 | PV15.f | DG10 Asphalt (40mm) | tonne | 4592 | 16 | 16 | 16 | 4707.2 | 4707.2 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 16 | 100% | 16 | 100% | 16 | 100% | 0 | 0 | 0 | 0 | 0 | 4707.2 | 4707.2 | 4707.2
235 | PV16 | Bin Area | item | 0 | 1 | 1 | 1
236 | PV16.a | General Fill | m³ | 1026.2841 | 76 | 76 | 76 | 1307.96 | 1307.96 |  |  | 0% |  | 0% |  | 0% |  | 0% | 76 | 100% | 76 | 100% | 76 | 100% | 76 | 100% | 0 | 0 | 0 | 0 | 1307.96 | 1307.96 | 1307.96 | 1307.96
237 | PV16.b | Supply & Place Type 2.1 Gravel | m³ | 1572.9045 | 25 | 25 | 25 | 2004.25 | 2004.25 |  |  | 0% |  | 0% |  | 0% |  | 0% | 25 | 100% | 25 | 100% | 25 | 100% | 25 | 100% | 0 | 0 | 0 | 0 | 2004.25 | 2004.25 | 2004.25 | 2004.25
238 | PV16.c | Colourbonfd Fence (1800 High - 20m) | item | 2323 | 1 | 1 | 1 | 2904 | 2904 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 2904 | 2904
239 | PV17 | Additional Edge Restraint | m | 2911.5842 | 71 | 71 | 52.25 | 3709.75 | 3709.75 |  |  | 0% |  | 0% |  | 0% |  | 0% | 71 | 100% | 71 | 100% | 71 | 100% | 71 | 100% | 0 | 0 | 0 | 0 | 3709.75 | 3709.75 | 3709.75 | 3709.75
240 | PV18 | Supply & Install Additional Electrical Pit | each | 1210 | 1 | 1 | 1592.49 | 1592.49 | 1592.49 |  |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 1592.49 | 1592.49 | 1592.49 | 1592.49
241 | PV19 | Extra Over Log Barrier Fenec - Monowills Pedestrian Safety Fence | m | 2146 | 1 | 58 | 37 | 2146 | 2146 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 58 | 100% | 58 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 2146 | 2146
242 | PV20 | Additional AC | tonne | 20290.9 | 70.7 | 70.7 | 294.2 | 20799.94 | 20799.94 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 70.7 | 100% | 70.7 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 20799.94 | 20799.94
243 | PV21 | Miscellaneous Additional Works | item | 22691.1516 | 1 | 1 | 25429.61 | 25429.61 | 25429.61 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25429.61
|  | Total, all contract items and variations |  | 1852261.4285 |  |  |  |  | 2311232.539 |  |  | 6.011% |  | 20.02% |  | 31.58% |  | 51.74% |  | 79.94% |  | 95.11% |  | 98.87% |  | 100% | 137061.0155 | 456584.371 | 720058.3301 | 1179851.3079 | 1822861.238 | 2168688.0825 | 2254563.63 | 2280303.24
[9 empty] | 2284134.2 | [24 empty] | 2284134.2
[9 empty] | -27098.339 | [24 empty] | 3830.96

## Portfolio WBS
Portfolio WBS | Description | Quantity | UOM | BAC | BAC Rate | Final Qty | Final Cost | Final Rate |  |  | 2011-04-01 |  |  |  |  | 2011-05-01 |  |  |  |  | 2011-06-01 |  |  |  |  | 2011-07-01 |  |  |  |  | 2011-08-01 |  |  |  |  | 2011-09-01 |  |  |  |  | 2011-10-01 |  |  |  |  | 2011-11-01
|  | SQ |  |  |  | AQ | AC |  | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV
11 | Survey - Construction | 94 | hrs | 23680 | 251.9149 | 146 | 27030 | 185.137 | 10 | 2519.1489 | 7.6 | 1400 | 1232.6575 | 10 | 2519.1489 | 7.6 | 1400 | 1232.6575 | 35 | 8817.0213 | 31.9 | 5908.3 | 5173.9178 | 50 | 12595.7447 | 49 | 9071.75 | 7947.3973 | 70 | 17634.0426 | 107.4 | 19878.3 | 17419.3973 | 90 | 22672.3404 | 111.7 | 20668.8 | 18116.8219 | 90 | 22672.3404 | 130.9 | 24220.2 | 24220 | 94 | 23680 | 146 | 28430.2 | 23680
13 | QA Testing | 1 | item | 14950 | 14950 | 1 | 7650 | 7650 | 0 | 0 | 0 | 0 | 0 | 0.1 | 1495 | 0 | 90 | 0 | 0.25 | 3737.5 | 0.25 | 2650 | 3737.5 | 0.5 | 7475 | 0.65 | 5050 | 9717.5 | 0.75 | 11212.5 | 0.9 | 6850 | 13455 | 1 | 14950 | 1 | 7650 | 14950 | 1 | 14950 | 1 | 7650 | 14950 | 1 | 14950 | 1 | 7650 | 14950
15 | Service Locations | 0 |  | 0 | 0 | 1 | 1105 | 1105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 130 | 0 | 0 | 0 | 0.1 | 130 | 0 | 0 | 0 | 0.9 | 910 | 0 | 0 | 0 | 1 | 1105 | 0 | 0 | 0 | 1 | 1105 | 0
21 | Clearing to Stockpile | 2350 | m3 | 4482 | 1.9072 | 2350 | 12096 | 5.1472 | 500 | 953.617 | 0 | 0 | 0 | 2350 | 4482 | 1750 | 9101.37 | 3337.6596 | 2350 | 4482 | 1750 | 9101.37 | 3337.6596 | 2350 | 4482 | 2200 | 11312.405 | 4195.9149 | 2350 | 4482 | 2350 | 12095.585 | 4482 | 2350 | 4482 | 2350 | 12095.585 | 4482 | 2350 | 4482 | 2350 | 12095.585 | 4482 | 2350 | 4482 | 2350 | 12095.585 | 4482
22 | Disposal offsite - Clearing waste | 14033 |  | 8832 | 0.62937 | 0 | 0 | 0 | 4500 | 2832.1813 | 0 | 0 | 0 | 14033 | 8832 | 0 | 0 | 0 | 14033 | 8832 | 0 | 0 | 0 | 14033 | 8832 | 0 | 0 | 8268.2553 | 14033 | 8832 | 0 | 0 | 8832 | 14033 | 8832 | 0 | 0 | 8832 | 14033 | 8832 | 0 | 0 | 8832 | 14033 | 8832 | 0 | 0 | 8832
23 | Mulching | 14033 |  | 7000 | 0.49882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14033 | 7000 | 0 | 0 | 0 | 14033 | 7000 | 0 | 0 | 0 | 14033 | 7000 | 0 | 0 | 7000 | 14033 | 7000 | 0 | 0 | 7000 | 14033 | 7000 | 0 | 0 | 7000 | 14033 | 7000 | 0 | 0 | 7000
31 | Strip Topsoil to Stockpile | 1151 | m3 | 9869.825 | 8.575 | 1151 | 17447 | 15.1581 | 500 | 4287.5 | 0 | 0 | 0 | 1151 | 9869.825 | 850 | 13286.15 | 7288.75 | 1151 | 9869.825 | 850 | 13286.15 | 7288.75 | 1151 | 9869.825 | 1050 | 16303.485 | 9003.75 | 1151 | 9869.825 | 1151 | 17446.665 | 9869.825 | 1151 | 9869.825 | 1151 | 17446.665 | 9869.825 | 1151 | 9869.825 | 1151 | 17446.665 | 9869.825 | 1151 | 9869.825 | 1151 | 17446.665 | 9869.825
32 | Disposal offsite - topsoil | 27 | m3 | 353.025 | 13.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 353.025 | 0 | 0 | 0 | 27 | 353.025 | 0 | 0 | 0 | 27 | 353.025 | 0 | 0 | 0 | 27 | 353.025 | 0 | 0 | 353.025 | 27 | 353.025 | 0 | 0 | 353.025 | 27 | 353.025 | 0 | 0 | 353.025 | 27 | 353.025 | 0 | 0 | 353.025
33 | Re-spread topsoil | 389 | m3 | 5539.36 | 14.24 | 389 | 14500 | 37.2751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 4051.73 | 1424 | 389 | 5539.36 | 325 | 12235.91 | 4628 | 389 | 5539.36 | 389 | 14500.11 | 5539.36 | 389 | 5539.36 | 389 | 14500.11 | 5539.36
41 | Demolition works | 1 | item | 29059.425 | 29059.425 | 1 | 13911 | 13911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 7264.8563 | 0 | 0 | 0 | 0.5 | 14529.7125 | 0.6 | 8267.735 | 17435.655 | 0.75 | 21794.5688 | 0.65 | 9050.675 | 18888.6263 | 1 | 29059.425 | 1 | 13910.675 | 29059.425 | 1 | 29059.425 | 1 | 13910.675 | 29059.425 | 1 | 29059.425 | 1 | 13910.675 | 29059.425
51 | Cut to Fill | 2848 | m3 | 20085.7311 | 7.0526 | 2848 | 49136 | 17.2528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 2823.9 | 1410.5148 | 0 | 0 | 200 | 2823.9 | 1410.5148 | 1400 | 9873.6038 | 1100 | 19971.645 | 7757.8315 | 2848 | 20085.7311 | 2100 | 36896.175 | 14810.4057 | 2848 | 20085.7311 | 2848 | 49136.349 | 20085.7311 | 2848 | 20085.7311 | 2848 | 49136.349 | 20085.7311 | 2848 | 20085.7311 | 2848 | 49136.349 | 20085.7311
52 | Stockpile to Fill | 7508 | m3 | 94981.4379 | 12.6507 | 7508 | 164871 | 21.9594 | 0 | 0 | 0 | 0 | 0 | 1000 | 12650.6976 | 0 | 1484 | 0 | 5000 | 63253.4882 | 3500 | 87840.845 | 44277.4418 | 6000 | 75904.1859 | 5900 | 130649.97 | 74639.1161 | 7508 | 94981.4379 | 7508 | 164870.94 | 94981.4379 | 7508 | 94981.4379 | 7508 | 164870.94 | 94981.4379 | 7508 | 94981.4379 | 7508 | 164870.94 | 94981.4379 | 7508 | 94981.4379 | 7508 | 164870.94 | 94981.4379
53 | Cut to Spoil | 2052 | m3 | 33153.1583 | 16.1565 | 2052 | 11630 | 5.6676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 8078.255 | 10 | 317.56 | 161.5651 | 1500 | 24234.7649 | 0 | 317.56 | 0 | 2052 | 33153.1583 | 645 | 3858.56 | 10420.9489 | 2052 | 33153.1583 | 2052 | 11630.28 | 33153.1583 | 2052 | 33153.1583 | 2052 | 11630.28 | 33153.1583 | 2052 | 33153.1583 | 2052 | 11630.28 | 33153.1583
57 | Remove & Replace unsuitable | 473 | m3 | 27999.4232 | 59.1954 | 473 | 29372 | 62.0973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 11839.0796 | 90 | 8333.54 | 5327.5858 | 473 | 27999.4232 | 330 | 29372.455 | 19534.4813 | 473 | 27999.4232 | 460 | 40753.905 | 27229.883 | 473 | 27999.4232 | 473 | 41783.66 | 27999.4232 | 473 | 27999.4232 | 473 | 41783.66 | 27999.4232 | 473 | 27999.4232 | 473 | 41783.66 | 27999.4232
61 | Subgrade Preparation | 22003 | m2 | 44898.2013 | 2.0405 | 22003 | 6723 | 0.30555 | 0 | 0 | 0 | 0 | 0 | 2500 | 5101.3727 | 6000 | 2730.24 | 12243.2944 | 6000 | 12243.2944 | 15000 | 4354.06 | 30608.2361 | 12500 | 25506.8634 | 14500 | 4354.06 | 29587.9616 | 22003 | 44898.2013 | 21000 | 6279.92 | 42851.5305 | 22003 | 44898.2013 | 22003 | 6722.72 | 44898.2013 | 22003 | 44898.2013 | 22003 | 6722.72 | 44898.2013 | 22003 | 44898.2013 | 22003 | 6722.72 | 44898.2013
62 | Place & Compact Gravel | 7995 | tonne | 40636.3231 | 5.0827 | 5536 | 91849 | 16.5912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 12706.7927 | 275 | 4650.18 | 2018.6035 | 4000 | 20330.8683 | 1036 | 17611.695 | 7604.6298 | 7000 | 35579.0196 | 2423 | 48779.54 | 17785.7317 | 7995 | 40636.3231 | 5100 | 84713.125 | 37435.919 | 7995 | 40636.3231 | 5536 | 91849.125 | 40636.3231 | 7995 | 40636.3231 | 5536 | 91849.125 | 40636.3231
63 | Trim All Layers | 18417 | m2 | 45346.7467 | 2.4622 | 18417 | 45940 | 2.4944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.78 | 0 | 3050 | 7509.7778 | 2700 | 6951.665 | 6648 | 9000 | 22160 | 8460 | 21171.29 | 20830.4 | 14000 | 34471.1111 | 14350 | 35928.425 | 35332.8889 | 18417 | 45346.7467 | 18417 | 45939.655 | 45346.7467 | 18417 | 45346.7467 | 18417 | 45939.655 | 45346.7467 | 18417 | 45346.7467 | 18417 | 45939.655 | 45346.7467
64 | Sweep & Prime / Primer seal or Seal | 14781 | m2 | 69649.1045 | 4.7121 | 14781 | 105958 | 7.1685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3050 | 14371.8131 | 0 | 0 | 0 | 3050 | 14371.8131 | 3075 | 22054.7472 | 14489.6148 | 8200 | 38638.9728 | 8150 | 58444.7472 | 38403.3693 | 14781 | 69649.1045 | 14781 | 105957.8072 | 69649.1045 | 14781 | 69649.1045 | 14781 | 105957.8072 | 69649.1045 | 14781 | 69649.1045 | 14781 | 105957.8072 | 69649.1045
65 | Asphalt | 1369 | tonne | 392816.9 | 307.8502 | 1276 | 307649 | 241.1042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 200855.9752 | 0 | 0 | 0 | 1369 | 392816.9 | 509 | 315.12 | 156695.7697 | 1369 | 392816.9 | 1276 | 185012.62 | 392816.9 | 1369 | 392816.9 | 1276 | 185012.62 | 392816.9
66 | Linemarking | 1 | item | 12634.3374 | 12634.3374 | 1 | 11724 | 11724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 6317.1687 | 0 | 753.39 | 0 | 1 | 12634.3374 | 0 | 753.39 | 0 | 1 | 12634.3374 | 0 | 753.39 | 0 | 1 | 12634.3374 | 1 | 11724.39 | 12634.3374
67 | Install Road Furniture | 96 | each | 16715.5 | 174.1198 | 96 | 2865 | 29.8438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 4527.1146 | 0 | 0 | 0 | 96 | 16715.5 | 20 | 713.5 | 3482.3958 | 96 | 16715.5 | 20 | 713.5 | 3482.3958 | 96 | 16715.5 | 96 | 2865.175 | 16715.5
68 | In-situ Stabilising | 3890 | m2 | 42787.1214 | 10.9993 | 3890 | 13280 | 3.4139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3250 | 0 | 35747.595 | 0 | 0 | 3500 | 0 | 38497.41 | 3890 | 42787.1214 | 3500 | 0 | 0 | 3890 | 42787.1214 | 3890 | 868.4 | 42787.1214
71 | Place Kerb & Channel / Inverts | 1517 | m | 30932.8221 | 20.3908 | 1517 | 37067 | 24.4344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2039.0786 | 0 | 0 | 0 | 100 | 2039.0786 | 81 | 1995.8 | 1651.6537 | 400 | 8156.3143 | 81 | 2580.3 | 1651.6537 | 1571 | 32033.9246 | 150 | 3724.5 | 3058.6179 | 1517 | 30932.8221 | 200 | 5024.5 | 4078.1572 | 1517 | 30932.8221 | 1517 | 37066.6 | 30932.8221
73 | Form & Place Footpath | 1005 | m2 | 19964.4465 | 19.8651 | 1005 | 33677 | 33.5095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 4966.2802 | 0 | 0 | 0 | 500 | 9932.5604 | 475 | 16041.175 | 9435.9324 | 500 | 9932.5604 | 535 | 18009.8 | 10627.8397 | 1005 | 19964.4465 | 940 | 31516.9 | 18673.2136 | 1005 | 19964.4465 | 1005 | 33676.9 | 19964.4465
81 | > 450 | 202 | m | 10313.8071 | 51.0585 | 202 | 17495 | 86.6089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 2552.9226 | 0 | 157.56 | 0 | 202 | 10313.8071 | 151 | 13194.42 | 7709.8261 | 202 | 10313.8071 | 151 | 13464.42 | 7709.8261 | 202 | 10313.8071 | 202 | 17494.82 | 10313.8071 | 202 | 10313.8071 | 202 | 17494.82 | 10313.8071 | 202 | 10313.8071 | 202 | 17494.82 | 10313.8071
85 | Install SW Pits & Chambers | 24 | each | 21867 | 911.125 | 24 | 25121 | 1046.7083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.75 | 4000 | 3416.7188 | 18 | 16400.25 | 12.5 | 13197.58 | 11389.0625 | 24 | 21867 | 23.5 | 24799.29 | 21411.4375 | 24 | 21867 | 24 | 25120.69 | 21867 | 24 | 21867 | 24 | 25120.69 | 21867
95 | Sewer Sub-contractors | 1 | item | 174672.4 | 174672.4 | 1 | 139556 | 139556 | 0 | 0 | 0 | 0 | 0 | 0.15 | 26200.86 | 0.17 | 29539.91 | 29694.308 | 0.45 | 78602.58 | 0.4 | 62560.92 | 69868.96 | 0.5 | 87336.2 | 0.45 | 63546.92 | 78602.58 | 0.5 | 87336.2 | 0.47 | 65136.92 | 82096.028 | 1 | 174672.4 | 0.99 | 138951.92 | 172925.676 | 1 | 174672.4 | 1 | 139556.12 | 174672.4 | 1 | 174672.4 | 1 | 145242.12 | 174672.4
103 | Water Sub-contractor | 285 | m | 24123.6432 | 84.6444 | 285 | 8135 | 28.5439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 2320 | 2539.3309 | 50 | 4232.2181 | 35 | 2905 | 2962.5527 | 50 | 4232.2181 | 95 | 2905 | 8041.2144 | 285 | 24123.6432 | 285 | 8135 | 24123.6432 | 285 | 24123.6432 | 285 | 8135 | 24123.6432 | 285 | 24123.6432 | 285 | 8135 | 24123.6432 | 285 | 24123.6432 | 285 | 8325 | 24123.6432
111 | Install Conduits / pits / rag bolts | 995 | m | 65406.5226 | 65.7352 | 995 | 39338 | 39.5357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 26294.0794 | 295 | 13375 | 19391.8836 | 995 | 65406.5226 | 860 | 34451.34 | 56532.2707 | 995 | 65406.5226 | 860 | 34631.34 | 56532.2707 | 995 | 65406.5226 | 930 | 37173.59 | 61133.7346 | 995 | 65406.5226 | 995 | 39337.69 | 65406.5226 | 995 | 65406.5226 | 995 | 40668.49 | 65406.5226
112 | Electrical Conduit Sub-contractor | 1 | item | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 150 | 0
113 | Electrical Sub-contract works | 1 | item | 69827 | 69827 | 1 | 84469 | 84469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1705.425 | 0 | 0 | 0 | 0.15 | 12625.425 | 10474.05 | 1 | 69827 | 0.35 | 29136.825 | 24439.45 | 1 | 69827 | 1 | 84469.435 | 69827 | 1 | 69827 | 1 | 84469.435 | 69827
121 | Landscaping Sub-contractors | 3271 | m2 | 0 | 0 | 3271 | 7800 | 2.3846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3271 | 0 | 0 | 0 | 0 | 3271 | 0 | 3271 | 7800 | 0
131 | Fencing Sub-contractors | 1602 | m | 54957.334 | 34.3055 | 1602 | 59187 | 36.9457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 27444.3615 | 45 | 1680.35 | 1543.7453 | 800 | 27444.3615 | 45 | 1680.35 | 1543.7453 | 1602 | 54957.334 | 53 | 1963.53 | 1818.189 | 1602 | 54957.334 | 1602 | 63042.17 | 54957.334
134 | Hire of Temporary Fencing |  |  | 0 |  |  |  |  | 2011-04-01 AC: 0; 2011-05-01 AC: 0; 2011-06-01 AC: 0; 2011-07-01 AC: 0; 2011-08-01 AC: 0; 2011-09-01 AC: 0; 2011-10-01 AC: 0; 2011-11-01 AC: 708.3
141 | Traffic Controllers | 177 | hrs | 9194.4 | 51.9458 | 285 | 14798 | 51.9228 | 0 | 0 | 0 | 0 | 0 | 24 | 1246.6983 | 0 | 0 | 0 | 48 | 2493.3966 | 0 | 0 | 0 | 72 | 3740.0949 | 0 | 0 | 0 | 96 | 4986.7932 | 28 | 1485.7 | 903.3095 | 177 | 9194.4 | 94 | 4892 | 3032.5389 | 177 | 9194.4 | 120 | 6323.675 | 3871.3263 | 177 | 9194.4 | 285 | 14798.475 | 9194.4
142 | Hire of Control Devices | 16 | week | 16500 | 1031.25 | 8 | 4339 | 542.375 | 0 | 0 | 0 | 0 | 0 | 2 | 2062.5 | 0 | 0 | 0 | 6 | 6187.5 | 0 | 0 | 0 | 10 | 10312.5 | 0 | 0 | 0 | 14 | 14437.5 | 4 | 1454.11 | 8250 | 16 | 16500 | 4 | 1454.11 | 8250 | 16 | 16500 | 8 | 4339.41 | 16500 | 16 | 16500 | 8 | 4339.41 | 16500
151 | Supply & Place Silt fences & protective devices | 2000 | m | 19140.0308 | 9.57 | 0 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 9570.0154 | 0 | 0 | 0 | 2000 | 19140.0308 | 0 | 177.255 | 0 | 2000 | 19140.0308 | 0 | 177.255 | 19140.0308 | 2000 | 19140.0308 | 0 | 177.255 | 19140.0308 | 2000 | 19140.0308 | 0 | 177.255 | 19140.0308 | 2000 | 19140.0308 | 0 | 177.255 | 19140.0308 | 2000 | 19140.0308 | 0 | 177.255 | 19140.0308
152 | Supply & install safety devices | 1 | item | 12768 | 12768 | 1 | 2806 | 2806 | 0 | 0 | 0 | 0 | 0 | 1 | 12768 | 0.05 | 590.85 | 638.4 | 1 | 12768 | 0.4 | 1343.85 | 5107.2 | 1 | 12768 | 0.6 | 1931.275 | 7660.8 | 1 | 12768 | 1 | 2805.915 | 12768 | 1 | 12768 | 1 | 2805.915 | 12768 | 1 | 12768 | 1 | 2805.915 | 12768 | 1 | 12768 | 1 | 2805.915 | 12768
221 | Day Works | 1 | item | 325.24 | 325.24 | 1 | 424 | 424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 325.24 | 1 | 491.47 | 325.24
901 | Project Management | 9 | week | 29792.75 | 3310.3056 | 15 | 2728 | 181.8667 | 0 | 0 | 1.9 | 342.19 | 3773.7483 | 2 | 6620.6111 | 5.7 | 1035.5 | 11321.245 | 4 | 13241.2222 | 11.1 | 2025.5 | 22046.635 | 6 | 19861.8333 | 12.9 | 2340.5 | 25621.765 | 8 | 26482.4444 | 15 | 2727.54 | 29792.75 | 9 | 29792.75 | 15 | 2727.54 | 29792.75 | 9 | 29792.75 | 15 | 2727.54 | 29792.75 | 9 | 29792.75 | 15 | 2727.54 | 29792.75
902 | Project Supervision | 16 | week | 38411.1 | 2400.6937 | 30 | 83151 | 2771.7 | 1 | 2400.6937 | 0.6 | 1723.44 | 768.222 | 3 | 7202.0812 | 5.3 | 14752.42 | 6785.961 | 7 | 16804.8563 | 10.5 | 29150.325 | 13443.885 | 11 | 26407.6312 | 16.6 | 45989.77 | 21254.142 | 15 | 36010.4062 | 22.7 | 62865.12 | 29064.399 | 16 | 38411.1 | 28.4 | 78771.035 | 36362.508 | 16 | 38411.1 | 29.5 | 81894.77 | 37770.915 | 16 | 38411.1 | 30 | 84084.975 | 38411.1
903 | Project Facilities | 16 | week | 30636.8 | 1914.8 | 30 | 16884 | 562.8 | 1 | 1914.8 | 0 | 0 | 0 | 3 | 5744.4 | 5.7 | 3200 | 5820.992 | 7 | 13403.6 | 10 | 5655.58 | 10212.2667 | 11 | 21062.8 | 12.3 | 6907.74 | 12561.088 | 15 | 28722 | 17.9 | 10075.24 | 18279.9573 | 16 | 30636.8 | 18.3 | 10310.44 | 18688.448 | 16 | 30636.8 | 27.7 | 15568.75 | 28287.9787 | 16 | 30636.8 | 30 | 16883.86 | 30636.8
904 | Project Insurance, Fees & Levies | 1 | item | 26060 | 26060 | 1 | 18189 | 18189 | 0.5 | 13030 | 0.3 | 5968.45 | 7818 | 1 | 26060 | 0.9 | 16540.17 | 23454 | 1 | 26060 | 0.98 | 17953.64 | 25538.8 | 1 | 26060 | 1 | 18142.96 | 26060 | 1 | 26060 | 1 | 18188.8 | 26060 | 1 | 26060 | 1 | 18188.8 | 26060 | 1 | 26060 | 1 | 18188.8 | 26060 | 1 | 26060 | 1 | 18188.8 | 26060
905 | Small Tools | 1 | item | 4224 | 4224 | 1.08 | 4559 | 4221.2963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 98 | 78.2222 | 0.25 | 1056 | 0.6 | 2503.936 | 2346.6667 | 0.5 | 2112 | 0.7 | 3037.006 | 2737.7778 | 0.75 | 3168 | 1.02 | 4319.696 | 3989.3333 | 1 | 4224 | 1 | 4374.156 | 3911.1111 | 1 | 4224 | 1 | 4428.606 | 3911.1111 | 1 | 4224 | 1.08 | 4558.836 | 4224
907 | Site Establishment | 1 | item | 13900 | 13900 | 1 | 8228 | 8228 | 0.25 | 3475 | 0 | 0 | 0 | 1 | 13900 | 0.2 | 2425.73 | 2780 | 1 | 13900 | 0.5 | 4334.78 | 6950 | 1 | 13900 | 0.5 | 4334.78 | 6950 | 1 | 13900 | 0.5 | 4594.78 | 6950 | 1 | 13900 | 0.5 | 4594.78 | 6950 | 1 | 13900 | 1 | 8228.36 | 13900 | 1 | 13900 | 1 | 8728.36 | 13900
910 | De-Establishment & Cleanup | 1 | item | 16740 | 16740 | 1 | 3875 | 3875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 16740 | 0 | 350 | 0 | 1 | 16740 | 1 | 3874.9 | 16740
C25 | 25 Mpa | 100.7 | m3 | 15804.8256 | 156.9496 | 136.5 | 21588 | 158.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 3923.7402 | 4.5 | 708.96 | 521.0382 | 50 | 7847.4804 | 58 | 9225.8 | 6715.6036 | 50 | 7847.4804 | 112 | 16426.64 | 12968.062 | 100.7 | 15804.8256 | 125 | 18574.52 | 14473.2835 | 100.7 | 15804.8256 | 136.5 | 20388.2 | 15804.8256
C32 | 32 Mpa | 51.26 | m3 | 9507.2157 | 185.4705 | 213 | 39263 | 184.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 9010.3 | 2187.106 | 35 | 6491.466 | 84 | 15597.72 | 3749.3245 | 51.26 | 9507.2157 | 186 | 34343.428 | 8302.0757 | 51.26 | 9507.2157 | 213 | 39263.228 | 9507.2157 | 51.26 | 9507.2157 | 213 | 39263.228 | 9507.2157
CKM | Kerb Mix | 111 | m3 | 25589.6987 | 230.5378 | 136 | 25054 | 184.2206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1844.3026 | 0 | 0 | 0 | 8 | 1844.3026 | 7.5 | 1377.4 | 1411.1966 | 29 | 6685.597 | 9 | 1673.43 | 1693.4359 | 111 | 25589.6987 | 16 | 2873.13 | 3010.5528 | 111 | 25589.6987 | 19 | 3561.83 | 3575.0314 | 111 | 25589.6987 | 136 | 3561.83 | 25589.6987
CSA | Cement Powder ( stabilising) | 36 | tonne | 332 | 9.2222 | 36 | 12852 | 357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 36 | 332 |  | 12852 | 0 | 36 | 332 | 36 | 12852 | 332 | 36 | 332 | 36 | 12852 | 332 | 36 | 332 | 36 | 12852 | 332
ETC | Conduits | 1465 | m | 7656.1375 | 5.226 | 1465 | 12317 | 8.4075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1465 | 7656.1375 | 1465 | 6927.4 | 7656.1375 | 1465 | 7656.1375 | 1465 | 9843.5 | 7656.1375 | 1465 | 7656.1375 | 1465 | 12304.5 | 7656.1375 | 1465 | 7656.1375 | 1465 | 12317.34 | 7656.1375 | 1465 | 7656.1375 | 1465 | 12317.34 | 7656.1375 | 1465 | 7656.1375 | 1465 | 12317.34 | 7656.1375
ETM | Miscellaneous (rope, glue, plugs etc) | 1 | item | 14766.488 | 14766.488 | 1 | 9591 | 9591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 14766.488 | 0 | 133.5 | 0 | 1 | 14766.488 |  | 1367.31 | 0 | 1 | 14766.488 |  | 7011.31 | 0 | 1 | 14766.488 | 0.75 | 8711.31 | 11074.866 | 1 | 14766.488 | 1 | 8711.31 | 14766.488 | 1 | 14766.488 | 1 | 9591.31 | 14766.488
ETP | Pits & Lids | 21 | each | 17803.8 | 847.8 | 21 | 13861 | 660.0476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 11286 | 7630.2 | 21 | 17803.8 | 15 | 11286 | 12717 | 21 | 17803.8 | 21 | 11286 | 17803.8 | 21 | 17803.8 | 21 | 13786 | 17803.8 | 21 | 17803.8 | 21 | 13786 | 17803.8 | 21 | 17803.8 | 21 | 13861 | 17803.8
QM2.1 | CBR80 | 7995 | tonne | 170720.1562 | 21.3534 | 5536 | 120191 | 21.7108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 53383.4135 | 1472 | 31974.728 | 45393.7988 | 4000 | 85413.4615 | 1472 | 31974.728 | 45393.7988 | 7000 | 149473.5577 | 2423 | 104735.335 | 74720.9065 | 7995 | 170720.1562 | 5536 | 179448.091 | 170720.1562 | 7995 | 170720.1562 | 5536 | 275197.551 | 170720.1562 | 7995 | 170720.1562 | 5536 | 275197.551 | 170720.1562
QMR | Rock | 9.4 | tonne | 385.4 | 41 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.4 | 385.4 | 9.4 | 0 | 385.4
QMS | Sand | 2200 | tonne | 10432.6795 | 4.7421 | 2297 | 50632 | 22.0427 | 0 | 0 | 0 | 0 | 0 | 100 | 474.2127 | 0 | 0 | 0 | 300 | 1422.6381 | 15 | 337.16 | 68.1281 | 1300 | 6164.7652 | 51 | 1132.0014 | 231.6355 | 2200 | 10432.6795 | 2297 | 1418.3574 | 10432.6795 | 2200 | 10432.6795 | 2297 | 117805.621 | 10432.6795 | 2200 | 10432.6795 | 2297 | 117965.4818 | 10432.6795 | 2200 | 10432.6795 | 2297 | 117965.4818 | 10432.6795
RFS | Signs | 1 | item | 840 | 840 | 1 | 4982 | 4982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132.8 | 0 | 0 | 0 | 0 | 132.8 | 0 | 0 | 0 | 0 | 132.8 | 0 | 0 | 0 | 0.5 | 2814.84 | 420 | 1 | 840 | 1 | 4982.43 | 840 | 1 | 840 | 1 | 4982.43 | 840 | 1 | 840 | 1 | 4982.43 | 840
RSB | Straight / Bent Bar | 750 | m | 1243.65 | 1.6582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1243.65 | 0 | 0 | 0 | 750 | 1243.65 | 0 | 0 | 1243.65 | 750 | 1243.65 | 0 | 0 | 0 | 750 | 1243.65 | 0 | 0 | 1243.65
RSM | Mesh | 1009 | m2 | 7815.0187 | 7.7453 | 1009 | 2626 | 2.6026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 3872.6554 | 0 | 0 | 0 | 500 | 3872.6554 | 0 | 136.65 | 0 | 1009 | 7815.0187 | 1009 | 2625.85 | 7815.0187 | 1009 | 7815.0187 | 1009 | 2625.85 | 7815.0187 | 1009 | 7815.0187 | 1009 | 2625.85 | 7815.0187
SWH | Headwalls | 4 | each | 1378 | 344.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1378 | 0 | 0 | 0 | 4 | 1378 | 0 | 0 | 0 | 4 | 1378 | 0 | 0 | 0 | 4 | 1378 | 0 | 0 | 0 | 4 | 1378 | 0 | 0 | 0 | 4 | 1378 | 0 | 0 | 1378
SWL | Grates, Frames & Lids | 13 | each | 17624 | 1355.6923 | 13 | 17615 | 1355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 16131 | 16268.3077 | 13 | 17624 | 13 | 17615 | 17624 | 13 | 17624 | 13 | 17615 | 17624 | 13 | 17624 | 13 | 17615 | 17624 | 13 | 17624 | 13 | 17615 | 17624
SWP | RCP | 197.6 | m | 15635.4424 | 79.1267 | 197.6 | 13684 | 69.251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 7912.6733 | 183 | 12762 | 14480.1921 | 197.6 | 15635.4424 | 183 | 12762 | 14480.1921 | 197.6 | 15635.4424 | 197.6 | 13464 | 15635.4424 | 197.6 | 15635.4424 | 197.6 | 13684 | 15635.4424 | 197.6 | 15635.4424 | 197.6 | 13684 | 15635.4424 | 197.6 | 15635.4424 | 197.6 | 13684 | 15635.4424
WW | Wet Weather Allowance for labourers for down time | 117 | hrs | 380 | 3.2479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 81.1966 | 0 | 0 | 0 | 50 | 162.3932 | 0 | 0 | 0 | 75 | 243.5897 |  | 0 | 0 | 100 | 324.7863 |  |  | 0 | 117 | 380 |  |  | 0 | 117 | 380 | 0 | 0 | 0 | 117 | 380 | 0 | 0 | 380
| Totals |  |  | 1953141.4285 |  |  | 1890995 |  |  | 31412.941 |  | 9434.08 | 13592.6279 |  | 157233.6446 |  | 101629.82 | 108625.3355 |  | 507660.2589 |  | 351914.504 | 367518.7815 |  | 773880.2092 |  | 596024.9876 | 617289.3689 |  | 1319041.8493 |  | 952390.1656 | 925399.6181 |  | 1847494.9063 |  | 1442327.1472 | 1458213.4095 |  | 1951423.1289 |  | 1834086.588 | 1758815.9862 |  | 1953141.4285 |  | 1982828.898 | 1953141.4285
|  |  | PV | EV | AC
|  | 2011-04-01 | 31412.941 | 13592.6279 | 9434.08
|  | 2011-05-01 | 157233.6446 | 108625.3355 | 101629.82
|  | 2011-06-01 | 507660.2589 | 367518.7815 | 351914.504
|  | 2011-07-01 | 773880.2092 | 617289.3689 | 596024.9876
|  | 2011-08-01 | 1319041.8493 | 925399.6181 | 952390.1656
|  | 2011-09-01 | 1847494.9063 | 1458213.4095 | 1442327.1472
|  | 2011-10-01 | 1951423.1289 | 1758815.9862 | 1834086.588
|  | 2011-11-01 | 1953141.4285 | 1953141.4285 | 1982828.898

## Actual Costs
Date | Description | Resource | Unit | Quantity | Rate | BOQ No. | Total | Portfolio WBS | 2007 | Portfolio WBS | TOTAL | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01
Portfolio WBS 011
2011-04-13 | Survey Team - Inv SI3621340 | Surveyor |  | 1 | 1400 |  | 1400 | 11 |  | 11 | 28430.2 | 1400 | 1400 | 5908.3 | 9071.75 | 19878.3 | 20668.8 | 24220.2 | 28430.2
2011-06-28 | Survey Team - Inv SI3624729 | Surveyor |  | 1 | 4508.3 |  | 4508.3 | 11 |  | 13 | 7650 | 0 | 90 | 2650 | 5050 | 6850 | 7650 | 7650 | 7650
2011-07-13 | Survey Team - Inv SI3626127 | Surveyor |  | 1 | 3163.45 |  | 3163.45 | 11 |  | 15 | 1105 | 0 | 0 | 0 | 130 | 130 | 910 | 1105 | 1105
2011-08-15 | Survey Team - Inv SI3627800 | Surveyor |  | 1 | 10806.55 |  | 10806.55 | 11 |  | 21 | 12095.585 | 0 | 9101.37 | 9101.37 | 11312.405 | 12095.585 | 12095.585 | 12095.585 | 12095.585
2011-09-22 | Survey Team Inv - SI3630067 | Surveyor |  | 1 | 790.5 |  | 790.5 | 11 |  | 31 | 17446.665 | 0 | 13286.15 | 13286.15 | 16303.485 | 17446.665 | 17446.665 | 17446.665 | 17446.665
2011-10-21 | Survey Team Inv - SI3631479 | Surveyor |  | 1 | 3551.4 |  | 3551.4 | 11 |  | 33 | 14500.11 | 0 | 0 | 0 | 0 | 4051.73 | 12235.91 | 14500.11 | 14500.11
2011-11-30 | Survey Team Inv No Si3633885 | Surveyor |  | 1 | 2268.75 |  | 2268.75 | 11 |  | 41 | 13910.675 | 0 | 0 | 0 | 8267.735 | 9050.675 | 13910.675 | 13910.675 | 13910.675
2011-11-30 | Inv No - SI3636319 | Field Density |  | 1 | 1941.25 |  | 1941.25 | 11 |  | 51 | 49136.349 | 0 | 2823.9 | 2823.9 | 19971.645 | 36896.175 | 49136.349 | 49136.349 | 49136.349
| Subtotal for 011 | [5 empty] | 28430.2 |  |  | 52 | 164870.94 | 0 | 1484 | 87840.845 | 130649.97 | 164870.94 | 164870.94 | 164870.94 | 164870.94
[10 empty] | 53 | 11630.28 | 0 | 0 | 317.56 | 317.56 | 3858.56 | 11630.28 | 11630.28 | 11630.28
| Portfolio WBS 013 | [8 empty] | 57 | 41783.66 | 0 | 0 | 8333.54 | 29372.455 | 40753.905 | 41783.66 | 41783.66 | 41783.66
2011-05-27 | Inv 69103134 | Field Density |  | 1 | 90 |  | 90 | 13 |  | 61 | 6722.72 | 0 | 2730.24 | 4354.06 | 4354.06 | 6279.92 | 6722.72 | 6722.72 | 6722.72
2011-06-17 | Inv 69103259 | Field Density |  | 1 | 1030 |  | 1030 | 13 |  | 62 | 91849.125 | 0 | 0 | 4650.18 | 17611.695 | 48779.54 | 84713.125 | 91849.125 | 91849.125
2011-06-30 | Inv 69103326 | Field Density |  | 1 | 1530 |  | 1530 | 13 |  | 63 | 45939.655 | 0 | 78.78 | 6951.665 | 21171.29 | 35928.425 | 45939.655 | 45939.655 | 45939.655
2011-07-19 | inv 69121055 | Field Density |  | 1 | 1440 |  | 1440 | 13 |  | 64 | 105957.8072 | 0 | 0 | 0 | 22054.7472 | 58444.7472 | 105957.8072 | 105957.8072 | 105957.8072
2011-07-29 | Inv 69121114 | Field Density |  | 1 | 840 |  | 840 | 13 |  | 65 | 185012.62 | 0 | 0 | 0 | 0 | 0 | 315.12 | 185012.62 | 185012.62
2011-07-29 | Inv 69121246 - Compressive test | Field Density |  | 1 | 120 |  | 120 | 13 |  | 66 | 11724.39 | 0 | 0 | 0 | 0 | 753.39 | 753.39 | 753.39 | 11724.39
2011-08-19 | inv-69121327 | Field Density |  | 1 | 720 |  | 720 | 13 |  | 67 | 2865.175 | 0 | 0 | 0 | 0 | 0 | 713.5 | 713.5 | 2865.175
2011-08-26 | inv -69121355 | Field Density |  | 1 | 1080 |  | 1080 | 13 |  | 68 | 868.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 868.4
2011-09-26 | Survey Team Moisture Dentisty Relationship Inv - 69121624 | Surveyor |  | 1 | 480 |  | 480 | 13 |  | 71 | 37066.6 | 0 | 0 | 0 | 1995.8 | 2580.3 | 3724.5 | 5024.5 | 37066.6
2011-09-30 | Survey Team Inv - CBW 69121780 | Surveyor |  | 1 | 320 |  | 320 | 13 |  | 73 | 33676.9 | 0 | 0 | 0 | 0 | 16041.175 | 18009.8 | 31516.9 | 33676.9
| Subtotal for 013 | [5 empty] | 7650 |  |  | 81 | 17494.82 | 0 | 0 | 157.56 | 13194.42 | 13464.42 | 17494.82 | 17494.82 | 17494.82
[10 empty] | 85 | 25120.69 | 0 | 0 | 0 | 4000 | 13197.58 | 24799.29 | 25120.69 | 25120.69
| Portfolio WBS 015 | [8 empty] | 95 | 145242.12 | 0 | 29539.91 | 62560.92 | 63546.92 | 65136.92 | 138951.92 | 139556.12 | 145242.12
2011-07-13 | Inv 102480 | Service Locator |  | 1 | 130 |  | 130 | 15 |  | 103 | 8325 | 0 | 2320 | 2905 | 2905 | 8135 | 8135 | 8135 | 8325
2011-09-09 | Inv - 102578 | Service Locator |  | 6 | 130 |  | 780 | 15 |  | 111 | 40668.49 | 0 | 0 | 13375 | 34451.34 | 34631.34 | 37173.59 | 39337.69 | 40668.49
2011-10-31 | Survey Team Inv - 102651 | Surveyor |  | 1.5 | 130 |  | 195 | 15 |  | 112 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150
| Subtotal for 015 | [5 empty] | 1105 |  |  | 113 | 84469.435 | 0 | 0 | 0 | 1705.425 | 12625.425 | 29136.825 | 84469.435 | 84469.435
[10 empty] | 121 | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7800
| Portfolio WBS 021 | [8 empty] | 131 | 63042.17 | 0 | 0 | 0 | 0 | 1680.35 | 1680.35 | 1963.53 | 63042.17
2011-05-19 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 21 |  | 134 | 708.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 708.3
2011-05-19 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9 | 135 |  | 1215 | 21 |  | 141 | 14798.475 | 0 | 0 | 0 | 0 | 1485.7 | 4892 | 6323.675 | 14798.475
2011-05-20 | Labour | Labour | hr | 8.5 | 39.39 |  | 334.815 | 21 |  | 142 | 4339.41 | 0 | 0 | 0 | 0 | 1454.11 | 1454.11 | 4339.41 | 4339.41
2011-05-20 | Tipper Hire | K.C Truck Hire | hr | 9.5 | 95 |  | 902.5 | 21 |  | 151 | 177.255 | 0 | 0 | 177.255 | 177.255 | 177.255 | 177.255 | 177.255 | 177.255
2011-05-20 | Tipper Hire | Berry Excavations -Tipper | hr | 9.5 | 95 |  | 902.5 | 21 |  | 152 | 2805.915 | 0 | 590.85 | 1343.85 | 1931.275 | 2805.915 | 2805.915 | 2805.915 | 2805.915
2011-05-20 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9 | 135 |  | 1215 | 21 |  | 221 | 491.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491.47
2011-05-20 | Chainsaw Hire - Flexihire | Chainsaw | day | 1 | 89 |  | 89 | 21 |  | 901 | 2727.54 | 342.19 | 1035.5 | 2025.5 | 2340.5 | 2727.54 | 2727.54 | 2727.54 | 2727.54
2011-05-21 | Tipper Hire | Berry Excavations -Tipper | hr | 2 | 95 |  | 190 | 21 |  | 902 | 84084.975 | 1723.44 | 14752.42 | 29150.325 | 45989.77 | 62865.12 | 78771.035 | 81894.77 | 84084.975
2011-05-21 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 2 | 135 |  | 270 | 21 |  | 903 | 16883.86 | 0 | 3200 | 5655.58 | 6907.74 | 10075.24 | 10310.44 | 15568.75 | 16883.86
2011-05-21 | Tipper Hire | K.C Truck Hire | hr | 2 | 95 |  | 190 | 21 |  | 904 | 18188.8 | 5968.45 | 16540.17 | 17953.64 | 18142.96 | 18188.8 | 18188.8 | 18188.8 | 18188.8
2011-05-21 | Labour | Labour | hr | 1 | 39.39 |  | 39.39 | 21 |  | 905 | 4558.836 | 0 | 98 | 2503.936 | 3037.006 | 4319.696 | 4374.156 | 4428.606 | 4558.836
2011-05-27 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 5.5 | 135 |  | 742.5 | 21 |  | 907 | 8728.36 | 0 | 2425.73 | 4334.78 | 4334.78 | 4594.78 | 4594.78 | 8228.36 | 8728.36
2011-05-27 | Labour | Labour | hr | 1 | 39.39 |  | 39.39 | 21 |  | 910 | 3874.9 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 3874.9
2011-05-27 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 21 |  | C25 | 20388.2 | 0 | 0 | 0 | 708.96 | 9225.8 | 16426.64 | 18574.52 | 20388.2
2011-05-30 | Tipper Hire | Berry Excavations -Tipper | hr | 2 | 95 |  | 190 | 21 |  | C32 | 39263.228 | 0 | 0 | 0 | 9010.3 | 15597.72 | 34343.428 | 39263.228 | 39263.228
2011-05-30 | Tipper Hire | K.C Truck Hire | hr | 4 | 95 |  | 380 | 21 |  | CKM | 3561.83 | 0 | 0 | 0 | 1377.4 | 1673.43 | 2873.13 | 3561.83 | 3561.83
2011-05-30 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 21 |  | CSA | 12852 | 0 | 0 | 0 | 0 | 12852 | 12852 | 12852 | 12852
2011-05-30 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 4 | 135 |  | 540 | 21 |  | ETC | 12317.34 | 0 | 0 | 6927.4 | 9843.5 | 12304.5 | 12317.34 | 12317.34 | 12317.34
2011-05-31 | Tipper Hire | K.C Truck Hire | hr | 3 | 95 |  | 285 | 21 |  | ETM | 9591.31 | 0 | 0 | 133.5 | 1367.31 | 7011.31 | 8711.31 | 8711.31 | 9591.31
2011-05-31 | Tipper Hire | Pollards Earthmoving | hr | 3 | 95 |  | 285 | 21 |  | ETP | 13861 | 0 | 0 | 11286 | 11286 | 11286 | 13786 | 13786 | 13861
2011-05-31 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 3 | 135 |  | 405 | 21 |  | QM2.1 | 275197.551 | 0 | 0 | 31974.728 | 31974.728 | 104735.335 | 179448.091 | 275197.551 | 275197.551
2011-05-31 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 21 |  | QMS | 117965.4818 | 0 | 0 | 337.16 | 1132.0014 | 1418.3574 | 117805.621 | 117965.4818 | 117965.4818
2011-05-31 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 21 |  | RFS | 4982.43 | 0 | 132.8 | 132.8 | 132.8 | 2814.84 | 4982.43 | 4982.43 | 4982.43
2011-07-21 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 21 |  | RSM | 2625.85 | 0 | 0 | 0 | 0 | 136.65 | 2625.85 | 2625.85 | 2625.85
2011-07-21 | Labour | Labour | hr | 2.5 | 39.39 |  | 98.475 | 21 |  | SWL | 17615 | 0 | 0 | 0 | 16131 | 17615 | 17615 | 17615 | 17615
2011-07-21 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 4.5 | 135 |  | 607.5 | 21 |  | SWP | 13684 | 0 | 0 | 12762 | 12762 | 13464 | 13684 | 13684 | 13684
2011-07-21 | Tipper Hire | Lovell Earthmoving | hr | 4 | 90 |  | 360 | 21
2011-07-21 | Tipper Hire | Labour | hr | 4 | 95 |  | 380 | 21 |  | TOTAL | 1982828.898 | 9434.08 | 101629.82 | 351914.504 | 596024.9876 | 952390.1656 | 1442327.1472 | 1834086.588 | 1982828.898
2011-07-25 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 4.5 | 135 |  | 607.5 | 21
2011-08-29 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 2 | 135 |  | 270 | 21
2011-08-29 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 21
2011-08-29 | Labour | Labour | hr | 2 | 32.2 |  | 64.4 | 21
2011-08-29 | Tipper Hire | Lovell Earthmoving | hr | 2 | 90 |  | 180 | 21
2011-08-29 | Tipper Hire | Labour | hr | 2 | 95 |  | 190 | 21
| Subtotal for 021 | [5 empty] | 12095.585
Portfolio WBS 031
2011-05-20 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 5 | 80 |  | 400 | 31
2011-05-21 | Labour | Labour | hr | 5.5 | 39.39 |  | 216.645 | 31
2011-05-21 | Tipper Hire | Berry Excavations -Tipper | hr | 4 | 95 |  | 380 | 31
2011-05-21 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 6 | 80 |  | 480 | 31
2011-05-21 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 4 | 135 |  | 540 | 31
2011-05-21 | Tipper Hire | K.C Truck Hire | hr | 4 | 95 |  | 380 | 31
2011-05-24 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 31
2011-05-24 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 3 | 135 |  | 405 | 31
2011-05-24 | Tipper Hire | Berry Excavations -Tipper | hr | 3 | 95 |  | 285 | 31
2011-05-25 | Tipper Hire | Berry Excavations -Tipper | hr | 9 | 95 |  | 855 | 31
2011-05-25 | Tipper Hire | K.C Truck Hire | hr | 9 | 95 |  | 855 | 31
2011-05-25 | Labour | Labour | hr | 4.5 | 39.39 |  | 177.255 | 31
2011-05-25 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9 | 135 |  | 1215 | 31
2011-05-26 | Labour | Labour | hr | 4.5 | 39.39 |  | 177.255 | 31
2011-05-26 | Tipper Hire | K.C Truck Hire | hr | 9 | 95 |  | 855 | 31
2011-05-26 | Tipper Hire | Berry Excavations -Tipper | hr | 9 | 95 |  | 855 | 31
2011-05-26 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9 | 135 |  | 1215 | 31
2011-05-30 | Tipper Hire | K.C Truck Hire | hr | 4 | 95 |  | 380 | 31
2011-05-30 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 3.5 | 135 |  | 472.5 | 31
2011-05-30 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 31
2011-05-30 | Labour | Labour | hr | 4.5 | 39.39 |  | 177.255 | 31
2011-05-31 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 4 | 80 |  | 320 | 31
2011-05-31 | Tipper Hire | K.C Truck Hire | hr | 5.5 | 95 |  | 522.5 | 31
2011-05-31 | Tipper Hire | Pollards Earthmoving | hr | 5.5 | 95 |  | 522.5 | 31
2011-05-31 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 6 | 135 |  | 810 | 31
2011-05-31 | Labour | Labour | hr | 6.5 | 39.39 |  | 256.035 | 31
2011-05-31 | Labour | Labour | hr | 6.5 | 39.39 |  | 256.035 | 31
2011-07-11 | Tipper Hire | Michael J Biles | hr | 2.5 | 95 |  | 237.5 | 31
2011-07-11 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 2 | 135 |  | 270 | 31
2011-07-11 | Labour | Labour | hr | 3.5 | 39.39 |  | 137.865 | 31
2011-07-12 | Tipper Hire | Lovell Earthmoving | hr | 2.5 | 90 |  | 225 | 31
2011-07-12 | Tipper Hire | Michael J Biles | hr | 2.5 | 95 |  | 237.5 | 31
2011-07-12 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 2 | 135 |  | 270 | 31
2011-07-22 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 3.5 | 135 |  | 472.5 | 31
2011-07-22 | Tipper Hire | Lovell Earthmoving | hr | 3.5 | 90 |  | 315 | 31
2011-07-22 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 31
2011-07-22 | Tipper Hire | Labour | hr | 3 | 95 |  | 285 | 31
2011-07-26 | Labour | Labour | hr | 4 | 32.2 |  | 128.8 | 31
2011-07-26 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 4 | 80 |  | 320 | 31
2011-08-29 | Labour | Labour | hr | 2 | 32.2 |  | 64.4 | 31
2011-08-29 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 31
2011-08-29 | Tipper Hire | Labour | hr | 2 | 95 |  | 190 | 31
2011-08-29 | Tipper Hire | Lovell Earthmoving | hr | 2 | 90 |  | 180 | 31
2011-08-29 | Backhoe Hire | McDowall Earthmoving | hr | 4 | 90 |  | 360 | 31
2011-08-29 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 2 | 135 |  | 270 | 31
| Subtotal for 031 | [5 empty] | 17446.665
Portfolio WBS 033
2011-08-09 | Tipper Hire | Lovell Earthmoving | hr | 3 | 90 |  | 270 | 33
2011-08-09 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 33
2011-08-09 | Tipper Hire | Pollards Earthmoving | hr | 3.5 | 95 |  | 332.5 | 33
2011-08-09 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 3 | 135 |  | 405 | 33
2011-08-23 | Backhoe Hire | McDowall Earthmoving | hr | 3.25 | 90 |  | 292.5 | 33
2011-08-24 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 33
2011-08-25 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 33
2011-08-25 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 33
2011-08-30 | Backhoe Hire | McDowall Earthmoving | hr | 4 | 90 |  | 360 | 33
2011-08-31 | Backhoe Hire | McDowall Earthmoving | hr | 5 | 90 |  | 450 | 33
2011-08-31 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 5 | 80 |  | 400 | 33
2011-08-31 | Tipper Hire | Pollards Earthmoving | hr | 5 | 95 |  | 475 | 33
2011-08-31 | Labour | Labour | hr | 5 | 39.39 |  | 196.95 | 33
2011-08-31 | Labour | Labour | hr | 5 | 32.2 |  | 161 | 33
2011-09-01 | Tipper Hire | Lovell Earthmoving | hr | 7 | 90 |  | 630 | 33
2011-09-01 | Labour | Labour | hr | 5 | 32.2 |  | 161 | 33
2011-09-01 | Backhoe Hire | McDowall Earthmoving | hr | 7 | 90 |  | 630 | 33
2011-09-01 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 33
2011-09-01 | Labour | Labour | hr | 5 | 39.39 |  | 196.95 | 33
2011-09-01 | Tipper Hire | Pollards Earthmoving | hr | 7 | 95 |  | 665 | 33
2011-09-02 | Tipper Hire | Lovell Earthmoving | hr | 2 | 90 |  | 180 | 33
2011-09-02 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 33
2011-09-05 | Backhoe Hire | McDowall Earthmoving | hr | 2.25 | 90 |  | 202.5 | 33
2011-09-05 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 2 | 135 |  | 270 | 33
2011-09-06 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 6 | 135 |  | 810 | 33
2011-09-06 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 33
2011-09-06 | Backhoe Hire | McDowall Earthmoving | hr | 6 | 90 |  | 540 | 33
2011-09-09 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 33
2011-09-09 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 3 | 135 |  | 405 | 33
2011-09-10 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 33
2011-09-15 | Backhoe Hire | McDowall Earthmoving | hr | 4 | 90 |  | 360 | 33
2011-09-20 | Backhoe Hire | McDowall Earthmoving | hr | 4.75 | 90 |  | 427.5 | 33
2011-09-20 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 3 | 80 |  | 240 | 33
2011-09-22 | Backhoe Hire | McDowall Earthmoving | hr | 6 | 90 |  | 540 | 33
2011-09-27 | Backhoe Hire | McDowall Earthmoving | hr | 6 | 90 |  | 540 | 33
2011-09-27 | Labour | Labour | hr | 2.5 | 35.35 |  | 88.375 | 33
2011-09-27 | Labour | Labour | hr | 2.5 | 35.35 |  | 88.375 | 33
2011-09-28 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 33
2011-09-28 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 33
2011-10-03 | Tipper Hire | Lovell Earthmoving | hr | 2 | 90 |  | 180 | 33
2011-10-03 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 33
2011-10-03 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 33
2011-10-03 | Backhoe Hire | McDowall Earthmoving | hr | 7 | 90 |  | 630 | 33
2011-10-04 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 33
2011-10-04 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 33
2011-10-04 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 33
2011-10-05 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 5 | 80 |  | 400 | 33
2011-10-05 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 33
2011-10-05 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 33
2011-10-05 | Tipper Hire | Lovell Earthmoving | hr | 3 | 90 |  | 270 | 33
2011-10-05 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 33
| Subtotal for 033 | [5 empty] | 14500.11
Portfolio WBS 041
2011-07-11 | Tipper Hire | Michael J Biles | hr | 3 | 95 |  | 285 | 41
2011-07-11 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 3 | 135 |  | 405 | 41
2011-07-12 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 41
2011-07-12 | Tipper Hire | Lovell Earthmoving | hr | 3 | 90 |  | 270 | 41
2011-07-12 | Tipper Hire | Michael J Biles | hr | 3 | 95 |  | 285 | 41
2011-07-12 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 3 | 135 |  | 405 | 41
2011-07-12 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 41
2011-07-13 | Labour | Labour | hr | 5 | 39.39 |  | 196.95 | 41
2011-07-13 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 6 | 135 |  | 810 | 41
2011-07-13 | Tipper Hire | Lovell Earthmoving | hr | 6 | 90 |  | 540 | 41
2011-07-13 | Tipper Hire | K.C Truck Hire | hr | 2 | 95 |  | 190 | 41
2011-07-13 | Labour | Labour | hr | 5 | 39.39 |  | 196.95 | 41
2011-07-14 | Labour | Labour | hr | 5 | 39.39 |  | 196.95 | 41
2011-07-14 | Tipper Hire | Lovell Earthmoving | hr | 3.5 | 90 |  | 315 | 41
2011-07-14 | Tipper Hire | K.C Truck Hire | hr | 3 | 95 |  | 285 | 41
2011-07-14 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 4 | 135 |  | 540 | 41
2011-07-14 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 41
2011-07-22 | Tipper Hire | Lovell Earthmoving | hr | 6 | 90 |  | 540 | 41
2011-07-22 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 6 | 135 |  | 810 | 41
2011-07-22 | Labour | Labour | hr | 6.5 | 39.39 |  | 256.035 | 41
2011-07-23 | Tipper Hire | Labour | hr | 5 | 95 |  | 475 | 41
2011-07-23 | Labour | Labour | hr | 6 | 39.39 |  | 236.34 | 41
2011-07-23 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 5 | 135 |  | 675 | 41
2011-08-30 | Labour | Labour | hr | 3 | 32.2 |  | 96.6 | 41
2011-08-30 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 41
2011-08-30 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 41
2011-08-30 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 2 | 135 |  | 270 | 41
2011-08-30 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 41
2011-09-13 | Tipper Hire | Raymond Truck Hire |  | 10.5 | 125 |  | 1312.5 | 41
2011-09-13 | Side Tipper Hire | Raymond Truck Hire |  | 10.75 | 125 |  | 1343.75 | 41
2011-09-13 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 8.5 | 135 |  | 1147.5 | 41
2011-09-14 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 2.5 | 135 |  | 337.5 | 41
2011-09-14 | Side Tipper Hire | Raymond Truck Hire |  | 1.75 | 125 |  | 218.75 | 41
2011-09-14 | Tipper Hire | Raymond Truck Hire |  | 4 | 125 |  | 500 | 41
| Subtotal for 041 | [5 empty] | 13910.675
Portfolio WBS 051
2011-05-24 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 6 | 135 |  | 810 | 51
2011-05-24 | Labour | Labour | hr | 6.5 | 39.39 |  | 256.035 | 51
2011-05-24 | Tipper Hire | Berry Excavations -Tipper | hr | 6 | 95 |  | 570 | 51
2011-05-24 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 51
2011-05-24 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 51
2011-05-25 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 51
2011-05-25 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 51
2011-05-26 | Labour | Labour | hr | 3.5 | 39.39 |  | 137.865 | 51
2011-07-12 | Tipper Hire | Michael J Biles | hr | 4 | 95 |  | 380 | 51
2011-07-12 | Tipper Hire | Lovell Earthmoving | hr | 4 | 90 |  | 360 | 51
2011-07-12 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 3 | 80 |  | 240 | 51
2011-07-12 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 4 | 135 |  | 540 | 51
2011-07-12 | Labour | Labour | hr | 7 | 39.39 |  | 275.73 | 51
2011-07-12 | Tipper Hire | K.C Truck Hire | hr | 4 | 95 |  | 380 | 51
2011-07-12 | Labour | Labour | hr | 7 | 39.39 |  | 275.73 | 51
2011-07-13 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 51
2011-07-13 | Labour | Labour | hr | 3.5 | 39.39 |  | 137.865 | 51
2011-07-13 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 3.5 | 135 |  | 472.5 | 51
2011-07-13 | Tipper Hire | Lovell Earthmoving | hr | 3 | 90 |  | 270 | 51
2011-07-13 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 51
2011-07-13 | Tipper Hire | K.C Truck Hire | hr | 7 | 95 |  | 665 | 51
2011-07-14 | Tipper Hire | Lovell Earthmoving | hr | 2 | 90 |  | 180 | 51
2011-07-14 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 51
2011-07-14 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 51
2011-07-14 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 51
2011-07-14 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 2.5 | 135 |  | 337.5 | 51
2011-07-14 | Tipper Hire | K.C Truck Hire | hr | 2 | 95 |  | 190 | 51
2011-07-27 | Tipper Hire | Lovell Earthmoving | hr | 6.5 | 90 |  | 585 | 51
2011-07-27 | Tipper Hire | Labour | hr | 4 | 95 |  | 380 | 51
2011-07-27 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 51
2011-07-27 | Backhoe Hire | McDowall Earthmoving | hr | 9 | 90 |  | 810 | 51
2011-07-27 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 4 | 80 |  | 320 | 51
2011-07-27 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 51
2011-07-27 | Pad Foot Roller - Dry - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 51
2011-07-28 | Labour | Labour | hr | 4 | 32.2 |  | 128.8 | 51
2011-07-28 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 51
2011-07-28 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 51
2011-07-28 | Pad Foot Roller - Dry - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 51
2011-07-28 | Tipper Hire | Lovell Earthmoving | hr | 6 | 90 |  | 540 | 51
2011-07-28 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 5.5 | 135 |  | 742.5 | 51
2011-07-29 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 51
2011-07-29 | Pad Foot Roller - Dry - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 51
2011-07-29 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 1 | 80 |  | 80 | 51
2011-07-29 | Labour | Labour | hr | 4 | 32.2 |  | 128.8 | 51
2011-07-29 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 4 | 135 |  | 540 | 51
2011-07-29 | Tipper Hire | Labour | hr | 2 | 95 |  | 190 | 51
2011-07-30 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 6 | 135 |  | 810 | 51
2011-07-30 | Tipper Hire | Labour | hr | 6 | 95 |  | 570 | 51
2011-07-30 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 5 | 80 |  | 400 | 51
2011-07-30 | Labour | Labour | hr | 2.5 | 39.39 |  | 98.475 | 51
2011-07-30 | Labour | Labour | hr | 6.5 | 32.2 |  | 209.3 | 51
2011-07-30 | Tipper Hire | Lovell Earthmoving | hr | 6 | 90 |  | 540 | 51
2011-07-30 | SD Roller - Dry - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 51
2011-07-30 | Pad Foot Roller - Dry - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 51
2011-07-30 | Backhoe Hire | McDowall Earthmoving | hr | 4 | 90 |  | 360 | 51
2011-07-30 | Tipper Hire | Pollards Earthmoving | hr | 6 | 95 |  | 570 | 51
2011-08-01 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9.5 | 135 |  | 1282.5 | 51
2011-08-01 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 51
2011-08-01 | Tipper Hire | Labour | hr | 9.5 | 95 |  | 902.5 | 51
2011-08-01 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 51
2011-08-01 | Tipper Hire | Lovell Earthmoving | hr | 9.5 | 90 |  | 855 | 51
2011-08-01 | Labour | Labour | hr | 9.5 | 32.2 |  | 305.9 | 51
2011-08-01 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 51
2011-08-01 | SD Roller - Dry - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 51
2011-08-01 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 7 | 80 |  | 560 | 51
2011-08-01 | Pad Foot Roller - Dry - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 51
2011-08-02 | Labour | Labour | hr | 9.5 | 32.2 |  | 305.9 | 51
2011-08-02 | Tipper Hire | Lovell Earthmoving | hr | 5 | 90 |  | 450 | 51
2011-08-02 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 51
2011-08-02 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 51
2011-08-02 | Pad Foot Roller - Dry - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 51
2011-08-02 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 51
2011-08-02 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 51
2011-08-02 | 20 Tonne Excavator Hire | Berry Excavations - 20T |  | 6 | 135 |  | 810 | 51
2011-08-02 | Labour | Labour | hr | 3.5 | 39.39 |  | 137.865 | 51
2011-08-02 | Tipper Hire | Labour | hr | 7 | 95 |  | 665 | 51
2011-08-03 | Backhoe Hire | McDowall Earthmoving | hr | 4 | 90 |  | 360 | 51
2011-08-22 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 |  | 365 | 51
2011-08-23 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 |  | 365 | 51
2011-08-24 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 |  | 365 | 51
2011-08-25 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 |  | 365 | 51
2011-08-26 | Pad Foot Roller - Dry - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 51
2011-08-30 | Labour | Labour | hr | 7 | 32.2 |  | 225.4 | 51
2011-08-30 | Labour | Labour | hr | 7 | 39.39 |  | 275.73 | 51
2011-08-30 | Labour | Labour | hr | 7 | 39.39 |  | 275.73 | 51
2011-08-31 | SD Roller - Dry | SD Roller | day | 1 | 365 |  | 365 | 51
2011-08-31 | Tipper Hire | Pollards Earthmoving | hr | 5 | 95 |  | 475 | 51
2011-08-31 | Pad Foot Roller - Dry - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 51
2011-08-31 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 51
2011-08-31 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 51
2011-08-31 | Labour | Labour | hr | 5.5 | 32.2 |  | 177.1 | 51
2011-08-31 | Backhoe Hire | McDowall Earthmoving | hr | 2.75 | 90 |  | 247.5 | 51
2011-08-31 | Tipper Hire | Lovell Earthmoving | hr | 10 | 90 |  | 900 | 51
2011-08-31 | Labour | Labour | hr | 5 | 39.39 |  | 196.95 | 51
2011-08-31 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9.5 | 135 |  | 1282.5 | 51
2011-08-31 | Labour | Labour | hr | 10.5 | 39.39 |  | 413.595 | 51
2011-09-01 | Labour | Labour | hr | 5 | 39.39 |  | 196.95 | 51
2011-09-01 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 1 | 80 |  | 80 | 51
2011-09-01 | Tipper Hire | Pollards Earthmoving | hr | 3 | 95 |  | 285 | 51
2011-09-01 | Tipper Hire | Lovell Earthmoving | hr | 2.5 | 90 |  | 225 | 51
2011-09-01 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 51
2011-09-01 | Backhoe Hire | McDowall Earthmoving | hr | 2.5 | 90 |  | 225 | 51
2011-09-01 | Labour | Labour | hr | 5.5 | 32.2 |  | 177.1 | 51
2011-09-01 | Labour | Labour | hr | 10.5 | 39.39 |  | 413.595 | 51
2011-09-01 | Tipper Hire | Labour | hr | 5.5 | 95 |  | 522.5 | 51
2011-09-01 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9.5 | 135 |  | 1282.5 | 51
2011-09-02 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 51
2011-09-02 | Labour | Labour | hr | 6.5 | 39.39 |  | 256.035 | 51
2011-09-02 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 51
2011-09-02 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 1 | 80 |  | 80 | 51
2011-09-02 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 4.5 | 135 |  | 607.5 | 51
2011-09-02 | Tipper Hire | Labour | hr | 7 | 95 |  | 665 | 51
2011-09-02 | Labour | Labour | hr | 6 | 39.39 |  | 236.34 | 51
2011-09-02 | Labour | Labour | hr | 3.5 | 32.2 |  | 112.7 | 51
2011-09-02 | Tipper Hire | Lovell Earthmoving | hr | 3 | 90 |  | 270 | 51
2011-09-09 | Pad Foot Roller - Dry Inv - 253679 | PF Roller |  | 1 | 2197.254 |  | 2197.254 | 51
2011-09-14 | Backhoe Hire | McDowall Earthmoving | hr | 13.5 | 90 |  | 1215 | 51
2011-09-16 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 51
2011-09-16 | Labour | Labour | hr | 3 | 35.35 |  | 106.05 | 51
2011-09-16 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 3 | 80 |  | 240 | 51
2011-09-21 | Backhoe Hire | McDowall Earthmoving | hr | 9 | 90 |  | 810 | 51
2011-09-21 | Labour | Labour | hr | 9.5 | 35.35 |  | 335.825 | 51
2011-09-21 | Labour | Labour | hr | 9.5 | 35.35 |  | 335.825 | 51
| Subtotal for 051 | [5 empty] | 49136.349
Portfolio WBS 052
2011-05-17 | Copp & Co Plant Hire | Service Locator | hr | 1.5 | 130 |  | 195 | 52
2011-05-17 | Location of Services Inv 102382 | Service Locator |  | 1.5 | 130 |  | 195 | 52
2011-05-31 | Hire trash Pump & Hoses - Delivery | Pump |  | 1 | 80 |  | 80 | 52
2011-05-31 | Hire trash Pump & Hoses - 24/5/11 to 31/5/11 | Pump |  | 6 | 169 |  | 1014 | 52
2011-06-01 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-06-01 | Hire trash Pump & Hoses | Pump | week | 1 | 169 |  | 169 | 52
2011-06-01 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 52
2011-06-01 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9.5 | 135 |  | 1282.5 | 52
2011-06-01 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 6 | 80 |  | 480 | 52
2011-06-01 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 52
2011-06-01 | Tipper Hire | Pollards Earthmoving | hr | 8 | 95 |  | 760 | 52
2011-06-01 | Tipper Hire | K.C Truck Hire | hr | 10 | 95 |  | 950 | 52
2011-06-02 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-06-02 | Hire trash Pump & Hoses | Pump | week | 1 | 169 |  | 169 | 52
2011-06-02 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 3 | 80 |  | 240 | 52
2011-06-02 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 52
2011-06-02 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9 | 135 |  | 1215 | 52
2011-06-03 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 52
2011-06-03 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9 | 135 |  | 1215 | 52
2011-06-03 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 52
2011-06-03 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-06-03 | Hire trash Pump & Hoses | Pump | week | 1 | 169 |  | 169 | 52
2011-06-04 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 6.5 | 135 |  | 877.5 | 52
2011-06-04 | Truck Driver | Labour | hr | 6.5 | 39.18 |  | 254.67 | 52
2011-06-04 | Labour | Labour | hr | 7 | 39.39 |  | 275.73 | 52
2011-06-04 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 6 | 80 |  | 480 | 52
2011-06-04 | Labour | Labour | hr | 7 | 39.39 |  | 275.73 | 52
2011-06-04 | Tipper Hire | PR & HT Gourlay | hr | 6.5 | 65 |  | 422.5 | 52
2011-06-04 | Tipper Hire | Talbot Earthmoving | hr | 6 | 95 |  | 570 | 52
2011-06-04 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-06-04 | Hire trash Pump & Hoses | Pump | week | 1 | 169 |  | 169 | 52
2011-06-04 | Tipper Hire | K.C Truck Hire | hr | 7.5 | 95 |  | 712.5 | 52
2011-06-04 | Tipper Hire | Pollards Earthmoving | hr | 7 | 95 |  | 665 | 52
2011-06-04 | Tipper Hire | Pollards Earthmoving | hr | 7 | 95 |  | 665 | 52
2011-06-06 | Hire trash Pump & Hoses | Pump | week | 1 | 169 |  | 169 | 52
2011-06-06 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9.5 | 135 |  | 1282.5 | 52
2011-06-07 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-06-07 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9.5 | 135 |  | 1282.5 | 52
2011-06-07 | Hire trash Pump & Hoses | Pump | week | 1 | 169 |  | 169 | 52
2011-06-07 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 5 | 80 |  | 400 | 52
2011-06-07 | Labour | Labour | hr | 5 | 39.39 |  | 196.95 | 52
2011-06-07 | Labour | Labour | hr | 5 | 39.39 |  | 196.95 | 52
2011-06-07 | Tipper Hire | PR & HT Gourlay | hr | 8 | 65 |  | 520 | 52
2011-06-07 | Truck Driver | Labour | hr | 8 | 39.18 |  | 313.44 | 52
2011-06-08 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 9 | 80 |  | 720 | 52
2011-06-08 | Tipper Hire | K.C Truck Hire | hr | 9 | 95 |  | 855 | 52
2011-06-08 | Hire trash Pump & Hoses | Pump | week | 1 | 169 |  | 169 | 52
2011-06-08 | Tipper Hire x 2 | Pollards Earthmoving | hr | 17 | 95 |  | 1615 | 52
2011-06-08 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-06-08 | Truck Driver | Labour | hr | 8.5 | 39.18 |  | 333.03 | 52
2011-06-08 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 52
2011-06-08 | Labour | Labour | hr | 8 | 39.39 |  | 315.12 | 52
2011-06-08 | Tipper Hire | PR & HT Gourlay | hr | 8.5 | 65 |  | 552.5 | 52
2011-06-08 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9.5 | 135 |  | 1282.5 | 52
2011-06-09 | Hire trash Pump & Hoses | Pump | week | 1 | 169 |  | 169 | 52
2011-06-09 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 7 | 135 |  | 945 | 52
2011-06-09 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-06-09 | Labour | Labour | hr | 5.5 | 39.39 |  | 216.645 | 52
2011-06-09 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 4 | 80 |  | 320 | 52
2011-06-09 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 52
2011-06-10 | Tipper Hire | Askew Truck Hire | hr | 4 | 90 |  | 360 | 52
2011-06-10 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-06-10 | Tipper Hire | Pollards Earthmoving | hr | 3 | 95 |  | 285 | 52
2011-06-10 | Tipper Hire | Talbot Earthmoving | hr | 4 | 95 |  | 380 | 52
2011-06-10 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 4 | 135 |  | 540 | 52
2011-06-10 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 52
2011-06-10 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 52
2011-06-10 | Hire trash Pump & Hoses | Pump | week | 1 | 169 |  | 169 | 52
2011-06-10 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 52
2011-06-14 | Tipper Hire | PR & HT Gourlay | hr | 10 | 65 |  | 650 | 52
2011-06-14 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 10 | 135 |  | 1350 | 52
2011-06-14 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-06-14 | Labour | Labour | hr | 10 | 39.39 |  | 393.9 | 52
2011-06-14 | Labour | Labour | hr | 10 | 39.39 |  | 393.9 | 52
2011-06-14 | Truck Driver | Labour | hr | 10 | 39.18 |  | 391.8 | 52
2011-06-14 | Dozer Hire | Allans Earthmoving | hr | 2 | 160 |  | 320 | 52
2011-06-14 | Hire trash Pump & Hoses | Pump | week | 1 | 169 |  | 169 | 52
2011-06-14 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 7.5 | 80 |  | 600 | 52
2011-06-14 | Tipper Hire | Pollards Earthmoving | hr | 10.5 | 95 |  | 997.5 | 52
2011-06-14 | Tipper Hire | K.C Truck Hire | hr | 9.5 | 95 |  | 902.5 | 52
2011-06-14 | Tipper Hire | Lovell Earthmoving | hr | 8 | 90 |  | 720 | 52
2011-06-15 | Tipper Hire | Pollards Earthmoving | hr | 9.5 | 95 |  | 902.5 | 52
2011-06-15 | Tipper Hire | Lovell Earthmoving | hr | 9.5 | 90 |  | 855 | 52
2011-06-15 | Tipper Hire | K.C Truck Hire | hr | 9 | 95 |  | 855 | 52
2011-06-15 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 9.5 | 80 |  | 760 | 52
2011-06-15 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-06-15 | Dozer Hire | Allans Earthmoving | hr | 9.5 | 160 |  | 1520 | 52
2011-06-15 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9 | 135 |  | 1215 | 52
2011-06-15 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 52
2011-06-15 | Hire trash Pump & Hoses | Pump | week | 1 | 169 |  | 169 | 52
2011-06-15 | Tipper Hire | PR & HT Gourlay | hr | 9.5 | 65 |  | 617.5 | 52
2011-06-15 | Truck Driver | Labour | hr | 9.5 | 39.18 |  | 372.21 | 52
2011-06-16 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9 | 135 |  | 1215 | 52
2011-06-16 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-06-16 | Tipper Hire | PR & HT Gourlay | hr | 9.5 | 65 |  | 617.5 | 52
2011-06-16 | Tipper Hire | Pollards Earthmoving | hr | 9.5 | 95 |  | 902.5 | 52
2011-06-16 | Dozer Hire | Allans Earthmoving | hr | 9 | 160 |  | 1440 | 52
2011-06-16 | Tipper Hire | K.C Truck Hire | hr | 9.5 | 95 |  | 902.5 | 52
2011-06-16 | Tipper Hire | Lovell Earthmoving | hr | 8.5 | 90 |  | 765 | 52
2011-06-16 | Truck Driver | Labour | hr | 10 | 39.18 |  | 391.8 | 52
2011-06-16 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 52
2011-06-16 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 52
2011-06-16 | Hire trash Pump & Hoses | Pump | week | 1 | 169 |  | 169 | 52
2011-06-16 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 9.5 | 80 |  | 760 | 52
2011-06-17 | Truck Driver | Labour | hr | 10 | 39.18 |  | 391.8 | 52
2011-06-17 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9 | 135 |  | 1215 | 52
2011-06-17 | Tipper Hire | PR & HT Gourlay | hr | 9.5 | 65 |  | 617.5 | 52
2011-06-17 | Tipper Hire | K.C Truck Hire | hr | 9 | 95 |  | 855 | 52
2011-06-17 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-06-17 | Hire trash Pump & Hoses | Pump | week | 1 | 169 |  | 169 | 52
2011-06-17 | Dozer Hire | Allans Earthmoving | hr | 9 | 160 |  | 1440 | 52
2011-06-17 | Tipper Hire | Lovell Earthmoving | hr | 9.5 | 90 |  | 855 | 52
2011-06-17 | Tipper Hire | Pollards Earthmoving | hr | 9.5 | 95 |  | 902.5 | 52
2011-06-17 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 52
2011-06-17 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 9.5 | 80 |  | 760 | 52
2011-06-17 | Labour | Labour | hr | 8.5 | 39.39 |  | 334.815 | 52
2011-06-18 | Tipper Hire | K.C Truck Hire | hr | 8 | 95 |  | 760 | 52
2011-06-18 | Labour | Labour | hr | 8 | 39.39 |  | 315.12 | 52
2011-06-18 | Truck Driver | Labour | hr | 7.5 | 39.18 |  | 293.85 | 52
2011-06-18 | Hire trash Pump & Hoses | Pump | week | 1 | 169 |  | 169 | 52
2011-06-18 | Tipper Hire | PR & HT Gourlay | hr | 7 | 65 |  | 455 | 52
2011-06-18 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 7 | 135 |  | 945 | 52
2011-06-18 | Labour | Labour | hr | 8 | 39.39 |  | 315.12 | 52
2011-06-18 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-06-18 | Tipper Hire | Pollards Earthmoving | hr | 7.5 | 95 |  | 712.5 | 52
2011-06-18 | Dozer Hire | Allans Earthmoving | hr | 7.5 | 160 |  | 1200 | 52
2011-06-18 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 8 | 80 |  | 640 | 52
2011-06-18 | Tipper Hire | Lovell Earthmoving | hr | 7.5 | 90 |  | 675 | 52
2011-06-20 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-06-20 | Truck Driver | Labour | hr | 9.5 | 39.18 |  | 372.21 | 52
2011-06-20 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 52
2011-06-20 | Dozer Hire | Allans Earthmoving | hr | 9 | 160 |  | 1440 | 52
2011-06-20 | Tipper Hire | K.C Truck Hire | hr | 9.5 | 95 |  | 902.5 | 52
2011-06-20 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 8 | 135 |  | 1080 | 52
2011-06-20 | Tipper Hire | Pollards Earthmoving | hr | 8 | 95 |  | 760 | 52
2011-06-20 | Tipper Hire | Lovell Earthmoving | hr | 9.5 | 90 |  | 855 | 52
2011-06-20 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 52
2011-06-20 | Tipper Hire | PR & HT Gourlay | hr | 8 | 65 |  | 520 | 52
2011-06-20 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 6 | 80 |  | 480 | 52
2011-06-20 | Hire trash Pump & Hoses | Pump | week | 1 | 169 |  | 169 | 52
2011-06-20 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 52
2011-06-21 | Hire trash Pump & Hoses | Pump | week | 1 | 169 |  | 169 | 52
2011-06-21 | Dozer Hire | Allans Earthmoving | hr | 8 | 160 |  | 1280 | 52
2011-06-21 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-06-22 | Dozer Hire | Allans Earthmoving | hr | 9.5 | 160 |  | 1520 | 52
2011-06-22 | Hire trash Pump & Hoses | Pump | week | 1 | 169 |  | 169 | 52
2011-06-22 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 5 | 135 |  | 675 | 52
2011-06-22 | Truck Driver | Labour | hr | 6 | 39.18 |  | 235.08 | 52
2011-06-22 | Tipper Hire | PR & HT Gourlay | hr | 6 | 65 |  | 390 | 52
2011-06-23 | Dozer Hire | Allans Earthmoving | hr | 9.5 | 160 |  | 1520 | 52
2011-06-23 | Hire trash Pump & Hoses | Pump | week | 1 | 169 |  | 169 | 52
2011-06-27 | Tipper Hire | Lovell Earthmoving | hr | 4 | 90 |  | 360 | 52
2011-06-27 | Dozer Hire | Allans Earthmoving | hr | 9 | 160 |  | 1440 | 52
2011-06-27 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 4 | 135 |  | 540 | 52
2011-07-01 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-07-04 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9 | 135 |  | 1215 | 52
2011-07-04 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 9 | 80 |  | 720 | 52
2011-07-04 | Tipper Hire | Pollards Earthmoving | hr | 10 | 95 |  | 950 | 52
2011-07-04 | Tipper Hire | Lovell Earthmoving | hr | 9 | 90 |  | 810 | 52
2011-07-04 | Grader Operator | Barry Thompson |  | 9.5 | 32.2 |  | 305.9 | 52
2011-07-04 | Labour | Labour | hr | 7.5 | 39.39 |  | 295.425 | 52
2011-07-04 | Truck Driver | Labour | hr | 7.5 | 39.18 |  | 293.85 | 52
2011-07-04 | Tipper Hire | PR & HT Gourlay | hr | 9.5 | 65 |  | 617.5 | 52
2011-07-04 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-07-04 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 52
2011-07-04 | Tipper Hire | K.C Truck Hire | hr | 9 | 95 |  | 855 | 52
2011-07-05 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 52
2011-07-05 | Tipper Hire | Pollards Earthmoving | hr | 9.5 | 95 |  | 902.5 | 52
2011-07-05 | Tipper Hire | Lovell Earthmoving | hr | 9.5 | 90 |  | 855 | 52
2011-07-05 | Hire trash Pump & Hoses | Pump | week | 2 | 169 |  | 338 | 52
2011-07-05 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 9 | 80 |  | 720 | 52
2011-07-05 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-07-05 | Tipper Hire | K.C Truck Hire | hr | 9.5 | 95 |  | 902.5 | 52
2011-07-05 | Grader Operator | Barry Thompson |  | 9.5 | 32.2 |  | 305.9 | 52
2011-07-05 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 52
2011-07-05 | Truck Driver | Labour | hr | 7.5 | 39.18 |  | 293.85 | 52
2011-07-05 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9 | 135 |  | 1215 | 52
2011-07-05 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 52
2011-07-05 | Tipper Hire | PR & HT Gourlay | hr | 7 | 65 |  | 455 | 52
2011-07-06 | Tipper Hire | Lovell Earthmoving | hr | 9.5 | 90 |  | 855 | 52
2011-07-06 | Tipper Hire | K.C Truck Hire | hr | 9 | 95 |  | 855 | 52
2011-07-06 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9 | 135 |  | 1215 | 52
2011-07-06 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 8 | 80 |  | 640 | 52
2011-07-06 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-07-06 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 52
2011-07-06 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 52
2011-07-06 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 52
2011-07-06 | Truck Driver | Labour | hr | 10 | 39.18 |  | 391.8 | 52
2011-07-06 | Tipper Hire | PR & HT Gourlay | hr | 9.5 | 65 |  | 617.5 | 52
2011-07-06 | Grader Operator | Barry Thompson |  | 9.5 | 32.2 |  | 305.9 | 52
2011-07-07 | Tipper Hire | Lovell Earthmoving | hr | 9.5 | 90 |  | 855 | 52
2011-07-07 | Tipper Hire | K.C Truck Hire | hr | 9 | 95 |  | 855 | 52
2011-07-07 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9 | 135 |  | 1215 | 52
2011-07-07 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 9 | 80 |  | 720 | 52
2011-07-07 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-07-07 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 52
2011-07-07 | Tipper Hire | PR & HT Gourlay | hr | 9.5 | 65 |  | 617.5 | 52
2011-07-07 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 52
2011-07-07 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 52
2011-07-07 | Grader Operator | Barry Thompson |  | 9.5 | 32.2 |  | 305.9 | 52
2011-07-07 | Truck Driver | Labour | hr | 9.5 | 39.18 |  | 372.21 | 52
2011-07-08 | Tipper Hire | PR & HT Gourlay | hr | 5 | 65 |  | 325 | 52
2011-07-08 | Grader Operator | Barry Thompson |  | 8.5 | 32.2 |  | 273.7 | 52
2011-07-08 | Truck Driver | Labour | hr | 7 | 39.18 |  | 274.26 | 52
2011-07-08 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 7 | 135 |  | 945 | 52
2011-07-08 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 52
2011-07-08 | Tipper Hire | K.C Truck Hire | hr | 8 | 95 |  | 760 | 52
2011-07-08 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-07-08 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 7 | 80 |  | 560 | 52
2011-07-08 | Labour | Labour | hr | 7 | 39.39 |  | 275.73 | 52
2011-07-08 | Labour | Labour | hr | 8.5 | 39.39 |  | 334.815 | 52
2011-07-09 | Truck Driver | Labour | hr | 6 | 39.18 |  | 235.08 | 52
2011-07-09 | Tipper Hire | PR & HT Gourlay | hr | 4 | 65 |  | 260 | 52
2011-07-09 | Labour | Labour | hr | 5 | 39.39 |  | 196.95 | 52
2011-07-09 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 5.5 | 135 |  | 742.5 | 52
2011-07-09 | Tipper Hire | K.C Truck Hire | hr | 6.5 | 95 |  | 617.5 | 52
2011-07-11 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 52
2011-07-11 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-07-12 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-07-12 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 52
2011-07-14 | Tipper Hire | K.C Truck Hire | hr | 4 | 95 |  | 380 | 52
2011-07-14 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 52
2011-07-14 | Tipper Hire | Lovell Earthmoving | hr | 2 | 90 |  | 180 | 52
2011-07-14 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 3 | 135 |  | 405 | 52
2011-07-15 | Tipper Hire | Lovell Earthmoving | hr | 7.5 | 90 |  | 675 | 52
2011-07-15 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 52
2011-07-15 | Labour | Labour | hr | 8 | 39.39 |  | 315.12 | 52
2011-07-15 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-07-15 | Labour | Labour | hr | 10 | 39.39 |  | 393.9 | 52
2011-07-15 | Tipper Hire | K.C Truck Hire | hr | 9.5 | 95 |  | 902.5 | 52
2011-07-15 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9.5 | 135 |  | 1282.5 | 52
2011-07-15 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 5 | 80 |  | 400 | 52
2011-07-16 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 3 | 80 |  | 240 | 52
2011-07-16 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 52
2011-07-16 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 52
2011-07-16 | Tipper Hire | K.C Truck Hire | hr | 4 | 95 |  | 380 | 52
2011-07-16 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-07-16 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 52
2011-08-03 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 52
2011-08-03 | Tipper Hire | Pollards Earthmoving | hr | 6 | 95 |  | 570 | 52
2011-08-03 | Tipper Hire | Pollards Earthmoving | hr | 2.75 | 95 |  | 261.25 | 52
2011-08-03 | Pad Foot Roller - Dry - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-08-03 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 6 | 80 |  | 480 | 52
2011-08-03 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 52
2011-08-03 | Labour | Labour | hr | 9.5 | 32.2 |  | 305.9 | 52
2011-08-03 | Labour | Labour | hr | 3.5 | 39.39 |  | 137.865 | 52
2011-08-03 | Labour | Labour | hr | 5.5 | 39.39 |  | 216.645 | 52
2011-08-03 | Tipper Hire | Lovell Earthmoving | hr | 8.5 | 90 |  | 765 | 52
2011-08-03 | Tipper Hire | Labour | hr | 9 | 95 |  | 855 | 52
2011-08-03 | 20 Tonne Excavator Hire | Berry Excavations - 20T |  | 9 | 135 |  | 1215 | 52
2011-08-04 | Labour | Labour | hr | 9.5 | 32.2 |  | 305.9 | 52
2011-08-04 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 52
2011-08-04 | Labour | Labour | hr | 3.5 | 39.39 |  | 137.865 | 52
2011-08-04 | SD Roller - Dry - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 52
2011-08-04 | Pad Foot Roller - Dry - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-08-04 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 8 | 80 |  | 640 | 52
2011-08-04 | Tipper Hire | Pollards Earthmoving | hr | 1.5 | 95 |  | 142.5 | 52
2011-08-04 | 20 Tonne Excavator Hire | Berry Excavations - 20T |  | 9 | 135 |  | 1215 | 52
2011-08-04 | Tipper Hire | Labour | hr | 9 | 95 |  | 855 | 52
2011-08-04 | Tipper Hire | Pollards Earthmoving | hr | 7 | 95 |  | 665 | 52
2011-08-05 | Backhoe Hire | McDowall Earthmoving | hr | 5.75 | 90 |  | 517.5 | 52
2011-08-05 | Tipper Hire | Lovell Earthmoving | hr | 9.5 | 90 |  | 855 | 52
2011-08-05 | Tipper Hire | Pollards Earthmoving | hr | 5.5 | 95 |  | 522.5 | 52
2011-08-05 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 8 | 80 |  | 640 | 52
2011-08-05 | Pad Foot Roller - Dry - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-08-05 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 52
2011-08-05 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 52
2011-08-05 | Labour | Labour | hr | 9.5 | 32.2 |  | 305.9 | 52
2011-08-05 | Tipper Hire | Labour | hr | 9 | 95 |  | 855 | 52
2011-08-05 | 20 Tonne Excavator Hire | Berry Excavations - 20T |  | 9 | 135 |  | 1215 | 52
2011-08-08 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 52
2011-08-08 | Tipper Hire | Labour | hr | 9 | 95 |  | 855 | 52
2011-08-08 | SD Roller - Dry - flexi hire | SD Roller | day | 1 | 365 |  | 365 | 52
2011-08-08 | Pad Foot Roller - Dry - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-08-08 | Labour | Labour | hr | 9.5 | 32.2 |  | 305.9 | 52
2011-08-08 | labour | Labour | hr | 7.5 | 39.39 |  | 295.425 | 52
2011-08-08 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 4.5 | 135 |  | 607.5 | 52
2011-08-08 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 3 | 80 |  | 240 | 52
2011-08-09 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 4 | 80 |  | 320 | 52
2011-08-09 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 |  | 365 | 52
2011-08-09 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 6 | 135 |  | 810 | 52
2011-08-09 | Labour | Labour | hr | 6.5 | 39.39 |  | 256.035 | 52
2011-08-09 | Labour | Labour | hr | 5.5 | 39.39 |  | 216.645 | 52
2011-08-09 | Tipper Hire | Pollards Earthmoving | hr | 6 | 95 |  | 570 | 52
2011-08-09 | Backhoe Hire | McDowall Earthmoving | hr | 6 | 90 |  | 540 | 52
2011-08-09 | Labour | Labour | hr | 7.5 | 39.39 |  | 295.425 | 52
2011-08-09 | Tipper Hire | Lovell Earthmoving | hr | 6 | 90 |  | 540 | 52
2011-08-09 | truck hire | Labour | hr | 9 | 95 |  | 855 | 52
2011-08-09 | Labour | Labour | hr | 7.5 | 32.2 |  | 241.5 | 52
2011-08-10 | Tipper Hire | Labour | hr | 5 | 95 |  | 475 | 52
2011-08-10 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 4 | 80 |  | 320 | 52
2011-08-10 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 |  | 365 | 52
2011-08-10 | Labour | Labour | hr | 4.5 | 39.39 |  | 177.255 | 52
2011-08-10 | Labour | Labour | hr | 5.5 | 39.39 |  | 216.645 | 52
2011-08-10 | Labour | Labour | hr | 5 | 39.39 |  | 196.95 | 52
2011-08-10 | Labour | Labour | hr | 4.5 | 32.2 |  | 144.9 | 52
2011-08-11 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 |  | 365 | 52
2011-08-11 | Labour | Labour | hr | 4.5 | 32.2 |  | 144.9 | 52
2011-08-12 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 |  | 365 | 52
2011-08-29 | Tipper Hire | Lovell Earthmoving | hr | 5 | 90 |  | 450 | 52
2011-08-29 | Tipper Hire | Labour | hr | 5 | 95 |  | 475 | 52
2011-08-29 | Labour | Labour | hr | 5.5 | 39.39 |  | 216.645 | 52
2011-08-29 | Labour | Labour | hr | 5.5 | 32.2 |  | 177.1 | 52
2011-08-29 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 4.5 | 135 |  | 607.5 | 52
2011-08-29 | Backhoe Hire | McDowall Earthmoving | hr | 5 | 90 |  | 450 | 52
2011-08-29 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 52
2011-08-29 | Pad Foot Roller - Dry - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-08-29 | SD Roller - Dry | SD Roller | day | 1 | 365 |  | 365 | 52
2011-08-30 | SD Roller - Dry | SD Roller | day | 1 | 365 |  | 365 | 52
2011-08-30 | Pad Foot Roller - Dry - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 52
2011-08-30 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 52
2011-08-30 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 52
2011-08-30 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 7 | 135 |  | 945 | 52
2011-08-30 | Tipper Hire | Lovell Earthmoving | hr | 6 | 90 |  | 540 | 52
| Subtotal for 052 | [5 empty] | 164870.94
Portfolio WBS 053
2011-06-10 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 53
2011-06-10 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 53
2011-06-10 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 53
2011-08-15 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 1 | 80 |  | 80 | 53
2011-08-15 | Labour | Labour | hr | 105 | 32.2 |  | 3381 | 53
2011-08-16 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 1 | 80 |  | 80 | 53
2011-09-05 | Backhoe Hire | McDowall Earthmoving | hr | 7 | 90 |  | 630 | 53
2011-09-05 | Tipper Hire | Labour | hr | 5 | 95 |  | 475 | 53
2011-09-05 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 7 | 135 |  | 945 | 53
2011-09-05 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 53
2011-09-05 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 1 | 80 |  | 80 | 53
2011-09-05 | Tipper Hire | Pollards Earthmoving | hr | 4.5 | 95 |  | 427.5 | 53
2011-09-05 | Labour | Labour | hr | 6.5 | 39.39 |  | 256.035 | 53
2011-09-05 | Tipper Hire | Lovell Earthmoving | hr | 9.25 | 90 |  | 832.5 | 53
2011-09-05 | Labour | Labour | hr | 3.5 | 32.2 |  | 112.7 | 53
2011-09-05 | Labour | Labour | hr | 6.5 | 39.39 |  | 256.035 | 53
2011-09-06 | Tipper Hire | Lovell Earthmoving | hr | 9 | 90 |  | 810 | 53
2011-09-06 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 53
2011-09-06 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 4 | 135 |  | 540 | 53
2011-09-06 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 53
2011-09-07 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 53
2011-09-07 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 4 | 135 |  | 540 | 53
2011-09-07 | Backhoe Hire | McDowall Earthmoving | hr | 4 | 90 |  | 360 | 53
2011-09-09 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 53
2011-09-09 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 3 | 135 |  | 405 | 53
| Subtotal for 053 | [5 empty] | 11630.28
Portfolio WBS 057
2011-06-20 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 1 | 135 |  | 135 | 57
2011-06-21 | Truck Driver | Labour | hr | 6 | 39.18 |  | 235.08 | 57
2011-06-21 | Labour | Labour | hr | 10 | 39.39 |  | 393.9 | 57
2011-06-21 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9.5 | 135 |  | 1282.5 | 57
2011-06-22 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 57
2011-06-22 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 1 | 80 |  | 80 | 57
2011-06-22 | Truck Driver | Labour | hr | 3.5 | 39.18 |  | 137.13 | 57
2011-06-22 | Tipper Hire | PR & HT Gourlay | hr | 3.5 | 65 |  | 227.5 | 57
2011-06-22 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 57
2011-06-22 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 4 | 135 |  | 540 | 57
2011-06-23 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 57
2011-06-23 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9 | 135 |  | 1215 | 57
2011-06-23 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 57
2011-06-23 | Labour | Labour | hr | 1.5 | 39.39 |  | 59.085 | 57
2011-06-23 | Truck Driver | Labour | hr | 9.5 | 39.18 |  | 372.21 | 57
2011-06-23 | Tipper Hire | PR & HT Gourlay | hr | 9.5 | 65 |  | 617.5 | 57
2011-06-23 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 1 | 80 |  | 80 | 57
2011-06-27 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 57
2011-06-27 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 5 | 135 |  | 675 | 57
2011-06-27 | Tipper Hire | PR & HT Gourlay | hr | 2.5 | 65 |  | 162.5 | 57
2011-06-27 | Truck Driver | Labour | hr | 3 | 39.18 |  | 117.54 | 57
2011-06-27 | Labour | Labour | hr | 3.5 | 39.39 |  | 137.865 | 57
2011-06-27 | Tipper Hire | Lovell Earthmoving | hr | 5.5 | 90 |  | 495 | 57
2011-07-08 | Tipper Hire | PR & HT Gourlay | hr | 1.5 | 65 |  | 97.5 | 57
2011-07-08 | Truck Driver | Labour | hr | 1.5 | 39.18 |  | 58.77 | 57
2011-07-08 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 1 | 135 |  | 135 | 57
2011-07-08 | Labour | Labour | hr | 1.5 | 39.39 |  | 59.085 | 57
2011-07-09 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 1 | 135 |  | 135 | 57
2011-07-09 | Tipper Hire | PR & HT Gourlay | hr | 1 | 65 |  | 65 | 57
2011-07-09 | Truck Driver | Labour | hr | 1 | 39.18 |  | 39.18 | 57
2011-07-11 | Tipper Hire | Michael J Biles | hr | 4 | 95 |  | 380 | 57
2011-07-11 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 57
2011-07-11 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 4 | 135 |  | 540 | 57
2011-07-11 | Tipper Hire | K.C Truck Hire | hr | 4 | 95 |  | 380 | 57
2011-07-19 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 57
2011-07-19 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9.5 | 135 |  | 1282.5 | 57
2011-07-19 | Tipper Hire | K.C Truck Hire | hr | 3 | 95 |  | 285 | 57
2011-07-19 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 57
2011-07-19 | Tipper Hire | Lovell Earthmoving | hr | 9.5 | 90 |  | 855 | 57
2011-07-20 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 3 | 80 |  | 240 | 57
2011-07-20 | Tipper Hire | Lovell Earthmoving | hr | 6 | 90 |  | 540 | 57
2011-07-20 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 57
2011-07-20 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 6 | 135 |  | 810 | 57
2011-07-20 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 57
2011-07-20 | Tipper Hire | K.C Truck Hire | hr | 6 | 95 |  | 570 | 57
2011-07-20 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 57
2011-07-21 | Tipper Hire | Labour | hr | 2 | 95 |  | 190 | 57
2011-07-21 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 57
2011-07-21 | Tipper Hire | Lovell Earthmoving | hr | 6 | 90 |  | 540 | 57
2011-07-21 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 57
2011-07-21 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 6 | 135 |  | 810 | 57
2011-07-22 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 57
2011-07-25 | Pad Foot Roller - Dry - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 57
2011-07-26 | Pad Foot Roller - Dry - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 57
2011-07-26 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9.5 | 135 |  | 1282.5 | 57
2011-07-26 | Labour | Labour | hr | 3.5 | 39.39 |  | 137.865 | 57
2011-07-26 | Labour | Labour | hr | 7.5 | 39.39 |  | 295.425 | 57
2011-07-26 | Tipper Hire | Labour | hr | 9 | 95 |  | 855 | 57
2011-07-26 | Tipper Hire | Berry Excavations -Tipper | hr | 9 | 95 |  | 855 | 57
2011-07-26 | Tipper Hire | Pollards Earthmoving | hr | 9 | 95 |  | 855 | 57
2011-07-26 | Tipper Hire | Lovell Earthmoving | hr | 8.5 | 90 |  | 765 | 57
2011-07-27 | Tipper Hire | Labour | hr | 5 | 95 |  | 475 | 57
2011-07-27 | Tipper Hire | Lovell Earthmoving | hr | 3 | 90 |  | 270 | 57
2011-07-27 | Tipper Hire | Pollards Earthmoving | hr | 9 | 95 |  | 855 | 57
2011-07-27 | Tipper Hire | Berry Excavations -Tipper | hr | 9 | 95 |  | 855 | 57
2011-07-27 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 9 | 135 |  | 1215 | 57
2011-07-27 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 57
2011-07-28 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 4 | 135 |  | 540 | 57
2011-07-28 | Tipper Hire | Lovell Earthmoving | hr | 4 | 90 |  | 360 | 57
2011-08-13 | Tipper Hire | Labour | hr | 2 | 95 |  | 190 | 57
2011-08-13 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 3 | 80 |  | 240 | 57
2011-08-13 | Labour | Labour | hr | 3.5 | 39.39 |  | 137.865 | 57
2011-08-13 | Labour | Labour | hr | 3.5 | 39.39 |  | 137.865 | 57
2011-08-13 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 5.5 | 66.07 |  | 363.385 | 57
2011-08-13 | SD Roller - Dry | SD Roller | day | 1 | 365 |  | 365 | 57
2011-08-13 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 |  | 365 | 57
2011-08-13 | Labour | Labour | hr | 2.5 | 32.2 |  | 80.5 | 57
2011-08-13 | UD Spreader Truck - No Driver | UD Spreader | hr | 5.5 | 21.61 |  | 118.855 | 57
2011-08-15 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 |  | 365 | 57
2011-08-15 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 57
2011-08-15 | Backhoe Hire | McDowall Earthmoving | hr | 7 | 90 |  | 630 | 57
2011-08-15 | SD Roller - Dry | SD Roller | day | 1 | 365 |  | 365 | 57
2011-08-15 | Labour | Labour | hr | 8 | 32.2 |  | 257.6 | 57
2011-08-15 | Labour | Labour | hr | 4 | 32.2 |  | 128.8 | 57
2011-08-15 | Labour | Labour | hr | 4.5 | 39.39 |  | 177.255 | 57
2011-08-15 | project supervisor | Supervisor | hr | 8 | 57.7 |  | 461.6 | 57
2011-08-15 | Labour | Labour | hr | 8 | 32.2 |  | 257.6 | 57
2011-08-15 | UD Spreader Truck - No Driver | UD Spreader | hr | 7.5 | 21.61 |  | 162.075 | 57
2011-08-15 | Tipper Hire | Labour | hr | 6.5 | 95 |  | 617.5 | 57
2011-08-15 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7.5 | 66.07 |  | 495.525 | 57
2011-08-15 | Labour | Labour | hr | 4.5 | 39.39 |  | 177.255 | 57
2011-08-15 | Labour | Labour | hr | 4.5 | 39.39 |  | 177.255 | 57
2011-08-16 | project supervisor | Supervisor | hr | 8 | 57.7 |  | 461.6 | 57
2011-08-16 | Labour | Labour | hr | 8 | 32.2 |  | 257.6 | 57
2011-08-16 | Labour | Labour | hr | 4 | 32.2 |  | 128.8 | 57
2011-08-16 | Labour | Labour | hr | 4.5 | 39.39 |  | 177.255 | 57
2011-08-16 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 57
2011-08-16 | Backhoe Hire | McDowall Earthmoving | hr | 7 | 90 |  | 630 | 57
2011-08-16 | Tipper Hire | Labour | hr | 2.5 | 95 |  | 237.5 | 57
2011-08-16 | SD Roller - Dry | SD Roller | day | 1 | 365 |  | 365 | 57
2011-08-16 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 57
2011-08-16 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 |  | 365 | 57
2011-08-16 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7.5 | 66.07 |  | 495.525 | 57
2011-08-16 | Labour | Labour | hr | 8 | 32.2 |  | 257.6 | 57
2011-08-16 | UD Spreader Truck - No Driver | UD Spreader | hr | 7.5 | 21.61 |  | 162.075 | 57
2011-08-17 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 |  | 365 | 57
2011-08-18 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 |  | 365 | 57
2011-08-19 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 |  | 365 | 57
2011-09-03 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 3.5 | 135 |  | 472.5 | 57
2011-09-03 | Labour | Labour | hr | 4.5 | 39.39 |  | 177.255 | 57
2011-09-03 | Tipper Hire | Labour | hr | 4 | 95 |  | 380 | 57
| Subtotal for 057 | [5 empty] | 41783.66
Portfolio WBS 061
2011-05-25 | Labour | Labour | hr | 5 | 39.39 |  | 196.95 | 61
2011-05-25 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 4 | 80 |  | 320 | 61
2011-05-26 | Labour | Labour | hr | 6 | 39.39 |  | 236.34 | 61
2011-05-26 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 61
2011-05-26 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 4 | 80 |  | 320 | 61
2011-05-26 | Pad Foot Roller - Dry | PF Roller | day | 1 | 365 |  | 365 | 61
2011-05-27 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 61
2011-05-27 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 61
2011-05-30 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 61
2011-05-31 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 61
2011-06-03 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 61
2011-06-03 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 61
2011-06-03 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 3 | 80 |  | 240 | 61
2011-06-23 | Bulk GP / GB Cement - Inv 8161557 | Cement |  | 84 | 7.82 |  | 656.88 | 61
2011-06-23 | Delivery Costs - Inv 8161557 | Freight |  | 1 | 31.82 |  | 31.82 | 61
2011-06-27 | Tipper Hire | K.C Truck Hire | hr | 4 | 95 |  | 380 | 61
2011-08-08 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 61
2011-08-08 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 61
2011-08-08 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 61
2011-08-08 | 20 Tonne Excavator Hire | Berry Excavations - 20T |  | 3 | 135 |  | 405 | 61
2011-08-09 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 61
2011-08-09 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 61
2011-08-10 | Backhoe Hire | McDowall Earthmoving | hr | 1 | 90 |  | 90 | 61
2011-08-10 | truck hire | Labour | hr | 2 | 95 |  | 190 | 61
2011-08-10 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 1 | 80 |  | 80 | 61
2011-08-10 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 61
2011-08-10 | SD Roller - Dry | SD Roller | day | 1 | 365 |  | 365 | 61
2011-08-10 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 61
2011-08-10 | Labour | Labour | hr | 2 | 32.2 |  | 64.4 | 61
2011-09-14 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 61
2011-09-14 | Labour | Labour | hr | 4 | 35.35 |  | 141.4 | 61
2011-09-14 | Labour | Labour | hr | 4 | 35.35 |  | 141.4 | 61
| Subtotal for 061 | [5 empty] | 6722.72
Portfolio WBS 062
2011-06-27 | Hire trash Pump & Hoses | Pump | week | 1 | 169 |  | 169 | 62
2011-06-27 | Tipper Hire | PR & HT Gourlay | hr | 6.5 | 65 |  | 422.5 | 62
2011-06-27 | Truck Driver | Labour | hr | 6.5 | 39.18 |  | 254.67 | 62
2011-06-27 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 62
2011-06-27 | Tipper Hire | K.C Truck Hire | hr | 5 | 95 |  | 475 | 62
2011-06-27 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 4 | 80 |  | 320 | 62
2011-06-28 | Truck Driver | Labour | hr | 2 | 39.18 |  | 78.36 | 62
2011-06-28 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 62
2011-06-28 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 62
2011-06-30 | Labour | Labour | hr | 8 | 39.39 |  | 315.12 | 62
2011-06-30 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 7 | 80 |  | 560 | 62
2011-06-30 | Tipper Hire | PR & HT Gourlay | hr | 6 | 65 |  | 390 | 62
2011-06-30 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 62
2011-06-30 | Labour | Labour | hr | 8 | 39.39 |  | 315.12 | 62
2011-06-30 | Hire trash Pump & Hoses | Pump | week | 1 | 169 |  | 169 | 62
2011-06-30 | Truck Driver | Labour | hr | 7.5 | 39.18 |  | 293.85 | 62
2011-07-01 | Labour | Labour | hr | 7.5 | 39.39 |  | 295.425 | 62
2011-07-01 | Labour | Labour | hr | 7.5 | 39.39 |  | 295.425 | 62
2011-07-01 | Tipper Hire | K.C Truck Hire | hr | 9 | 95 |  | 855 | 62
2011-07-01 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 62
2011-07-01 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 7 | 80 |  | 560 | 62
2011-07-01 | Truck Driver | Labour | hr | 7.5 | 39.18 |  | 293.85 | 62
2011-07-01 | Tipper Hire | PR & HT Gourlay | hr | 6 | 65 |  | 390 | 62
2011-07-04 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 62
2011-07-04 | Truck Driver | Labour | hr | 2 | 39.18 |  | 78.36 | 62
2011-07-04 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 62
2011-07-11 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 62
2011-07-11 | Tipper Hire | K.C Truck Hire | hr | 5 | 95 |  | 475 | 62
2011-07-11 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 4 | 80 |  | 320 | 62
2011-07-14 | Tipper Hire | Lovell Earthmoving | hr | 2 | 90 |  | 180 | 62
2011-07-21 | Tipper Hire | Labour | hr | 3 | 95 |  | 285 | 62
2011-07-21 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 1 | 80 |  | 80 | 62
2011-07-21 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 62
2011-07-21 | Labour | Labour | hr | 3.5 | 39.39 |  | 137.865 | 62
2011-07-22 | Tipper Hire | Labour | hr | 3.5 | 95 |  | 332.5 | 62
2011-07-22 | Labour | Labour | hr | 7 | 39.39 |  | 275.73 | 62
2011-07-22 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 62
2011-07-22 | Backhoe Hire | McDowall Earthmoving |  | 6.5 | 90 |  | 585 | 62
2011-07-25 | Tipper Hire | Labour | hr | 5 | 95 |  | 475 | 62
2011-07-25 | Backhoe Hire | McDowall Earthmoving | hr | 5 | 90 |  | 450 | 62
2011-07-25 | SD Roller - Dry - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 62
2011-07-25 | Labour | Labour | hr | 5 | 39.39 |  | 196.95 | 62
2011-07-26 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 4 | 80 |  | 320 | 62
2011-07-26 | SD Roller - Dry - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 62
2011-07-26 | Labour | Labour | hr | 4 | 32.2 |  | 128.8 | 62
2011-07-26 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 62
2011-07-27 | SD Roller - Dry - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 62
2011-07-28 | Backhoe Hire | McDowall Earthmoving | hr | 4 | 90 |  | 360 | 62
2011-07-28 | Tipper Hire | Labour | hr | 6 | 95 |  | 570 | 62
2011-07-28 | Labour | Labour | hr | 6 | 39.39 |  | 236.34 | 62
2011-07-28 | Labour | Labour |  | 6 | 39.39 |  | 236.34 | 62
2011-07-28 | Labour | Labour | hr | 6 | 32.2 |  | 193.2 | 62
2011-07-28 | SD Roller - Dry - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 62
2011-07-28 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 3 | 80 |  | 240 | 62
2011-07-28 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-07-29 | Tipper Hire | Labour | hr | 2 | 95 |  | 190 | 62
2011-07-29 | SD Roller - Dry - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 62
2011-08-04 | Backhoe Hire | McDowall Earthmoving | hr | 3.75 | 90 |  | 337.5 | 62
2011-08-04 | Tipper Hire | Lovell Earthmoving | hr | 9.5 | 90 |  | 855 | 62
2011-08-05 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 62
2011-08-08 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 62
2011-08-08 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-08-11 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 7 | 80 |  | 560 | 62
2011-08-11 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-08-11 | Labour | Labour | hr | 9.5 | 32.2 |  | 305.9 | 62
2011-08-11 | SD Roller - Dry | SD Roller | day | 1 | 365 |  | 365 | 62
2011-08-11 | Backhoe Hire | McDowall Earthmoving | hr | 1 | 90 |  | 90 | 62
2011-08-11 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 62
2011-08-11 | Labour | Labour | hr | 10 | 39.39 |  | 393.9 | 62
2011-08-11 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 62
2011-08-11 | truck hire | Labour | hr | 10 | 95 |  | 950 | 62
2011-08-12 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 1 | 80 |  | 80 | 62
2011-08-12 | SD Roller - Dry | SD Roller | day | 1 | 365 |  | 365 | 62
2011-08-12 | Backhoe Hire | McDowall Earthmoving | hr | 3.5 | 90 |  | 315 | 62
2011-08-12 | Tipper Hire | Labour | hr | 8.5 | 95 |  | 807.5 | 62
2011-08-12 | Labour | Labour | hr | 9 | 32.2 |  | 289.8 | 62
2011-08-12 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-08-12 | Labour | Labour | hr | 9 | 32.2 |  | 289.8 | 62
2011-08-12 | Labour | Labour | hr | 6 | 39.39 |  | 236.34 | 62
2011-08-12 | Labour | Labour | hr | 9 | 39.39 |  | 354.51 | 62
2011-08-13 | Labour | Labour | hr | 4 | 32.2 |  | 128.8 | 62
2011-08-13 | Backhoe Hire | McDowall Earthmoving | hr | 5.5 | 90 |  | 495 | 62
2011-08-13 | Tipper Hire | Labour | hr | 4 | 95 |  | 380 | 62
2011-08-13 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 62
2011-08-13 | project supervisor | Supervisor | hr | 6 | 57.7 |  | 346.2 | 62
2011-08-13 | Labour | Labour | hr | 7 | 32.2 |  | 225.4 | 62
2011-08-13 | Labour | Labour | hr | 6 | 32.2 |  | 193.2 | 62
2011-08-13 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 62
2011-08-13 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-08-13 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 62
2011-08-15 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 62
2011-08-15 | Truck Driver | Labour | hr | 3 | 39.18 |  | 117.54 | 62
2011-08-15 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 62
2011-08-15 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 62
2011-08-15 | Labour | Labour | hr | 3 | 32.2 |  | 96.6 | 62
2011-08-15 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-08-16 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-08-16 | Labour | Labour | hr | 3 | 32.2 |  | 96.6 | 62
2011-08-16 | Truck Driver | Labour | hr | 3 | 39.18 |  | 117.54 | 62
2011-08-16 | Tipper Hire | Labour | hr | 4 | 95 |  | 380 | 62
2011-08-16 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 62
2011-08-16 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 62
2011-08-17 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 4 | 80 |  | 320 | 62
2011-08-17 | Labour | Labour | hr | 7 | 39.39 |  | 275.73 | 62
2011-08-17 | Labour | Labour | hr | 7 | 39.39 |  | 275.73 | 62
2011-08-17 | Labour | Labour | hr | 7 | 32.2 |  | 225.4 | 62
2011-08-17 | SD Roller - Dry | SD Roller | day | 1 | 365 |  | 365 | 62
2011-08-17 | Tipper Hire | Labour | hr | 7 | 95 |  | 665 | 62
2011-08-18 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-08-18 | Labour | Labour | hr | 8 | 32.2 |  | 257.6 | 62
2011-08-18 | Tipper Hire | Labour | hr | 7.5 | 95 |  | 712.5 | 62
2011-08-18 | SD Roller - Dry | SD Roller | day | 1 | 365 |  | 365 | 62
2011-08-18 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 5 | 80 |  | 400 | 62
2011-08-18 | Labour | Labour | hr | 8 | 39.39 |  | 315.12 | 62
2011-08-18 | Labour | Labour | hr | 10 | 39.39 |  | 393.9 | 62
2011-08-19 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 62
2011-08-19 | Labour | Labour | hr | 3 | 32.2 |  | 96.6 | 62
2011-08-19 | Labour | Labour | hr | 4.5 | 39.39 |  | 177.255 | 62
2011-08-19 | Tipper Hire | Labour | hr | 9 | 95 |  | 855 | 62
2011-08-19 | SD Roller - Dry | SD Roller | day | 1 | 365 |  | 365 | 62
2011-08-19 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 62
2011-08-22 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 62
2011-08-22 | SD Roller - Dry | SD Roller | day | 1 | 365 |  | 365 | 62
2011-08-22 | Tipper Hire | Labour | hr | 7 | 95 |  | 665 | 62
2011-08-22 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 62
2011-08-22 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 62
2011-08-22 | Labour | Labour | hr | 7.5 | 32.2 |  | 241.5 | 62
2011-08-23 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-08-23 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 62
2011-08-23 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 8 | 80 |  | 640 | 62
2011-08-23 | Labour | Labour | hr | 6 | 39.39 |  | 236.34 | 62
2011-08-23 | Labour | Labour | hr | 5.5 | 39.39 |  | 216.645 | 62
2011-08-23 | Labour | Labour | hr | 9.5 | 32.2 |  | 305.9 | 62
2011-08-23 | SD Roller - Dry | SD Roller | day | 1 | 365 |  | 365 | 62
2011-08-23 | Tipper Hire | Labour | hr | 7 | 95 |  | 665 | 62
2011-08-24 | SD Roller - Dry | SD Roller | day | 1 | 365 |  | 365 | 62
2011-08-24 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-08-24 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 4.5 | 80 |  | 360 | 62
2011-08-24 | Labour | Labour | hr | 5 | 39.39 |  | 196.95 | 62
2011-08-24 | Labour | Labour | hr | 5 | 39.39 |  | 196.95 | 62
2011-08-24 | Labour | Labour | hr | 5 | 32.2 |  | 161 | 62
2011-08-24 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 62
2011-08-24 | Tipper Hire | Labour | hr | 7 | 95 |  | 665 | 62
2011-08-25 | SD Roller - Dry | SD Roller | day | 1 | 365 |  | 365 | 62
2011-08-25 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 1 | 80 |  | 80 | 62
2011-08-25 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-08-25 | Labour | Labour | hr | 6.5 | 39.39 |  | 256.035 | 62
2011-08-25 | Labour | Labour | hr | 5 | 39.39 |  | 196.95 | 62
2011-08-25 | Labour | Labour | hr | 6.5 | 32.2 |  | 209.3 | 62
2011-08-25 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 62
2011-08-25 | Tipper Hire | Labour | hr | 7 | 95 |  | 665 | 62
2011-08-26 | SD Roller - Dry - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 62
2011-08-26 | Tipper Hire | Labour | hr | 8 | 95 |  | 760 | 62
2011-08-26 | Plate Compactor - Dry Hire Inv - 2511181 | Plate Compactor |  | 1 | 238.56 |  | 238.56 | 62
2011-08-26 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-09-05 | Tipper Hire | Labour | hr | 4 | 95 |  | 380 | 62
2011-09-05 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 5 | 80 |  | 400 | 62
2011-09-05 | Labour | Labour | hr | 6.5 | 32.2 |  | 209.3 | 62
2011-09-05 | Labour | Labour | hr | 3.5 | 39.39 |  | 137.865 | 62
2011-09-05 | Labour | Labour | hr | 3.5 | 39.39 |  | 137.865 | 62
2011-09-06 | Labour | Labour | hr | 11 | 39.39 |  | 433.29 | 62
2011-09-06 | Labour | Labour | hr | 6 | 39.39 |  | 236.34 | 62
2011-09-06 | Labour | Labour | hr | 9.5 | 32.2 |  | 305.9 | 62
2011-09-06 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-09-06 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 5 | 80 |  | 400 | 62
2011-09-06 | Tipper Hire | Labour | hr | 9 | 95 |  | 855 | 62
2011-09-07 | Tipper Hire | Labour | hr | 7 | 95 |  | 665 | 62
2011-09-07 | Backhoe Hire | McDowall Earthmoving | hr | 10 | 90 |  | 900 | 62
2011-09-07 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 62
2011-09-07 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 4 | 135 |  | 540 | 62
2011-09-07 | Labour | Labour | hr | 6 | 39.39 |  | 236.34 | 62
2011-09-07 | Labour | Labour | hr | 7.5 | 39.39 |  | 295.425 | 62
2011-09-07 | Labour | Labour | hr | 8 | 32.2 |  | 257.6 | 62
2011-09-08 | Tipper Hire | Labour | hr | 7 | 95 |  | 665 | 62
2011-09-08 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 62
2011-09-08 | Labour | Labour | hr | 5.5 | 32.2 |  | 177.1 | 62
2011-09-08 | Labour | Labour | hr | 2.5 | 39.39 |  | 98.475 | 62
2011-09-08 | Labour | Labour | hr | 5.5 | 39.39 |  | 216.645 | 62
2011-09-09 | Tipper Hire | Labour | hr | 7.5 | 95 |  | 712.5 | 62
2011-09-09 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 5 | 80 |  | 400 | 62
2011-09-09 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 62
2011-09-09 | Labour | Labour | hr | 7.5 | 39.39 |  | 295.425 | 62
2011-09-09 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 62
2011-09-09 | Labour | Labour | hr | 8 | 32.2 |  | 257.6 | 62
2011-09-10 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 62
2011-09-10 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-09-10 | Tipper Hire | Labour | hr | 4 | 95 |  | 380 | 62
2011-09-10 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 62
2011-09-12 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 62
2011-09-12 |  | Raymond Truck Hire |  | 3 | 125 |  | 375 | 62
2011-09-12 | Tipper Hire | Labour | hr | 8 | 95 |  | 760 | 62
2011-09-12 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 5 | 135 |  | 675 | 62
2011-09-13 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-09-13 | Tipper Hire | Labour | hr | 9 | 95 |  | 855 | 62
2011-09-14 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 4 | 80 |  | 320 | 62
2011-09-14 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-09-14 | Labour | Labour | hr | 5.5 | 35.35 |  | 194.425 | 62
2011-09-14 | Labour | Labour | hr | 5.5 | 35.35 |  | 194.425 | 62
2011-09-14 | Tipper Hire | Labour | hr | 7.5 | 95 |  | 712.5 | 62
2011-09-15 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 62
2011-09-15 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-09-15 | Labour | Labour | hr | 4 | 35.35 |  | 141.4 | 62
2011-09-15 | Labour | Labour | hr | 4 | 35.35 |  | 141.4 | 62
2011-09-15 | Tipper Hire | Labour | hr | 6 | 95 |  | 570 | 62
2011-09-16 | Tipper Hire | Labour | hr | 3.5 | 95 |  | 332.5 | 62
2011-09-19 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-09-19 | Tipper Hire | Labour | hr | 5 | 95 |  | 475 | 62
2011-09-20 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-09-20 | Tipper Hire | Labour | hr | 7.75 | 95 |  | 736.25 | 62
2011-09-21 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 4 | 80 |  | 320 | 62
2011-09-21 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-09-21 | Tipper Hire | Labour | hr | 3.5 | 95 |  | 332.5 | 62
2011-09-22 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 6 | 80 |  | 480 | 62
2011-09-22 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-09-22 | Labour | Labour | hr | 5.5 | 35.35 |  | 194.425 | 62
2011-09-22 | Labour | Labour | hr | 3.5 | 35.35 |  | 123.725 | 62
2011-09-22 | Tipper Hire | Labour | hr | 6.75 | 95 |  | 641.25 | 62
2011-09-23 | Labour | Labour | hr | 5 | 35.35 |  | 176.75 | 62
2011-09-23 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 3 | 80 |  | 240 | 62
2011-09-23 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-09-23 | Labour | Labour | hr | 5 | 35.35 |  | 176.75 | 62
2011-09-23 | Tipper Hire | Labour | hr | 6.5 | 95 |  | 617.5 | 62
2011-09-24 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 62
2011-09-24 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-09-24 | Tipper Hire | Labour | hr | 5 | 95 |  | 475 | 62
2011-09-24 | Labour | Labour | hr | 5.5 | 35.35 |  | 194.425 | 62
2011-09-24 | Labour | Labour | hr | 5.5 | 35.35 |  | 194.425 | 62
2011-09-26 | Tipper Hire | Labour | hr | 2.5 | 95 |  | 237.5 | 62
2011-09-26 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-09-27 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-09-28 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 62
2011-09-28 | Tipper Hire | Labour | hr | 4 | 95 |  | 380 | 62
2011-09-28 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 62
2011-09-29 | Tipper Hire | Labour | hr | 4 | 95 |  | 380 | 62
2011-09-29 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 62
2011-09-30 | SD Roller - Dry Inv 2563991 | SD Roller |  | 1 | 7392 |  | 7392 | 62
2011-10-05 | Inv - 257484 | MW Roller |  | 1 | 80 |  | 80 | 62
2011-10-31 | SD Roller - Damage Waiver Inv - 260718 | Insurances |  | 1 | 756 |  | 756 | 62
2011-10-31 | SD Roller - DryFrom the 30/09/2011 to the 31/10/2011 Inv - 260718 | SD Roller |  | 1 | 6300 |  | 6300 | 62
| Subtotal for 062 | [5 empty] | 91849.125
Portfolio WBS 063
2011-05-26 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 63
2011-06-21 | Tipper Hire | PR & HT Gourlay | hr | 3 | 65 |  | 195 | 63
2011-06-21 | Tipper Hire | K.C Truck Hire | hr | 9.5 | 95 |  | 902.5 | 63
2011-06-21 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 63
2011-06-21 | Labour | Labour | hr | 10 | 39.39 |  | 393.9 | 63
2011-06-21 | Truck Driver | Labour | hr | 4.5 | 39.18 |  | 176.31 | 63
2011-06-21 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 8 | 80 |  | 640 | 63
2011-06-22 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 63
2011-06-22 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 63
2011-06-22 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 4 | 80 |  | 320 | 63
2011-06-22 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 63
2011-06-22 | Tipper Hire | K.C Truck Hire | hr | 9 | 95 |  | 855 | 63
2011-06-23 | Tipper Hire | K.C Truck Hire | hr | 6 | 95 |  | 570 | 63
2011-06-23 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 63
2011-06-23 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 63
2011-06-23 | Labour | Labour | hr | 6 | 39.39 |  | 236.34 | 63
2011-06-23 | Labour | Labour | hr | 6.5 | 39.39 |  | 256.035 | 63
2011-06-24 | Tipper Hire | K.C Truck Hire | hr | 1.5 | 95 |  | 142.5 | 63
2011-06-25 | Tipper Hire | K.C Truck Hire | hr | 1.5 | 95 |  | 142.5 | 63
2011-06-27 | Labour | Labour | hr | 6.5 | 39.39 |  | 256.035 | 63
2011-07-01 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 63
2011-07-01 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 63
2011-07-02 | Labour | Labour | hr | 7.5 | 39.39 |  | 295.425 | 63
2011-07-02 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 5 | 80 |  | 400 | 63
2011-07-02 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 63
2011-07-02 | Tipper Hire | K.C Truck Hire | hr | 6.5 | 95 |  | 617.5 | 63
2011-07-02 | Labour | Labour | hr | 7.5 | 39.39 |  | 295.425 | 63
2011-07-16 | Tipper Hire | K.C Truck Hire | hr | 2 | 95 |  | 190 | 63
2011-07-16 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 1 | 80 |  | 80 | 63
2011-07-16 | Labour | Labour | hr | 1.5 | 39.39 |  | 59.085 | 63
2011-07-18 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 3 | 80 |  | 240 | 63
2011-07-18 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 63
2011-07-18 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 63
2011-07-18 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 63
2011-07-18 | Tipper Hire | K.C Truck Hire | hr | 9 | 95 |  | 855 | 63
2011-07-18 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 63
2011-07-19 | Labour | Labour | hr | 6.5 | 39.39 |  | 256.035 | 63
2011-07-19 | SD Roller - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 63
2011-07-19 | Tipper Hire | K.C Truck Hire | hr | 6 | 95 |  | 570 | 63
2011-07-19 | Pad Foot Roller - Flexihire | PF Roller | day | 1 | 365 |  | 365 | 63
2011-07-19 | Labour | Labour | hr | 6.5 | 39.39 |  | 256.035 | 63
2011-07-19 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 3 | 80 |  | 240 | 63
2011-07-20 | Backhoe Hire | McDowall Earthmoving |  | 7 | 90 |  | 630 | 63
2011-07-20 | Tipper Hire | K.C Truck Hire | hr | 3 | 95 |  | 285 | 63
2011-07-20 | Labour | Labour | hr | 9.5 | 39.39 |  | 374.205 | 63
2011-07-21 | Labour | Labour | hr | 8 | 39.39 |  | 315.12 | 63
2011-07-21 | Tipper Hire | Labour | hr | 1 | 95 |  | 95 | 63
2011-07-21 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 63
2011-07-21 | Backhoe Hire | McDowall Earthmoving |  | 9 | 90 |  | 810 | 63
2011-07-22 | Backhoe Hire | McDowall Earthmoving |  | 3 | 90 |  | 270 | 63
2011-07-22 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 63
2011-07-22 | Tipper Hire | Labour | hr | 2.5 | 95 |  | 237.5 | 63
2011-07-22 | Labour | Labour | hr | 2.5 | 39.39 |  | 98.475 | 63
2011-07-25 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 63
2011-07-25 | Tipper Hire | Labour | hr | 4 | 95 |  | 380 | 63
2011-07-25 | Backhoe Hire | McDowall Earthmoving | hr | 4.5 | 90 |  | 405 | 63
2011-07-25 | Labour | Labour | hr | 4.5 | 39.39 |  | 177.255 | 63
2011-07-26 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 63
2011-07-28 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 63
2011-07-28 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 63
2011-07-28 | Backhoe Hire | McDowall Earthmoving | hr | 5.5 | 90 |  | 495 | 63
2011-07-28 | Tipper Hire | Labour | hr | 3.5 | 95 |  | 332.5 | 63
2011-07-29 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 63
2011-07-29 | Labour | Labour | hr | 2 | 32.2 |  | 64.4 | 63
2011-07-29 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 63
2011-07-29 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 2 | 135 |  | 270 | 63
2011-07-29 | Tipper Hire | Labour | hr | 1 | 95 |  | 95 | 63
2011-07-29 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 63
2011-07-29 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 63
2011-08-01 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 63
2011-08-02 | Tipper Hire | Labour | hr | 3.5 | 95 |  | 332.5 | 63
2011-08-02 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 63
2011-08-02 | SD Roller - Dry - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 63
2011-08-02 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 63
2011-08-02 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 1 | 80 |  | 80 | 63
2011-08-03 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 63
2011-08-03 | SD Roller - Dry - Flexihire | SD Roller | day | 1 | 365 |  | 365 | 63
2011-08-03 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 63
2011-08-04 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 63
2011-08-09 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 63
2011-08-09 | Labour | Labour | hr | 2 | 32.2 |  | 64.4 | 63
2011-08-09 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 63
2011-08-09 | flexi hire | Twin Drum Roller | day | 1 | 365 |  | 365 | 63
2011-08-09 | SD Roller - Dry | SD Roller | day | 1 | 365 |  | 365 | 63
2011-08-09 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 63
2011-08-10 | Tipper Hire | Labour | hr | 2 | 95 |  | 190 | 63
2011-08-10 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 63
2011-08-10 | Labour | Labour | hr | 3 | 32.2 |  | 96.6 | 63
2011-08-10 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 63
2011-08-10 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 63
2011-08-15 | Labour | Labour | hr | 2 | 32.2 |  | 64.4 | 63
2011-08-15 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 63
2011-08-15 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 63
2011-08-15 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 63
2011-08-15 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 63
2011-08-15 | Tipper Hire | Labour | hr | 3 | 95 |  | 285 | 63
2011-08-15 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 63
2011-08-16 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 63
2011-08-16 | Labour | Labour | hr | 3 | 32.2 |  | 96.6 | 63
2011-08-16 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 63
2011-08-16 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 63
2011-08-16 | Tipper Hire | Labour | hr | 3 | 95 |  | 285 | 63
2011-08-16 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 63
2011-08-17 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 63
2011-08-17 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 63
2011-08-17 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 63
2011-08-17 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 63
2011-08-17 | Labour | Labour | hr | 3 | 32.2 |  | 96.6 | 63
2011-08-17 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 63
2011-08-17 | Tipper Hire | Labour | hr | 2.5 | 95 |  | 237.5 | 63
2011-08-18 | Tipper Hire | Labour | hr | 2 | 95 |  | 190 | 63
2011-08-18 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 1 | 80 |  | 80 | 63
2011-08-18 | Labour | Labour | hr | 2 | 32.2 |  | 64.4 | 63
2011-08-18 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 63
2011-08-18 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 63
2011-08-19 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 4 | 80 |  | 320 | 63
2011-08-19 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 63
2011-08-19 | Labour | Labour | hr | 5 | 39.39 |  | 196.95 | 63
2011-08-19 | Labour | Labour | hr | 6.3 | 32.2 |  | 202.86 | 63
2011-08-19 | Backhoe Hire | McDowall Earthmoving | hr | 7 | 90 |  | 630 | 63
2011-08-20 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 63
2011-08-20 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 5 | 80 |  | 400 | 63
2011-08-20 | Labour | Labour | hr | 6.5 | 39.39 |  | 256.035 | 63
2011-08-20 | Labour | Labour | hr | 6.3 | 32.2 |  | 202.86 | 63
2011-08-20 | Labour | Labour | hr | 6.5 | 32.2 |  | 209.3 | 63
2011-08-20 | SD Roller - Dry | SD Roller | day | 1 | 365 |  | 365 | 63
2011-08-20 | Backhoe Hire | McDowall Earthmoving | hr | 5 | 90 |  | 450 | 63
2011-08-20 | Tipper Hire | Labour | hr | 6 | 95 |  | 570 | 63
2011-08-22 | Tipper Hire | Labour | hr | 2 | 95 |  | 190 | 63
2011-08-22 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 63
2011-08-22 | Labour | Labour | hr | 2 | 32.2 |  | 64.4 | 63
2011-08-22 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 63
2011-08-24 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 63
2011-08-24 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2.5 | 80 |  | 200 | 63
2011-08-24 | Labour | Labour | hr | 4 | 32.2 |  | 128.8 | 63
2011-08-24 | Tipper Hire | Labour | hr | 2 | 95 |  | 190 | 63
2011-08-25 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 63
2011-08-25 | Labour | Labour | hr | 3 | 32.2 |  | 96.6 | 63
2011-08-25 | Tipper Hire | Labour | hr | 2 | 95 |  | 190 | 63
2011-08-25 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 63
2011-09-02 | Labour | Labour | hr | 2.5 | 32.2 |  | 80.5 | 63
2011-09-02 | Tipper Hire | Labour | hr | 2 | 95 |  | 190 | 63
2011-09-02 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 63
2011-09-02 | Labour | Labour | hr | 2.5 | 39.39 |  | 98.475 | 63
2011-09-07 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 63
2011-09-07 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 63
2011-09-07 | Labour | Labour | hr | 2 | 32.2 |  | 64.4 | 63
2011-09-07 | Tipper Hire | Labour | hr | 2 | 95 |  | 190 | 63
2011-09-07 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 63
2011-09-08 | Backhoe Hire | McDowall Earthmoving | hr | 5 | 90 |  | 450 | 63
2011-09-08 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 4 | 80 |  | 320 | 63
2011-09-08 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 63
2011-09-08 | Tipper Hire | Labour | hr | 2 | 95 |  | 190 | 63
2011-09-08 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 63
2011-09-08 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 63
2011-09-08 | Labour | Labour | hr | 4 | 32.2 |  | 128.8 | 63
2011-09-09 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 63
2011-09-10 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 63
2011-09-10 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 1 | 80 |  | 80 | 63
2011-09-10 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 63
2011-09-15 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 63
2011-09-15 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 63
2011-09-20 | Labour | Labour | hr | 1.5 | 35.35 |  | 53.025 | 63
2011-09-20 | Labour | Labour | hr | 1.5 | 35.35 |  | 53.025 | 63
2011-09-23 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 63
2011-09-23 | Backhoe Hire | McDowall Earthmoving | hr | 2.5 | 90 |  | 225 | 63
2011-09-23 | Tipper Hire | Labour | hr | 2.5 | 95 |  | 237.5 | 63
2011-09-23 | Labour | Labour | hr | 2.5 | 35.35 |  | 88.375 | 63
2011-09-23 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 63
2011-09-27 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 3 | 80 |  | 240 | 63
2011-09-27 | Backhoe Hire | McDowall Earthmoving | hr | 2.5 | 90 |  | 225 | 63
2011-09-27 | Labour | Labour | hr | 7.5 | 35.35 |  | 265.125 | 63
2011-09-27 | Labour | Labour | hr | 3.5 | 35.35 |  | 123.725 | 63
2011-09-27 | Tipper Hire | Labour | hr | 10 | 95 |  | 950 | 63
2011-09-28 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 63
2011-09-28 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 63
2011-09-28 | Tipper Hire | Labour | hr | 4 | 95 |  | 380 | 63
2011-09-28 | Labour | Labour | hr | 4 | 35.35 |  | 141.4 | 63
2011-09-29 | Backhoe Hire | McDowall Earthmoving | hr | 4 | 90 |  | 360 | 63
2011-09-29 | Tipper Hire | Labour | hr | 4 | 95 |  | 380 | 63
2011-09-29 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 63
2011-09-29 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 63
2011-09-29 | Labour | Labour | hr | 4 | 35.35 |  | 141.4 | 63
2011-09-29 | Labour | Labour | hr | 4 | 35.35 |  | 141.4 | 63
2011-09-30 | SD Roller - Dry | SD Roller | day | 1 | 365 |  | 365 | 63
2011-09-30 | 5T Twin Drum Roller | Twin Drum Roller | day | 1 | 365 |  | 365 | 63
| Subtotal for 063 | [5 empty] | 45939.655
Portfolio WBS 064
2011-07-04 | Inv AQCQB4008-001 | 7mm Aggregate |  | 33.56 | 87.12 |  | 2923.7472 | 64
2011-07-12 | Primer Seal - Subcontract Rate sqm - Inv 264740 | Primer Seal |  | 2606 | 7.25 |  | 18893.5 | 64
2011-07-12 | Tipper Hire | K.C Truck Hire | hr | 2.5 | 95 |  | 237.5 | 64
2011-08-23 | Tipper Hire | Labour | hr | 2 | 95 |  | 190 | 64
2011-08-24 | Primer Seal - Subcontract Rate sqm | Primer Seal |  | 1 | 36200 |  | 36200 | 64
2011-09-30 | Inv - 256400 | Twin Drum Droller |  | 1 | 5918 |  | 5918 | 64
2011-09-30 | Tipper Hire | Labour | hr | 5.5 | 95 |  | 522.5 | 64
2011-09-30 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 64
2011-09-30 | Primer Seal - Subcontract Rate sqm Inv - 00264926 | Primer Seal |  | 5932 | 6.75 |  | 40041 | 64
2011-09-30 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 64
2011-09-30 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 64
2011-09-30 | Inv - 256400 | Insurances |  | 1 | 710.16 |  | 710.16 | 64
| Subtotal for 064 | [5 empty] | 105957.8072
Portfolio WBS 065
2011-09-13 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 65
2011-09-13 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 65
2011-10-20 | ( Water Truck ) | Talbots | hr | 6.5 | 95 |  | 617.5 | 65
2011-10-31 | Primer Seal - Subcontract Rate sqm Inv - 5613257 RI | Primer Seal |  | 767 | 240 |  | 184080 | 65
| Subtotal for 065 | [5 empty] | 185012.62
Portfolio WBS 066
2011-08-23 | Inv - 01286732 | Line Marking |  | 1 | 395.44 |  | 395.44 | 66
2011-08-26 | Labour | Labour | hr | 5 | 32.2 |  | 161 | 66
2011-08-26 | Labour | Labour | hr | 5 | 39.39 |  | 196.95 | 66
2011-11-15 | Line Marking of the Whitsunday Airport Inv - 19027 | Line Marking | 7 | 1 | 7660 |  | 7660 | 66
2011-11-30 | Inv No - 20052 | Line Marking |  | 1 | 3311 |  | 3311 | 66
| Subtotal for 066 | [5 empty] | 11724.39
Portfolio WBS 067
2011-09-29 | Labour | Labour | hr | 2.5 | 35.35 |  | 88.375 | 67
2011-09-29 | Labour | Labour | hr | 2.5 | 35.35 |  | 88.375 | 67
2011-09-29 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 67
2011-09-30 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 67
2011-09-30 | Labour | Labour | hr | 2.5 | 35.35 |  | 88.375 | 67
2011-09-30 | Labour | Labour | hr | 2.5 | 35.35 |  | 88.375 | 67
2011-11-03 | Rock Hammer Inv - 10136 | Hammer |  | 1 | 66.75 |  | 66.75 | 67
2011-11-04 | ( Bobcat Hire ) | Labour | hr | 4 | 95 |  | 380 | 67
2011-11-04 | Labour Hire | Labour | hr | 5 | 35.35 |  | 176.75 | 67
2011-11-04 | Labour | Labour | hr | 4.5 | 35.35 |  | 159.075 | 67
2011-11-04 | Labour | Labour | hr | 3.5 | 35.35 |  | 123.725 | 67
2011-11-04 | Labour | Labour | hr | 4.5 | 35.35 |  | 159.075 | 67
2011-11-04 | Backhoe Hire | McDowall Earthmoving | hr | 5 | 90 |  | 450 | 67
2011-11-26 | Labour Hire | Labour | hr | 2 | 35.35 |  | 70.7 | 67
2011-11-26 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 67
2011-11-26 | Labour Day Works | Labour | hr | 2 | 35.35 |  | 70.7 | 67
2011-11-30 | Labour | Labour | hr | 3 | 35.35 |  | 106.05 | 67
2011-11-30 | Labour Hire | Labour | hr | 3 | 35.35 |  | 106.05 | 67
2011-11-30 | Labour | Labour | hr | 3 | 35.35 |  | 106.05 | 67
2011-11-30 | Labour Hire | Labour | hr | 3 | 35.35 |  | 106.05 | 67
| Subtotal for 067 | [5 empty] | 2865.175
Portfolio WBS 068
2011-11-01 | SD Rolle 13 Tonne Hire from the 31/10/2011 to the 1/11/2011 Inv No 261473 | SD Roller |  | 1 | 868.4 |  | 868.4 | 68
| Subtotal for 068 | [5 empty] | 868.4
Portfolio WBS 071
2011-07-25 | Brass Kerb Markers - Inv 19198 | Kerb Adaptors |  | 48 | 6 |  | 288 | 71
2011-07-29 | Labour | Labour | hr | 8 | 39.39 |  | 315.12 | 71
2011-07-29 | Backhoe Hire | McDowall Earthmoving | hr | 4 | 90 |  | 360 | 71
2011-07-29 | Tipper Hire | Labour | hr | 4 | 95 |  | 380 | 71
2011-07-29 | Labour | Labour | hr | 8 | 39.39 |  | 315.12 | 71
2011-07-30 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 71
2011-07-30 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 71
2011-08-31 | Slab on Ground Inv 32 | Concrete Subbie |  | 1 | 584.5 |  | 584.5 | 71
2011-09-20 | Backhoe Hire | McDowall Earthmoving | hr | 4 | 90 |  | 360 | 71
2011-09-20 | Labour | Labour | hr | 4 | 35.35 |  | 141.4 | 71
2011-09-20 | Labour | Labour | hr | 4 | 35.35 |  | 141.4 | 71
2011-09-27 | Labour | Labour | hr | 4 | 35.35 |  | 141.4 | 71
2011-09-27 | Backhoe Hire | McDowall Earthmoving | hr | 4 | 90 |  | 360 | 71
2011-10-01 | Concrete Sub-contractor (Slab on Ground) Inv - 401 | Concrete Sub-contract |  | 1 | 1300 |  | 1300 | 71
2011-11-06 | 1456 L/M of Various Kerb | Kerb Subbie |  | 1456 | 20 |  | 29120 | 71
2011-11-30 | Inv 956508 | Concrete Subbie |  | 1 | 1330 |  | 1330 | 71
2011-11-30 | Labour | Labour | hr | 3 | 35.35 |  | 106.05 | 71
2011-11-30 | Labour Hire | Labour | hr | 3 | 35.35 |  | 106.05 | 71
2011-11-30 | Entrance to traffic Island & Parking. Inv No - 95611 | Concrete Subbie |  | 1 | 1380 |  | 1380 | 71
| Subtotal for 071 | [5 empty] | 37066.6
Portfolio WBS 073
2011-08-10 | Backhoe Hire | McDowall Earthmoving | hr | 6 | 90 |  | 540 | 73
2011-08-10 | inv-00019291 Bar Chairs, Tie Wire, Crane Truck Hire | Pipes |  | 1 | 318.7 |  | 318.7 | 73
2011-08-10 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 73
2011-08-10 | inv-00019291 Square Rib Mesh | Pipes |  | 34 | 59.3 |  | 2016.2 | 73
2011-08-11 | Labour | Labour | hr | 3.5 | 39.39 |  | 137.865 | 73
2011-08-11 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 73
2011-08-22 | Backhoe Hire | McDowall Earthmoving | hr | 7 | 90 |  | 630 | 73
2011-08-22 | Labour | Labour | hr | 5.5 | 39.39 |  | 216.645 | 73
2011-08-23 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 73
2011-08-23 | Labour | Labour | hr | 5.5 | 39.39 |  | 216.645 | 73
2011-08-31 | Slab on Ground Inv - 32 | Concrete Subbie |  | 1 | 11380 |  | 11380 | 73
2011-09-19 | Labour | Labour | hr | 7.5 | 35.35 |  | 265.125 | 73
2011-09-19 | Backhoe Hire | McDowall Earthmoving | hr | 7.5 | 90 |  | 675 | 73
2011-09-20 | Labour | Labour | hr | 4 | 35.35 |  | 141.4 | 73
2011-09-22 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 73
2011-09-22 | Labour | Labour | hr | 4 | 35.35 |  | 141.4 | 73
2011-09-23 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 73
2011-09-23 | Backhoe Hire | McDowall Earthmoving | hr | 4.5 | 90 |  | 405 | 73
2011-10-01 | Concrete Sub-contractor (Slab on Ground) Inv - 40 | Concrete Sub-contract |  | 1 | 1260 |  | 1260 | 73
2011-10-01 | Concrete Sub-contractor (Slab on Ground) Inv - 40 | Concrete Sub-contract |  | 1 | 4989.6 |  | 4989.6 | 73
2011-10-01 | Set and place footpaths Inv - 40 | Concrete Subbie |  | 1 | 6537.5 |  | 6537.5 | 73
2011-10-01 | Concrete Sub-contractor (Slab on Ground) Inv - 40 | Concrete Sub-contract |  | 1 | 720 |  | 720 | 73
2011-11-30 | Pram & Baggage Entrance. Inv No 956511 | Concrete Subbie |  | 1 | 1080 |  | 1080 | 73
2011-11-30 | Pram ramp & Baggage Entrance . Inv No - 956511 | Concrete Subbie |  | 1 | 1080 |  | 1080 | 73
| Subtotal for 073 | [5 empty] | 33676.9
Portfolio WBS 081
2011-06-02 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 81
2011-07-05 | Truck Driver | Labour | hr | 2 | 39.18 |  | 78.36 | 81
2011-07-05 | Tipper Hire | PR & HT Gourlay | hr | 2.5 | 65 |  | 162.5 | 81
2011-07-25 | 20 Tonne Excavator Hire | Berry Excavations - 20T | hr | 5 | 135 |  | 675 | 81
2011-07-26 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 81
2011-07-29 | Inv 103 | Sewer Subbie |  | 1 | 11851 |  | 11851 | 81
2011-08-11 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 81
2011-09-28 | Inv - 286428 | Pipes |  | 1 | 180 |  | 180 | 81
2011-09-30 | inv 00000026 | Sewer Subbie |  | 1 | 2130.4 |  | 2130.4 | 81
2011-09-30 | Inv - 00000026 | Sewer Subbie |  | 1 | 1720 |  | 1720 | 81
| Subtotal for 081 | [5 empty] | 17494.82
Portfolio WBS 085
2011-07-29 | Inv 103 | Sewer Subbie |  | 1 | 4000 |  | 4000 | 85
2011-08-01 | Labour | Labour | hr | 8 | 39.39 |  | 315.12 | 85
2011-08-01 | Backhoe Hire | McDowall Earthmoving | hr | 6 | 90 |  | 540 | 85
2011-08-02 | Labour | Labour | hr | 6.5 | 39.39 |  | 256.035 | 85
2011-08-02 | Backhoe Hire | McDowall Earthmoving | hr | 6 | 90 |  | 540 | 85
2011-08-03 | Hire of Concrete Saw & Diamond Blade inv-248738 | Concrete Saw & Diamond Bl |  | 1 | 382 |  | 382 | 85
2011-08-03 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 85
2011-08-03 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 85
2011-08-04 | Labour | Labour | hr | 6 | 39.39 |  | 236.34 | 85
2011-08-08 | Labour | Labour | hr | 6.5 | 39.39 |  | 256.035 | 85
2011-08-08 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 85
2011-08-11 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 85
2011-08-11 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 85
2011-08-11 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 85
2011-08-12 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 85
2011-08-16 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 85
2011-08-24 | Inv 18 | Sewer Subbie |  | 1 | 5681.81 |  | 5681.81 | 85
2011-09-08 | Backhoe Hire | McDowall Earthmoving | hr | 4 | 90 |  | 360 | 85
2011-09-08 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 85
2011-09-09 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 85
2011-09-10 | Labour | Labour | hr | 6 | 39.39 |  | 236.34 | 85
2011-09-13 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 85
2011-09-13 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 85
2011-09-15 | Labour | Labour | hr | 2.5 | 35.35 |  | 88.375 | 85
2011-09-15 | Labour | Labour | hr | 2.5 | 35.35 |  | 88.375 | 85
2011-09-16 | Labour | Labour | hr | 4 | 35.35 |  | 141.4 | 85
2011-09-16 | Labour | Labour | hr | 4 | 35.35 |  | 141.4 | 85
2011-09-21 | Inv - 285869 | Pipes |  | 1 | 873.75 |  | 873.75 | 85
2011-09-30 | Inv - 00000026 | Sewer Subbie |  | 1 | 6560 |  | 6560 | 85
2011-09-30 | Inv - 00000026 | Sewer Subbie |  | 1 | 2600 |  | 2600 | 85
2011-10-06 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 85
2011-10-06 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 85
2011-10-06 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 85
| Subtotal for 085 | [5 empty] | 25120.69
Portfolio WBS 095
2011-05-18 | Tanks - Freight Inv I26559 | Tanks |  | 1 | 1440.91 |  | 1440.91 | 95
2011-05-18 | Tanks - Inv I26559 | Tanks |  | 2 | 4176 |  | 8352 | 95
2011-05-31 | Inv 98 | Sewer Subbie |  | 1 | 19747 |  | 19747 | 95
2011-06-03 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 95
2011-06-06 | Labour | Labour | hr | 6 | 39.39 |  | 236.34 | 95
2011-06-06 | Hire of Concrete Saw & Diamond Blade | Concrete Saw & Diamond Bl |  | 1 | 160.16 |  | 160.16 | 95
2011-06-07 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 95
2011-06-07 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 95
2011-06-10 | Inv 099 | Sewer Subbie |  | 1 | 32270 |  | 32270 | 95
2011-07-19 | Inv 143743228 - Visiball Water Kevel Indicator | Sewer Subbie |  | 1 | 171 |  | 171 | 95
2011-07-26 | Inv C29 | Sewer Subbie |  | 1 | 815 |  | 815 | 95
2011-08-29 | Inv - 19 | Sewer Subbie |  | 1 | 1590 |  | 1590 | 95
2011-09-30 | Inv 00000026 | Sewer Subbie |  | 1 | 73815 |  | 73815 | 95
2011-10-03 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 95
2011-10-03 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 95
2011-10-05 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 95
2011-10-05 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 95
2011-10-05 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 95
2011-10-06 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 95
2011-10-06 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 95
2011-11-30 | Inv No - 0562 | Sewer Subbie |  | 1 | 5686 |  | 5686 | 95
| Subtotal for 095 | [5 empty] | 145242.12
Portfolio WBS 103
2011-05-31 | Inv 98 | Sewer Subbie |  | 1 | 2320 |  | 2320 | 103
2011-06-10 | Inv 99 | Sewer Subbie |  | 1 | 585 |  | 585 | 103
2011-08-24 | Inv 18 | Sewer Subbie |  | 1 | 5230 |  | 5230 | 103
2011-11-30 | Inv No 130 | Water Subbie |  | 1 | 190 |  | 190 | 103
| Subtotal for 103 | [5 empty] | 8325
Portfolio WBS 111
2011-06-27 | Inv 100 | Sewer Subbie |  | 1 | 13375 |  | 13375 | 111
2011-07-26 | Labour | Labour | hr | 6 | 39.39 |  | 236.34 | 111
2011-07-26 | Backhoe Hire | McDowall Earthmoving | hr | 6 | 90 |  | 540 | 111
2011-07-29 | Inv 103 | Sewer Subbie |  | 1 | 20300 |  | 20300 | 111
2011-08-10 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 111
2011-09-15 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 111
2011-09-22 | Labour | Labour | hr | 6 | 35.35 |  | 212.1 | 111
2011-09-26 | Backhoe Hire | McDowall Earthmoving | hr | 2.5 | 90 |  | 225 | 111
2011-09-28 | Backhoe Hire | McDowall Earthmoving | hr | 4 | 90 |  | 360 | 111
2011-09-28 | Labour | Labour | hr | 11 | 35.35 |  | 388.85 | 111
2011-09-29 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 111
2011-09-29 | Labour | Labour | hr | 3 | 35.35 |  | 106.05 | 111
2011-09-29 | Labour | Labour | hr | 3 | 35.35 |  | 106.05 | 111
2011-09-30 | Labour | Labour | hr | 5 | 35.35 |  | 176.75 | 111
2011-09-30 | Labour | Labour | hr | 5 | 35.35 |  | 176.75 | 111
2011-09-30 | Backhoe Hire | McDowall Earthmoving | hr | 5 | 90 |  | 450 | 111
2011-10-03 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 111
2011-10-03 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 111
2011-10-03 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 111
2011-10-04 | Labour | Labour | hr | 4 | 35.35 |  | 141.4 | 111
2011-10-04 | Backhoe Hire | McDowall Earthmoving | hr | 4 | 90 |  | 360 | 111
2011-10-04 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 111
2011-10-05 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 111
2011-10-05 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 111
2011-10-05 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 111
2011-10-06 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 111
2011-10-06 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 111
2011-10-07 | Labour | Labour | hr | 4 | 35.35 |  | 141.4 | 111
2011-10-07 | Labour | Labour | hr | 4 | 35.35 |  | 141.4 | 111
2011-10-13 | Inv - 6585 | Electrical Pit - Precast |  | 1 | 525 |  | 525 | 111
2011-11-30 | Terry Flanagan Backhoe Hire | Terry Flanagan | hr | 8 | 110 |  | 880 | 111
2011-11-30 | Coring into man hole, hand drilles & Generator & Water Tank Hire. | Concrete Sub-contract |  | 1 | 450.8 |  | 450.8 | 111
| Subtotal for 111 | [5 empty] | 40668.49
Portfolio WBS 112
2011-11-30 | Service Call to Oziklean sewrage treatment plant. Inv N0 - 94 | Electrician |  | 1 | 150 |  | 150 | 112
| Subtotal for 112 | [5 empty] | 150
Portfolio WBS 113
2011-07-07 | Inv 57 | Electrician |  | 1 | 1410 |  | 1410 | 113
2011-07-18 | Labour | Labour | hr | 7.5 | 39.39 |  | 295.425 | 113
2011-08-17 | inv 69 | Electrician |  | 1 | 820 |  | 820 | 113
2011-08-24 | Drainage Aggregate Inv - 18 | Sewer Subbie |  | 1 | 10100 |  | 10100 | 113
2011-09-20 | Labour | Labour | hr | 4 | 35.35 |  | 141.4 | 113
2011-09-30 | Inv - 80 | Electrician |  | 1 | 2720 |  | 2720 | 113
2011-09-30 | Inv - 82 | Electrician |  | 1 | 3650 |  | 3650 | 113
2011-09-30 | Inv - 81 | Electrician |  | 1 | 10000 |  | 10000 | 113
2011-10-25 | Sewer Treatment Plant Power Inv - 85 | Electrician |  | 1 | 2017 |  | 2017 | 113
2011-10-25 | Final Payment Inv - 84 | Electrician |  | 1 | 53315.61 |  | 53315.61 | 113
| Subtotal for 113 | [5 empty] | 84469.435
Portfolio WBS 121
2011-11-16 | Hydromulching of Proserpine Airport Inv- 6075 | landscaping |  | 1 | 7800 |  | 7800 | 121
| Subtotal for 121 | [5 empty] | 7800
Portfolio WBS 131
2011-08-23 | Hire of Temperary Fencing Inv- 206662 | Fencing |  | 1 | 1680.35 |  | 1680.35 | 131
2011-10-19 | Purchase of Gate and posts Inv 23131 | Gates |  | 1 | 283.18 |  | 283.18 | 131
2011-11-16 | Inv 6204 | Fencing Subbie |  | 1 | 10460 |  | 10460 | 131
2011-11-16 | Inv - 6205 | Fencing |  | 1 | 46763.64 |  | 46763.64 | 131
2011-11-30 | Inv 369935 | Fencing Subbie |  | 1 | 3855 |  | 3855 | 131
| Subtotal for 131 | [5 empty] | 63042.17
Portfolio WBS 134
2011-11-30 | Hire of Temperary Fencing. Inv N0 - 1202090 | Fencing |  | 1 | 708.3 |  | 708.3 | 134
| Subtotal for 134 | [5 empty] | 708.3
Portfolio WBS 141
2011-08-02 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 141
2011-08-03 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 141
2011-08-15 | Truck Driver | Labour | hr | 5 | 39.18 |  | 195.9 | 141
2011-08-16 | Truck Driver | Labour | hr | 5 | 39.18 |  | 195.9 | 141
2011-08-26 | Labour | Labour | hr | 3 | 39.39 |  | 118.17 | 141
2011-08-26 | General signs - Inv ACC18308 | Signs - General |  | 1 | 700 |  | 700 | 141
2011-09-20 | Traffic Controller with Vehicle Inv - 18019 | Traffic Controller |  | 1 | 3406.3 |  | 3406.3 | 141
2011-10-19 | Labour | Labour | hr | 8 | 35.35 |  | 282.8 | 141
2011-10-20 | Labour Hire | Labour | hr | 8.5 | 35.35 |  | 300.475 | 141
2011-10-21 | Labour Hire | Labour | hr | 8 | 35.35 |  | 282.8 | 141
2011-10-24 | Labour Hire | Labour | hr | 8.5 | 35.35 |  | 300.475 | 141
2011-10-25 | Labour Hire | Labour | hr | 4.5 | 35.35 |  | 159.075 | 141
2011-10-27 | Labour Hire | Labour | hr | 3 | 35.35 |  | 106.05 | 141
2011-11-02 | Docket No 14924 Inv- 19797 | Wheel Stops |  | 1 | 7900 |  | 7900 | 141
2011-11-15 | Traffic Control Bruce Hwy Proserpine 20/09/2011 Inv - 19027 | Line Marking |  | 1 | 574.8 |  | 574.8 | 141
| Subtotal for 141 | [5 empty] | 14798.475
Portfolio WBS 142
2011-08-02 | Inv - In-8188186 - Various signs | Signs - General |  | 1 | 1257.04 |  | 1257.04 | 142
2011-08-02 | Inv IN-8188204 - BEP Lateral Shift Marker & Cardi Clamp Box edge | Signs - General |  | 1 | 197.07 |  | 197.07 | 142
2011-10-31 | Traffic Controller with Vehicle Inv - 18798 | Traffic Controller |  | 1 | 2885.3 |  | 2885.3 | 142
| Subtotal for 142 | [5 empty] | 4339.41
Portfolio WBS 151
2011-06-06 | Labour | Labour | hr | 1 | 39.39 |  | 39.39 | 151
2011-06-09 | Labour | Labour | hr | 3.5 | 39.39 |  | 137.865 | 151
| Subtotal for 151 | [5 empty] | 177.255
Portfolio WBS 152
2011-05-17 | Labour | Labour | hr | 8 | 39.39 |  | 315.12 | 152
2011-05-27 | Labour | Labour | hr | 3.5 | 39.39 |  | 137.865 | 152
2011-05-27 | Labour | Labour | hr | 3.5 | 39.39 |  | 137.865 | 152
2011-06-15 |  | Barrier Mesh |  | 4 | 54.45 |  | 217.8 | 152
2011-06-15 | Star Pickets | Pickets |  | 100 | 5.352 |  | 535.2 | 152
2011-07-09 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 152
2011-07-10 | Inv 8467/22232 Cable Ties | Small Tools |  | 1 | 16.27 |  | 16.27 | 152
2011-07-13 | Labour | Labour | hr | 3.5 | 39.39 |  | 137.865 | 152
2011-07-14 | Labour | Labour | hr | 4.5 | 39.39 |  | 177.255 | 152
2011-07-14 | Labour | Labour | hr | 2.5 | 39.39 |  | 98.475 | 152
2011-07-15 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 152
2011-08-24 | Backhoe Hire | McDowall Earthmoving | hr | 2 | 90 |  | 180 | 152
2011-08-24 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 152
2011-08-25 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 152
2011-08-26 | Labour | Labour | hr | 2 | 39.39 |  | 78.78 | 152
2011-08-26 | Labour | Labour | hr | 2 | 32.2 |  | 64.4 | 152
2011-08-26 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 152
2011-08-29 | Labour | Labour | hr | 4 | 39.39 |  | 157.56 | 152
| Subtotal for 152 | [5 empty] | 2805.915
Portfolio WBS 221
2011-11-26 | Labour | Labour | hr | 4 | 35.35 |  | 141.4 | 221
2011-11-26 | Labour | Labour | hr | 4 | 35.35 |  | 141.4 | 221
2011-11-26 | Labour Hire | Labour | hr | 4 | 35.35 |  | 141.4 | 221
2011-11-30 | Inv - 177227-251 | PVC Conduit |  | 1 | 67.27 |  | 67.27 | 221
| Subtotal for 191 | [5 empty] | 491.47
Portfolio WBS 901
2011-03-16 | Project Technical Officer | Project Technical Officer |  | 5.5 | 36.02 |  | 198.11 | 901
2011-03-23 | Project Technical Officer | Project Technical Officer |  | 2.5 | 36.02 |  | 90.05 | 901
2011-03-24 | Project Technical Officer | Project Technical Officer |  | 1.5 | 36.02 |  | 54.03 | 901
2011-05-03 | Project Technical Officer | Project Technical Officer |  | 4.5 | 36.02 |  | 162.09 | 901
2011-05-10 | Project Technical Officer | Project Technical Officer |  | 1 | 36.02 |  | 36.02 | 901
2011-05-11 | Project Technical Officer | Project Technical Officer |  | 1 | 36.02 |  | 36.02 | 901
2011-05-12 | Project Technical Officer | Project Technical Officer |  | 4.5 | 36.02 |  | 162.09 | 901
2011-05-17 | Project Technical Officer | Project Technical Officer |  | 1 | 36.02 |  | 36.02 | 901
2011-05-18 | Project Technical Officer | Project Technical Officer |  | 3.5 | 36.02 |  | 126.07 | 901
2011-05-30 | Work Place Health & Safety Officer | WHSO | week | 3 | 45 |  | 135 | 901
2011-06-02 | Work Place Health & Safety Officer | WHSO | week | 2 | 45 |  | 90 | 901
2011-06-15 | Work Place Health & Safety Officer | WHSO | week | 4 | 45 |  | 180 | 901
2011-06-16 | Work Place Health & Safety Officer | WHSO | week | 3 | 45 |  | 135 | 901
2011-06-17 | Work Place Health & Safety Officer | WHSO | week | 2 | 45 |  | 90 | 901
2011-06-21 | Work Place Health & Safety Officer | WHSO | week | 2 | 45 |  | 90 | 901
2011-06-22 | Work Place Health & Safety Officer | WHSO | week | 7 | 45 |  | 315 | 901
2011-06-23 | Work Place Health & Safety Officer | WHSO | week | 2 | 45 |  | 90 | 901
2011-07-04 | Work Place Health & Safety Officer | WHSO |  | 4 | 45 |  | 180 | 901
2011-07-05 | Work Place Health & Safety Officer | WHSO |  | 3 | 45 |  | 135 | 901
2011-08-01 | Work Place Health & Safety Officer | WHSO | week | 3 | 45 |  | 135 | 901
2011-08-02 | Work Place Health & Safety Officer | WHSO | week | 2 | 45 |  | 90 | 901
2011-08-09 | Project Technical Officer | Project Technical Officer |  | 2 | 36.02 |  | 72.04 | 901
2011-08-10 | Work Place Health & Safety Officer | WHSO | week | 2 | 45 |  | 90 | 901
| Subtotal for 901 | [5 empty] | 2727.54
Portfolio WBS 902
2011-04-27 | Project Supervisor | Project Supervisor | hr | 8 | 71.81 |  | 574.48 | 902
2011-04-28 | Project Supervisor | Project Supervisor | hr | 8 | 71.81 |  | 574.48 | 902
2011-04-29 | Project Supervisor | Project Supervisor | hr | 8 | 71.81 |  | 574.48 | 902
2011-05-03 | Project Supervisor | Project Supervisor | hr | 8 | 71.81 |  | 574.48 | 902
2011-05-04 | Project Supervisor | Project Supervisor | hr | 8 | 71.81 |  | 574.48 | 902
2011-05-05 | Project Supervisor | Project Supervisor | hr | 8 | 71.81 |  | 574.48 | 902
2011-05-09 | Project Supervisor | Project Supervisor | hr | 8 | 71.81 |  | 574.48 | 902
2011-05-10 | Project Supervisor | Project Supervisor | hr | 8 | 71.81 |  | 574.48 | 902
2011-05-11 | Project Supervisor | Project Supervisor | hr | 8 | 71.81 |  | 574.48 | 902
2011-05-12 | Project Supervisor | Project Supervisor | hr | 8 | 71.81 |  | 574.48 | 902
2011-05-13 | Project Supervisor | Project Supervisor | hr | 6.5 | 71.81 |  | 466.765 | 902
2011-05-16 | Project Supervisor | Project Supervisor | hr | 8 | 71.81 |  | 574.48 | 902
2011-05-17 | Project Supervisor | Project Supervisor | hr | 8 | 71.81 |  | 574.48 | 902
2011-05-18 | Project Supervisor | Project Supervisor | hr | 8 | 71.81 |  | 574.48 | 902
2011-05-18 | Project Supervisor | Project Supervisor | hr | 4 | 57.7 |  | 230.8 | 902
2011-05-19 | Project Supervisor | Project Supervisor | hr | 6.5 | 57.7 |  | 375.05 | 902
2011-05-19 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-05-20 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-05-21 | Project Supervisor | Project Supervisor | hr | 6.5 | 71.81 |  | 466.765 | 902
2011-05-23 | Project Supervisor | Project Supervisor | hr | 8 | 71.81 |  | 574.48 | 902
2011-05-24 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-05-25 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-05-26 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-05-27 | Project Supervisor | Project Supervisor | hr | 6.5 | 71.81 |  | 466.765 | 902
2011-05-30 | Project Supervisor | Project Supervisor | hr | 8.5 | 71.81 |  | 610.385 | 902
2011-05-31 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-06-01 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-06-02 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-06-03 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-06-04 | Project Supervisor | Project Supervisor | hr | 7 | 71.81 |  | 502.67 | 902
2011-06-06 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-06-07 | Project Supervisor | Project Supervisor | hr | 8 | 71.81 |  | 574.48 | 902
2011-06-08 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-06-09 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-06-10 | Project Supervisor | Project Supervisor | hr | 8 | 71.81 |  | 574.48 | 902
2011-06-14 | Project Supervisor | Project Supervisor | hr | 10 | 71.81 |  | 718.1 | 902
2011-06-15 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-06-16 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-06-17 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-06-18 | Project Supervisor | Project Supervisor | hr | 8 | 71.81 |  | 574.48 | 902
2011-06-20 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-06-21 | Project Supervisor | Project Supervisor | hr | 10.5 | 71.81 |  | 754.005 | 902
2011-06-22 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-06-23 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-06-27 | Project Supervisor | Project Supervisor | hr | 10 | 71.81 |  | 718.1 | 902
2011-06-28 | Project Supervisor | Project Supervisor | hr | 8 | 71.81 |  | 574.48 | 902
2011-06-29 | Project Supervisor | Project Supervisor | hr | 8 | 71.81 |  | 574.48 | 902
2011-06-30 | Project Supervisor | Project Supervisor | hr | 9 | 71.81 |  | 646.29 | 902
2011-07-01 | Project Supervisor | Project Supervisor | hr | 9 | 71.81 |  | 646.29 | 902
2011-07-02 | Project Supervisor | Project Supervisor | hr | 7.5 | 71.81 |  | 538.575 | 902
2011-07-04 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-07-05 | Project Supervisor | Project Supervisor | hr | 10 | 71.81 |  | 718.1 | 902
2011-07-06 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-07-07 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-07-08 | Project Supervisor | Project Supervisor | hr | 8.5 | 71.81 |  | 610.385 | 902
2011-07-09 | Project Supervisor | Project Supervisor | hr | 7 | 71.81 |  | 502.67 | 902
2011-07-11 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-07-12 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-07-13 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-07-14 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-07-15 | Project Supervisor | Project Supervisor | hr | 10 | 71.81 |  | 718.1 | 902
2011-07-16 | Project Supervisor | Project Supervisor | hr | 6.5 | 71.81 |  | 466.765 | 902
2011-07-18 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-07-19 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-07-20 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-07-21 | Project Supervisor | Project Supervisor | hr | 10.5 | 71.81 |  | 754.005 | 902
2011-07-22 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-07-23 | Project Supervisor | Project Supervisor | hr | 6 | 71.81 |  | 430.86 | 902
2011-07-25 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-07-26 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-07-27 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-07-28 | Project Supervisor | Project Supervisor | hr | 10 | 71.81 |  | 718.1 | 902
2011-07-29 | Project Supervisor | Project Supervisor | hr | 10 | 71.81 |  | 718.1 | 902
2011-07-30 | Project Supervisor | Project Supervisor | hr | 6.5 | 71.81 |  | 466.765 | 902
2011-08-01 | Project Supervisor | Project Supervisor | hr | 10 | 71.81 |  | 718.1 | 902
2011-08-02 | Project Supervisor | Project Supervisor | hr | 10 | 71.81 |  | 718.1 | 902
2011-08-03 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-08-04 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-08-05 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-08-08 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-08-09 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-08-10 | Project Supervisor | Project Supervisor | hr | 10 | 71.81 |  | 718.1 | 902
2011-08-11 | Project Supervisor | Project Supervisor | hr | 10.5 | 71.81 |  | 754.005 | 902
2011-08-12 | Project Supervisor | Project Supervisor | hr | 9 | 71.81 |  | 646.29 | 902
2011-08-13 | Project Supervisor | Project Supervisor | hr | 6.5 | 71.81 |  | 466.765 | 902
2011-08-15 | Project Supervisor | Project Supervisor | hr | 10.5 | 71.81 |  | 754.005 | 902
2011-08-16 | Project Supervisor | Project Supervisor | hr | 10 | 71.81 |  | 718.1 | 902
2011-08-17 | Project Supervisor | Project Supervisor | hr | 10 | 71.81 |  | 718.1 | 902
2011-08-18 | Project Supervisor | Project Supervisor | hr | 10 | 71.81 |  | 718.1 | 902
2011-08-19 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-08-20 | Project Supervisor | Project Supervisor | hr | 6.5 | 71.81 |  | 466.765 | 902
2011-08-22 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-08-23 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-08-24 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-08-25 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-08-26 | Project Supervisor | Project Supervisor | hr | 7 | 71.81 |  | 502.67 | 902
2011-08-29 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-08-30 | Project Supervisor | Project Supervisor | hr | 10 | 71.81 |  | 718.1 | 902
2011-08-31 | Project Supervisor | Project Supervisor | hr | 10.5 | 71.81 |  | 754.005 | 902
2011-09-01 | Project Supervisor | Project Supervisor | hr | 10.5 | 71.81 |  | 754.005 | 902
2011-09-02 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-09-03 | Project Supervisor | Project Supervisor | hr | 4.5 | 71.81 |  | 323.145 | 902
2011-09-05 | Project Supervisor | Project Supervisor | hr | 10 | 71.81 |  | 718.1 | 902
2011-09-06 | Project Supervisor | Project Supervisor | hr | 11 | 71.81 |  | 789.91 | 902
2011-09-07 | Project Supervisor | Project Supervisor | hr | 10 | 71.81 |  | 718.1 | 902
2011-09-08 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-09-09 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-09-10 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-09-13 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-09-14 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-09-15 | Project Supervisor | Project Supervisor | hr | 8.5 | 71.81 |  | 610.385 | 902
2011-09-16 | Project Supervisor | Project Supervisor | hr | 7 | 71.81 |  | 502.67 | 902
2011-09-19 | Project Supervisor | Project Supervisor | hr | 8.5 | 71.81 |  | 610.385 | 902
2011-09-20 | Project Supervisor | Project Supervisor | hr | 10.5 | 71.81 |  | 754.005 | 902
2011-09-21 | Project Supervisor | Project Supervisor | hr | 10 | 71.81 |  | 718.1 | 902
2011-09-22 | Project Supervisor | Project Supervisor | hr | 10 | 71.81 |  | 718.1 | 902
2011-09-23 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-09-24 | Project Supervisor | Project Supervisor | hr | 5.5 | 71.81 |  | 394.955 | 902
2011-09-26 | Project Supervisor | Project Supervisor | hr | 9 | 71.81 |  | 646.29 | 902
2011-09-27 | Project Supervisor | Project Supervisor | hr | 11 | 71.81 |  | 789.91 | 902
2011-09-28 | Project Supervisor | Project Supervisor | hr | 10 | 71.81 |  | 718.1 | 902
2011-09-29 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-09-30 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-10-03 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-10-04 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-10-05 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-10-06 | Project Supervisor | Project Supervisor | hr | 8 | 71.81 |  | 574.48 | 902
2011-10-07 | Project Supervisor | Project Supervisor | hr | 7 | 71.81 |  | 502.67 | 902
2011-11-07 | Project Supervisor | Project Supervisor | hr | 9.5 | 71.81 |  | 682.195 | 902
2011-11-10 | Project Supervisor | Project Supervisor | hr | 2 | 71.81 |  | 143.62 | 902
2011-11-26 | Supervisor | Supervisor | hr | 4 | 71.81 |  | 287.24 | 902
2011-11-26 | Supervisor | Supervisor | hr | 2 | 71.81 |  | 143.62 | 902
2011-11-30 | Supervisor | Supervisor | hr | 3 | 71.81 |  | 215.43 | 902
2011-11-30 | Supervisor | Supervisor | hr | 3 | 71.81 |  | 215.43 | 902
2011-11-30 | Supervisor | Supervisor | hr | 7 | 71.81 |  | 502.67 | 902
| Subtotal for 902 | [5 empty] | 84084.975
Portfolio WBS 903
2011-05-09 | Inv 117746 | Container |  | 1 | 3200 |  | 3200 | 903
2011-06-07 | Tiolet - Delivery | Crib Facilities |  | 1 | 88 |  | 88 | 903
2011-06-07 | Tiolet - Weekly Rate | Crib Facilities |  | 1 | 49 |  | 49 | 903
2011-06-09 | Site Office - Delivery | Crib Facilities |  | 1 | 1100 |  | 1100 | 903
2011-06-09 | Site Office Weekly rate | Crib Facilities |  | 1 | 125.02 |  | 125.02 | 903
2011-06-14 | Tiolet - Weekly Rate. | Crib Facilities |  | 1 | 49 |  | 49 | 903
2011-06-16 | Site Office Weekly Rate | Crib Facilities |  | 1 | 125.02 |  | 125.02 | 903
2011-06-21 | Tiolet - Weekly rate | Crib Facilities |  | 1 | 49 |  | 49 | 903
2011-06-22 | Inv 210236018 - garbage Bin & Bags | Small Tools |  | 1 | 29.92 |  | 29.92 | 903
2011-06-23 | Site OfficeWeekly Rate | Crib Facilities |  | 1 | 125.02 |  | 125.02 | 903
2011-06-28 | Tiolet - Weekly rate | Crib Facilities |  | 1 | 49 |  | 49 | 903
2011-06-30 | 9/6/11 to 30/6/11 - Inv243896 | Crib Facilities |  | 22 | 17.86 |  | 392.92 | 903
2011-06-30 | Tiolet Hire - 7/6/11 to 30/6/11 Inv 243895 | Crib Facilities |  | 1 | 168 |  | 168 | 903
2011-06-30 | Hire trash Pump & Hoses | Pump |  | 1 | 105.68 |  | 105.68 | 903
2011-07-31 | Tiolet, 1 Pump out during project. Inv 247671 | Crib Facilities |  | 31 | 7 |  | 217 | 903
2011-07-31 | Hire of Concrete Saw & Diamond Blade - Inv 247675 | Concrete Saw & Diamond Bl |  | 1 | 481.5 |  | 481.5 | 903
2011-07-31 | Site Office - Inv 247672 | Crib Facilities |  | 31 | 17.86 |  | 553.66 | 903
2011-08-13 | Accommodation Fred Giardina inv 55494 | Accommodation |  | 1 | 116.27 |  | 116.27 | 903
2011-08-18 | Accommodation for Fred Giardina inv 55495 | Accommodation |  | 1 | 316.09 |  | 316.09 | 903
2011-08-31 | Inv - 252046 Generator | Crib Facilities |  | 1 | 1680 |  | 1680 | 903
2011-08-31 | Site Office & Tiolet, 1 Pump out during project. Inv - 252043 | Crib Facilities |  | 1 | 620.1 |  | 620.1 | 903
2011-08-31 | Site Office & Tiolet, 1 Pump out during project. Inv- 252042 | Crib Facilities |  | 1 | 243.04 |  | 243.04 | 903
2011-08-31 | Project Insurances Inv - 252046 Generator | Insurances |  | 1 | 192 |  | 192 | 903
2011-09-30 | chemical Toilets Inv 256397. | Crib Facilities |  | 1 | 235.2 |  | 235.2 | 903
2011-10-12 | Hire of Office Shell, fridge microwave, tables chairs Inv - 256398 | Crib Facilities |  | 1 | 600.1 |  | 600.1 | 903
2011-10-30 | generator | Generator |  | 1 | 1971.2 |  | 1971.2 | 903
2011-10-31 | Site Office & Tiolet, 1 Pump out during project. From the 30/09/2011 to the 31/10/2011 Inv - 260717 | Crib Facilities |  | 1 | 620.01 |  | 620.01 | 903
2011-10-31 | Generator 10 KVA | Generator |  | 1 | 2067 |  | 2067 | 903
2011-11-04 | Foreman | Supervisor | day | 0.45 | 580 |  | 261 | 903
2011-11-05 | Foreman | Supervisor | day | 0.3 | 580 |  | 174 | 903
2011-11-30 | Office,Fridge,Microwave,Table & Chairs Hired from the 31/10/2011 to the 30/11/2011 Inv No - 265608 | Crib Facilities |  | 1 | 880.11 |  | 880.11 | 903
| Subtotal for 903 | [5 empty] | 16883.86
Portfolio WBS 904
2011-04-19 | Project Insurances - Inv I0923625 | Insurances |  | 1 | 5968.45 |  | 5968.45 | 904
2011-05-07 | Project Insurances - QLeave | Insurances |  | 1 | 10418 |  | 10418 | 904
2011-05-23 | Damage Waiver for Chainsaw hire - Flexihire Inv 237992 | Insurances |  | 1 | 32.04 |  | 32.04 | 904
2011-05-31 | Hire trash Pump & Hoses - Damage Waiver | Pump |  | 1 | 121.68 |  | 121.68 | 904
2011-06-30 | Damage Waiver - Site Office Inv 243896 | Insurances |  | 1 | 47.15 |  | 47.15 | 904
2011-06-30 | Damage Waiver | Insurances |  | 1 | 252 |  | 252 | 904
2011-06-30 | Damage waiver fees - Pump Hire Inv 243894 | Insurances |  | 1 | 446.16 |  | 446.16 | 904
2011-06-30 | Damage Waiver - PF Roller Inv 243893 | Insurances |  | 1 | 648 |  | 648 | 904
2011-06-30 | Damage Waiver - Toilet Inv 243895 | Insurances |  | 1 | 20.16 |  | 20.16 | 904
2011-07-05 | Project Insurances - Inv 244648 | Insurances |  | 1 | 40.56 |  | 40.56 | 904
2011-07-31 | Project Insurances - Damage Waiver Fees inv 247675 | Insurances |  | 1 | 56.28 |  | 56.28 | 904
2011-07-31 | Project Insurances - Inv 247672 | Insurances |  | 1 | 66.44 |  | 66.44 | 904
2011-07-31 | Project Insurances - Damage Waiver inv 247671 | Insurances |  | 1 | 26.04 |  | 26.04 | 904
2011-08-03 | inv -248738 Damage Waver | Insurances |  | 1 | 45.84 |  | 45.84 | 904
| Subtotal for 904 | [5 empty] | 18188.8
Portfolio WBS 905
2011-05-18 | Bar guards for Steel posts | Small Tools |  | 200 | 0.49 |  | 98 | 905
2011-06-14 | 12 x Spray & Mark Inv 200108848 | Small Tools |  | 12 | 6.183 |  | 74.196 | 905
2011-06-15 | Fittings for Honda pump | Small Tools |  | 1 | 552.72 |  | 552.72 | 905
2011-06-16 | Honda Pump | Small Tools |  | 1 | 798 |  | 798 | 905
2011-06-22 | Cutting Edges - Puccini Grader | Cutting Edges |  | 1 | 336.7 |  | 336.7 | 905
2011-06-24 | Pipelifter - Longshank | Small Tools |  | 1 | 585.15 |  | 585.15 | 905
2011-06-28 | Inv 8467/21938 | Small Tools |  | 1 | 59.17 |  | 59.17 | 905
2011-07-15 | Inv 8186699 | Small Tools |  | 1 | 212.16 |  | 212.16 | 905
2011-07-23 | Inv 8467/22567 | Small Tools |  | 1 | 38.27 |  | 38.27 | 905
2011-07-30 | Cable Ties | Small Tools |  | 1 | 12.64 |  | 12.64 | 905
2011-07-30 | Chain Sling | Small Tools |  | 1 | 270 |  | 270 | 905
2011-08-02 | Inv 8467/22839 - 3 x Paint Spray | Small Tools |  | 3 | 8.46 |  | 25.38 | 905
2011-08-02 | inv- 8467/22839 | Small Tools |  | 1 | 30.76 |  | 30.76 | 905
2011-08-03 | inv- 8467/22877 | Small Tools |  | 1 | 112.63 |  | 112.63 | 905
2011-08-10 | inv-00019291 | Swift Lifters |  | 4 | 165 |  | 660 | 905
2011-08-16 | Inv - 8467/23244 | Small Tools |  | 1 | 82.24 |  | 82.24 | 905
2011-08-17 | Inv - 8226740 RodThreded Dog, Wheel Metal Ultra Thin, Battery Energizer. | Small Tools |  | 1 | 120.75 |  | 120.75 | 905
2011-08-23 | inv-8467/23448 | Small Tools |  | 1 | 59.85 |  | 59.85 | 905
2011-08-24 | inv- 8467-23472 | Small Tools |  | 1 | 43.14 |  | 43.14 | 905
2011-08-26 | Cartridges Inv -8593 | Small Tools |  | 1 | 57.26 |  | 57.26 | 905
2011-08-29 | Labour Inv- 8467/23592 | Small Tools |  | 1 | 90.68 |  | 90.68 | 905
2011-09-26 | Inv - 8467/24169 | Small Tools |  | 1 | 54.46 |  | 54.46 | 905
2011-10-05 | Rack s Inv - 8467/24169 | Small Tools |  | 1 | 54.45 |  | 54.45 | 905
2011-11-02 | Hose Garden, Hose Fittings, Inv - 8467/25098 | Small Tools |  | 1 | 110.17 |  | 110.17 | 905
2011-11-02 | Acid Hydro Spirit, Batteries Inv - 8467/25090 | Small Tools |  | 1 | 20.06 |  | 20.06 | 905
| Subtotal for 905 | [5 empty] | 4558.836
Portfolio WBS 907
2011-05-17 | Silt Fence & Cable Ties | Silt Fence |  | 1 | 189.81 |  | 189.81 | 907
2011-05-18 | Labour | Labour | hr | 4 | 32.2 |  | 128.8 | 907
2011-05-18 | Labour | Labour | hr | 8 | 39.39 |  | 315.12 | 907
2011-05-18 | Inv 189 - Float Grader to Whitsunday Airport | Float |  | 1 | 665 |  | 665 | 907
2011-05-18 | Labour | Labour | hr | 4 | 30 |  | 120 | 907
2011-05-18 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 3 | 80 |  | 240 | 907
2011-05-23 | Chainsaw Hire - Flexihire | Chainsaw |  | 3 | 89 |  | 267 | 907
2011-05-24 | Deliver container to site Inv 1026 | Float |  | 1 | 500 |  | 500 | 907
2011-06-14 | Float of Dozer | Allans Earthmoving | hr | 1 | 225 |  | 225 | 907
2011-06-20 | Inv 7681 | Spill Kit |  | 1 | 154.5 |  | 154.5 | 907
2011-06-20 | Float of Dozer Offsite | Allans Earthmoving | hr | 1 | 249.55 |  | 249.55 | 907
2011-06-30 | Delivery of Office - Inv 243896 | Float |  | 1 | 1000 |  | 1000 | 907
2011-06-30 | SD Roller - Delivery | SD Roller |  | 1 | 200 |  | 200 | 907
2011-06-30 | Delivery of toilet - Inv 243895 | Float |  | 1 | 80 |  | 80 | 907
2011-08-03 | Inv- 6493 Float Excavator | Float |  | 1 | 260 |  | 260 | 907
2011-10-03 | Labour | Labour | hr | 3.5 | 35.35 |  | 123.725 | 907
2011-10-03 | Tipper Hire | Lovell Earthmoving | hr | 6 | 90 |  | 540 | 907
2011-10-03 | Labour | Labour | hr | 3.5 | 35.35 |  | 123.725 | 907
2011-10-04 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 907
2011-10-04 | Labour | Labour | hr | 3.5 | 35.35 |  | 123.725 | 907
2011-10-04 | Labour | Labour | hr | 5.5 | 35.35 |  | 194.425 | 907
2011-10-05 | Labour | Labour | hr | 3.5 | 35.35 |  | 123.725 | 907
2011-10-05 | Labour | Labour | hr | 3.5 | 35.35 |  | 123.725 | 907
2011-10-05 | Tipper Hire | Lovell Earthmoving | hr | 6 | 90 |  | 540 | 907
2011-10-05 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 907
2011-10-06 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 907
2011-10-06 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 907
2011-10-06 | Backhoe Hire | McDowall Earthmoving | hr | 5.5 | 90 |  | 495 | 907
2011-10-07 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 907
2011-10-07 | Labour | Labour | hr | 2 | 35.35 |  | 70.7 | 907
2011-10-30 | Mini Float Airport Inv- 4826 | Float |  | 2 | 136.365 |  | 272.73 | 907
2011-10-30 | Mini Excavator with Hammer Doket No 17650 Inv- 4826 | Float |  | 2 | 130 |  | 260 | 907
2011-11-30 | Inv No - 97 | Electrician |  | 1 | 500 |  | 500 | 907
| Subtotal for 907 | [5 empty] | 8728.36
Portfolio WBS 910
2011-10-04 | Hire of Office Shell, fridge microwave, tables chairs Inv - 256398 | Crib Facilities |  | 1 | 80 |  | 80 | 910
2011-10-05 | Backhoe Hire | McDowall Earthmoving | hr | 3 | 90 |  | 270 | 910
2011-11-05 | Labour | Labour | hr | 3 | 35.35 |  | 106.05 | 910
2011-11-07 | ( Bobcat Hire ) | Labour | hr | 10.5 | 95 |  | 997.5 | 910
2011-11-07 | Labour Hire | Labour | hr | 9 | 35.35 |  | 318.15 | 910
2011-11-07 | Labour Hire | Labour | hr | 3 | 35.35 |  | 106.05 | 910
2011-11-07 | Leading Hand | Labour | hr | 6 | 44.2 |  | 265.2 | 910
2011-11-07 | Labour | Labour | hr | 9 | 35.35 |  | 318.15 | 910
2011-11-07 | Labour | Labour | hr | 9 | 35.35 |  | 318.15 | 910
2011-11-07 | Labour | Labour | hr | 9 | 35.35 |  | 318.15 | 910
2011-11-10 | Dry Hire - Grader Hire | Puccini Plant Hire | hr | 2 | 80 |  | 160 | 910
2011-11-10 | ( Bobcat Hire ) | Labour | hr | 6.5 | 95 |  | 617.5 | 910
| Subtotal for 910 | [5 empty] | 3874.9
Portfolio WBS C25
2011-07-14 | N25 Concrete - Inv 7329 | N25 |  | 1 | 288.96 |  | 288.96 | C25
2011-07-29 | Inv 103 | Sewer Subbie |  | 1 | 420 |  | 420 | C25
2011-08-17 | N25 Concrete inv 7578 | N25 |  | 5.4 | 168.2 |  | 908.28 | C25
2011-08-18 | N25 Concrete inv 7598 | N25 |  | 5.4 | 168.2 |  | 908.28 | C25
2011-08-19 | N25 Concrete Inv- 7624 | N25 |  | 5.6 | 168.2 |  | 941.92 | C25
2011-08-22 | N25 Concrete Inv 7620 | N25 |  | 5.4 | 168.2 |  | 908.28 | C25
2011-08-23 | N25 Concrete Inv- 7634 | N25 |  | 1 | 1127.48 |  | 1127.48 | C25
2011-08-24 | N25 Concrete Inv-7642 | N25 |  | 5.8 | 168.2 |  | 975.56 | C25
2011-08-25 | N25 Concrete Inv- 7655 | N25 |  | 1 | 1939.68 |  | 1939.68 | C25
2011-08-29 | N25 Concrete Inv- 7689 | N25 |  | 4.8 | 168.2 |  | 807.36 | C25
2011-09-06 | N25 Concrete Inv - 7764 | N25 |  | 5.8 | 168.2 |  | 975.56 | C25
2011-09-22 | Dock - 3257 Inv - 7881 | concrete |  | 5 | 168.2 |  | 841 | C25
2011-09-23 | N25 Concrete Inv - 7880 | N25 |  | 8 | 168.2 |  | 1345.6 | C25
2011-09-26 | Doc 3276 Inv - 7903 | concrete |  | 5 | 168.2 |  | 841 | C25
2011-09-27 | Doc - 3288 Inv - 7907 | N25 |  | 5 | 168.2 |  | 841 | C25
2011-09-28 | Doc 3304 Inv- 7927 | N25 |  | 4.6 | 133.2 |  | 612.72 | C25
2011-09-29 | Doc - 3309 Inv - 7932 | N25 |  | 3 | 168.2 |  | 504.6 | C25
2011-09-29 | Doc - 3309 - Inv - 7932 | N25 |  | 3 | 168.2 |  | 504.6 | C25
2011-09-30 |  | N25 |  | 1 | 162.88 |  | 162.88 | C25
2011-09-30 | Doc - 3327 Inv 7939 | concrete |  | 3.4 | 168.2 |  | 571.88 | C25
2011-10-04 | Doc - 3349 Inv7999 | concrete |  | 3.4 | 168.2 |  | 571.88 | C25
2011-10-06 | Doc - 3293/3294 - Inv - 7920 | N25 |  | 8 | 197 |  | 1576 | C25
2011-11-30 | N25 Concrete Inv No - 8405 | N25 |  | 4 | 173.2 |  | 692.8 | C25
2011-11-30 | N25 Concrete - Inv 8685 | N25 |  | 3.4 | 168.2 |  | 571.88 | C25
2011-11-30 | N25 Concrete Inv No - 66983955 | N25 |  | 1 | 549 |  | 549 | C25
| Subtotal for C25 | [5 empty] | 21588.3
Portfolio WBS C32
2011-08-04 | N32 Concrete - inv 7491 | N32 |  | 1 | 358.68 |  | 358.68 | C32
2011-08-08 | N32 Concrete - inv 7510 | N32 |  | 1 | 232.72 |  | 232.72 | C32
2011-08-10 | N32 Concrete- inv 7555 | N32 |  | 1 | 4712.5 |  | 4712.5 | C32
2011-08-12 | N32 Concrete- inv 7559 | N32 |  | 1 | 1112.76 |  | 1112.76 | C32
2011-08-22 | N25 Concrete Inv- 7619 | N32 |  | 1 | 170.76 |  | 170.76 | C32
2011-09-10 | Bulk GP / GB Cement Inv - 7794 | N32 |  | 1 | 296.04 |  | 296.04 | C32
2011-09-13 | Inv - 7801 | N32 |  | 1 | 296.03 |  | 296.03 | C32
2011-09-19 | Inv 8467024039 | concrete |  | 1 | 54.618 |  | 54.618 | C32
2011-09-20 | N32 Concrete Docket No 3240 3234 3235 3239 | N32 |  | 14.8 | 188.5 |  | 2789.8 | C32
2011-09-21 | N32 Concrete Doc No 3251 Inv- 7869 | N32 |  | 15 | 188.5 |  | 2827.5 | C32
2011-10-03 | Dock - 3338/3340 - Inv 7979 | concrete |  | 16.4 | 194.2 |  | 3184.88 | C32
2011-10-31 | Dock No 3614/17/22 - Inv- 8243 | N32 |  | 1 | 1734.92 |  | 1734.92 | C32
| Subtotal for C32 | [5 empty] | 17771.208
Portfolio WBS CKM
2011-07-19 | 20kg Bags of Cement - Inv 1568444 | Cement |  | 1 | 688.7 |  | 688.7 | CKM
2011-07-25 | 20kg bags of cement - Inv 1569588 | Cement |  | 1 | 688.7 |  | 688.7 | CKM
2011-07-29 | N32 Concrete - Inv 7432 | N32 |  | 47.8 | 188.5 |  | 9010.3 | C32
2011-08-16 | N32 Concrete inv 7583 | N32 |  | 1 | 296.03 |  | 296.03 | CKM
2011-09-01 | Bulk GP / GB Cement Plus Delivery Inv - 1577397 | Cement |  | 1 | 688.7 |  | 688.7 | CKM
2011-09-08 | Bulk GP / GB Cement Inv - 7816 | N32 |  | 31.6 | 188.5 |  | 5956.6 | C32
2011-09-09 | Bulk GP / GB Cement Inv - 8254979 | Cement |  | 50 | 7.82 |  | 391 | CKM
2011-09-19 | Brass Kerb Markers "E" Inv - 19506 | Kerb Adaptors |  | 6 | 20 |  | 120 | CKM
2011-09-20 | Inv - 3231, 3233, 3236, 3238 Inv - 7866 | N32 |  | 16.2 | 194.2 |  | 3146.04 | C32
2011-09-30 | doc - 3320/3316 | concrete |  | 17.4 | 194.2 |  | 3379.08 | C32
2011-10-19 | Bulk GP / GB Cement Inv 1580203 | Cement |  | 1 | 688.7 |  | 688.7 | CKM
| Subtotal for CKM | [5 empty] | 25053.85
Portfolio WBS CSA
2011-08-10 | Bulk GP / GB Cement- inv 94419715 | Cement |  | 36 | 357 |  | 12852 | CSA
| Subtotal for CSA | [5 empty] | 12852
Portfolio WBS ETC
2011-06-01 | Inv 5841128 | Conduits |  | 1 | 6927.4 |  | 6927.4 | ETC
2011-07-05 | Inv 279964 | Pipes |  | 3 | 490 |  | 1470 | ETC
2011-07-05 | Inv 279965 | Pipes |  | 1 | 504 |  | 504 | ETC
2011-07-27 | Inv 116288 | Conduits |  | 1 | 540.25 |  | 540.25 | ETC
2011-07-27 | Inv 172293-251 | Conduits |  | 1 | 401.85 |  | 401.85 | ETC
2011-08-10 | Inv 172836-251 | Conduits |  | 25 | 8.2 |  | 205 | ETC
2011-08-10 | Inv 1556 | Conduits |  | 3 | 752 |  | 2256 | ETC
2011-09-06 | inv - 173889-251 | Conduit Subbie |  | 3 | 4.28 |  | 12.84 | ETC
| Subtotal for ETC | [5 empty] | 12317.34
Portfolio WBS ETM
2011-06-27 | Inv 19038 | Marker Tape |  | 1 | 133.5 |  | 133.5 | ETM
2011-07-19 | Inv SIP29759 - 4 x Foudation Cages and templates | Conduits |  | 1 | 1180 |  | 1180 | ETM
2011-07-26 | Inv 116274 | Rope |  | 1 | 53.81 |  | 53.81 | ETM
2011-08-08 | 4 x RND Boulevard & X-Arm - Inv SIP30066 | Conduits |  | 4 | 1411 |  | 5644 | ETM
2011-09-28 | Inv 13420 - Electrical Cages | Conduits |  | 1 | 1700 |  | 1700 | ETM
2011-11-30 | Supply Cut Weld and Paint Bollard & Fabricate 3/16mm Threaded Rod Bolts Cages | Bollards |  | 1 | 880 |  | 880 | ETM
| Subtotal for ETM | [5 empty] | 9591.31
Portfolio WBS ETP
2011-06-29 | Inv 279566 | Electrical Pit - Precast |  | 1 | 2752 |  | 2752 | ETP
2011-06-29 | Inv 279567 | Electrical Pit - Precast |  | 1 | 490 |  | 490 | ETP
2011-06-29 | Inv 279568 | Electrical Pit - Precast |  | 1 | 1470 |  | 1470 | ETP
2011-06-30 | Inv 279758 | Electrical Pit - Precast |  | 1 | 6574 |  | 6574 | ETP
2011-09-30 | Type 66 Lid Doc - 226407 | Pit Builder - Modify |  | 1 | 2500 |  | 2500 | ETP
2011-11-30 | Inv No - 299874 | Electrical Pit - Precast |  | 1 | 75 |  | 75 | ETP
| Subtotal for ETP | [5 empty] | 13861
Portfolio WBS QM2.1
2011-06-30 | CBR45 Road Base Inv 2902 | CBR45 |  | 1526.24 | 20.95 |  | 31974.728 | QM2.1
2011-08-09 | 2.1 road base- 3201 | 2.1 road base |  | 132.76 | 20.95 |  | 2781.322 | QM2.1
2011-08-09 | 2.1 road base- inv 3215 | 2.1 road base |  | 852.34 | 20.95 |  | 17856.523 | QM2.1
2011-08-17 | Bedding Sand Inv - 10010964 - FD | Sand |  | 1104.06 | 20.95 |  | 23130.057 | QM2.1
2011-08-17 | Bulk GP / GB Cement Inv -10010873 FD | Sand |  | 25.58 | 20.95 |  | 535.901 | QM2.1
2011-08-18 | Bedding Sand Inv - 10011034- FD | Sand |  | 1245.04 | 20.95 |  | 26083.588 | QM2.1
2011-08-24 | Bulk GP / GB Cement Inv 10011220 - FD | Sand |  | 113.28 | 20.95 |  | 2373.216 | QM2.1
2011-09-08 | 2.1 road base Inv 3324 | 2.1 road base |  | 1704.48 | 20.95 |  | 35708.856 | QM2.1
2011-09-22 | Inv - 10012668 / 1001221 | Sand |  | 200.02 | 195 |  | 39003.9 | QM2.1
2011-10-12 | Bedding Sand 2374.68 T | Sand |  | 1 | 52122.76 |  | 52122.76 | QM2.1
2011-10-14 | Bedding Sand 1332.92 T Inv - 3819 | Sand |  | 1 | 27924.67 |  | 27924.67 | QM2.1
2011-10-26 | Bedding Sand Inv - 4014 | Sand |  | 1 | 15702.03 |  | 15702.03 | QM2.1
| Subtotal for QM2.1 | [5 empty] | 275197.551
Portfolio WBS QMS
2011-06-06 | Stabilised Sand - Inv 7073 | Stabilised Sand |  | 1 | 337.16 |  | 337.16 | QMS
2011-07-13 | Bedding Sand - Inv 3944 | Sand |  | 25.94 | 20.31 |  | 526.8414 | QMS
2011-07-28 | Fine Sand - Inv 7409 | Sand |  | 1 | 268 |  | 268 | QMS
2011-08-05 | Bedding Sand - Inv 4018 | Sand |  | 5.6 | 51.135 |  | 286.356 | QMS
2011-09-06 | Bedding Sand Inv - 10011863- FD | Sand |  | 493.74 | 51.135 |  | 25247.3949 | QMS
2011-09-07 | Bedding Sand Inv - 10011906 - FD | Sand |  | 329.34 | 51.135 |  | 16840.8009 | QMS
2011-09-09 | Bedding Sand Inv 10012058- FD | Sand |  | 296.44 | 51.135 |  | 15158.4594 | QMS
2011-09-21 | Bedding Sand Inv - 10011810 - FD | Sand |  | 213.4 | 51.135 |  | 10912.209 | QMS
2011-09-21 | Bedding Sand 10012058- FD | Sand |  | 296.44 | 51.135 |  | 15158.4594 | QMS
2011-09-23 | 2.1 road base Inv - 100127370/10012677 | Sand |  | 549.48 | 58 |  | 31869.84 | QMS
2011-09-30 | Inv - 4125 | Sand |  | 1 | 1200.1 |  | 1200.1 | QMS
2011-10-03 | Bedding Sand Docket No 35593 Inv 4225 | Sand |  | 11.72 | 13.64 |  | 159.8608 | QMS
| Subtotal for QMS | [5 empty] | 117965.4818
Portfolio WBS RFS
2011-05-20 | General signs & delineation for traffic control. | Signs - General |  | 2 | 66.4 |  | 132.8 | RFS
2011-08-12 | General signs & delineation for traffic control. iNV -8188186 | Signs - General |  | 1 | 2616.76 |  | 2616.76 | RFS
2011-08-24 | General signs & delineation for traffic control. Inv- 8467/23477 | Signs - General |  | 1 | 65.28 |  | 65.28 | RFS
2011-09-15 | General signs & delineation for traffic control. Inv - 8195601 | Signs - General |  | 1 | 1307 |  | 1307 | RFS
2011-09-21 | General signs & delineation for traffic control. Inv - SH-195202 | Signs - General |  | 1 | 654.89 |  | 654.89 | RFS
2011-09-27 | GeneIral signs & delineation for traffic control. Inv 8195965 | Single Check Detector |  | 1 | 205.7 |  | 205.7 | RFS
| Subtotal for RFS | [5 empty] | 4982.43
Portfolio WBS RSM
2011-08-25 | Inv - 00019364 | Steel Fixing |  | 1 | 136.65 |  | 136.65 | RSM
2011-09-05 | NF72 Suare Ribmesh, 50/65 Bar Chairs Inv - 19421 | Steel Fixing |  | 1 | 2489.2 |  | 2489.2 | RSM
| Subtotal for RSM | [5 empty] | 2625.85
Portfolio WBS SWL
2011-07-05 | Inv 19076 | Precast Kerb |  | 1 | 16131 |  | 16131 | SWL
2011-08-10 | inv=00019291 Kerb Entry Unit | Pipes |  | 1 | 1484 |  | 1484 | SWL
| Subtotal for SWL | [5 empty] | 17615
Portfolio WBS SWP
2011-06-07 | Inv 18919 | Pipes |  | 1 | 12762 |  | 12762 | SWP
2011-08-10 | inv-00019291 | Pipes |  | 4 | 175.5 |  | 702 | SWP
2011-09-01 | 2.34m x 450 mm class 2 RRJ RC Inv - 19395 | Pipes |  | 1 | 220 |  | 220 | SWP
| Subtotal for SWP | [5 empty] | 13684
| Grand Total | [5 empty] | 1982828.898